## Data Sources
SN | Connectivity Application Status | Frequency
1 | CTU ¦ Central Transmission Utility of India Limited CMETS (Agenda and Minutes: Region wise) link:https://ctuil.in/ists-consultation-meeting | Daily
2 | CTU ¦ Central Transmission Utility of India Limited JCC (Region wise as per document release Agenda/Minutes) link https://ctuil.in/ists-joint-coordination-meeting | Daily
3 | Status of effectiveness of connectivity granted to RE generators (Effective date of connectivity wise) link | Daily
4 | CTU ¦ Central Transmission Utility of India Limited Re-allocation meetings (Agenda and Minutes: Region wise) link | Weekly
5 | CTU ¦ Central Transmission Utility of India Limited Bidding Calendar link | Weekly
6 | Transmission Reports - Central Electricity Authority TBCB report from CEA transmission (monthly comparison) link | Daily
7 | CTUIL (OPEN ACCESS) (Compliance of Land and Financial Closure) link | Daily
8 | Monitoring of Connectivity (all 3 Annexures and monthly document release comparison) link | Daily
SN | Substation and Transmission Tracking | Frequency
9 | (Status of allocation of bays at ISTS substations for connectivity grantees, Connectivity margins at existing ISTS (non RE) substations for future RE integration and Connectivity Margin in ISTS RE Substations available by Mar-2030) link | Weekly
10a | Potential RE Zones Report link | Weekly
10b | NCT (Agenda and Minutes Summary and Comparison of Scheme wise elements) link Link: https://cea.nic.in/comm-trans/national-committee-on-transmission/?lang=en | Daily
10c | Tender websites PFCCL and RECPDCL mentioned in NCT under TBCB and RTM (RFP and other tender documents in folders; Bidding Status: Bid Submission Date or Deadline, Commissioning Timeline and Expected SCOD) RECPDCL: https://www.recpdcl.in/rectpcltender PFCCL:https://www.pfcclindia.com/tender-new.php PFCCL Notice: https://www.pfcclindia.com/notice.php?AM1 | Daily
10d | CEA monthly transmission reports: (track status for tender elements timelines from 1) CEA Monthly report for actual physical progress of elements and 2) Actual COD from completion report) CEA https://cea.nic.in/transmission-reports/?lang=en | Daily
10e | Map of the above Section 2 data to be created for review and edit by users
11 | Bulk Consumers and Green Hydrogen link | Weekly
12 | CEA: transmission schemes, substations (transformation capacity) and transmission lines published each month on CEA monthly reports section under transmission. | Weekly
13 | Global Wind Atlas (India Map Visualization) | Weekly
14 | Open Infrastructure Map (India Map Visualization) | Weekly

## Data to be captured
| Sr.no. | Region | State | Substation | Coordinates | Name of Developers | Group | GNA/ST II Application ID | LTA Application ID | Application ID under Enhancement 5.2 or revision | CMETS GNA Approved | CMETS LTA Approved | CMETS GNA Meeting Date | CMETS LTA Meeting Date | Type | Application Quantum (MW)(ST II) | Granted Quantum GNA/LTA(MW) | Installed/Break-up Capacity (MW) |  |  | Battery |  |  | PSP |  |  | Commissioned |  | Application/Submission Date | Mode(Criteria for applying) | Applied Start of Connectivity sought by developer date( start date of connectivity as per the application) | GNA Operationalization Date | GNA Operationalization (Yes/No) | Date from which additional capacity is to be added | Nature of Applicant | Status of application(Withdrawn / granted. Revoked.) | Voltage level | Bay No | CTS Element Unique Code | ATS Element Unique Code | DTL Element Code Unique | Date of Last Element Unique Code | In-principle Grant | Final Grant | In case of Land BG Conversion Date | Remarks
[18 empty] | Solar | Wind | Hybrid | MWh | Injection (MW) | Drawl (MW) | MWh | Injection (MW) | Drawl (MW) | TGNA | GNA
Data Scoure (Sl. No.(s) 1,2,3,4,7,8,9,11)
as per GNA Regulations.
|  |  | Nagaur | Nagaur
[6 empty] | Enren-III Energy | [23 empty] | Land BG |  |  |  |  | Generator
|  |  | distt., | Complex |  |  |  | 7. 2200000860 | [7 empty] | 300 | [12 empty] | 31.05.2024 |  | 31.01.2027
[6 empty] | Private Limited | [23 empty] | Route |  |  |  |  | (Solar)
|  |  | Rajasthan | (Merta-II) PS
evacuation of power beyond 2100 MW from Merta-II PS. It may be noted that transmission system for evacuation of power from Merta-II PS was planned
for net evacuation capacity of 2000 MW only.
rom the studies, considering upcoming RE generation in Northern and Western region by 2028-29 timeframe, severe transmission constraints were
observed in Western region under N-1 contingency. Therefore, considering the severe evacuation constraints in Western Region as well as low Short
evacuation shall be through proposed Beawar HVDC scheme.
kV bay shall be under ISTS & DTL tower configuration shall be S/c line on D/c tower. The same was noted.
t was mentioned that, the transmission system for evacuation of power from Nagaur(Merta) & Pali complexes through Beawer(HVDC) is presently under
|  |  | Jaisalmer |  |  | ACME Cleantech
Generator
|  |  | distt., |  |  | Solutions Private |  | 2200001065 | [20 empty] | 17.07.2024
(Solar)
|  |  | Rajasthan |  |  | Limited
|  | NR | Rajasthan | Barmer-I |  | ENREN-I ENERGY PRIVATE LIMITED |  | 2200000286 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ANBOTO SOLAR PRIVATE LIMITED |  | 2200000281 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-I |  | AUXO SUNLIGHT PRIVATE LIMITED |  | 2200000312 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200000153 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000161 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Barmer-I |  | EDEN RENEWABLE CADET PRIVATE LIMITED |  | 2200000181 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ANBOTO SOLAR PRIVATE LIMITED |  | 2200000492 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | RENEW SUN POWER PRIVATE LIMITED |  | 2200000316 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ENFINITY GLOBAL SURYA KIRAN PRIVATE LIMITED |  | 2200000411 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ANDHRA PRADESH RESCO ROOFTOP SOLAR PRIVATE LIMITED |  | 2200000412 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | HINDUJA RENEWABLES ENERGY PRIVATE LIMITED |  | 2200000425 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-I |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000305 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | GREEN INFRA RENEWABLE PROJECTS LIMITED |  | 2200000410 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Barmer-II |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000636 | [6 empty] | Solar | 450
|  | NR | Rajasthan | Barmer-II |  | SPRNG URJA PRIVATE LIMITED |  | 2200000681 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Barmer-II |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000810 | [6 empty] | Solar | 717
|  | NR | Rajasthan | Barmer-II |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000906 | [6 empty] | Solar | 500
|  | NR | Rajasthan | Barmer-II |  | ADITYA BIRLA RENEWABLES LIMITED |  | 2200001128 | [6 empty] | Hybrid (RHGS) | 100
|  | NR | Rajasthan | Barmer-II |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000973 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Barmer-II |  | VISMAYA FIVE RENEWABLES PRIVATE LIMITED |  | 2200000954 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-II |  | VISMAYA FIVE RENEWABLES PRIVATE LIMITED |  | 2200001285 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Barmer-II |  | GREEN INFRA CLEAN SOLAR FARMS LIMITED |  | 2200000408 | [6 empty] | Solar | 130
|  | NR | Rajasthan | Barmer-II |  | SPRNG RENEWABLE RESOURCES PRIVATE LIMITED |  | 2200000531 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Barmer-II |  | SPRNG URJA PRIVATE LIMITED |  | 2200000539 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Barmer-II |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000567 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-II |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000580 | [6 empty] | Solar | 500
|  | NR | Rajasthan | Barmer-II |  | AMARESHA RENAWABLES INDIA PROJECT PRIVATE LIMITED |  | 2200000715 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-II |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000778 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | GREEN INFRA RENEWABLE ENERGY FARMS PRIVATE LIMITED |  | 2200001141 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II |  | ADANI RENEWABLE ENERGY HOLDING EIGHTEEN LIMITED |  | 2200001044 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bhadla-II |  | GREEN INFRA CLEAN WIND LIMITED |  | 2200000437 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II PS |  | NTPC Ltd. |  | St-II:1200002501 (300 MW) (TSSPDCL | 1200003110 | [5 empty] | Solar | 211.65
|  | NR | Rajasthan | Bhadla-II PS |  | NTPC Ltd. |  | St-II:1200002483 (300 MW) (TSSPDCL | 1200003109 | [5 empty] | Solar | 211.65
|  | NR | Rajasthan | Bhadla-II PS |  | NTPC Ltd. |  | St-II:1200002483 (300 MW) (TSNPDCL | 1200003120 | [5 empty] | Solar | 88.35
|  | NR | Rajasthan | Bhadla-II PS |  | NTPC Ltd. |  | St-II:1200002340 (250 MW) (TSNPDCL | 1200003122 | [5 empty] | Solar | 73.625
|  | NR | Rajasthan | Bhadla-II PS |  | NTPC Ltd. |  | St-II:1200002501 (300 MW) (TSNPDCL | 1200003121 | [5 empty] | Solar | 88.35
|  | NR | Rajasthan | Bhadla-II PS |  | ABC Solar (India) Private Limited |  | St-II:1200002359 (300 MW | 1200003357 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II PS |  | ACME Solar Holdings Private Limited |  | St-II:1200002471 (300 MW | 1200003505 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II PS |  | Azure Power India Private Limited |  | St-II: 1200002401 (500 MW | 1200003586 | [5 empty] | Solar | 267
|  | NR | Rajasthan | Bhadla-II PS |  | Azure Power India Private Limited |  | St-II:1200002403(500 MW | 1200003843 | [5 empty] | Solar | 50
|  | NR | Rajasthan | Bhadla-II PS |  | AMP Energy Green Private Limited |  | St-II:1200002676 (100 MW | 1200003882 | [5 empty] | Solar | 100
|  | NR | Rajasthan | Bhadla-II PS |  | AMP Energy Green Private Limited |  | 1200002987 (Enh.) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bhadla-II PS |  | Eden Renewable Alma Private Limited |  | 1200002554 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II PS |  | Solarpack Corporacion Technologica S.A. |  | 1200002742 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II PS |  | AMP Energy Green Pvt. Ltd. |  | 1200002559 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bhadla-II PS |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED |  | 2200000037 | [6 empty] | Solar | 450
|  | NR | Rajasthan | Bhadla-III |  | JUNIPER GREEN INDIA SIX PRIVATE LIMITED |  | 2200000062 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III |  | FRUGAL ENERGY PRIVATE LIMITED |  | 2200000118 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bhadla-III |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000144 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III |  | SOLARCRAFT POWER INDIA 4 PRIVATE LIMITED |  | 2200000192 | [6 empty] | Solar | 110
|  | NR | Rajasthan | Bhadla-III |  | GREEN INFRA CLEAN ENERGY GENERATION LIMITED |  | 2200000232 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III |  | RENEW SOLAR (SHAKTI SIX) PRIVATE LIMITED |  | 2200000275 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bhadla-III |  | MALUR RENEWABLES PRIVATE LIMITED |  | 2200000266 | [6 empty] | Solar | 650
|  | NR | Rajasthan | Bhadla-III |  | SOLARCRAFT POWER INDIA 4 PRIVATE LIMITED |  | 2200000300 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bhadla-III |  | RENEW SOLAR (SHAKTI SIX) PRIVATE LIMITED |  | 2200000309 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bhadla-III |  | PRERAK SOLAR URJA PRIVATE LIMITED |  | 2200000360 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bhadla-III |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000407 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bhadla-III PS |  | Juniper Green Beta Pvt. Ltd. |  | 412100013, 0312100013 (St-II), 1670400777119 (St-II) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bhadla-III PS |  | Tepsol Sun Sparkle Pvt. Ltd. |  | SW9990897533- M029_D001_A007- 1672319027575, 0212100030 (St-II) | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III PS |  | Juniper Green Beta Private Limited |  | 412100027 (SW5102826596- M029_D001_A003- 1670400777119 (10MW out of 70MW) + 0312100011 (40MW)) | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bhadla-III PS |  | ReNew Solar (Shakti Six) Private Limited |  | 1200003848 | [6 empty] | Solar | 550
|  | NR | Rajasthan | Bhadla-III PS |  | ReNew Solar (Shakti Six) Private Limited |  | 312100004 (Enh.) | [6 empty] | Solar | 450
|  | NR | Rajasthan | Bhadla-III PS |  | Abu Renewables India Private Limited |  | 212100026 | [6 empty] | Solar | 340
|  | NR | Rajasthan | Bhadla-III PS |  | Seven Renewable Power Pvt. Ltd. |  | 212100028 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III PS |  | Frugal Energy Pvt. Ltd. |  | 212100031 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bhadla-III PS |  | Bhadla Three SKP Green Ventures Pvt. Ltd. |  | 212100033 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000516 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000521 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Bhadla-IV |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000522 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | KANTIDA RENEWABLES INDIA PROJECT PRIVATE LIMITED |  | 2200000761 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000811 | [6 empty] | Solar | 765
|  | NR | Rajasthan | Bhadla-IV |  | DEMETER SUN POWER PRIVATE LIMITED |  | 2200000875 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001085 | [6 empty] | Solar | 700
|  | NR | Rajasthan | Bhadla-IV |  | VISMAYA FOUR RENEWABLES PRIVATE LIMITED |  | 2200000910 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bhadla-IV |  | VISMAYA FOUR RENEWABLES PRIVATE LIMITED |  | 2200001284 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner |  | AK RENEWABLE INFRA PRIVATE LIMITED |  | 2200000284 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner PS |  | Shikhar Surya (One) Private Limited |  | 1200003115 | [6 empty] | Solar | 70
|  | NR | Rajasthan | Bikaner PS |  | ReNew Surya Ravi Pvt. Ltd. |  | 1200003301 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner PS |  | Shikhar Surya (One) Private Limited |  | 1200003772 | [6 empty] | Solar | 105
|  | NR | Rajasthan | Bikaner PS |  | Shikhar Surya (One) Private Limited |  | 312100003 | [6 empty] | Solar | 125
|  | NR | Rajasthan | Bikaner-II PS |  | ACME Solar Holdings Private Limited |  | St-II:1200003683 (300 MW | 1200003829 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II PS |  | SJVN Limited |  | St- II:1200003559(1000MW | 1200003937 | [5 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-II PS |  | Onevolt Energy Private Limited |  | St-II:1200003626 (100 MW | 412100004 | [5 empty] | Solar | 62
|  | NR | Rajasthan | Bikaner-II PS |  | NHPC Ltd. |  | St-II:1200003915 (300 MW | 412100006 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II PS |  | Juniper Green Cosmic Private Limited |  | St-II:1200003740 (100 MW | 0412100008 | [5 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-II PS |  | Grian Energy Private Limited |  | St-II: 1200003625 (100 MW) LTA: SW…1544323119(62 MW) | [6 empty] | Solar | 62
|  | NR | Rajasthan | Bikaner-II PS |  | Renew Dinkar Urja Pvt. Ltd. |  | St-II:1200003380 (200 MW | 1200003935 | [5 empty] | Solar | 200
|  | NR | Rajasthan | Bikaner-II PS |  | Amplus Ages Private Limited |  | SW9999482858- M029_D001_A007- 1671556542236 | [6 empty] | Solar | 62
|  | NR | Rajasthan | Bikaner-II PS |  | Prerak Greentech Private Limited |  | 412100025 | [6 empty] | Solar | 226
|  | NR | Rajasthan | Bikaner-II PS |  | Juna Renewable Energy Pvt Ltd |  | 1200003233 | [6 empty] | Solar | 290
|  | NR | Rajasthan | Bikaner-II PS |  | Juna Renewable Energy Pvt Ltd |  | 1200003389 | [6 empty] | Solar | 45
|  | NR | Rajasthan | Bikaner-II PS |  | Amplus Ages Private Limited |  | 1200003624 | [6 empty] | Solar | 38
|  | NR | Rajasthan | Bikaner-II PS |  | Grian Energy Private Limited |  | 1200003625 | [6 empty] | Solar | 38
|  | NR | Rajasthan | Bikaner-II PS |  | Onevolt Energy Private Limited |  | 1200003626 | [6 empty] | Solar | 38
|  | NR | Rajasthan | Bikaner-II PS |  | Khidrat Renewable Energy Private Limited |  | 1200003390 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II PS |  | Litsolaire Energy Private Limited |  | 1200003893 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-II PS |  | ALF Solar Amarsar Private Limited |  | 1200003785 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-II PS |  | ALF Solar Amarsar Private Limited |  | 1200003831 (Enh.) | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-II PS |  | Serentica Renewables India Pvt. Ltd. (erstwhile Sterlite Power Technologies Private Limited) |  | 1200003628 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-II PS |  | Serentica Renewables India Pvt. Ltd. (erstwhile Sterlite Power Technologies Private Limited) |  | 1200003838 | [6 empty] | Solar | 120
|  | NR | Rajasthan | Bikaner-II PS |  | Juniper Nirjara Energy Private Limited |  | 1200003623 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-II PS |  | Prerak Greentech Private Limited |  | 1200003770 | [6 empty] | Solar | 114
|  | NR | Rajasthan | Bikaner-II PS |  | Prerak Greentech Private Limited |  | 1200003839 | [6 empty] | Solar | 60
|  | NR | Rajasthan | Bikaner-II PS |  | ALF Solar Amarsar Private Limited |  | 312100008 (Enh.) | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-II PS |  | Sourya Manthan Renewable Energy Private Limited |  | 212100005 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-II PS 212100007 |  | Soltown Infra Private Limited (Park) | [8 empty] | Solar | 350
|  | NR | Rajasthan | Bikaner-II PS 212100008 |  | Soltown Infra Private Limited (Park) | [8 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-II PS 1200003889 |  | Soltown Infra Private Limited (Park) |  | (Enh.) | [6 empty] | Solar | 200
|  | NR | Rajasthan | Bikaner-III |  | JUNIPER GREEN COSMIC PRIVATE LIMITED |  | 2200000073 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-III |  | SUNBREEZE RENEWABLES NINE PRIVATE LIMITED |  | 2200000111 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-III |  | SUNBREEZE RENEWABLES NINE PRIVATE LIMITED |  | 2200000163 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000172 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000227 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000228 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III |  | MRS BUILDVISION PRIVATE LIMITED |  | 2200000098 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-III |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000179 | [6 empty] | Solar | 500
|  | NR | Rajasthan | Bikaner-III |  | DESHRAJ SOLAR ENERGY PRIVATE LIMITED |  | 2200000184 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-III |  | FIRST ENERGY PRIVATE LIMITED |  | 2200000221 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-III |  | SAIMAA SOLAR PRIVATE LIMITED |  | 2200000167 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000164 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III PS |  | Proteus Energy Private Limited (Park) |  | 212100042 | [6 empty] | Solar | 217
|  | NR | Rajasthan | Bikaner-III PS |  | TP Saurya Limited |  | 212100025 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | SJVN GREEN ENERGY LIMITED |  | 2200000423 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-IV |  | FURIES SOLREN PRIVATE LIMITED |  | 2200000419 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000244 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-IV |  | AVAADA RJBIKANER PRIVATE LIMITED |  | 2200000013 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-IV |  | SOLARCRAFT POWER INDIA 17 PRIVATE LIMITED |  | 2200000210 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | AVAADA RJBIKANER PRIVATE LIMITED |  | 2200000254 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Bikaner-IV |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000289 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | SHUDH SOLAR POWER PRIVATE LIMITED |  | 2200000306 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000308 | [6 empty] | Solar | 700
|  | NR | Rajasthan | Bikaner-IV |  | HAZEL HYBREN PRIVATE LIMITED |  | 2200000334 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | AM GREEN ENERGY PRIVATE LIMITED |  | 2200000319 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | FURIES SOLREN PRIVATE LIMITED |  | 2200000333 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | IRAAX INTERNATIONAL (OPC) PRIVATE LIMITED |  | 2200000343 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | CLEAN MAX GAMMA PRIVATE LIMITED |  | 2200000344 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000373 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000358 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000420 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-IV |  | SUNSURE SOLARPARK FOURTEEN PRIVATE LIMITED |  | 2200000285 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | SAURYA URJA COMPANY OF RAJASTHAN LIMITED |  | 2200000475 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-V |  | IRAAX INTERNATIONAL (OPC) PRIVATE LIMITED |  | 2200000484 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-V |  | IRAAX INTERNATIONAL (OPC) PRIVATE LIMITED |  | 2200000540 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-V |  | AVAADA RJBIKANER PRIVATE LIMITED |  | 2200000561 | [6 empty] | Solar | 136
|  | NR | Rajasthan | Bikaner-V |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000726 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-V |  | SA RENEWABLE INFRA PRIVATE LIMITED |  | 2200000755 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-V |  | VENA ENERGY VINDHYA WIND POWER PRIVATE LIMITED |  | 2200000796 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | SOLARCRAFT POWER INDIA 8 PRIVATE LIMITED |  | 2200000866 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200001021 | [6 empty] | Solar | 350
|  | NR | Rajasthan | Bikaner-V |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200001056 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-V |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200001261 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200001262 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | AVAADA SURYAENERGY PRIVATE LIMITED |  | 2200001254 | [6 empty] | Solar | 560
|  | NR | Rajasthan | Fatehgarh-II |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000387 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Fatehgarh-II |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000396 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Fatehgarh-II |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200001065 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Fatehgarh-II PS |  | NTPC Ltd. |  | St-II:1200002339 (150 MW)(TSNPDCL | 1200003124 | [5 empty] | Solar | 44.17
|  | NR | Rajasthan | Fatehgarh-II PS |  | NTPC Ltd. |  | St-II:1200002497(90 MW) (TSSPDCL | 1200003248 | [5 empty] | Solar | 63.5
|  | NR | Rajasthan | Fatehgarh-II PS |  | NTPC Ltd. |  | St-II:1200002497 (90 MW) (TSNPDCL | 1200003314 | [5 empty] | Solar | 26.5
|  | NR | Rajasthan | Fatehgarh-II PS |  | Adani Renewable Energy Holding Four Limited |  | St-II:1200002430 (500 MW | 1200003684 | [5 empty] | Solar | 500
|  | NR | Rajasthan | Fatehgarh-II PS |  | Eden Renewable Bercy Private Limited |  | St-II:1200002688 (300 MW | 1200003947 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III |  | JSW Renew Energy Five Limited |  | 212100039 | [6 empty] | Storage | 250
|  | NR | Rajasthan | Fatehgarh-III |  | JSW Renew Energy Five Limited |  | 212100040 | [6 empty] | Storage | 250
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | Khaba Renewable Energy Private Limited |  | 1200003502 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | ReNew Surya Jyoti Private Limited |  | 1200002746 | [6 empty] | Solar | 210
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | RENEW SURYA PRATAP PRIVATE LIMITED |  | 1200002778 | [6 empty] | Solar | 210
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | ReNew Solar (Shakti Three) Private Limited |  | 1200003447 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | ReNew Solar (Shakti Five) Private Limited |  | 1200003488 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | ReNew Solar (Shakti Five) Private Limited |  | 1200003496 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | ReNew Samir Shakti Private Limited |  | 1200003504 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | ReNew Samir Shakti Private Limited |  | 1200003514 (Enh. St-II) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | Energizent Power Private Limited |  | 1200002907 | [6 empty] | Solar | 125
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | Energizent Power Private Limited |  | 1200002939 | [6 empty] | Solar | 80
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | XL Xergi Power Private Limited |  | 412100020 (St-II: 1200002847) | [6 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000020 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | SPRNG POWER PRIVATE LIMITED |  | 2200000024 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | SPRNG ENERGY PRIVATE LIMITED |  | 2200000116 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200000123 | [6 empty] | Solar | 95
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | Serentica Renewable India Pvt. Ltd. |  | 212100034 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | Serentica Renewable India Pvt. Ltd. |  | 212100036 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III PS |  | Renew Surya Roshni Private Limited |  | St-II:1200002628(400 MW | 1200003269 | [5 empty] | Solar | 400
|  | NR | Rajasthan | Fatehgarh-III PS |  | ABC Renewable Energy Pvt. Ltd. |  | St-II:1200002699 (400 MW | 1200003096 | [5 empty] | Solar | 400
|  | NR | Rajasthan | Fatehgarh-III PS |  | ReNew Dinkar Jyoti Private Limited |  | St-II:1200003813 (100 MW | 1200003879 | [5 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III PS |  | IB Vogt Solar Seven Private Limited |  | St-II:1200002700 (300 MW | 1200003931 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III PS |  | XL Xergi Power Pvt. Ltd. |  | St-II:1200002847 (400 MW | 412100007 | [5 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-III PS |  | Azure Power India Private Limited |  | St-II:1200003532 (100 MW | 412100002 | [5 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-IV (Sec-I) |  | SPRNG AKSHAYA URJA PRIVATE LIMITED |  | 2200000065 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-IV (Sec-I) |  | BN HYBRID POWER-1 PRIVATE LIMITED |  | 2200000102 | [6 empty] | Hybrid (RHGS) | 180.8
|  | NR | Rajasthan | Fatehgarh-IV (Sec-I) |  | JUNIPER GREEN STELLAR PRIVATE LIMITED |  | 2200000063 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000077 | [6 empty] | Hybrid (RHGS) | 50
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | BN DISPATCHABLE-1 PRIVATE LIMITED |  | 2200000103 | [6 empty] | Hybrid (RHGS) | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | HELIA ENERGY PARK PRIVATE LIMITED |  | 2200000120 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | RADIANT STAR SOLAR PARK PRIVATE LIMITED |  | 2200000212 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | ABREL (RJ) PROJECTS LIMITED |  | 2200000140 | [6 empty] | Solar | 260
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED |  | 2200000138 | [6 empty] | Hybrid (RHGS) | 390
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000187 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | GAMMA RENEWABLES INDIA PROJECT ONE PRIVATE LIMITED |  | 2200000355 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000348 | [6 empty] | Solar | 900
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | GREEN INFRA CLEAN WIND TECHNOLOGY LIMITED |  | 2200000054 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | UTKRRISHT SOLAR ENERGY PRIVATE LIMITED |  | 2200000067 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000186 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000485 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Fatehgarh-IV PS |  | AMP Energy Green Pvt. Ltd. |  | St-II:1200003022 (130 MW | 1200003416 | [5 empty] | Solar | 130
|  | NR | Rajasthan | Fatehgarh-IV PS |  | ABC Renewable Energy Private Limited |  | St-II:1200003002 (380 MW | 1200003531 | [5 empty] | Solar | 380
|  | NR | Rajasthan | Fatehgarh-IV PS |  | Juniper Green Stellar Private Limited |  | 412100009 (St-II: 1200003827, 1200003910, 1200003958, 0312100010 & 0312100012) | [6 empty] | Hybrid | 150
|  | NR | Rajasthan | Fatehgarh-IV PS |  | AMP Energy Green Pvt. Ltd. |  | 412100019 (St-II: 0312100005) | [6 empty] | Hybrid | 120
|  | NR | Rajasthan | Fatehgarh-IV PS |  | ABC RJ Land 01 Private Limited |  | 1200003332 | [6 empty] | Solar | 110
|  | NR | Rajasthan | Fatehgarh-IV PS |  | ABC RJ Land 01 Private Limited |  | 1200003575 | [6 empty] | Solar | 270
|  | NR | Rajasthan | Fatehgarh-IV PS |  | Juniper Green Stellar Private Limited |  | 412100010 (St-II: 1200003827, 1200003910, 1200003958, 0312100010 & 0312100012) | [6 empty] | Hybrid | 150
|  | NR | Rajasthan | Fatehgarh-IV PS |  | AMP Energy Green Pvt. Ltd. |  | 312100007 | [6 empty] | Hybrid | 50
|  | NR | Rajasthan | Fatehgarh-IV PS |  | Cannice Renewables Energy Private Limited |  | 312100019 | [6 empty] | Hybrid | 90
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-I) |  | Luceo Solar Pvt. Ltd. |  | 212100032 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-I) |  | Luceo Solar Pvt. Ltd. |  | 0312100018 (Enhancement) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-II) |  | Helia Energy Park Private Limited |  | 212100035 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-II) |  | Radiant Star Solar Park Private Limited |  | 212100037 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-II) |  | EG Saur Urja Pvt. Ltd. (earlier Tepsol Saur Urja Private Limited) |  | 212100043 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-II) |  | Cannice Renewables Energy Private Limited |  | SW…1671600589106 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-II) |  | Cannice Renewable Energy Private Limited |  | 212100004 | [6 empty] | Solar | 80
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-II) |  | SPRNG PAVANA URJA PRIVATE LIMITED |  | 2200000018 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-II) |  | Sprng Pavana Urja Private Limited |  | 1200003719 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-II) |  | SPRNG PAVANA URJA PRIVATE LIMITED |  | 2200000034 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000850 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000886 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000887 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000888 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000889 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000890 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Jalore |  | SPRNG VAAYU URJA PRIVATE LIMITED |  | 2200001006 | [6 empty] | Solar | 600
|  | NR | Rajasthan Merta-II |  |  | BANYAN ENERGY PRIVATE LIMITED |  | 2200000823 | [6 empty] | Solar | 300
|  | NR | Rajasthan Merta-II |  |  | ACME SOLAR HOLDINGS PRIVATE LIMITED |  | 2200000840 | [6 empty] | Solar | 300
|  | NR | Rajasthan Merta-II |  |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED |  | 2200000848 | [6 empty] | Solar | 300
|  | NR | Rajasthan Merta-II |  |  | GREEN INFRA WIND ENERGY PRIVATE LIMITED |  | 2200000812 | [6 empty] | Solar | 300
|  | NR | Rajasthan Merta-II |  |  | GREEN INFRA WIND ENERGY PRIVATE LIMITED |  | 2200000813 | [6 empty] | Solar | 300
|  | NR | Rajasthan Merta-II |  |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000842 | [6 empty] | Solar | 300
|  | NR | Rajasthan Merta-II |  |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000879 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Ramgarh |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000499 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Ramgarh |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000550 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Ramgarh |  | MIGOS HYBREN PRIVATE LIMITED |  | 2200000618 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Ramgarh |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000661 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Ramgarh |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000662 | [6 empty] | Solar | 284
|  | NR | Rajasthan | Ramgarh |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000672 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Ramgarh |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000599 | [6 empty] | Solar | 500
|  | NR | Rajasthan | Ramgarh PS |  | Adani Renewable Energy Holding Four Ltd. |  | St-II: 1200002432(500 MW | 1200003689 | [5 empty] | Solar | 500
|  | NR | Rajasthan | Ramgarh PS |  | Adani Solar Energy AP Three Ltd. |  | 212100038 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Ramgarh-II |  | ADANI RENEWABLE ENERGY PARK RAJASTHAN LIMITED |  | 2200000600 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Ramgarh-II |  | ADANI RENEWABLE ENERGY PARK RAJASTHAN LIMITED |  | 2200000601 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Ramgarh-II |  | JSW NEO ENERGY LIMITED |  | 2200000689 | [6 empty] | Solar | 700
|  | NR | Rajasthan | Ramgarh-II |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000777 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Ramgarh-II |  | RJS RENEWABLES PRIVATE LIMITED |  | 2200000782 | [6 empty] | Wind | 150
|  | NR | Rajasthan | Ramgarh-II |  | SHN GREEN POWER PRIVATE LIMITED |  | 2200001198 | [6 empty] | Wind | 297
|  | NR | Rajasthan | Sanchore |  | HR SARASWATI ENERGY PRIVATE LIMITED |  | 2200000946 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000644 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | ILLUMINATE HYBREN PRIVATE LIMITED |  | 2200000646 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | VAYUNA RENEWABLES INDIA PROJECT PRIVATE LIMITED |  | 2200000758 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | CESC LTD |  | 2200000518 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000551 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Sirohi |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000779 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | IZHMA SOLAR PRIVATE LIMITED |  | 2200000743 | [6 empty] | Solar | 200
|  | NR | Rajasthan Barmer-III |  |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001026 | [6 empty] | Solar | 200
|  | NR | Rajasthan Barmer-III |  |  | FOXTROT SOLAR RENEWABLES ENERGY PRIVATE LIMITED |  | 2200001057 | [6 empty] | Solar | 100
|  | NR | Rajasthan Barmer-III |  |  | GREEN INFRA RENEWABLE ENERGY FARMS PRIVATE LIMITED |  | 2200001194 | [6 empty] | Solar | 300
|  | NR | Rajasthan Barmer-III |  |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001188 | [6 empty] | Solar | 250
|  | NR | Rajasthan Barmer-III |  |  | FOXTROT SOLAR RENEWABLES ENERGY PRIVATE LIMITED |  | 2200001252 | [6 empty] | Solar | 74
|  | NR | Rajasthan Barmer-III |  |  | FOXTROT SOLAR RENEWABLES ENERGY PRIVATE LIMITED |  | 2200001088 | [6 empty] | Solar | 80
|  | NR | Rajasthan Merta-III |  |  | ENREN-III ENERGY PRIVATE LIMITED |  | 2200000860 | [6 empty] | Solar | 300
|  | NR | Rajasthan Pali |  |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200001089 | [6 empty] | Solar | 300
|  | NR | Rajasthan Pali |  |  | DIYOS THREE RENEWABLES PRIVATE LIMITED |  | 2200001100 | [6 empty] | Solar | 300
|  | NR | UP | Orai |  | BUNDELKHAND SAUR URJA LIMITED |  | 2200000345 | [6 empty] | Solar | 1200
|  | NR | UP | Robertsganj |  | GREENKO UP01 IREP PRIVATE LIMITED |  | 2200000524 | [6 empty] | Pump Storage | 672
|  | NR | UP | Robertsganj |  | GREENKO UP01 IREP PRIVATE LIMITED |  | 2200000525 | [6 empty] | Pump Storage | 672
|  | NR | UP | Robertsganj |  | GREENKO UP01 IREP PRIVATE LIMITED |  | 2200000526 | [6 empty] | Pump Storage | 672
|  | NR | UP | Robertsganj |  | AVAADA WATERBATTERY PRIVATE LIMITED |  | 2200000553 | [6 empty] | Pump Storage | 1120
|  | NR | UP | Robertsganj |  | AVAADA WATERBATTERY PRIVATE LIMITED |  | 2200001086 | [6 empty] | Pump Storage | 520
|  | SR | Andhra Pradesh | Anantapur PS 2200000162 |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | [8 empty] | Wind | 295
|  | SR | Andhra Pradesh | Anantapur PS 2200000372 |  | RENEW VIKRAM SHAKTI PRIVATE LIMITED | [8 empty] | Hybrid (RHGS) | 160 (Solar:40 MW, Wind: 120 MW)
|  | SR | Andhra Pradesh | Anantapur PS 2200000069 |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED | [8 empty] | Wind | 400
|  | SR | Andhra Pradesh | Anantapur PS 2200000273 |  | ABC CT RE PARK (03) PRIVATE LIMITED | [8 empty] | Wind | 250
|  | SR | Andhra Pradesh | Anantapur PS 2200000318 |  | AYANA RENEWABLE POWER FOUR PRIVATE LIMITED | [8 empty] | Wind | 50
|  | SR | Andhra Pradesh | Anantapur PS 2200000032 |  | RENEW VIKRAM SHAKTI PRIVATE LIMITED | [8 empty] | Hybrid (RHGS) | Solar-750MW, Wind:960MW, BESS-288)
|  | SR | Andhra Pradesh | Anantapur PS 2200000271 |  | ABC CLEANTECH PRIVATE LIMITED | [8 empty] | Wind | 250
|  | SR | Andhra Pradesh | Anantapur PS 2200000274 |  | ABC CT RE PARK (02) PRIVATE LIMITED | [8 empty] | Wind | 250
|  | SR | Andhra Pradesh | Anantapur PS 2200000276 |  | ABC CT RE PARK (01) PRIVATE LIMITED | [8 empty] | Wind | 250
|  | SR | Andhra Pradesh | Anantapur PS 2200000713 |  | AMPLUS CENEDUS SOLAR PRIVATE LIMITED | [8 empty] | Wind | 350
|  | SR | Andhra Pradesh | Anantapur PS 2200000583 |  | RENEW VIKRAM SHAKTI PRIVATE LIMITED | [8 empty] | Wind | 140
|  | SR | Andhra Pradesh | Anantapur-II PS |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000872 | [6 empty] | Wind | 349.8
|  | SR | Andhra Pradesh | Anantapur-II PS |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000881 | [6 empty] | Wind | 339.9
|  | SR | Andhra Pradesh | Anantapur-II PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000780 | [6 empty] | Wind | 400
|  | SR | Andhra Pradesh | Anantapur-II PS |  | ORION HYBREN PRIVATE LIMITED |  | 2200001000 | [6 empty] | Hybrid (RHGS) | 300 MW (100 MW Wind, 200 MW Solar)
|  | SR | Andhra Pradesh | Anantapur-II PS |  | JSW NEO ENERGY LIMITED |  | 2200001074 | [6 empty] | Solar | 500
|  | SR | Andhra Pradesh | Anantapur-II PS |  | GREEN INFRA WIND ENERGY PRIVATE LIMITED |  | 2200000820 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh | Kurnool (new) |  | AM GREEN ENERGY PRIVATE LIMITED |  | 2200000012 | [6 empty] | Hybrid (RHGS) | 989 (Solar- 675MW, Wind:314MW)
|  | SR | Andhra Pradesh | Kurnool-III PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000335 | [6 empty] | Solar | Solar-400MW, BESS:380 MWh)
|  | SR | Andhra Pradesh | Kurnool-III PS |  | AMP ENERGY GREEN PRIVATE LIMITED |  | 2200000150 | [6 empty] | Hybrid (RHGS) | Total: 187 MW Solar: 137.5 MW Wind: 49.5 MW
|  | SR | Andhra Pradesh | Kurnool-III PS |  | AMP ENERGY C&I TWELVE PRIVATE LIMITED |  | 2200000231 | [6 empty] | Solar | 100
|  | SR | Andhra Pradesh | Kurnool-III PS |  | ADANI RENEWABLE ENERGY FORTY TWO LIMITED |  | 2200000158 | [6 empty] | Pump Storage | 600
|  | SR | Andhra Pradesh | Kurnool-III PS |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000383 | [6 empty] | Hybrid (RHGS) | Solar: 150MW Wind: 150MW BESS: 30MWh
|  | SR | Andhra Pradesh | Kurnool-III PS |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000236 | [6 empty] | Hybrid (RHGS) | Solar: 150 MW Wind:159 MW
|  | SR | Andhra Pradesh | Kurnool-III PS |  | AMPLUS EVEREST SOLAR PRIVATE LIMITED |  | 2200000543 | [6 empty] | Hybrid (RHGS) | 228(Solar:105M W; Wind: 126 MW)
|  | SR | Andhra Pradesh | Kurnool-III PS |  | AMPLUS IIFA SOLAR PRIVATE LIMITED |  | 2200000544 | [6 empty] | Hybrid (RHGS) | 228(Solar:105M W; Wind: 126 MW)
|  | SR | Andhra Pradesh | Kurnool-III PS |  | INDOSOL SOLAR PRIVATE LIMITED |  | 2200000733 | [6 empty] | Solar | 800
|  | SR | Andhra Pradesh | Kurnool-III PS |  | INDOSOL SOLAR PRIVATE LIMITED |  | 2200000734 | [6 empty] | Solar | 900
|  | SR | Andhra Pradesh | Kurnool-III PS |  | AMP ENERGY GREEN PRIVATE LIMITED |  | 2200000229 | [6 empty] | Hybrid (RHGS) | Solar: 85 MW Wind:118.8 MW
|  | SR | Andhra Pradesh | Kurnool-III PS |  | INDOSOL SOLAR PRIVATE LIMITED |  | 2200000735 | [6 empty] | Solar | 900
|  | SR | Andhra Pradesh | Kurnool-III PS |  | INDOSOL SOLAR PRIVATE LIMITED |  | 2200000736 | [6 empty] | Solar | 900
|  | SR | Andhra Pradesh | Kurnool-III PS |  | ADANI RENEWABLE ENERGY FIFTY ONE LIMITED |  | 2200000508 | [6 empty] | Pump Storage | 1250
|  | SR | Andhra Pradesh | Kurnool-IV PS 2200000844 |  | SAEL INDUSTRIES LIMITED | [8 empty] | Solar | 300
|  | SR | Andhra Pradesh | Kurnool-IV PS 2200001099 |  | PRATAPATI ENERGY (SEVEN) PRIVATE LIMITED | [8 empty] | Hybrid (RHGS) | 354 (Solar-255 MW, Wind- 99MW)
|  | SR | Andhra Pradesh | Nellore PS |  | JINDAL POWER LIMITED |  | 2200000633 | [6 empty] | Solar | 52.6
|  | SR | Andhra Pradesh | NP Kunta PS |  | FIRST ENERGY PRIVATE LIMITED |  | 2200000388 | [6 empty] | Solar | 100
|  | SR | Andhra Pradesh | NP Kunta PS |  | NHPC LIMITED |  | 2200000250 | [6 empty] | Solar | 100
|  | SR | AP | Kurnool (new) |  | Greenko AP01 IREP Pvt. Ltd |  | LTA app no.1200003664 | [6 empty] | Hybrid | 900
|  | SR | AP | Kurnool (new) |  | Greenko AP01 IREP Pvt. Ltd |  | LTA app no. 450200009 | [6 empty] | PSP | 565
|  | SR | AP | Kurnool (new) |  | Greenko AP01 IREP Pvt. Ltd. |  | 0350200006 | [6 empty] | PSP | 260
|  | SR | AP | Ramagundam 1200002271 |  | NTPC Ltd. (Ramagundam FSP) | [8 empty] | Solar | 100
|  | SR | AP | Simhadri |  | NTPC Ltd. (Simhadri FSP) |  | 1200002272 | [6 empty] | Solar | 25
|  | SR | Karnataka Bidar PS |  |  | WELSPUN NARMADA PRIVATE LIMITED |  | 2200000716 | [6 empty] | Hybrid (RHGS) | 250 (150 MW Wind & 100 MW Solar)
|  | SR | Karnataka Bidar PS |  |  | SAEL INDUSTRIES LIMITED |  | 2200000759 | [6 empty] | Solar | 300
|  | SR | Karnataka Bidar PS |  |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000422 | [6 empty] | Hybrid (RHGS) | Solar: 188MW Wind: 201 MW BESS: 30MWh
|  | SR | Karnataka Bidar PS |  |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000640 | [6 empty] | Hybrid (RHGS) | Total: 312 MW Solar: 132 MW Wind:180 MW
|  | SR | Karnataka Bidar PS |  |  | PULSE HYBREN PRIVATE LIMITED |  | 2200001001 | [6 empty] | Solar | 300
|  | SR | Karnataka Bidar PS |  |  | QUEST HYBREN PRIVATE LIMITED |  | 2200001002 | [6 empty] | Solar | 300
|  | SR | Karnataka Bidar PS |  |  | AMPIN ENERGY UTILITY PRIVATE LIMITED |  | 2200000762 | [6 empty] | Hybrid (RHGS) | 185.4 (Solar- 135; Wind 50.4)
|  | SR | Karnataka Bidar PS |  |  | AMPIN ENERGY UTILITY PRIVATE LIMITED |  | 2200000763 | [6 empty] | Hybrid (RHGS) | 185.4 (Solar- 135; Wind 50.4)
|  | SR | Karnataka Bidar PS |  |  | AMPIN ENERGY UTILITY PRIVATE LIMITED |  | 2200000892 | [6 empty] | Hybrid (RHGS) | 185.4 (Solar- 135; Wind 50.4)
|  | SR | Karnataka Bijapur PS |  |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000393 | [6 empty] | Wind | 252
|  | SR | Karnataka Bijapur PS |  |  | TEQ GREEN POWER XVI PRIVATE LIMITED |  | 2200000397 | [6 empty] | Wind | 125
|  | SR | Karnataka Bijapur PS |  |  | TEQ GREEN POWER XVI PRIVATE LIMITED |  | 2200000429 | [6 empty] | Wind | 175
|  | SR | Karnataka Bijapur PS |  |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000447 | [6 empty] | Wind | 50.4
|  | SR | Karnataka Bijapur PS |  |  | UPC RENEWABLES INDIA MANAGEMENT PRIVATE LIMITED |  | 2200000584 | [6 empty] | Wind | 160
|  | SR | Karnataka Bijapur PS |  |  | TEPSOL GREEN ENERGY PRIVATE LIMITED |  | 2200000657 | [6 empty] | Hybrid (RHGS) | 200 (Wind- 160 & Solar-40)
|  | SR | Karnataka Bijapur PS |  |  | EG SOLWIN RENEWABLES PRIVATE LIMITED |  | 2200000687 | [6 empty] | Wind | 100
|  | SR | Karnataka Bijapur PS |  |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000586 | [6 empty] | Wind | 252
|  | SR |  | Karnataka Davangere PS 2200000714 |  | GENTARI RENEWABLES INDIA CASTOR ONE PVT. LTD | [8 empty] | Wind | 350
|  | SR |  | Karnataka Davangere PS 2200000932 |  | JSW NEO ENERGY LIMITED | [8 empty] | Wind | 325
|  | SR |  | Karnataka Davangere PS 2200000876 |  | JADE HYBREN PRIVATE LIMITED | [8 empty] | Hybrid (RHGS) | 300(Solar-200 MW, Wind-100 MW)
|  | SR |  | Karnataka Davangere PS 2200000625 |  | LAYER HYBREN PRIVATE LIMITED | [8 empty] | Hybrid (RHGS) | 140 (100- Solar; 40 Wind)
|  | SR |  | Karnataka Davangere PS 2200000660 |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | [8 empty] | Hybrid (RHGS) | 720(Solar:360 MW; Wind: 360)
|  | SR |  | Karnataka Davangere PS 2200000701 |  | ILLUMINATE HYBREN PRIVATE LIMITED | [8 empty] | Solar | 300
|  | SR |  | Karnataka Davangere PS 2200000700 |  | FURIES SOLREN PRIVATE LIMITED | [8 empty] | Solar | 300
|  | SR |  | Karnataka Davangere PS 2200000702 |  | LAYER HYBREN PRIVATE LIMITED | [8 empty] | Hybrid (RHGS) | 160 (110- Solar; 50 Wind)
|  | SR | Karnataka Gadag PS |  |  | Azure Power India Pvt. Ltd. |  | LTA app no. 451100008 (120 MW) & 0451100003 (50 MW) | [6 empty] | Wind | 170
|  | SR | Karnataka Gadag PS |  |  | Green Infra Wind |  | LTA app no. 451100007 | [6 empty] | Wind | 178.5
|  | SR | Karnataka Gadag PS |  |  | ReNew Naveen Urja Pvt. Ltd |  | LTA app no. 451100009 | [6 empty] | Wind | 300
|  | SR | Karnataka Gadag PS |  |  | Serentica Renewables India Pvt. Ltd |  | 0451100011 | [6 empty] | Hybrid | 132
|  | SR | Karnataka Gadag PS |  |  | Serentica Renewables India Pvt. Ltd |  | 1200003761 | [6 empty] | Hybrid | 107
|  | SR | Karnataka Gadag PS |  |  | Serentica Renewables India Pvt. Ltd |  | 1200003828 | [6 empty] | Hybrid | 66
|  | SR | Karnataka Gadag PS |  |  | Serentica Renewables India Pvt. Ltd |  | 0451100010 | [6 empty] | Hybrid | 165
|  | SR | Tamil Nadu | Karur PS |  | LTA app no. 1200003536 JSW Neo Energy Ltd. (earstwhile JSW Future Energy Ltd.) | [8 empty] | Wind | 150
|  | SR | Tamil Nadu | Karur PS |  | JSW Renew Energy |  | LTA app no. 1200003533 (170 MW) | [6 empty] | Wind | 170
|  | SR | Tamil Nadu | Karur PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000242 | [6 empty] | Wind | 198
|  | SR | Tamil Nadu | Karur PS |  | FIRST ENERGY PRIVATE LIMITED |  | 2200000441 | [6 empty] | Wind | 100
|  | SR | Tamil Nadu | Karur PS |  | JSP GREEN WIND 1 PRIVATE LIMITED |  | 2200000438 | [6 empty] | Wind | 300
|  | SR | Tamil Nadu | Karur PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000448 | [6 empty] | Wind | 93.6
|  | SR | Tamil Nadu | Karur PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000967 | [6 empty] | Wind | 82.5
|  | SR | Tamil Nadu | Karur PS |  | NANNAI SOLAR PARK PRIVATE LIMITED |  | 2200000628 | [6 empty] | Wind | 93
|  | SR | Tamil Nadu | Pugalur |  | SPRNG AKSHAYA URJA PRIVATE LIMITED |  | 2200000197 | [6 empty] | Wind | 52.8
|  | SR | Tamil Nadu | Pugalur |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000394 | [6 empty] | Wind | 151
|  | SR | Tamil Nadu | Pugalur |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000449 | [6 empty] | Wind | 151.2
|  | SR | Tamil Nadu | Tuticorin-II PS |  | GRT JEWELLERS (INDIA) PRIVATE LIMITED |  | 2200000594 | [6 empty] | Solar | 150
|  | WR | Gujarat | Bhuj PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000218 | [6 empty] | Wind | 155
|  | WR | Gujarat | Bhuj PS |  | SEVEN RENEWABLE POWER PRIVATE LIMITED |  | 2200000317 | [6 empty] | Wind | 50
|  | WR | Gujarat | Bhuj PS |  | NLC INDIA LIMITED |  | 2200000386 | [6 empty] | Solar | 200
|  | WR | Gujarat | Bhuj PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000566 | [6 empty] | Wind | 20
|  | WR | Gujarat | Bhuj PS |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000658 | [6 empty] | Wind | 99
|  | WR | Gujarat | Bhuj PS |  | NLC INDIA LIMITED |  | 2200000729 | [6 empty] | Solar | 100
|  | WR | Gujarat | Bhuj PS |  | OYSTER GREEN HYBRID ONE PRIVATE LIMITED |  | 2200000783 | [6 empty] | Wind | 99
|  | WR | Gujarat | Bhuj PS |  | NLC INDIA LIMITED |  | 2200000808 | [6 empty] | Wind | 50
|  | WR | Gujarat | Bhuj PS |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED |  | 2200000981 | [6 empty] | Wind | Wind - 75.6, BESS - 20)
|  | WR | Gujarat | Bhuj PS |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED |  | 2200000634 | [6 empty] | Solar | 600
|  | WR | Gujarat | Bhuj-II PS |  | SJVN GREEN ENERGY LIMITED |  | 2200000204 | [6 empty] | Solar | 360
|  | WR | Gujarat | Bhuj-II PS |  | ABREL (RJ) PROJECTS LIMITED |  | 2200000288 | [6 empty] | Hybrid (RHGS) | 314
|  | WR | Gujarat | Bhuj-II PS |  | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED |  | 2200000321 | [6 empty] | Hybrid (RHGS) | 362
|  | WR | Gujarat | Bhuj-II PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000382 | [6 empty] | Solar | 350
|  | WR | Gujarat | Bhuj-II PS |  | CGE RENEWABLES PRIVATE LIMITED |  | 2200000389 | [6 empty] | Hybrid (RHGS) | Wind: 30 MW Solar: 60 MW
|  | WR | Gujarat | Bhuj-II PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000431 | [6 empty] | Wind | 50
|  | WR | Gujarat | Bhuj-II PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000444 | [6 empty] | Solar | 100
|  | WR | Gujarat | Bhuj-II PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000497 | [6 empty] | Wind | 100
|  | WR | Gujarat | Bhuj-II PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000537 | [6 empty] | Solar | 300
|  | WR | Gujarat | Jam Khambhaliya PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000180 | [6 empty] | Wind | 500
|  | WR | Gujarat | Jam Khambhaliya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000142 | [6 empty] | Hybrid (RHGS) | 25 MW Wind + 25 MW Solar
|  | WR | Gujarat | Jam Khambhaliya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000190 | [6 empty] | Wind | 100
|  | WR | Gujarat | Jam Khambhaliya PS |  | Powerica Limited |  | 0230700018 | [6 empty] | Wind | 53
|  | WR | Gujarat | Jam Khambhaliya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000209 | [6 empty] | Wind | 200
|  | WR | Gujarat | Jam Khambhaliya PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000565 | [6 empty] | Wind | 80
|  | WR | Gujarat | Jam Khambhaliya PS |  | MOUNTING RENEWABLE POWER LIMITED |  | 2200000246 | [6 empty] | Hybrid (RHGS) | 250
|  | WR | Gujarat | Jam Khambhaliya PS |  | AIRPOWER WINDFARMS PRIVATE LIMITED |  | 2200000261 | [6 empty] | Wind | 175
|  | WR | Gujarat | Jam Khambhaliya PS |  | ACME SUN POWER PRIVATE LIMITED |  | 2200000263 | [6 empty] | Wind | 400
|  | WR | Gujarat | Jam Khambhaliya PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000241 | [6 empty] | Wind | 545
|  | WR | Gujarat | Jam Khambhaliya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000445 | [6 empty] | Wind | 100
|  | WR | Gujarat | Jam Khambhaliya PS |  | POWERICA LIMITED |  | 2200000473 | [6 empty] | Wind | 50
|  | WR | Gujarat | Jam Khambhaliya PS |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED |  | 2200000503 | [6 empty] | Wind | 308.49
|  | WR | Gujarat | Jam Khambhaliya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000556 | [6 empty] | Wind | 200
|  | WR | Gujarat | Jam Khambhaliya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000253 | [6 empty] | Wind | 100
|  | WR | Gujarat | Jam Khambhaliya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000379 | [6 empty] | Wind | 200
|  | WR | Gujarat | Jam Khambhaliya PS |  | MALAREN SOLAR PRIVATE LIMITED |  | 2200000337 | [6 empty] | Solar | 150
|  | WR | Gujarat | KPS1 |  | ADANI GREEN ENERGY LIMITED |  | 2200000478 | [6 empty] | Hybrid (RHGS) | 650
|  | WR | Gujarat | KPS1 |  | ADANI GREEN ENERGY LIMITED |  | 2200000479 | [6 empty] | Hybrid (RHGS) | 100
|  | WR | Gujarat | KPS1 |  | ADANI GREEN ENERGY LIMITED |  | 2200000784 | [6 empty] | Wind | 60
|  | WR | Gujarat | KPS-1 (Sec-I) |  | Adani Green Energy Limited Connectivity: 230700008; LTA: 430700009 (1050MW); |  | 230700008 | [6 empty] | Hybrid | 1250
|  | WR | Gujarat | KPS-1 (Sec-I) |  | Adani Green Energy Ltd. |  | 1670426092248 | [6 empty] | Hybrid | 1050
|  | WR | Gujarat | KPS-1 (Sec-II) |  | Adani Green Energy Limited Connectivity: 230700006; LTA: 430700007 (1000MW); |  | 230700006 | [6 empty] | Hybrid | 1200
|  | WR | Gujarat | KPS-1 (Sec-II) |  | Adani Green Energy Limited Connectivity: 230700007; LTA: 430700008 (1000MW); |  | 230700007 | [6 empty] | Hybrid | 1166.4
|  | WR | Gujarat | KPS-1 (Sec-II) |  | Adani Green Energy Limited Connectivity: 1670426695890; LTA: 1670929494955 (250MW); |  | SW6949744157- M029_D001_A002- 1670426695890 | [6 empty] | Wind | 250
|  | WR | Gujarat | KPS-1 (Sec-II) |  | Sarjan Realities Pvt. Ltd. (SRPL) |  | 0230700011 | [6 empty] | Hybrid | 1150
|  | WR | Gujarat | KPS-2 |  | Gujarat State Electricity Corporation Limited Connectivity: 1200003331 (600MW); LTA: 1200003326 (100MW) & 1200003327 (500MW); |  | 1200003331 | [6 empty] | Solar | 600
|  | WR | Gujarat | KPS-2 |  | Gujarat Industries Power Company Limited Connectivity: 1200003371; LTA: 1200003372; |  | 1200003371 | [6 empty] | Solar | 600
|  | WR | Gujarat | KPS-2 |  | NTPC Renewable Energy Limited (NREL) Connectivity: 1200003585 (265MW); LTA: 1200003712 (265+100MW); |  | 1200003585 | [6 empty] | Solar | 265
|  | WR | Gujarat | KPS-2 |  | NTPC Renewable Energy Limited (NREL) Connectivity: 1200003733 (100MW); LTA: 1200003712 (265+100MW); |  | 1200003733 | [6 empty] | Solar | 100
|  | WR | Gujarat | KPS-2 |  | NTPC Renewable Energy Limited (NREL) Connectivity: 1200003953 (890MW); LTA: 0430700002 (500); |  | 1200003953 | [6 empty] | Solar | 890
|  | WR | Gujarat | KPS-2 |  | Gujarat State Electricity Corporation Limited Connectivity: 230700005; LTA: 430000002; |  | 230700005 | [6 empty] | Solar | 1000
|  | WR | Gujarat | KPS-2 |  | NTPC Renewable Energy Limited (NREL) |  | 1200003953 | [6 empty] | Solar | 390
|  | WR | Gujarat | KPS-2 |  | NTPC Renewable Energy Limited (NTPC REL) |  | 0330700007 | [6 empty] | Solar | 300
|  | WR | Gujarat | KPS3 |  | ADANI GREEN ENERGY LIMITED |  | 2200000476 | [6 empty] | Hybrid (RHGS) | 1250
|  | WR | Gujarat | KPS3 |  | ADANI GREEN ENERGY LIMITED |  | 2200000477 | [6 empty] | Hybrid (RHGS) | 75
|  | WR | Gujarat | KPS3 |  | ADANI GREEN ENERGY LIMITED |  | 2200000602 | [6 empty] | Hybrid (RHGS) | 65 MW (Solar: 50MW Wind: 35MW)
|  | WR | Gujarat | KPS3 |  | ADANI GREEN ENERGY LIMITED |  | 2200000786 | [6 empty] | Wind | 195
|  | WR | Gujarat | KPS3 |  | ADANI GREEN ENERGY LIMITED |  | 2200000953 | [6 empty] | Hybrid (RHGS) | 1530 MW (Solar:1400 MW & Wind:130 MW)
|  | WR | Gujarat | KPS-3 (Sec-I) |  | Adani Green Energy Limited Connectivity: 230700009; LTA: 430700010 (1050MW); |  | 230700009 | [6 empty] | Hybrid | 1250
|  | WR | Gujarat | KPS-3 (Sec-I) |  | Sarjan Realities Pvt. Ltd. (SRPL) |  | 0230700012 | [6 empty] | Hybrid | 1332
|  | WR | Gujarat | KPS-3 (Sec-I) |  | Sarjan Realities Pvt. Ltd. (SRPL) |  | 0230700014 | [6 empty] | Hybrid | 1100
|  | WR | Gujarat | KPS-3 (Sec-I) |  | NTPC Renewable Energy Limited |  | 0230700010 | [6 empty] | Solar | 1200
|  | WR | Gujarat | KPS-3 (Sec-II) |  | Sarjan Realities Pvt. Ltd. (SRPL) |  | 0230700013 | [6 empty] | Hybrid | 1250
|  | WR | Gujarat | KPS-3 (Sec-II) |  | NHPC Limited |  | 0230700015 | [6 empty] | Solar | 600
|  | WR | Gujarat | Lakadiya PS |  | AVAADA INCLEAN PRIVATE LIMITED |  | 2200000011 | [6 empty] | Solar | 50
|  | WR | Gujarat | Lakadiya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000131 | [6 empty] | Solar | 300
|  | WR | Gujarat | Lakadiya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000200 | [6 empty] | Solar | 200
|  | WR | Gujarat | Lakadiya PS |  | ARCELORMITTAL NIPPON STEEL INDIA LIMITED |  | 2200000324 | [6 empty] | Hybrid (RHGS) | 550 (Wind 250MW+Solar 300MW)
|  | WR | Gujarat | Lakadiya PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000610 | [6 empty] | Hybrid (RHGS) | 480 (240 MW: Wind 240 MW: Solar)
|  | WR | Gujarat | Lakadiya PS |  | RDS SOLAR PARK PRIVATE LIMITED |  | 2200000639 | [6 empty] | Solar | 350
|  | WR | Gujarat | Lakadiya PS |  | PERCENTUM RENEWABLES PRIVATE LIMITED |  | 2200000673 | [6 empty] | Hybrid (RHGS) | 100MW: Solar 200MW: Wind Revised to 50MW Solar & 98MW Wind.
|  | WR | Gujarat | Lakadiya PS |  | RENEW SOLAR (SHAKTI EIGHT) PRIVATE LIMITED |  | 2200000341 | [6 empty] | Solar | 200
|  | WR | Gujarat | Lakadiya PS |  | TEQ GREEN POWER XVI PRIVATE LIMITED |  | 2200000398 | [6 empty] | Wind | 76
|  | WR | Gujarat | Lakadiya PS |  | RENEW SOLAR (SHAKTI EIGHT) PRIVATE LIMITED |  | 2200000403 | [6 empty] | Solar | 100
|  | WR | Gujarat | Lakadiya PS |  | TEQ GREEN POWER XVI PRIVATE LIMITED |  | 2200000427 | [6 empty] | Wind | 76
|  | WR | Gujarat | Lakadiya PS |  | TEQ GREEN POWER XVII PRIVATE LIMITED |  | 2200000311 | [6 empty] | Hybrid (RHGS) | 300 (200MW Solar & 100MW Wind: as per letter dated 30.11.2023 from applicant)
|  | WR | Gujarat | Lakadiya PS |  | GANEKO SOLAR PRIVATE LIMITED |  | 2200000458 | [6 empty] | Hybrid (RHGS) | 337.36
|  | WR | Gujarat | Lakadiya PS |  | GANEKO SOLAR PRIVATE LIMITED |  | 2200000515 | [6 empty] | Hybrid (RHGS) | 11.63
|  | WR | Gujarat | Lakadiya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000500 | [6 empty] | Wind | 150
|  | WR | Gujarat | Lakadiya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000511 | [6 empty] | Solar | 200
|  | WR | Gujarat | Radhanesda PS |  | SPRNG POWER EARTH PRIVATE LIMITED |  | 2200000247 | [6 empty] | Solar | 250
|  | WR | Gujarat | Radhanesda PS |  | SPRNG ENERGY PRIVATE LIMITED |  | 2200000461 | [6 empty] | Solar | 100
|  | WR | Gujarat | Radhanesda PS |  | SPRNG ENERGY PRIVATE LIMITED |  | 2200000460 | [6 empty] | Solar | 150
|  | WR | Gujarat | Radhanesda PS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000546 | [6 empty] | Solar | 50
|  | WR | Gujarat | Raghanesda PS |  | JSW NEO ENERGY LIMITED |  | 2200001014 | [6 empty] | Solar | 200
|  | WR | Gujarat | Raghanesda PS |  | JSW NEO ENERGY LIMITED |  | 2200001020 | [6 empty] | Solar | 200
|  | WR | Gujarat | Raghanesda PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000993 | [6 empty] | Solar | 300
|  | WR | Gujarat | Raghanesda PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000988 | [6 empty] | Solar | 300
|  | WR | Gujarat | Raghanesda PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000989 | [6 empty] | Solar | 100
|  | WR | Gujarat | Raghanesda PS |  | SPRNG WIND ENERGY PRIVATE LIMITED |  | 2200000612 | [6 empty] | Solar | 200
|  | WR | Gujarat | Raghanesda PS |  | SPRNG OJAS PRIVATE LIMITED |  | 2200000614 | [6 empty] | Solar | 200
|  | WR | Gujarat | Raghanesda PS |  | SPRNG VAYU KIRAN PRIVATE LIMITED |  | 2200000650 | [6 empty] | Solar | 200
|  | WR | Madhya Pradesh | Indore (PG) |  | RENEW URJA SHACHAR PRIVATE LIMITED |  | 2200000070 | [6 empty] | Wind | 300
|  | WR | Madhya Pradesh | Indore (PG) |  | RENEW SAMIR URJA PRIVATE LIMITED |  | 2200000298 | [6 empty] | Wind | 300
|  | WR | Madhya Pradesh | Mandsaur PS |  | GREENKO MP01 IREP PRIVATE LIMITED |  | 2200000089 | [6 empty] | Pump Storage | 504
|  | WR | Madhya Pradesh | Mandsaur PS |  | GREENKO MP01 IREP PRIVATE LIMITED |  | 2200000090 | [6 empty] | Pump Storage | 504
|  | WR | Madhya Pradesh | Mandsaur PS |  | GREENKO MP01 IREP PRIVATE LIMITED |  | 2200000091 | [6 empty] | Pump Storage | 504
|  | WR | Madhya Pradesh | Mandsaur PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000924 | [6 empty] | Solar | 150
|  | WR | Madhya Pradesh | Mandsaur PS |  | BHOJRAJ RENEWABLES ENERGY PRIVATE LIMITED |  | 2200000899 | [6 empty] | Wind | 300
|  | WR | Madhya Pradesh | Mandsaur PS |  | ADYANT ENERSOL PRIVATE LIMITED |  | 2200000976 | [6 empty] | Hybrid (RHGS) | 84 MW (60 MW Solar + 24 MW Wind)
|  | WR | Madhya Pradesh | Mandsaur PS |  | GANEKO ONE ENERGY PRIVATE LIMITED |  | 2200000720 | [6 empty] | Hybrid (RHGS) | Solar - 255 MW, Wind - 99 MW
|  | WR | Madhya Pradesh | Mandsaur PS |  | ADYANT POWER PRIVATE LIMITED |  | 2200000798 | [6 empty] | Hybrid (RHGS) | 200 (SOLAR 101 MW WIND 99 MW)
|  | WR | Madhya Pradesh | Mandsaur PS |  | ASNEN SOLAR PRIVATE LIMITED |  | 2200000752 | [6 empty] | Solar | 200
|  | WR | Madhya Pradesh | Mandsaur PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000428 | [6 empty] | Wind | 300
|  | WR | Madhya Pradesh | Neemuch PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000728 | [6 empty] | Solar | 500
|  | WR | Madhya Pradesh | Neemuch PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000938 | [6 empty] | Solar | 500
|  | WR | Madhya Pradesh | Pachora PS |  | BLUE LEAF ENERGY RENEWABLES PRIVATE LIMITED (BLERPL) |  | 2200000030 | [6 empty] | Solar | 235
|  | WR | Madhya Pradesh | Pachora PS |  | VEH SAUR URJA PRIVATE LIMITED (VSUPL ) |  | 2200000085 | [6 empty] | Wind | 163.2
|  | WR | Madhya Pradesh | Pachora PS |  | ABENERGIA RENEWABLES PRIVATE LIMITED |  | 2200000086 | [6 empty] | Hybrid (RHGS) | 100
|  | WR | Madhya Pradesh | Pachora PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000267 | [6 empty] | Solar | 250
|  | WR | Madhya Pradesh | Pachora PS |  | ABENERGIA RENEWABLES PRIVATE LIMITED |  | 2200000342 | [6 empty] | Hybrid (RHGS) | 81
|  | WR | Madhya Pradesh | Pachora PS |  | BHOJRAJ DEVELOPERS PRIVATE LIMITED |  | 2200000404 | [6 empty] | Hybrid (RHGS) | Wind: 160 MW Solar: 26 MW
|  | WR | Madhya Pradesh | Pachora PS |  | VEH DAMEN POWER PRIVATE LIMITED |  | 2200000356 | [6 empty] | Wind | 76.8
|  | WR | Madhya Pradesh | Pachora PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000502 | [6 empty] | Solar | 400
|  | WR | Madhya Pradesh | Pachora PS |  | AVAADA ENERGY PRIVATE LIMITED (AEPL) |  | 2200000082 | [6 empty] | Solar | 50
|  | WR | Madhya Pradesh | Pachora PS |  | JADE HYBREN PRIVATE LIMITED |  | 2200000617 | [6 empty] | Solar | 300
|  | WR | Madhya Pradesh | Pachora PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000817 | [6 empty] | Hybrid (RHGS) | 334 (250 MW Solar + 84 MW Wind)
|  | WR | Madhya Pradesh | Pachora PS |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000883 | [6 empty] | Wind | 297
|  | WR | Madhya Pradesh | Pachora PS |  | WAFT ENERGY PRIVATE LIMITED |  | 2200000923 | [6 empty] | Wind | 100
|  | WR | Madhya Pradesh | Pachora PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000956 | [6 empty] | Solar | 240
|  | WR | Madhya Pradesh | Pachora PS |  | OYSTER GREEN HYBRID THREE PRIVATE LIMITED |  | 2200000995 | [6 empty] | Hybrid (RHGS) | 140 (Solar: 100 MW Wind: 40 MW)
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG AKSHAYA URJA PRIVATE LIMITED |  | 2200000039 | [6 empty] | Wind | 100
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000028 | [6 empty] | Wind | 42
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000022 | [6 empty] | Wind | 100
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG AKSHAYA URJA PRIVATE LIMITED |  | 2200000133 | [6 empty] | Wind | 67.2
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000340 | [6 empty] | Wind | 82
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000819 | [6 empty] | Wind | 16.8
|  | WR | Maharash tra | Dhule PS (Sec- I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000081 | [6 empty] | Wind | 50
|  | WR | Maharash tra | Dhule PS (Sec- I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001036 | [6 empty] | Wind | 160
|  | WR | Maharash tra | Dhule PS (Sec- I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001035 | [6 empty] | Wind | 80
|  | WR | Maharash tra | Kallam PS |  | TEQ GREEN POWER XI PRIVATE LIMITED (TGPXIPL) |  | 2200000035 | [6 empty] | Wind | 29.7
|  | WR | Maharash tra | Kallam PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000193 | [6 empty] | Wind | 101
|  | WR | Maharash tra | Kallam PS |  | TORRENT SOLAR POWER PRIVATE LIMITED |  | 2200000198 | [6 empty] | Wind | 250
|  | WR | Maharash tra | Kallam PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000277 | [6 empty] | Wind | 200
|  | WR | Maharash tra | Kallam PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000302 | [6 empty] | Wind | 100
|  | WR | Maharash tra | Kallam PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200001090 | [6 empty] | Wind | 150
|  | WR | Maharash tra | Kallam PS |  | Serentica Renewables India 4 Pvt. Ltd. (SRI4PL) |  | 0231400004 | [6 empty] | Wind | 10
|  | WR | Maharash tra | Kallam PS |  | Serentica Renewables India 4 Pvt. Ltd. (SRI4PL) |  | 0331400007 | [6 empty] | Wind | 140
|  | WR | Maharash tra | Kallam PS |  | ReNew Green (MHP One) Private Limited |  | 1200003942 | [6 empty] | Wind | 33
|  | WR | Maharash tra | Kallam PS |  | TEQ Green Power XI Pvt. Ltd.(TGPXIPL) |  | 1200003901 | [6 empty] | Wind | 200
|  | WR | Maharash tra | Kallam PS |  | TEQ Green Power XI Pvt. Ltd.(TGPXIPL) |  | 1200003944 | [6 empty] | Wind | 99
|  | WR | Maharash tra | Kallam PS |  | TEQ Green Power XI Pvt. Ltd.(TGPXIPL) |  | 0331400002 | [6 empty] | Wind | 21.6
|  | WR | Maharash tra | Kallam PS |  | Torrent Solar Power Private Limited (TSPPL) |  | 1670224223993 | [6 empty] | Wind | 66
|  | WR | Maharash tra | Kallam PS |  | Torrent Solar Power Private Limited (TSPPL) |  | 0331400013 | [6 empty] | Wind | 92
|  | WR | Maharash tra | Kallam PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000395 | [6 empty] | Wind | 101
|  | WR | Maharash tra | Kallam PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000450 | [6 empty] | Wind | 100.8
|  | WR | Maharash tra | Kallam PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000075 | [6 empty] | Wind | 50
|  | WR | Maharash tra | Kallam PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000353 | [6 empty] | Wind | 250
|  | WR | Maharash tra | Parli |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000747 | [6 empty] | Wind | 180
|  | WR | Maharash tra | Parli (New) |  | Renew Pawan Shakti Private Limited (RPSPL) |  | 0231400018 | [6 empty] | Wind | 277
|  | WR | Maharash tra | Parli (New) |  | Renew Pawan Shakti Private Limited (RPSPL) |  | 0331400012 | [6 empty] | Wind | 23
|  | WR | Maharash tra | Parli PG SS |  | Renew Tej Shakti Private Limited(RTSPL) |  | 0231400008 | [6 empty] | Wind | 180
|  | WR | Maharash tra | Parli PG SS |  | Renew Tej Shakti Private Limited(RTSPL) |  | 0231400009 | [6 empty] | Wind | 69
|  | WR | Maharash tra | Parli PG SS |  | Renew Tej Shakti Private Limited(RTSPL) |  | 0231400010 | [6 empty] | Wind | 51
|  | WR | Maharash tra | Solapur PG |  | ReNew Green Energy Solutions Pvt. Ltd. |  | 0331400004 | [6 empty] | Solar | 32
|  | WR | Maharash tra | Solapur PG |  | ReNew Green Energy Solutions Pvt. Ltd. |  | 1670048864400 | [6 empty] | Solar | 50
|  | WR | Maharash tra | Solapur PG |  | ReNew Green Energy Solutions Pvt. Ltd. |  | 0331400010 | [6 empty] | Solar | 70
|  | WR | Maharash tra | Solapur PG |  | ReNew Green Energy Solutions Pvt. Ltd. |  | 0331400014 | [6 empty] | Solar | 100
|  | WR | Maharash tra | Solapur PG |  | RENEW GREEN ENERGY SOLUTIONS PRIVATE LIMITED |  | 2200000155 | [6 empty] | Wind | 73
|  | WR | Maharash tra | Solapur PG |  | JSW RENEW ENERGY THIRTEEN LIMITED |  | 2200001148 | [6 empty] | Solar | 300
|  | WR | Maharash tra | Solapur PG |  | WAAREE FOREVER ENERGIES PRIVATE LIMITED |  | 2200001158 | [6 empty] | Solar | 1000
|  | WR | Maharash tra | Solapur PS |  | SOLARCRAFT POWER INDIA 7 PRIVATE LIMITED |  | 2200000270 | [6 empty] | Wind | 52.8
|  | WR | Maharash tra | Solapur PS |  | JSW NEO ENERGY LIMITED |  | 2200000718 | [6 empty] | Wind | 300
|  | WR | Maharash tra | Solapur PS |  | SOLARCRAFT POWER INDIA 16 PVT. LTD. |  | 2200000440 | [6 empty] | Hybrid (RHGS) | Wind - 191.4 MW, Solar - 56 MW, BESS - 91 MW)
|  | WR | Maharash tra | Solapur PS |  | SKADAR SOLAR PRIVATE LIMITED |  | 2200000754 | [6 empty] | Solar | 200
|  | WR | Maharash tra | Solapur PS |  | SOLARCRAFT POWER INDIA 20 PRIVATE LIMITED |  | 2200000795 | [6 empty] | Hybrid (RHGS) | Wind - 66 MW, Solar - 18.75 MW, BESS - 12.56MW
|  | WR | Maharash tra | Solapur PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000083 | [6 empty] | Wind | 50
|  | WR | Maharash tra | Solapur PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000132 | [6 empty] | Hybrid (RHGS) | 25 MW Wind + 25 MW Solar
|  | WR | Maharash tra | Solapur PS |  | GANEKO TWO ENERGY PRIVATE LIMITED |  | 2200001008 | [6 empty] | Hybrid (RHGS) | 354 MW (Solar: 255 Wind: 99)
|  | WR | Maharash tra | South Kalamb 2200000177 |  | THE TATA POWER COMPANY LIMITED | [8 empty] | Pump Storage | 1150
|  | WR | MP | Mandsaur PS |  | WAAREE RENEWABLE TECHNOLOGIES LIMITED |  | 2200001192 | [6 empty] | Solar | 300
|  | WR | MP | Mandsaur PS |  | ADYANT ENERSOL PRIVATE LIMITED |  | 2200001214 | [6 empty] | Hybrid (RHGS) | 164 MW Hybrid (NTPC LOA: 70 MW Solar + 24 MW Wind and SJVN LOA: 70 MW Wind)
|  | WR | MP | Mandsaur PS |  | ACME SOLAR HOLDINGS LIMITED |  | 2200001289 | [6 empty] | Solar | 200
|  | WR | MP | Mandsaur PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001280 | [6 empty] | Solar | 300
|  | WR | MP | Mandsaur PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001279 | [6 empty] | Solar | 300
|  | WR | MP | Mandsaur PS |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED |  | 2200001037 | [6 empty] | Hybrid (RHGS) | Solar- 135 MW Wind - 160 MW BESS - 40
|  | WR | MP | Neemuch PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000991 | [6 empty] | Solar | 200
|  | WR | MP | Rajgarh SS |  | Sprng Vayu Vidyut Pvt Ltd (SVVPL) |  | 1200003510 | [6 empty] | Wind | 50.4
|  | WR | MP | Rajgarh SS |  | Sprng Vayu Vidyut Pvt Ltd (SVVPL) |  | 1200003345 | [6 empty] | Wind | 55.44
|  | WR | MP | Rajgarh SS |  | Sprng Vayu Vidyut Pvt Ltd (SVVPL) |  | 0331300005 | [6 empty] | Wind | 50.4
|  | WR | MP | Rajgarh SS |  | Veh Jayin Renewables Private Limited |  | 0231300002 | [6 empty] | Wind | 151.8
|  | WR | Maharashtra | Solapur PG |  | NTPC LIMITED |  | 2200001878 | [6 empty] | Solar | 13
|  | WR | Gujarat | Lakadiya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000131 | [6 empty] | Solar | 300
|  | WR | Gujarat | Lakadiya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000200 | [6 empty] | Solar | 200
|  | WR | Gujarat | Bhuj PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000218 | [6 empty] | Wind | 155
|  | WR | Madhya Pradesh | Indore (PG) |  | RENEW URJA SHACHAR PRIVATE LIMITED |  | 2200000070 | [6 empty] | Wind | 300
|  | WR | Gujarat | KPS-2 (Sec-I) |  | Gujarat State Electricity Corporation Limited Connectivity: 1200003331 (600MW); LTA: 1200003326 (100MW) & 1200003327 (500MW); |  | 1200003331 | [6 empty] | Solar | 600
|  | WR | Gujarat | KPS-2 (Sec-I) |  | Gujarat Industries Power Company Limited Connectivity: 1200003371; LTA: 1200003372; |  | 1200003371 | [6 empty] | Solar | 600
|  | WR | Gujarat | KPS-2 (Sec-II) |  | NTPC Renewable Energy Limited (NREL) Connectivity: 1200003585 (265MW); LTA: 1200003712 (265+100MW); |  | 1200003585 | [6 empty] | Solar | 265
|  | WR | Gujarat | KPS-2 (Sec-II) |  | NTPC Renewable Energy Limited (NREL) Connectivity: 1200003733 (100MW); LTA: 1200003712 (265+100MW); |  | 1200003733 | [6 empty] | Solar | 100
|  | WR | Gujarat | KPS-2 (Sec-II) |  | NTPC Renewable Energy Limited (NREL) Connectivity: 1200003953 (890MW); LTA: 0430700002 (500); |  | 1200003953 | [6 empty] | Solar | 890
|  | WR | Maharashtra | Parli PG SS |  | Renew Tej Shakti Private Limited(RTSPL) |  | 0231400008 | [6 empty] | Wind | 180
|  | WR | Maharashtra | Parli PG SS |  | Renew Tej Shakti Private Limited(RTSPL) |  | 0231400009 | [6 empty] | Wind | 69
|  | WR | Maharashtra | Parli PG SS |  | Renew Tej Shakti Private Limited(RTSPL) |  | 0231400010 | [6 empty] | Wind | 51
|  | SR | Tamil Nadu | Karur PS |  | JSW NEO ENERGY LIMITED |  | 2200000818 | [6 empty] | Hybrid (RHGS) | 175
|  | WR | Gujarat | Bhuj PS |  | AYANA RENEWABLE POWER FOUR PRIVATE LIMITED |  | 2200000239 | [6 empty] | Hybrid (RHGS) | 129.9
|  | WR | Gujarat | KPS-1 (Sec-I) |  | Adani Green Energy Limited Connectivity: 230700008; LTA: 430700009 (1050MW); |  | 230700008 | [6 empty] | Hybrid (RHGS) | 1250
|  | WR | Gujarat | KPS-1 (Sec-II) |  | Adani Green Energy Limited Connectivity: 230700006; LTA: 430700007 (1000MW); |  | 230700006 | [6 empty] | Hybrid (RHGS) | 1200
|  | WR | Gujarat | KPS-1 (Sec-II) |  | Adani Green Energy Limited Connectivity: 230700007; LTA: 430700008 (1000MW); |  | 230700007 | [6 empty] | Hybrid (RHGS) | 1166.4
|  | WR | Gujarat | KPS-2 (Sec-I) |  | Gujarat State Electricity Corporation Limited Connectivity: 230700005; |  | 230700005 | [6 empty] | Solar | 1000
|  | WR | Gujarat | KPS-3 (Sec-I) |  | Adani Green Energy Limited Connectivity: 230700009; LTA: 430700010 (1050MW); |  | 230700009 | [6 empty] | Hybrid (RHGS) | 1250
|  | WR | Gujarat | Lakadiya PS |  | AVAADA INCLEAN PRIVATE LIMITED |  | 2200000011 | [6 empty] | Solar | 50
|  | WR | Maharashtra | Solapur PG |  | RENEW GREEN ENERGY SOLUTIONS PRIVATE LIMITED |  | 2200000155 | [6 empty] | Wind | 73
|  | WR | Maharashtra | Kallam PS |  | Serentica Renewables India 4 Pvt. Ltd. (SRI4PL) |  | 0231400004 | [6 empty] | Wind | 10
|  | WR | Maharashtra | Kallam PS |  | Serentica Renewables India 4 Pvt. Ltd. (SRI4PL) |  | 0331400007 | [6 empty] | Wind | 140
|  | WR | Maharashtra | Kallam PS |  | ReNew Green (MHP One) Private Limited |  | 1200003942 | [6 empty] | Wind | 33
|  | WR | Maharashtra | Kallam PS |  | TEQ Green Power XI Pvt. Ltd.(TGPXIPL) |  | 1200003901 | [6 empty] | Wind | 200
|  | WR | Maharashtra | Kallam PS |  | TEQ Green Power XI Pvt. Ltd.(TGPXIPL) |  | 1200003944 | [6 empty] | Wind | 99
|  | WR | Maharashtra | Kallam PS |  | TEQ Green Power XI Pvt. Ltd.(TGPXIPL) |  | 0331400002 | [6 empty] | Wind | 21.6
|  | WR | Maharashtra | Kallam PS |  | Torrent Solar Power Private Limited (TSPPL) |  | 1670224223993 | [6 empty] | Wind | 66
|  | WR | Maharashtra | Kallam PS |  | Torrent Solar Power Private Limited (TSPPL) |  | 0331400013 | [6 empty] | Wind | 92
|  | WR | Maharashtra | Kallam PS |  | TEQ GREEN POWER XI PRIVATE LIMITED (TGPXIPL) |  | 2200000035 | [6 empty] | Wind | 29.7
|  | WR | Maharashtra | Kallam PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000193 | [6 empty] | Wind | 101
|  | WR | Maharashtra | Kallam PS |  | TORRENT SOLAR POWER PRIVATE LIMITED |  | 2200000198 | [6 empty] | Wind | 250
|  | WR | Maharashtra | Kallam PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000277 | [6 empty] | Wind | 200
|  | WR | Maharashtra | Kallam PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000302 | [6 empty] | Wind | 100
|  | WR | Maharashtra | Kallam PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200001090 | [6 empty] | Wind | 150
|  | WR | Maharashtra | Kallam PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200001244 | [6 empty] | Wind | 111.8
|  | WR | Gujarat | Bhuj PS |  | SEVEN RENEWABLE POWER PRIVATE LIMITED |  | 2200000317 | [6 empty] | Wind | 50
|  | WR | Gujarat | Bhuj PS |  | NLC INDIA LIMITED |  | 2200000386 | [6 empty] | Solar | 200
|  | WR | Madhya Pradesh | Rajgarh SS |  | Veh Jayin Renewables Private Limited |  | 0231300002 | [6 empty] | Wind | 151.8
|  | WR | Madhya Pradesh | Rajgarh SS |  | Veh Wind Energy Private Limited |  | 0231300004 | [6 empty] | Wind | 75
|  | SR | Andhra Pradesh 30-11-25 | Anantapur PS |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED |  | 2200000162 | [6 empty] | Wind | 295
|  | SR | Andhra Pradesh 30-11-25 | Anantapur PS |  | AYANA RENEWABLE POWER FOUR PRIVATE LIMITED |  | 2200000318 | [6 empty] | Wind | 50
|  | NR | Rajasthan | Bhadla-II |  | NTPC Ltd. |  | St-II:1200002501 (300 MW) (TSSPDCL | 1200003110 | [5 empty] | Solar | 211.65
|  | NR | Rajasthan | Bhadla-II |  | NTPC Ltd. |  | St-II:1200002483 (300 MW) (TSSPDCL | 1200003109 | [5 empty] | Solar | 211.65
|  | NR | Rajasthan | Bhadla-II |  | NTPC Ltd. |  | St-II:1200002483 (300 MW) (TSNPDCL | 1200003120 | [5 empty] | Solar | 88.35
|  | NR | Rajasthan | Bhadla-II |  | ABC Solar (India) Private Limited |  | St-II:1200002359 (300 MW | 1200003357 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II |  | ACME Solar Holdings Private Limited |  | St-II:1200002471 (300 MW | 1200003505 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II |  | Azure Power India Private Limited |  | St-II: 1200002401 (500 MW | 1200003586 | [5 empty] | Solar | 267
|  | NR | Rajasthan | Bhadla-II |  | Azure Power India Private Limited |  | St-II: 1200002401 (500 MW) (233 out of 500 MW) 1200002403(500 MW) (100 | [6 empty] | Solar | 333
|  | NR | Rajasthan | Bhadla-II |  | Adani Renewable Energy Holding Four Ltd. |  | St-II:1200002428 (500 MW | 1200003685 | [5 empty] | Solar | 500
|  | NR | Rajasthan | Bhadla-II |  | Azure Power India Private Limited |  | St-II:1200002403(500 MW | 1200003843 | [5 empty] | Solar | 50
|  | NR | Rajasthan | Bhadla-II |  | AMP Energy Green Private Limited |  | St-II:1200002676 (100 MW | 1200003882 | [5 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner |  | The Tata Power Company Limited |  | St-II:1200003027 (110 MW | 1200003583 | [5 empty] | Solar | 110
|  | NR | Rajasthan | Bikaner |  | Ayana Renewable Power Three Private Limited |  | St-II:1200002986 (300 MW | 1200003933 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner |  | Shikhar Surya (One) Private Limited |  | 1200003115 | [6 empty] | Solar | 70
|  | NR | Rajasthan | Bikaner |  | ReNew Surya Ravi Pvt. Ltd. |  | 1200003301 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II |  | ACME Solar Holdings Private Limited |  | St-II:1200003683 (300 MW | 1200003829 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II |  | SJVN Limited |  | St-II:1200003559(1000MW | 1200003937 | [5 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-II |  | Onevolt Energy Private Limited |  | St-II:1200003626 (100 MW | 412100004 | [5 empty] | Solar | 62
|  | NR | Rajasthan | Bikaner-II |  | NHPC Ltd. |  | St-II:1200003915 (300 MW | 412100006 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II |  | Juniper Green Cosmic Private Limited |  | St-II:1200003740 (100 MW | 0412100008 | [5 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-II |  | Grian Energy Private Limited |  | St-II: 1200003625 (100 MW) LTA: SW…1544323119(62 MW) | [6 empty] | Solar | 62
|  | NR | Rajasthan | Bikaner-II |  | Renew Dinkar Urja Pvt. Ltd. |  | St-II:1200003380 (200 MW | 1200003935 | [5 empty] | Solar | 200
|  | NR | Rajasthan | Bikaner-II |  | Amplus Ages Private Limited |  | SW9999482858- M029_D001_A007- 1671556542236 | [6 empty] | Solar | 62
|  | NR | Rajasthan | Bikaner-II |  | Prerak Greentech Private Limited |  | 412100025 | [6 empty] | Solar | 226
|  | NR | Rajasthan | Bikaner-II |  | Juna Renewable Energy Pvt Ltd |  | 1200003233 | [6 empty] | Solar | 290
|  | NR | Rajasthan | Bikaner-II |  | Juna Renewable Energy Pvt Ltd |  | 1200003389 | [6 empty] | Solar | 45
|  | NR | Rajasthan | Bikaner-II |  | Serentica Renewables India Pvt. Ltd. (erstwhile Sterlite Power Technologies Private Limited) |  | 412100014 (1200003838-St-II) | [6 empty] | Solar | 180
|  | NR | Rajasthan | Fatehgarh-II |  | NTPC Ltd. |  | St-II:1200002339 (150 MW)(TSNPDCL | 1200003124 | [5 empty] | Solar | 44.17
|  | NR | Rajasthan | Fatehgarh-II |  | NTPC Ltd. |  | St-II:1200002497(90 MW) (TSSPDCL | 1200003248 | [5 empty] | Solar | 63.5
|  | NR | Rajasthan | Fatehgarh-II |  | NTPC Ltd. |  | St-II:1200002497 (90 MW) (TSNPDCL | 1200003314 | [5 empty] | Solar | 26.5
|  | NR | Rajasthan | Fatehgarh-II |  | Adani Renewable Energy Holding Four Limited |  | St-II:1200002430 (500 MW | 1200003684 | [5 empty] | Solar | 500
|  | NR | Rajasthan | Fatehgarh-II |  | Eden Renewable Bercy Private Limited |  | St-II:1200002688 (300 MW | 1200003947 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec- I) |  | Renew Surya Roshni Private Limited |  | St-II:1200002628(400 MW | 1200003269 | [5 empty] | Solar | 400
|  | SR | Karnataka | Gadag PS |  | Azure Power India Pvt. Ltd. |  | Connectivity Appl No.- 1200003497; LTA app no. 451100008 (120 MW) & | [6 empty] | Wind | 170
|  | SR | Karnataka | Gadag PS |  | Green Infra Wind Connectivity Appl No.- 0451100007 |  | LTA app no. 451100007 | [6 empty] | Wind | 178.5
|  | SR | Karnataka | Gadag PS |  | ReNew Naveen Urja Pvt. Ltd |  | LTA app no. 451100009 | [6 empty] | Wind | 300
|  | SR | Karnataka | Gadag PS |  | Serentica Renewables India Pvt. Ltd |  | 0451100011 | [6 empty] | Hybrid (RHGS) | 132
|  | SR | Karnataka | Gadag PS |  | Serentica Renewables India Pvt. Ltd |  | 1200003761 | [6 empty] | Hybrid (RHGS) | 107
|  | SR | Karnataka | Gadag PS |  | Serentica Renewables India Pvt. Ltd |  | 1200003828 | [6 empty] | Hybrid (RHGS) | 66
|  | SR | Karnataka | Gadag PS |  | Serentica Renewables India Pvt. Ltd |  | 0451100010 | [6 empty] | Hybrid (RHGS) | 165
|  | SR | Karnataka | Gadag PS |  | Green Infra Wind Energy Limited |  | 0251100003 | [6 empty] | Wind | 70
|  | SR | Karnataka | Gadag PS |  | Green Infra Wind Energy Limited |  | 0351100002 | [6 empty] | Wind | 50
|  | SR | Karnataka | Gadag PS |  | Green Infra Wind Energy Limited |  | SW5958957243-M029_D001_A007- 1670310631002 | [6 empty] | Wind | 1.5
|  | SR | Karnataka | Hiriyur |  | Zenataris Renewable Energy Pvt. Ltd. |  | 0251100011 | [6 empty] | Wind | 66
|  | SR | Karnataka | Hiriyur |  | ZENATARIS RENEWABLE ENERGY PRIVATE LIMITED |  | 2200000061 | [6 empty] | Wind | 171.6
|  | SR | Tamil Nadu | Karur PS |  | JSW Renew Energy Connectivity Appl No.-1200002868 |  | LTA app no. 1200003533 (170 MW) Connectivity Appl No.-1200002868 | [6 empty] | Wind | 170
|  | SR | Tamil Nadu | Karur PS |  | JSW Neo Energy Ltd. (earstwhile JSW Future Energy Ltd.) |  | LTA app no. 1200003536 | [6 empty] | Wind | 150
|  | SR | Tamil Nadu | Karur PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000242 | [6 empty] | Wind | 198
|  | SR | Karnataka | Koppal PS |  | Tunga Renewables Energy Pvt. Ltd. Connectivity Appl No.- 1200003577 |  | LTA app no. 1200003577 | [6 empty] | Wind | 189.84
|  | SR | Karnataka | Koppal PS |  | Project Ten Renewable Power Pvt. Ltd. ( Connectivity Appl No.-1200003530) |  | 1200003530 LTA app no. 0451100005 | [6 empty] | Wind | 150
|  | SR | Karnataka | Koppal PS |  | Kleio Solar Power Pvt. Ltd. |  | 1200003825 | [6 empty] | Hybrid (RHGS) | 209.39999999 999998
|  | SR | Karnataka | Koppal PS |  | Tunga Renewable Energy Pvt. Ltd. |  | 1200003849 | [6 empty] | Wind | 45.07
|  | SR | Karnataka | Koppal PS |  | Tunga Renewable Energy Pvt. Ltd. |  | 1200003392 | [6 empty] | Wind | 115
|  | SR | Karnataka | Koppal PS |  | Serentica Renewable India 1 Pvt. |  | 1200003822 | [6 empty] | Hybrid (RHGS) | 13.333333333 333334
|  | SR | Karnataka | Koppal PS |  | Serentica Renewable India 1 Pvt. |  | 1200003909 | [6 empty] | Hybrid (RHGS) | 120
|  | SR | Karnataka | Koppal PS |  | Serentica Renewable India 1 Pvt. |  | 0451100013 | [6 empty] | Hybrid (RHGS) | 133.33333333 333334
|  | SR | Andhra Pradesh 30-11-25 | Kurnool (new) |  | Greenko AP01 IREP Pvt. Ltd (Connectivity Appl No.- 1200002672) |  | LTA app no.1200003664 | [6 empty] | Hybrid (RHGS) | 900
|  | SR | Andhra Pradesh 30-11-25 | Kurnool (new) |  | Greenko AP01 IREP Pvt. Ltd Connectivity Appl No.-1200003962 ) |  | LTA app no. 450200009 | [6 empty] | PSP | 565
|  | SR | Andhra Pradesh 30-11-25 | Kurnool (new) |  | Greenko AP01 IREP Pvt. Ltd. |  | 0350200006 | [6 empty] | PSP | 260
|  | SR | Andhra Pradesh 30-11-25 | Kurnool (new) |  | AM GREEN ENERGY PRIVATE LIMITED |  | 2200000012 | [6 empty] | Hybrid (RHGS) | 989 (Solar- 675MW, Wind:314MW)
|  | SR | Andhra Pradesh 30-11-25 | Kurnool-III PS |  | AMP ENERGY GREEN PRIVATE LIMITED |  | 2200000150 | [6 empty] | Hybrid (RHGS) | Total: 187 MW Solar: 137.5
|  | SR | Andhra Pradesh 30-11-25 | Kurnool-III PS |  | AMP ENERGY C&I TWELVE PRIVATE LIMITED |  | 2200000231 | [6 empty] | Solar | 100
|  | SR | Andhra Pradesh 30-11-25 | Kurnool-III PS |  | SAEL INDUSTRIES LIMITED |  | 2200000329 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 30-11-25 | Kurnool-III PS |  | SAEL INDUSTRIES LIMITED |  | 2200000330 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 30-11-25 | Kurnool-III PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000335 | [6 empty] | Solar | Solar-400MW, 400
|  | SR | Andhra Pradesh 30-11-25 | NP Kunta PS |  | NHPC LIMITED |  | 2200000250 | [6 empty] | Solar | 100
|  | SR | Andhra Pradesh 30-11-25 | Nellore PS |  | JINDAL POWER LIMITED |  | 2200000633 | [6 empty] | Solar | 52.6
|  | SR | Karnataka | Pavagada PS |  | Project Ten Renewable Power Pvt. Ltd. |  | LTA app no. 451100004 | [6 empty] | Wind | 300
|  | SR | Karnataka | Pavagada PS |  | Solar Energy Corporation of India Ltd. |  | 1200003590 | [6 empty] | Solar | 200
|  | SR | Tamil Nadu | Pugalur |  | SPRNG AKSHAYA URJA PRIVATE LIMITED |  | 2200000197 | [6 empty] | Wind | 52.8
|  | SR | Andhra Pradesh 30-11-25 | Ramagundam |  | NTPC Ltd. (Ramagundam FSP) |  | 1200002271 | [6 empty] | Solar | 100
|  | SR | Andhra Pradesh 30-11-25 | Simhadri |  | NTPC Ltd. (Simhadri FSP) |  | 1200002272 | [6 empty] | Solar | 25
|  | SR | Tamil Nadu | Tuticorin-II PS |  | JSW RENEW ENERGY TWELVE LIMITED |  | 2200001115 | [6 empty] | Hybrid (RHGS) | 175
|  | SR | Tamil Nadu | Tuticorin-II PS |  | JSW GREEN ENERGY ONE LIMITED |  | 2200001120 | [6 empty] | Solar | 50
|  | SR | Tamil Nadu | Karur PS |  | JSP GREEN WIND 1 PRIVATE LIMITED |  | 2200000438 | [6 empty] | Wind | 300
|  | NR | Rajasthan | Bikaner |  | Shikhar Surya (One) Private Limited |  | 1200003772 | [6 empty] | Solar | 105
|  | NR | Rajasthan | Bikaner |  | Shikhar Surya (One) Private Limited |  | 312100003 | [6 empty] | Solar | 125
|  | NR | Rajasthan | Bikaner-II |  | TP Saurya Limited |  | 1200003582 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II |  | Amplus Ages Private Limited |  | 1200003624 | [6 empty] | Solar | 38
|  | NR | Rajasthan | Bikaner-II |  | Grian Energy Private Limited |  | 1200003625 | [6 empty] | Solar | 38
|  | NR | Rajasthan | Bikaner-II |  | Onevolt Energy Private Limited |  | 1200003626 | [6 empty] | Solar | 38
|  | NR | Rajasthan | Bikaner-II |  | Khidrat Renewable Energy Private Limited |  | 1200003390 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II |  | Litsolaire Energy Private Limited |  | 1200003893 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-II |  | ALF Solar Amarsar Private Limited |  | 1200003785 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-II |  | ALF Solar Amarsar Private Limited |  | 1200003831 (Enh.) | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-II |  | Serentica Renewables India Pvt. Ltd. (erstwhile Sterlite Power Technologies Private Limited) |  | 1200003628 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-II |  | Serentica Renewables India Pvt. Ltd. (erstwhile Sterlite Power Technologies Private Limited) |  | 1200003838 | [6 empty] | Solar | 120
|  | NR | Rajasthan | Bikaner-II |  | Juniper Nirjara Energy Private Limited |  | 1200003623 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-II |  | Prerak Greentech Private Limited |  | 1200003770 | [6 empty] | Solar | 114
|  | NR | Rajasthan | Bikaner-II |  | Prerak Greentech Private Limited |  | 1200003839 | [6 empty] | Solar | 60
|  | SR | Karnataka | Gadag-II PS |  | Green Infra Wind Energy Ltd. |  | 0251100010 | [6 empty] | Wind | 300
|  | SR | Karnataka | Gadag-II PS |  | TP Saurya Ltd. |  | 0251100006 | [6 empty] | Wind | 200
|  | SR | Karnataka | Gadag-II PS |  | Tata Power Renewable Energy Ltd. |  | 0251100012 | [6 empty] | Wind | 170
|  | SR | Karnataka | Gadag-II PS |  | Tata Power Renewable Energy Ltd. |  | 0351100009 | [6 empty] | Wind | 170
|  | SR | Karnataka | Gadag-II PS |  | GREENKO KA01 IREP PRIVATE LIMITED |  | 2200000088 | [6 empty] | Pump Storage | 640
|  | SR | Karnataka | Koppal-II PS |  | Tata Power Renewable Energy Ltd. |  | 0251100021 | [6 empty] | Wind | 300
|  | SR | Karnataka | Koppal-II PS |  | TATA Power Renewable Energy Ltd. |  | 0251100013 | [6 empty] | Wind | 85
|  | SR | Karnataka | Koppal-II PS |  | TATA Power Renewable Energy Ltd. |  | 0351100008 | [6 empty] | Wind | 85
|  | SR | Karnataka | Koppal-II PS |  | TORRENT SAURYA URJA 2 PRIVATE LIMITED |  | 2200000058 | [6 empty] | Wind | 300
|  | SR | Karnataka | Koppal-II PS |  | ABREL (RJ) PROJECTS LIMITED |  | 2200000141 | [6 empty] | Wind | 184
|  | SR | Karnataka | Koppal-II PS |  | VEH GREEN ENERGY PRIVATE LIMITED |  | 2200000126 | [6 empty] | Wind | 153.6
|  | SR | Andhra Pradesh 30-12-25 | NP Kunta PS |  | FIRST ENERGY PRIVATE LIMITED |  | 2200000388 | [6 empty] | Solar | 100
|  | SR | Karnataka | Pavagada PS |  | Ircon Renewable Power Ltd. |  | 1200003815 | [6 empty] | Solar | 500
|  | SR | Karnataka | Pavagada PS |  | SOLAR ENERGY CORPORATION OF INDIA LIMITED |  | 2200000057 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ABC Renewable Energy Pvt. Ltd. |  | St-II:1200002699 (400 MW | 1200003096 | [5 empty] | Solar | 400
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ReNew Dinkar Jyoti Private Limited |  | St-II:1200003813 (100 MW | 1200003879 | [5 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | IB Vogt Solar Seven Private Limited |  | St-II:1200002700 (300 MW | 1200003931 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | XL Xergi Power Pvt. Ltd. |  | St-II:1200002847 (400 MW | 412100007 | [5 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | Khaba Renewable Energy Private Limited |  | 1200003502 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ReNew Surya Jyoti Private Limited |  | 1200002746 | [6 empty] | Solar | 210
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | RENEW SURYA PRATAP PRIVATE LIMITED |  | 1200002778 | [6 empty] | Solar | 210
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ReNew Solar (Shakti Three) Private Limited |  | 1200003447 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ReNew Solar (Shakti Five) Private Limited |  | 1200003488 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ReNew Solar (Shakti Five) Private Limited |  | 1200003496 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ReNew Samir Shakti Private Limited |  | 1200003504 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ReNew Samir Shakti Private Limited |  | 1200003514 (Enh. St-II) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ReNew Samir Shakti Private Limited |  | 1200003562 (Enh. St-II) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | Energizent Power Private Limited |  | 1200002939 | [6 empty] | Solar | 80
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | XL Xergi Power Private Limited |  | 412100020 (St-II: 1200002847) | [6 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | AMP Energy Green Pvt. Ltd. |  | St-II:1200003022 (130 MW | 1200003416 | [5 empty] | Solar | 130
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | ABC Renewable Energy Private Limited |  | St-II:1200003002 (380 MW | 1200003531 | [5 empty] | Solar | 380
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | Juniper Green Stellar Private Limited |  | 412100009 (St-II: 1200003827, 1200003910, 1200003958, 0312100010 | [6 empty] | Hybrid (RHGS) | 150
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | AMP Energy Green Pvt. Ltd. |  | 412100019 (St-II: 0312100005) | [6 empty] | Hybrid (RHGS) | 120
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | ABC RJ Land 01 Private Limited |  | 1200003332 | [6 empty] | Solar | 110
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | ABC RJ Land 01 Private Limited |  | 1200003575 | [6 empty] | Solar | 270
|  | SR | Karnataka | Gadag-II PS |  | SOLARXL BETA ENERGY PRIVATE LIMITED |  | 2200000006 | [6 empty] | Hybrid (RHGS) | 207 (Solar-138 MW, Wind-69
|  | SR | Karnataka | Gadag-II PS |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED |  | 2200000072 | [6 empty] | Wind | 480
|  | SR | Karnataka | Gadag-II PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000074 | [6 empty] | Hybrid (RHGS) | 109
|  | SR | Karnataka | Gadag-II PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000096 | [6 empty] | Wind | 50
|  | SR | Karnataka | Gadag-II PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000099 | [6 empty] | Wind | 50
|  | SR | Karnataka | Gadag-II PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000100 | [6 empty] | Wind | 50
|  | SR | Karnataka | Gadag-II PS |  | ABREL (RJ) PROJECTS LIMITED |  | 2200000139 | [6 empty] | Wind | 184
|  | SR | Karnataka | Gadag-II PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000121 | [6 empty] | Hybrid (RHGS) | 327MW [Solar- 153 MW & Wind-174MW]
|  | SR | Karnataka | Gadag-II PS |  | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED |  | 2200000238 | [6 empty] | Wind | 102
|  | SR | Karnataka | Hiriyur |  | ZENATARIS RENEWABLE ENERGY PRIVATE LIMITED |  | 2200000920 | [6 empty] | Wind | 62.7
|  | WR | Gujarat | Jam Khambhaliya PS |  | Powerica Limited |  | 0230700018 | [6 empty] | Wind | 53
|  | WR | Gujarat | Jam Khambhaliya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000190 | [6 empty] | Wind | 100
|  | SR | Karnataka | Koppal-II PS |  | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED |  | 2200000237 | [6 empty] | Wind | 102
|  | SR | Karnataka | Koppal-II PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000243 | [6 empty] | Wind | 288
|  | SR | Karnataka | Koppal-II PS |  | JSP GREEN WIND 1 PRIVATE LIMITED |  | 2200000262 | [6 empty] | Wind | 400
|  | SR | Karnataka | Koppal-II PS |  | JSP GREEN WIND 1 PRIVATE LIMITED |  | 2200000402 | [6 empty] | Wind | 300
|  | SR | Karnataka | Koppal-II PS |  | GADAG POWER INDIA PRIVATE LIMITED |  | 2200000472 | [6 empty] | Wind | 300
|  | SR | Karnataka | Koppal-II PS |  | AYANA RENEWABLE POWER PRIVATE LIMITED |  | 2200000504 | [6 empty] | Wind | 100
|  | WR | Maharashtra | Parli (New) |  | Renew Pawan Shakti Private Limited (RPSPL) |  | 0231400018 | [6 empty] | Wind | 277
|  | WR | Maharashtra | Parli (New) |  | Renew Pawan Shakti Private Limited (RPSPL) |  | 0331400012 | [6 empty] | Wind | 23
|  | WR | Madhya Pradesh | Neemuch PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000709 | [6 empty] | Solar | 300
|  | SR | Karnataka | Koppal-II PS |  | TORRENT SOLAR POWER PRIVATE LIMITED |  | 2200000474 | [6 empty] | Wind | 125.4
|  | WR | Madhya Pradesh | Pachora PS (Sec- II) |  | Oyster Renewable Energy Private Limited (formerly Known as ABENERGIA RENEWABLES PRIVATE LIMITED) |  | 2200000086 | [6 empty] | Hybrid (RHGS) | 100
|  | WR | Madhya Pradesh | Pachora PS (Sec- II) |  | Oyster Renewable Energy Private Limited (Former name-ABENERGIA RENEWABLES PRIVATE LIMITED) |  | 2200000342 | [6 empty] | Hybrid (RHGS) | 81
|  | WR | Madhya Pradesh | Pachora PS (Sec- II) |  | BHOJRAJ DEVELOPERS PRIVATE LIMITED |  | 2200000404 | [6 empty] | Hybrid (RHGS) Wind: 160 | MW Solar: 26 MW
|  | SR | Karnataka | Gadag-II PS |  | GREENKO KA01 IREP PRIVATE LIMITED |  | 2200000092 | [6 empty] | Pump Storage | 260
|  | NR | Rajasthan | Bhadla-II |  | AMP Energy Green Private Limited |  | 1200002987 (Enh.) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bhadla-II |  | Eden Renewable Alma Private Limited |  | 1200002554 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II |  | Solarpack Corporacion Technologica S.A. |  | 1200002742 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II |  | AMP Energy Green Pvt. Ltd. |  | 1200002559 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bhadla-III |  | Prerak Greentech Solar Private Limited (Park) |  | SW9990894382- M029_D001_A007- 1671216520154 (0212100003) | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bhadla-III |  | Juniper Green Beta Pvt. Ltd. |  | 412100012, 0212100027 (St-II) | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bhadla-III |  | Juniper Green Beta Pvt. Ltd. |  | 412100013, 0312100013 (St-II), 1670400777119 (St-II) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bhadla-III |  | Tepsol Sun Sparkle Pvt. Ltd. |  | SW9990897533- M029_D001_A007- 1672319027575, 0212100030 (St-II) | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III |  | Juniper Green Beta Private Limited |  | 412100027 (SW5102826596- M029_D001_A003-1670400777119 (10MW out of 70MW) + 0312100011 | [6 empty] | Solar | 50
|  | SR | Karnataka | Bidar PS |  | WELSPUN NARMADA PRIVATE LIMITED |  | 2200000716 | [6 empty] | Hybrid (RHGS) | 250 (150 MW Wind & 100 MW Solar)
|  | SR | Tamil Nadu | Karur PS |  | FIRST ENERGY PRIVATE LIMITED |  | 2200000441 | [6 empty] | Wind | 100
|  | SR | Tamil Nadu | Karur PS |  | NANNAI SOLAR PARK PRIVATE LIMITED |  | 2200000628 | [6 empty] | Wind | 93
|  | NR | Rajasthan | Ramgarh |  | Adani Renewable Energy Holding Four Ltd. |  | St-II: 1200002432(500 MW | 1200003689 | [5 empty] | Solar | 500
|  | WR | Maharashtra | Kallam PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000395 | [6 empty] | Wind | 101
|  | WR | Maharashtra | Kallam PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000450 | [6 empty] | Wind | 100.8
|  | SR | Tamil Nadu | Karur PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000448 | [6 empty] | Wind | 93.6
|  | SR | Tamil Nadu | Pugalur |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000394 | [6 empty] | Wind | 151
|  | SR | Tamil Nadu | Pugalur |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000449 | [6 empty] | Wind | 151.2
|  | SR | Karnataka | Koppal-II PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000390 | [6 empty] | Solar | 200-Solar; 25-BESS
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | SOLARCRAFT POWER INDIA 7 PRIVATE LIMITED |  | 2200000270 | [6 empty] | Wind | 52.8
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | SOLARCRAFT POWER INDIA 7 PRIVATE LIMITED |  | 2200000409 | [6 empty] | Wind | 47.2
|  | WR | Madhya Pradesh | Pachora PS (Sec- I) |  | VEH DAMEN POWER PRIVATE LIMITED |  | 2200000356 | [6 empty] | Wind | 76.8
|  | SR | Andhra Pradesh 31-03-26 | Anantapur PS |  | RENEW VIKRAM SHAKTI PRIVATE LIMITED |  | 2200000032 | [6 empty] | Hybrid (RHGS) | Solar-750MW, Wind:960MW, BESS-288)
|  | SR | Andhra Pradesh 31-03-26 | Anantapur PS |  | ABC CLEANTECH PRIVATE LIMITED |  | 2200000271 | [6 empty] | Wind | 250
|  | SR | Andhra Pradesh 31-03-26 | Anantapur PS |  | ABC CT RE PARK (03) PRIVATE LIMITED |  | 2200000273 | [6 empty] | Wind | 250
|  | NR | Rajasthan | Fatehgarh-III |  | JSW Renew Energy Five Limited |  | 212100040 | [6 empty] | Storage | 250
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | Juniper Green Stellar Private Limited |  | 412100010 (St-II: 1200003827, 1200003910, 1200003958, 0312100010 & 0312100012) | [6 empty] | Hybrid (RHGS) | 150
|  | WR | Madhya Pradesh | Indore (PG) |  | RENEW SAMIR URJA PRIVATE LIMITED |  | 2200000298 | [6 empty] | Wind | 300
|  | WR | Maharashtra | Solapur PG |  | JSW RENEW ENERGY THIRTEEN LIMITED |  | 2200001148 | [6 empty] | Solar | 300
|  | WR | Maharashtra | Solapur PG |  | WAAREE FOREVER ENERGIES PRIVATE LIMITED |  | 2200001158 | [6 empty] | Solar | 1000
|  | WR | Maharashtra | Solapur PS |  | JSW Renew Energy Three Limited |  | 231400016 | [6 empty] | Wind | 200
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | JSW NEO ENERGY LIMITED |  | 2200000718 | [6 empty] | Wind | 300
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | SOLARCRAFT POWER INDIA 16 PVT. LTD. |  | 2200000440 | [6 empty] | Hybrid (RHGS) Wind - 191.4 | MW, Solar - 56 MW, BESS - 91 MW)
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | SOLARCRAFT POWER INDIA 16 PRIVATE LIMITED |  | 2200001047 | [6 empty] | Hybrid (RHGS) | 247.4
|  | WR | Gujarat | Bhuj PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000566 | [6 empty] | Wind | 20
|  | SR | Karnataka | Bidar PS |  | SAEL INDUSTRIES LIMITED |  | 2200000759 | [6 empty] | Solar | 300
|  | WR | Gujarat | Lakadiya PS |  | TEQ GREEN POWER XVII PRIVATE LIMITED |  | 2200000311 | [6 empty] | Hybrid (RHGS) | 300 (200MW Solar
|  | WR | Madhya Pradesh | Pachora PS (Sec- II) |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000502 | [6 empty] | Solar | 400
|  | SR | Tamil Nadu | Tuticorin-II PS |  | GRT JEWELLERS (INDIA) PRIVATE LIMITED |  | 2200000594 | [6 empty] | Solar | 150
|  | SR | Karnataka | Pavagada PS |  | TEQ GREEN POWER XVIII PRIVATE LIMITED |  | 2200000310 | [6 empty] | Wind | 250
|  | SR | Karnataka | Pavagada PS |  | KARNATAKA SOLAR POWER DEVELOPMENT CORPORATION LIMITED |  | 2200000339 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 31-05-26 | Anantapur PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000069 | [6 empty] | Wind | 400
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | SKADAR SOLAR PRIVATE LIMITED |  | 2200000754 | [6 empty] | Solar | 200
|  | SR | Andhra Pradesh 30-06-26 | Anantapur PS |  | ABC CT RE PARK (02) PRIVATE LIMITED |  | 2200000274 | [6 empty] | Wind | 250
|  | SR | Andhra Pradesh 30-06-26 | Anantapur PS |  | ABC CT RE PARK (01) PRIVATE LIMITED |  | 2200000276 | [6 empty] | Wind | 250
|  | NR | Rajasthan | Bhadla-III |  | ReNew Solar (Shakti Six) Private Limited |  | 1200003848 | [6 empty] | Solar | 550
|  | NR | Rajasthan | Bhadla-III |  | ReNew Solar (Shakti Six) Private Limited |  | 312100004 (Enh.) | [6 empty] | Solar | 450
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | Juniper Green Steller Pvt. Ltd. |  | St-II: 312100010 (45 MW) (5 out of 45 MW), 312100012 (60 MW | 0412100011 | [5 empty] | Solar | 65
|  | WR | Gujarat | Jam Khambhaliya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000209 | [6 empty] | Wind | 200
|  | WR | Gujarat | KPS-1 (Sec-I) |  | Adani Renewable Energy Holding Four Ltd. (AREH4L) |  | 1200002678 | [6 empty] | Solar | 1083
|  | WR | Gujarat | KPS-1 (Sec-I) |  | Adani Renewable Energy Holding Four Ltd. (AREH4L) |  | 1200002679 | [6 empty] | Solar | 1000
|  | WR | Gujarat | KPS-1 (Sec-I) |  | Adani Green Energy Ltd. |  | 1670426092248 | [6 empty] | Hybrid (RHGS) | 1050
|  | WR | Gujarat | KPS-1 (Sec-II) |  | Adani Green Energy Limited Connectivity: 1670426695890; LTA: 1670929494955 (250MW); |  | SW6949744157-M029_D001_A002- 1670426695890 Connectivity: 1670426695890 | [6 empty] | Wind | 250
|  | WR | Gujarat | KPS-1 (Sec-II) |  | Sarjan Realities Pvt. Ltd. (SRPL) |  | 0230700011 | [6 empty] | Hybrid (RHGS) | 1150
|  | WR | Gujarat | KPS-3 (Sec-I) |  | Sarjan Realities Pvt. Ltd. (SRPL) |  | 0230700012 | [6 empty] | Hybrid (RHGS) | 1332
|  | SR | Andhra Pradesh 30-06-26 | Kurnool-III PS |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000383 | [6 empty] | Hybrid (RHGS) | Solar: 150MW Wind: 150MW BESS: 30MWh
|  | WR | Gujarat | Lakadiya PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000610 | [6 empty] | Hybrid (RHGS) | 480 (240 MW: Wind 240 MW: Solar)
|  | WR | Maharashtra | Parli (New) |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000747 | [6 empty] | Wind | 180
|  | WR | Gujarat | Radhanesda PS |  | SPRNG POWER EARTH PRIVATE LIMITED |  | 2200000247 | [6 empty] | Solar | 250
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | SOLARCRAFT POWER INDIA 20 PRIVATE LIMITED |  | 2200000795 | [6 empty] | Hybrid (RHGS) | 97.31
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | SOLARCRAFT POWER INDIA 20 PRIVATE LIMITED |  | 2200001028 | [6 empty] | Hybrid (RHGS) | 84.75
|  | SR | Andhra Pradesh 01-07-26 | Kurnool-III PS |  | ADANI RENEWABLE ENERGY FORTY TWO LIMITED |  | 2200000158 | [6 empty] | Pump Storage | 600
|  | WR | Gujarat | KPS-3 (Sec-I) |  | Sarjan Realities Pvt. Ltd. (SRPL) |  | 0230700014 | [6 empty] | Hybrid (RHGS) | 1100
|  | WR | Gujarat | Lakadiya PS |  | ARCELORMITTAL NIPPON STEEL INDIA LIMITED |  | 2200000324 | [6 empty] | Hybrid (RHGS) | 550 (Wind 250MW+Solar 300MW)
|  | NR | Rajasthan | Bikaner |  | AK RENEWABLE INFRA PRIVATE LIMITED |  | 2200000284 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II |  | ALF Solar Amarsar Private Limited |  | 312100008 (Enh.) | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-II |  | Sourya Manthan Renewable Energy Private Limited |  | 212100005 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-II |  | Soltown Infra Private Limited (Park) |  | 212100007 | [6 empty] | Solar | 350
|  | NR | Rajasthan | Bikaner-II |  | Soltown Infra Private Limited (Park) |  | 212100008 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-III |  | Proteus Energy Private Limited (Park) |  | 212100042 | [6 empty] | Solar | 217
|  | NR | Rajasthan | Bikaner-III |  | TP Saurya Limited |  | 212100025 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-III |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000008 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-III |  | MRS BUILDVISION PRIVATE LIMITED |  | 2200000098 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III |  | SUNBREEZE RENEWABLES NINE PRIVATE LIMITED |  | 2200000111 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-III |  | SUNBREEZE RENEWABLES NINE PRIVATE LIMITED |  | 2200000163 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000172 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III |  | SAIMAA SOLAR PRIVATE LIMITED |  | 2200000167 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000164 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000165 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000227 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000228 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | Serentica Renewable India Pvt. Ltd. |  | 212100034 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | Serentica Renewable India Pvt. Ltd. |  | 212100036 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000020 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | SPRNG POWER PRIVATE LIMITED |  | 2200000024 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | SPRNG AKSHAYA URJA PRIVATE LIMITED |  | 2200000065 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | SPRNG ENERGY PRIVATE LIMITED |  | 2200000116 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ABREL (RJ) PROJECTS LIMITED |  | 2200000140 | [6 empty] | Solar | 260
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200000123 | [6 empty] | Solar | 95
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED |  | 2200000138 | [6 empty] | Hybrid (RHGS) | 390
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | Luceo Solar Pvt. Ltd. |  | 212100032 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | Luceo Solar Pvt. Ltd. |  | 0312100018 (Enhancement) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | AMP Energy Green Pvt. Ltd. |  | 312100007 | [6 empty] | Hybrid (RHGS) | 50
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | BN HYBRID POWER-1 PRIVATE LIMITED |  | 2200000003 | [6 empty] | Hybrid (RHGS) | 119.2
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | BN HYBRID POWER-1 PRIVATE LIMITED |  | 2200000102 | [6 empty] | Hybrid (RHGS) | 180.8
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000187 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III |  | Seven Renewable Power Pvt. Ltd. |  | 212100028 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III |  | Frugal Energy Pvt. Ltd. |  | 212100031 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bhadla-III |  | Bhadla Three SKP Green Ventures Pvt. Ltd. |  | 212100033 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Ramgarh |  | Adani Solar Energy AP Three Ltd. |  | 212100038 | [6 empty] | Solar | 150
|  | SR | Karnataka | Bijapur PS |  | TEPSOL GREEN ENERGY PRIVATE LIMITED |  | 2200000657 | [6 empty] | Hybrid (RHGS) | 200 (Wind- 160 & Solar- 40)
|  | SR | Karnataka | Davangere PS |  | LAYER HYBREN PRIVATE LIMITED |  | 2200000625 | [6 empty] | Hybrid (RHGS) | 140 (100- Solar; 40 Wind)
|  | SR | Karnataka | Tumkur-II PS |  | SAEL INDUSTRIES LIMITED |  | 2200000948 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 30-09-26 | Anantapur PS |  | SEVEN RENEWABLE POWER PRIVATE LIMITED |  | 2200000226 | [6 empty] | Wind | 150
|  | NR | Rajasthan | Bhadla-II |  | SOLARCRAFT POWER INDIA 4 PRIVATE LIMITED |  | 2200000152 | [6 empty] | Solar | 150
|  | SR | Karnataka | Davangere PS |  | LAYER HYBREN PRIVATE LIMITED |  | 2200000702 | [6 empty] | Hybrid (RHGS) | 160 (110- Solar; 50 Wind)
|  | WR | Maharashtra | Kallam PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000075 | [6 empty] | Wind | 50
|  | WR | Maharashtra | Kallam PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000353 | [6 empty] | Wind | 250
|  | WR | Gujarat | Lakadiya PS |  | RENEW SOLAR (SHAKTI EIGHT) PRIVATE LIMITED |  | 2200000341 | [6 empty] | Solar | 200
|  | WR | Gujarat | Lakadiya PS |  | TEQ GREEN POWER XVI PRIVATE LIMITED |  | 2200000398 | [6 empty] | Wind | 76
|  | WR | Gujarat | Lakadiya PS |  | RENEW SOLAR (SHAKTI EIGHT) PRIVATE LIMITED |  | 2200000403 | [6 empty] | Solar | 100
|  | WR | Gujarat | Lakadiya PS |  | TEQ GREEN POWER XVI PRIVATE LIMITED |  | 2200000427 | [6 empty] | Wind | 76
|  | SR | Karnataka | Tumkur-II PS |  | SAEL INDUSTRIES LIMITED |  | 2200001012 | [6 empty] | Solar | 300
|  | WR | Gujarat | KPS-1 (Sec-I) |  | Adani Renewable Energy Holding Four Ltd. (Erstwhile Adani Green Energy Four Ltd.) |  | 1200002678 | [6 empty] | Solar | 917
|  | WR | Maharashtra | Parli (New) |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200001054 | [6 empty] | Wind | 220
|  | WR | Gujarat | Jam Khambhaliya PS |  | MOUNTING RENEWABLE POWER LIMITED |  | 2200000246 | [6 empty] | Hybrid (RHGS) | 250
|  | WR | Gujarat | Jam Khambhaliya PS |  | AIRPOWER WINDFARMS PRIVATE LIMITED |  | 2200000261 | [6 empty] | Wind | 175
|  | WR | Gujarat | Jam Khambhaliya PS |  | ACME SUN POWER PRIVATE LIMITED |  | 2200000263 | [6 empty] | Wind | 400
|  | WR | Gujarat | Jam Khambhaliya PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000241 | [6 empty] | Wind | 545
|  | WR | Gujarat | Jam Khambhaliya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000445 | [6 empty] | Wind | 100
|  | WR | Gujarat | Jam Khambhaliya PS |  | POWERICA LIMITED |  | 2200000473 | [6 empty] | Wind | 50
|  | WR | Gujarat | Jam Khambhaliya PS |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED |  | 2200000503 | [6 empty] | Wind | 308.49
|  | WR | Gujarat | Jam Khambhaliya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000556 | [6 empty] | Wind | 200
|  | WR | Gujarat | Jam Khambhaliya PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000565 | [6 empty] | Wind | 80
|  | WR | Gujarat | Jam Khambhaliya PS |  | MALAREN SOLAR PRIVATE LIMITED |  | 2200000337 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | EG Saur Urja Pvt. Ltd. (earlier Tepsol Saur Urja Private Limited) |  | 212100043 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | Cannice Renewables Energy Private Limited |  | 312100019 | [6 empty] | Hybrid (RHGS) | 90
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | Cannice Renewables Energy Private Limited |  | SW…1671600589106 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | Cannice Renewable Energy Private Limited |  | 212100004 | [6 empty] | Solar | 80
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | GREENKO MP01 IREP PRIVATE LIMITED |  | 2200000089 | [6 empty] | Pump Storage | 504
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | GREENKO MP01 IREP PRIVATE LIMITED |  | 2200000090 | [6 empty] | Pump Storage | 504
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | GREENKO MP01 IREP PRIVATE LIMITED |  | 2200000091 | [6 empty] | Pump Storage | 504
|  | WR | Gujarat | Navinal |  | ADANI WIND ENERGY KUTCHH THREE LIMITED |  | 2200001083 | [6 empty] | Wind | 300
|  | NR | Rajasthan | Barmer-I |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200000153 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000161 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Barmer-I |  | EDEN RENEWABLE CADET PRIVATE LIMITED |  | 2200000181 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ENREN-I ENERGY PRIVATE LIMITED |  | 2200000286 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ANBOTO SOLAR PRIVATE LIMITED |  | 2200000281 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000244 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | GREEN INFRA CLEAN WIND TECHNOLOGY LIMITED |  | 2200000054 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | UTKRRISHT SOLAR ENERGY PRIVATE LIMITED |  | 2200000067 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000077 | [6 empty] | Hybrid (RHGS) | 50
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | BN DISPATCHABLE-1 PRIVATE LIMITED |  | 2200000103 | [6 empty] | Hybrid (RHGS) | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | HELIA ENERGY PARK PRIVATE LIMITED |  | 2200000120 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | GREEN INFRA CLEAN SOLAR FARMS LIMITED |  | 2200000135 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000186 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | RADIANT STAR SOLAR PARK PRIVATE LIMITED |  | 2200000212 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000290 | [6 empty] | Hybrid (RHGS) | 250
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000485 | [6 empty] | Solar | 50
|  | SR | Karnataka | Pavagada PS |  | AYANA RENEWABLE POWER PRIVATE LIMITED |  | 2200000320 | [6 empty] | Wind | 150
|  | NR | Rajasthan | Bikaner-III |  | DESHRAJ SOLAR ENERGY PRIVATE LIMITED |  | 2200000184 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-III |  | FIRST ENERGY PRIVATE LIMITED |  | 2200000221 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-IV |  | AVAADA RJBIKANER PRIVATE LIMITED |  | 2200000013 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-IV |  | SOLARCRAFT POWER INDIA 17 PRIVATE LIMITED |  | 2200000210 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | AVAADA RJBIKANER PRIVATE LIMITED |  | 2200000254 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Bikaner-IV |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000289 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | SHUDH SOLAR POWER PRIVATE LIMITED |  | 2200000306 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000308 | [6 empty] | Solar | 700
|  | NR | Rajasthan | Bikaner-IV |  | HAZEL HYBREN PRIVATE LIMITED |  | 2200000334 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | AM GREEN ENERGY PRIVATE LIMITED |  | 2200000319 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | FURIES SOLREN PRIVATE LIMITED |  | 2200000333 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | IRAAX INTERNATIONAL (OPC) PRIVATE LIMITED |  | 2200000343 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | CLEAN MAX GAMMA PRIVATE LIMITED |  | 2200000344 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000373 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000358 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bikaner-IV |  | SJVN GREEN ENERGY LIMITED |  | 2200000423 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000420 | [6 empty] | Solar | 1000
|  | WR | Gujarat | Bhuj PS |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED |  | 2200000634 | [6 empty] | Solar | 600
|  | WR | Gujarat | Bhuj PS |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000658 | [6 empty] | Wind | 99
|  | WR | Gujarat | Bhuj PS |  | NLC INDIA LIMITED |  | 2200000729 | [6 empty] | Solar | 100
|  | WR | Gujarat | Bhuj PS |  | OYSTER GREEN HYBRID ONE PRIVATE LIMITED |  | 2200000783 | [6 empty] | Wind | 99
|  | WR | Gujarat | Bhuj PS |  | NLC INDIA LIMITED |  | 2200000808 | [6 empty] | Wind | 50
|  | WR | Gujarat | Bhuj PS |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED |  | 2200000981 | [6 empty] | Wind | 75.6
|  | WR | Gujarat | Bhuj PS |  | CONTINUUM POWER TRADING (TN) PRIVATE LIMITED |  | 2200001070 | [6 empty] | Wind | 36
|  | WR | Gujarat | KPS-2 (Sec-I) |  | GUJARAT STATE ELECTRICITY CORPORATION LIMITED |  | 2200000048 | [6 empty] | Solar | 3325
|  | WR | Gujarat | KPS-2 (Sec-I) |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000093 | [6 empty] | Solar | 1995
|  | WR | Gujarat | KPS-2 (Sec-II) |  | NTPC Renewable Energy Limited (NREL) |  | 1200003953 | [6 empty] | Solar | 390
|  | WR | Gujarat | KPS-2 (Sec-II) |  | NTPC Renewable Energy Limited (NTPC REL) |  | 0330700007 | [6 empty] | Solar | 300
|  | WR | Gujarat | KPS-3 (Sec-I) |  | NTPC Renewable Energy Limited |  | 0230700010 | [6 empty] | Solar | 1200
|  | WR | Gujarat | KPS-3 (Sec-II) |  | Sarjan Realities Pvt. Ltd. (SRPL) |  | 0230700013 | [6 empty] | Hybrid (RHGS) | 1250
|  | WR | Gujarat | KPS-3 (Sec-II) |  | NHPC Limited |  | 0230700015 | [6 empty] | Solar | 600
|  | WR | Gujarat | Lakadiya PS |  | RDS SOLAR PARK PRIVATE LIMITED |  | 2200000639 | [6 empty] | Solar | 350
|  | WR | Gujarat | Lakadiya PS |  | PERCENTUM RENEWABLES PRIVATE LIMITED |  | 2200000673 | [6 empty] | Hybrid (RHGS) | 100MW: Solar 200MW: Wind Revised to 50MW Solar & 98MW Wind.
|  | WR | Gujarat | Bhuj-II PS (Sec-I) |  | SJVN GREEN ENERGY LIMITED |  | 2200000204 | [6 empty] | Solar | 360
|  | WR | Gujarat | Bhuj-II PS (Sec-II) |  | ABREL (RJ) PROJECTS LIMITED |  | 2200000288 | [6 empty] | Hybrid (RHGS) | 314
|  | WR | Gujarat | Bhuj-II PS (Sec-II) |  | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED |  | 2200000321 | [6 empty] | Hybrid (RHGS) | 362
|  | WR | Gujarat | Bhuj-II PS (Sec-II) |  | CGE RENEWABLES PRIVATE LIMITED |  | 2200000389 | [6 empty] | Hybrid (RHGS) Wind: 30 MW | Solar: 60 MW
|  | WR | Gujarat | Bhuj-II PS (Sec-II) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000444 | [6 empty] | Solar | 100
|  | WR | Gujarat | Bhuj-II PS (Sec-II) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000537 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-II |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000387 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Fatehgarh-II |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000396 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-I |  | ENFINITY GLOBAL SURYA KIRAN PRIVATE LIMITED |  | 2200000411 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | AUXO SUNLIGHT PRIVATE LIMITED |  | 2200000312 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | RENEW SUN POWER PRIVATE LIMITED |  | 2200000316 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ANDHRA PRADESH RESCO ROOFTOP SOLAR PRIVATE LIMITED |  | 2200000412 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | HINDUJA RENEWABLES ENERGY PRIVATE LIMITED |  | 2200000425 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-I |  | ANBOTO SOLAR PRIVATE LIMITED |  | 2200000492 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | GAMMA RENEWABLES INDIA PROJECT ONE PRIVATE LIMITED |  | 2200000355 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000348 | [6 empty] | Solar | 900
|  | SR | Karnataka | Bidar PS |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000422 | [6 empty] | Hybrid (RHGS) | Solar: 188MW Wind: 201 MW BESS: 30MWh
|  | NR | Rajasthan | Bikaner-II |  | Soltown Infra Private Limited (Park) |  | 1200003889 (Enh.) | [6 empty] | Solar | 200
|  | NER | Assam | Bokajan (ISTS) |  | ASSAM POWER DISTRIBUTION COMPANY LIMITED |  | 2200000050 | [6 empty] | Solar | 750
|  | WR | Maharashtra | Dhule PS (Sec-I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000081 | [6 empty] | Wind | 50
|  | WR | Maharashtra | Dhule PS (Sec-I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001036 | [6 empty] | Wind | 160
|  | WR | Maharashtra | Dhule PS (Sec-I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001035 | [6 empty] | Wind | 80
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | JUNIPER GREEN STELLAR PRIVATE LIMITED |  | 2200000063 | [6 empty] | Solar | 300
|  | SR | Karnataka | Gadag PS |  | Halvad Renewables Pvt. Ltd. |  | 0251100015 | [6 empty] | Wind | 130
|  | SR | Tamil Nadu | Karur PS |  | AMPLUS SUN BEAT PRIVATE LIMITED |  | 2200000698 | [6 empty] | Wind | 80
|  | SR | Tamil Nadu | Karur PS |  | AMPLUS THETA ENERGY PVT. LTD. [ERSTWHILE AMPLUS CENEDUS SOLAR PVT. LTD.] |  | 2200000699 | [6 empty] | Wind | 65
|  | SR | Karnataka | Koppal-II PS |  | VENA ENERGY AURA PRIVATE LIMITED |  | 2200000127 | [6 empty] | Wind | 50
|  | SR | Karnataka | Koppal-II PS |  | VENA ENERGY AURA PRIVATE LIMITED |  | 2200000282 | [6 empty] | Wind | 50
|  | SR | Karnataka | Koppal-II PS |  | VENA ENERGY AURA PRIVATE LIMITED |  | 2200000513 | [6 empty] | Wind | 40
|  | SR | Andhra Pradesh 31-12-26 | Kurnool-III PS |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000236 | [6 empty] | Hybrid (RHGS) | Solar: 150 MW Wind:159 MW
|  | SR | Andhra Pradesh 31-12-26 | Kurnool-III PS |  | AMPLUS EVEREST SOLAR PRIVATE LIMITED |  | 2200000543 | [6 empty] | Hybrid (RHGS) | 228(Solar:105 MW; Wind: 126 MW)
|  | SR | Andhra Pradesh 31-12-26 | Kurnool-III PS |  | AMPLUS IIFA SOLAR PRIVATE LIMITED |  | 2200000544 | [6 empty] | Hybrid (RHGS) | 228(Solar:105 MW; Wind: 126 MW)
|  | WR | Gujarat | Lakadiya PS |  | GANEKO SOLAR PRIVATE LIMITED |  | 2200000458 | [6 empty] | Hybrid (RHGS) | 337.36
|  | WR | Gujarat | Lakadiya PS |  | GANEKO SOLAR PRIVATE LIMITED |  | 2200000515 | [6 empty] | Hybrid (RHGS) | 11.63
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | ADYANT ENERSOL PRIVATE LIMITED |  | 2200000976 | [6 empty] | Hybrid (RHGS) | 84
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-II) |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000924 | [6 empty] | Solar | 150
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-II) |  | BHOJRAJ RENEWABLES ENERGY PRIVATE LIMITED |  | 2200000899 | [6 empty] | Wind | 300
|  | NR | UP | Orai |  | BUNDELKHAND SAUR URJA LIMITED |  | 2200000345 | [6 empty] | Solar | 1200
|  | WR | Madhya Pradesh | Pachora PS (Sec- II) |  | AVAADA ENERGY PRIVATE LIMITED (AEPL) |  | 2200000082 | [6 empty] | Solar | 50
|  | WR | Madhya Pradesh | Pachora PS (Sec- II) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000267 | [6 empty] | Solar | 250
|  | WR | Maharashtra | Parli (New) |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001437 | [6 empty] | Wind | 100
|  | WR | Gujarat | Radhanesda PS |  | SPRNG ENERGY PRIVATE LIMITED |  | 2200000461 | [6 empty] | Solar | 100
|  | WR | Madhya Pradesh | Rajgarh SS |  | Sprng Vayu Vidyut Pvt Ltd (SVVPL) |  | 0331300007 | [6 empty] | Wind | 100.8
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000022 | [6 empty] | Wind | 100
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG AKSHAYA URJA PRIVATE LIMITED |  | 2200000133 | [6 empty] | Wind | 67.2
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000083 | [6 empty] | Wind | 50
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000132 | [6 empty] | Hybrid (RHGS) | 50 (Wind) : revised from Hybrid (25S & 25W)after final grant
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | GANEKO TWO ENERGY PRIVATE LIMITED |  | 2200001008 | [6 empty] | Hybrid (RHGS) | 354
|  | SR | Karnataka | Pavagada PS |  | ACME SOLAR HOLDINGS LIMITED |  | 2200001082 | [6 empty] | Solar | 350
|  | SR | Karnataka | Bijapur PS |  | APRAAVA ENERGY PRIVATE LIMITED |  | 2200000171 | [6 empty] | Wind | 300
|  | SR | Karnataka | Bijapur PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000393 | [6 empty] | Wind | 252
|  | SR | Karnataka | Bijapur PS |  | TEQ GREEN POWER XVI PRIVATE LIMITED |  | 2200000397 | [6 empty] | Wind | 125
|  | SR | Karnataka | Bijapur PS |  | TEQ GREEN POWER XVI PRIVATE LIMITED |  | 2200000429 | [6 empty] | Wind | 175
|  | SR | Karnataka | Bijapur PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000447 | [6 empty] | Wind | 50.4
|  | SR | Karnataka | Bijapur PS |  | UPC RENEWABLES INDIA MANAGEMENT PRIVATE LIMITED |  | 2200000584 | [6 empty] | Wind | 160
|  | SR | Karnataka | Bijapur PS |  | EG SOLWIN RENEWABLES PRIVATE LIMITED |  | 2200000687 | [6 empty] | Wind | 100
|  | SR | Karnataka | Gadag-II PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000045 | [6 empty] | Solar | 500
|  | SR | Karnataka | Gadag-II PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000199 | [6 empty] | Wind | 50
|  | SR | Karnataka | Gadag-II PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000385 | [6 empty] | Solar | 250
|  | SR | Karnataka | Gadag-II PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000434 | [6 empty] | Wind | 350
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | ADYANT ENERSOL PRIVATE LIMITED |  | 2200001214 | [6 empty] | Hybrid (RHGS) | 164
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-II) |  | WAAREE RENEWABLE TECHNOLOGIES LIMITED |  | 2200001192 | [6 empty] | Solar | 300
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-II) |  | ACME SOLAR HOLDINGS LIMITED |  | 2200001289 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Bikaner-IV |  | FURIES SOLREN PRIVATE LIMITED |  | 2200000419 | [6 empty] | Solar | 300
|  | SR | Karnataka | Pavagada PS |  | TEQ GREEN POWER XX PRIVATE LIMITED |  | 2200001321 | [6 empty] | Solar | 300
|  | SR | Karnataka | Davangere PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000660 | [6 empty] | Hybrid (RHGS) | 720(Solar:360 MW; Wind: 360)
|  | SR | Karnataka | Davangere PS |  | ILLUMINATE HYBREN PRIVATE LIMITED |  | 2200000701 | [6 empty] | Solar | 300
|  | SR | Karnataka | Davangere PS |  | FURIES SOLREN PRIVATE LIMITED |  | 2200000700 | [6 empty] | Solar | 300
|  | SR | Karnataka | Davangere PS |  | GENTARI RENEWABLES INDIA CASTOR ONE PVT. LTD |  | 2200000714 | [6 empty] | Wind | 350
|  | NR | Rajasthan | Bhadla-II |  | ADANI RENEWABLE ENERGY HOLDING EIGHTEEN LIMITED |  | 2200001044 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Fatehgarh-II |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200001065 | [6 empty] | Solar | 150
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | GREENKO MP01 IREP PRIVATE LIMITED |  | 2200001375 | [6 empty] | Pump Storage | 512
|  | NR | Rajasthan | Merta-II |  | BANYAN ENERGY PRIVATE LIMITED |  | 2200000823 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000644 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | ILLUMINATE HYBREN PRIVATE LIMITED |  | 2200000646 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | CESC LTD |  | 2200000518 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000551 | [6 empty] | Solar | 400
|  | SR | Andhra Pradesh 25-03-27 | Kurnool-IV PS |  | SAEL INDUSTRIES LIMITED |  | 2200000843 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 25-03-27 | Kurnool-IV PS |  | SAEL INDUSTRIES LIMITED |  | 2200000844 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 25-03-27 | Kurnool-IV PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000919 | [6 empty] | Solar | 400
|  | SR | Andhra Pradesh 25-03-27 | Kurnool-IV PS |  | GENTARI RENEWABLES INDIA CASTOR ONE PRIVATE LIMITED |  | 2200000931 | [6 empty] | Wind | 230
|  | SR | Andhra Pradesh 28-03-27 | Anantapur PS |  | AMPLUS CENEDUS SOLAR PRIVATE LIMITED |  | 2200000713 | [6 empty] | Wind | 350
|  | SR | Andhra Pradesh 28-03-27 | Kurnool-III PS |  | INDOSOL SOLAR PRIVATE LIMITED |  | 2200000733 | [6 empty] | Solar | 800
|  | SR | Andhra Pradesh 28-03-27 | Kurnool-III PS |  | INDOSOL SOLAR PRIVATE LIMITED |  | 2200000735 | [6 empty] | Solar | 900
|  | SR | Andhra Pradesh 31-03-27 | Anantapur-II PS |  | ACME SOLAR HOLDINGS PRIVATE LIMITED |  | 2200001003 | [6 empty] | Solar | 500
|  | SR | Andhra Pradesh 31-03-27 | Anantapur-II PS |  | JSW NEO ENERGY LIMITED |  | 2200001074 | [6 empty] | Solar | 500
|  | SR | Andhra Pradesh 31-03-27 | Anantapur-II PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200001077 | [6 empty] | Hybrid (RHGS) | 432
|  | NR | Rajasthan | Barmer-I |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000305 | [6 empty] | Solar | 300
|  | SR | Karnataka | Bidar PS |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000640 | [6 empty] | Hybrid (RHGS) | Total: 312 MW Solar: 132 MW
|  | NR | Rajasthan | Bikaner-IV |  | SUNSURE SOLARPARK FOURTEEN PRIVATE LIMITED |  | 2200000285 | [6 empty] | Solar | 300
|  | SR | Karnataka | Gadag-II PS |  | RENEW VAYU ENERGY PRIVATE LIMITED |  | 2200000292 | [6 empty] | Hybrid (RHGS) | 300 Solar-200 MW Wind-100 MW
|  | SR | Andhra Pradesh 31-03-27 | Kurnool-III PS |  | AMP ENERGY GREEN PRIVATE LIMITED |  | 2200000229 | [6 empty] | Hybrid (RHGS) | Solar: 85 MW Wind:118.8
|  | WR | Gujarat | Lakadiya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000500 | [6 empty] | Wind | 150
|  | WR | Gujarat | Lakadiya PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000641 | [6 empty] | Hybrid (RHGS) | 480 (240 MW: Wind 240 MW: Solar)
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | GANEKO ONE ENERGY PRIVATE LIMITED |  | 2200000720 | [6 empty] | Hybrid (RHGS) | Solar - 255 MW, Wind - 99 MW
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | ADYANT POWER PRIVATE LIMITED |  | 2200000798 | [6 empty] | Hybrid (RHGS) | 200
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-II) |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001301 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Merta-II |  | ACME SOLAR HOLDINGS PRIVATE LIMITED |  | 2200000840 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Merta-II |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED |  | 2200000848 | [6 empty] | Solar | 300
|  | WR | Madhya Pradesh | Neemuch PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000728 | [6 empty] | Solar | 500
|  | WR | Madhya Pradesh | Neemuch PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000938 | [6 empty] | Solar | 500
|  | WR | Madhya Pradesh | Pachora PS (Sec- II) |  | JADE HYBREN PRIVATE LIMITED |  | 2200000617 | [6 empty] | Solar | 300
|  | WR | Madhya Pradesh | Pachora PS (Sec- III) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000817 | [6 empty] | Hybrid (RHGS) | 334
|  | WR | Madhya Pradesh | Pachora PS (Sec- III) |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000883 | [6 empty] | Wind | 297
|  | WR | Madhya Pradesh | Pachora PS (Sec- III) |  | WAFT ENERGY PRIVATE LIMITED |  | 2200000923 | [6 empty] | Wind | 100
|  | WR | Madhya Pradesh | Pachora PS (Sec- III) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000956 | [6 empty] | Solar | 240
|  | WR | Madhya Pradesh | Pachora PS (Sec- III) |  | OYSTER GREEN HYBRID THREE PRIVATE LIMITED |  | 2200000995 | [6 empty] | Hybrid (RHGS) | 140
|  | SR | Karnataka | Tumkur-II PS |  | JAGALURU SOLAR POWER PRIVATE LIMITED |  | 2200001061 | [6 empty] | Solar | 300
|  | SR | Tamil Nadu | Tuticorin-II PS |  | NCL INDUSTRIES LTD |  | 2200001124 | [6 empty] | Hybrid (RHGS) | 220
|  | SR | Tamil Nadu | Tuticorin-II PS |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED |  | 2200001996 | [6 empty] | Solar | 200
|  | SR | Tamil Nadu | Tuticorin-II PS |  | VIVID SOLAIRE ENERGY PRIVATE LIMITED |  | 2200002003 | [6 empty] | Wind | 50
|  | SR | Andhra Pradesh 01-04-27 | Anantapur-II PS |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000872 | [6 empty] | Wind | 349.8
|  | SR | Andhra Pradesh 01-04-27 | Kurnool-III PS |  | INDOSOL SOLAR PRIVATE LIMITED |  | 2200000736 | [6 empty] | Solar | 900
|  | NR | Rajasthan | Sirohi |  | VAYUNA RENEWABLES INDIA PROJECT PRIVATE LIMITED |  | 2200000758 | [6 empty] | Solar | 300
|  | SR | Karnataka | Bijapur PS |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000586 | [6 empty] | Wind | 252
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | ASNEN SOLAR PRIVATE LIMITED |  | 2200000752 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Merta-II |  | Sembcorp Green Infra Pvt. Ltd. (erstwhile Green Infra Wind Energy Private Limited) |  | 2200000812 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Merta-II |  | GREEN INFRA WIND ENERGY PRIVATE LIMITED |  | 2200000813 | [6 empty] | Solar | 300
|  | NR | UP | Robertsganj |  | GREENKO UP01 IREP PRIVATE LIMITED |  | 2200000524 | [6 empty] | Pump Storage | 672
|  | NR | UP | Robertsganj |  | GREENKO UP01 IREP PRIVATE LIMITED |  | 2200000525 | [6 empty] | Pump Storage | 672
|  | NR | UP | Robertsganj |  | GREENKO UP01 IREP PRIVATE LIMITED |  | 2200000526 | [6 empty] | Pump Storage | 672
|  | SR | Karnataka | Tumkur-II PS |  | ORION HYBREN PRIVATE LIMITED |  | 2200000999 | [6 empty] | Hybrid (RHGS) | 300
|  | NR | Rajasthan | Barmer-I |  | GREEN INFRA RENEWABLE PROJECTS LIMITED |  | 2200000410 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Bhadla-II |  | GREEN INFRA CLEAN WIND LIMITED |  | 2200000437 | [6 empty] | Solar | 300
|  | SR | Karnataka | Bidar PS |  | PULSE HYBREN PRIVATE LIMITED |  | 2200001001 | [6 empty] | Solar | 300
|  | SR | Karnataka | Gadag-II PS |  | GREEN INFRA RENEWABLE PROJECTS LIMITED |  | 2200000435 | [6 empty] | Wind | 300
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-III) |  | JSP GREEN PRIVATE LIMITED |  | 2200001356 | [6 empty] | Wind | 350
|  | SR | Andhra Pradesh 30-06-27 | Anantapur-II PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000780 | [6 empty] | Wind | 400
|  | SR | Andhra Pradesh 30-06-27 | Anantapur-II PS |  | ORION HYBREN PRIVATE LIMITED |  | 2200001000 | [6 empty] | Hybrid (RHGS) | 300
|  | SR | Karnataka | Bidar PS |  | SPRNG POWERINFRA PRIVATE LIMITED |  | 2200000560 | [6 empty] | Wind | 200
|  | WR | Maharashtra | Dhule PS (Sec-I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001150 | [6 empty] | Wind | 200
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | Sprng Pavana Urja Private Limited |  | 1200003719 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | SPRNG PAVANA URJA PRIVATE LIMITED |  | 2200000018 | [6 empty] | Solar | 100
|  | WR | Gujarat | Jam Khambhaliya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000253 | [6 empty] | Wind | 100
|  | WR | Gujarat | Lakadiya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000376 | [6 empty] | Wind | 300
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-II) |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001280 | [6 empty] | Solar | 300
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-II) |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001279 | [6 empty] | Solar | 300
|  | WR | Madhya Pradesh | Pachora PS (Sec- III) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001325 | [6 empty] | Solar | 47
|  | WR | Gujarat | Radhanesda PS |  | SPRNG ENERGY PRIVATE LIMITED |  | 2200000460 | [6 empty] | Solar | 150
|  | WR | Gujarat | Radhanesda PS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000546 | [6 empty] | Solar | 50
|  | WR | Gujarat | Raghanesda PS |  | JSW NEO ENERGY LIMITED |  | 2200001014 | [6 empty] | Solar | 200
|  | WR | Gujarat | Raghanesda PS |  | JSW NEO ENERGY LIMITED |  | 2200001020 | [6 empty] | Solar | 200
|  | WR | Gujarat | Raghanesda PS |  | ACME SOLAR HOLDINGS LIMITED |  | 2200001064 | [6 empty] | Solar | 400
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000340 | [6 empty] | Wind | 82
|  | NR | Rajasthan | Sirohi |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000779 | [6 empty] | Solar | 300
|  | SR | Karnataka | Bidar PS |  | QUEST HYBREN PRIVATE LIMITED |  | 2200001002 | [6 empty] | Solar | 300
|  | WR | Madhya Pradesh | Morena PS |  | GREENKO RJ01 IREP PRIVATE LIMITED |  | 2200000685 | [6 empty] | Pump Storage | 880
|  | NR | Rajasthan | Merta-II |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000842 | [6 empty] | Solar | 300
|  | SR | Karnataka | Bellary PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000825 | [6 empty] | Wind | 76
|  | SR | Karnataka | Bellary PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001103 | [6 empty] | Wind | 55
|  | SR | Karnataka | Bellary PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001102 | [6 empty] | Wind | 345
|  | SR | Karnataka | Bellary PS |  | GENTARI RENEWABLES INDIA UTILITIES 2 PRIVATE LIMITED |  | 2200001113 | [6 empty] | Solar | 400
|  | SR | Karnataka | Bellary PS |  | GENTARI RENEWABLES INDIA UTILITIES 2 PRIVATE LIMITED |  | 2200001114 | [6 empty] | Wind | 132
|  | SR | Karnataka | Bellary PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200001140 | [6 empty] | Solar | 300
|  | SR | Karnataka | Bellary PS |  | SERENTICA RENEWABLES INDIA 11 PRIVATE LIMITED |  | 2200001138 | [6 empty] | Wind | 100
|  | SR | Karnataka | Davangere PS |  | JADE HYBREN PRIVATE LIMITED |  | 2200000876 | [6 empty] | Hybrid (RHGS) | 300
|  | SR | Karnataka | Davangere PS |  | JSW NEO ENERGY LIMITED |  | 2200000932 | [6 empty] | Wind | 325
|  | SR | Karnataka | Davangere PS |  | JSW NEO ENERGY LIMITED |  | 2200001019 | [6 empty] | Wind | 100
|  | SR | Karnataka | Davangere PS |  | JSW NEO ENERGY LIMITED |  | 2200001015 | [6 empty] | Wind | 100
|  | WR | Madhya Pradesh | Neemuch PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000991 | [6 empty] | Solar | 200
|  | WR | Gujarat | Raghanesda PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000993 | [6 empty] | Solar | 300
|  | WR | Gujarat | Raghanesda PS |  | AZURE POWER SIXTY THREE PRIVATE LIMITED |  | 2200001107 | [6 empty] | Solar | 300
|  | SR | Karnataka | Bijapur PS |  | VISMAYA RENEWABLES INDIA PROJECT PRIVATELIMITED |  | 2200000692 | [6 empty] | Wind | 300
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | CLEAN MAX SOLARIS PRIVATE LIMITED |  | 2200000676 | [6 empty] | Hybrid (RHGS) | 150MW: Wind 50MW: Solar
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | CLEAN MAX ALCHEMY PRIVATE LIMITED |  | 2200000678 | [6 empty] | Hybrid (RHGS) | 150MW: Wind 50MW: Solar
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | TEQ GREEN POWER XIII PRIVATE LIMITED |  | 2200000669 | [6 empty] | Wind | 120.9
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000737 | [6 empty] | Hybrid (RHGS) | Solar 120 MW, Wind 180 MW & BESS 30 MW)
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000750 | [6 empty] | Solar | 300
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | AZURE POWER SIXTY THREE PRIVATE LIMITED |  | 2200000799 | [6 empty] | Hybrid (RHGS) | 300
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | FEMUND SOLAR PRIVATE LIMITED |  | 2200000902 | [6 empty] | Solar | 150
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | RELIANCE INDUSTRIES LIMITED |  | 2200001104 | [6 empty] | Solar | 1000
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | RELIANCE INDUSTRIES LIMITED |  | 2200001105 | [6 empty] | Solar | 1000
|  | WR | Gujarat | Lakadia-II (Sec-II) |  | JSW NEO ENERGY LIMITED |  | 2200000705 | [6 empty] | Wind | 700
|  | WR | Gujarat | Lakadia-II (Sec-II) |  | BN DISPATCHABLE-2 PRIVATE LIMITED |  | 2200000986 | [6 empty] | Hybrid (RHGS) | 250
|  | WR | Gujarat | Lakadia-II (Sec-II) |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200001004 | [6 empty] | Hybrid (RHGS) | 272.8
|  | WR | Gujarat | Lakadia-II (Sec-II) |  | BN PEAK POWER-2 PRIVATE LIMITED |  | 2200000987 | [6 empty] | Hybrid (RHGS) | 250
|  | WR | Gujarat | Lakadia-II (Sec-II) |  | ADANI RENEWABLE ENERGY TEN LIMITED |  | 2200001071 | [6 empty] | Wind | 225
|  | WR | Gujarat | Lakadia-II (Sec-II) |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200001093 | [6 empty] | Solar | 150
|  | WR | Gujarat | Lakadia-II (Sec-II) |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200001127 | [6 empty] | Hybrid (RHGS) | 139
|  | WR | Maharashtra | Solapur PS (400 Sec-II) |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200001135 | [6 empty] | Solar | 350
|  | WR | Maharashtra | Solapur PS (400 Sec-II) |  | TORRENT URJA 18 PRIVATE LIMITED |  | 2200001223 | [6 empty] | Hybrid (RHGS) | 650
|  | WR | Maharashtra | Solapur PS (400 Sec-II) |  | UNIQUE HYBRID GLOBAL RENEWABLE ENERGY PRIVATE LIMITED |  | 2200001359 | [6 empty] | Solar | 390
|  | WR | Gujarat | Raghanesda PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000988 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 31-12-27 | Anantapur-II PS |  | GANEKO THREE ENERGY PRIVATE LIMITED |  | 2200000869 | [6 empty] | Hybrid (RHGS) | 354
|  | SR | Karnataka | Bidar PS |  | AMPIN ENERGY UTILITY PRIVATE LIMITED |  | 2200000762 | [6 empty] | Hybrid (RHGS) | 185.4
|  | SR | Karnataka | Bidar PS |  | AMPIN ENERGY UTILITY PRIVATE LIMITED |  | 2200000763 | [6 empty] | Hybrid (RHGS) | 185.4
|  | SR | Karnataka | Bidar PS |  | AMPIN ENERGY UTILITY PRIVATE LIMITED |  | 2200000892 | [6 empty] | Hybrid (RHGS) | 185.4
|  | SR | Karnataka | Bidar PS |  | AMP ENERGY C&I THIRTEEN PRIVATE LIMITED |  | 2200000893 | [6 empty] | Hybrid (RHGS) | 68.9
|  | SR | Karnataka | Bijapur PS |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000708 | [6 empty] | Wind | 48
|  | WR | Gujarat | Jam Khambhaliya PS |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED |  | 2200000917 | [6 empty] | Wind | 207.9
|  | WR | Gujarat | Jam Khambhaliya PS |  | K.P. ENERGY LIMITED |  | 2200000913 | [6 empty] | Wind | 100
|  | SR | Tamil Nadu | Karur PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000967 | [6 empty] | Wind | 82.5
|  | SR | Tamil Nadu | Karur PS |  | NANNAI SOLAR PARK PRIVATE LIMITED |  | 2200001023 | [6 empty] | Wind | 57
|  | SR | Tamil Nadu | Karur PS |  | NAVALADI WIND PARK PRIVATE LIMITED |  | 2200001033 | [6 empty] | Wind | 100
|  | SR | Andhra Pradesh 31-12-27 | Kurnool-IV PS |  | PRATAPATI ENERGY (SEVEN) PRIVATE LIMITED |  | 2200001099 | [6 empty] | Hybrid (RHGS) | 354
|  | NR | Rajasthan | Merta-II |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000879 | [6 empty] | Solar | 300
|  | WR | Gujarat | Jamnagar S/s |  | MFA RENEWABLES PRIVATE LIMITED |  | 2200001137 | [6 empty] | Wind | 297
|  | WR | Gujarat | Jamnagar S/s |  | OPWIND ENERGY PRIVATE LIMITED |  | 2200001189 | [6 empty] | Hybrid (RHGS) | 254
|  | WR | Gujarat | Jamnagar S/s |  | KADODIYA WIND ENERGY PRIVATE LIMITED |  | 2200001230 | [6 empty] | Wind | 100
|  | WR | Gujarat | Jamnagar S/s |  | SATPURA RENEWABLE PRIVATE LIMITED |  | 2200001349 | [6 empty] | Solar | 349
|  | SR | Andhra Pradesh 01-01-28 | Kurnool-III PS |  | ADANI RENEWABLE ENERGY FIFTY ONE LIMITED |  | 2200000508 | [6 empty] | Pump Storage | 1250
|  | WR | Maharashtra | South Kalamb |  | THE TATA POWER COMPANY LIMITED |  | 2200000177 | [6 empty] | Pump Storage | 1150
|  | WR | Gujarat | Raghanesda PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001048 | [6 empty] | Solar | 200
|  | SR | Andhra Pradesh 29-02-28 | Anantapur PS |  | RENEW VIKRAM SHAKTI PRIVATE LIMITED |  | 2200000372 | [6 empty] | Hybrid (RHGS) | 160 (Solar:40 MW, Wind:
|  | SR | Andhra Pradesh 29-02-28 | Anantapur PS |  | RENEW VIKRAM SHAKTI PRIVATE LIMITED |  | 2200000583 | [6 empty] | Wind | 140
|  | WR | Gujarat | Raghanesda PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000989 | [6 empty] | Solar | 100
|  | WR | Gujarat | Raghanesda PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000992 | [6 empty] | Solar | 100
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-III) |  | TEQ GREEN POWER XXII PRIVATE LIMITED |  | 2200001431 | [6 empty] | Hybrid (RHGS) | 250
|  | SR | Andhra Pradesh 31-03-28 | Anantapur-II PS |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200001294 | [6 empty] | Hybrid (RHGS) | 272.8
|  | SR | Andhra Pradesh 31-03-28 | Anantapur-II PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001303 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 31-03-28 | Anantapur-II PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001304 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 31-03-28 | Anantapur-II PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001318 | [6 empty] | Wind | 300
|  | SR | Andhra Pradesh 31-03-28 | Anantapur-II PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001319 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 31-03-28 | Anantapur-II PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001341 | [6 empty] | Wind | 300
|  | SR | Andhra Pradesh 31-03-28 | Anantapur-II PS |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200001416 | [6 empty] | Hybrid (RHGS) | 281.8
|  | SR | Andhra Pradesh 31-03-28 | Kurnool-IV PS |  | ESSAR RENEWABLES LIMITED |  | 2200001364 | [6 empty] | Solar | 300
|  | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | [6 empty] | #REF! | #REF!
|  | SR | Andhra Pradesh 31-03-28 | Kurnool-IV PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001362 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 31-03-28 | Kurnool-IV PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001363 | [6 empty] | Solar | 600
|  | SR | Andhra Pradesh 31-03-28 | Kurnool-IV PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001383 | [6 empty] | Wind | 300
|  | SR | Andhra Pradesh 31-03-28 | Kurnool-IV PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001384 | [6 empty] | Wind | 300
|  | WR | Gujarat | Raghanesda PS |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200001018 | [6 empty] | Solar | 350
|  | NR | Rajasthan | Sirohi |  | IZHMA SOLAR PRIVATE LIMITED |  | 2200000743 | [6 empty] | Solar | 200
|  | SR | Karnataka | Tumkur-II PS |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200001017 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III |  | FRUGAL ENERGY PRIVATE LIMITED |  | 2200000118 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bhadla-III |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000144 | [6 empty] | Solar | 300
|  | WR | Maharashtra | Dhule PS (Sec-I) |  | JUNIPER GREEN GEM PRIVATE LIMITED |  | 2200001276 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | SPRNG PAVANA URJA PRIVATE LIMITED |  | 2200000034 | [6 empty] | Solar | 150
|  | WR | Gujarat | Jam Khambhaliya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000379 | [6 empty] | Wind | 200
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000926 | [6 empty] | Wind | 150
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000428 | [6 empty] | Wind | 300
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED |  | 2200001037 | [6 empty] | Hybrid (RHGS) | 295
|  | WR | Gujarat | Raghanesda PS |  | SPRNG WIND ENERGY PRIVATE LIMITED |  | 2200000612 | [6 empty] | Solar | 200
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000819 | [6 empty] | Wind | 16.8
|  | NR | Rajasthan | Bhadla-III |  | SOLARCRAFT POWER INDIA 4 PRIVATE LIMITED |  | 2200000192 | [6 empty] | Solar | 110
|  | NR | Rajasthan | Bhadla-III |  | GREEN INFRA CLEAN ENERGY GENERATION LIMITED |  | 2200000232 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III |  | RENEW SOLAR (SHAKTI SIX) PRIVATE LIMITED |  | 2200000275 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bhadla-III |  | MALUR RENEWABLES PRIVATE LIMITED |  | 2200000266 | [6 empty] | Solar | 650
|  | NR | Rajasthan | Bhadla-III |  | SOLARCRAFT POWER INDIA 4 PRIVATE LIMITED |  | 2200000300 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bhadla-III |  | RENEW SOLAR (SHAKTI SIX) PRIVATE LIMITED |  | 2200000309 | [6 empty] | Solar | 400
|  | SR | Andhra Pradesh 30-09-28 | Anantapur-II PS |  | GREEN INFRA WIND ENERGY PRIVATE LIMITED |  | 2200000820 | [6 empty] | Solar | 300
|  | WR | Gujarat | KPS-2 (Sec-I) |  | GUJARAT INDUSTRIES POWER COMPANY LTD. |  | 2200000159 | [6 empty] | Solar | 2375
|  | WR | Gujarat | Jam Khambhaliya PS |  | MIYANI POWER INFRA LLP |  | 2200001156 | [6 empty] | Wind | 321.3
|  | WR | Gujarat | Jam Khambhaliya PS |  | MIYANI POWER INFRA LLP |  | 2200001155 | [6 empty] | Wind | 321.3
|  | WR | Gujarat | Kalyanpur PS (Sec-I) |  | IRIS RENEWABLES ALPHA TWO PRIVATE LIMITED |  | 2200000674 | [6 empty] | Wind | 300
|  | WR | Gujarat | Kalyanpur PS (Sec-I) |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000935 | [6 empty] | Wind | 300
|  | WR | Gujarat | Kalyanpur PS (Sec-I) |  | TORRENT SAURYA URJA 2 PRIVATE LIMITED |  | 2200001069 | [6 empty] | Hybrid (RHGS) | 1200
|  | WR | Gujarat | Kalyanpur PS (Sec-I) |  | DEVPUR RENEWABLES PRIVATE LIMITED |  | 2200001132 | [6 empty] | Hybrid (RHGS) | 200
|  | WR | Gujarat | Kalyanpur PS (Sec-I) |  | ADITYA BIRLA RENEWABLES LIMITED |  | 2200001133 | [6 empty] | Hybrid (RHGS) | 300
|  | WR | Gujarat | Kalyanpur PS (Sec-I) |  | TORRENT SAURYA URJA 2 PRIVATE LIMITED |  | 2200001159 | [6 empty] | Hybrid (RHGS) | 300
|  | WR | Gujarat | Kalyanpur PS (Sec-I) |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200001209 | [6 empty] | Wind | 50
|  | NR | Rajasthan | Bhadla-III |  | PRERAK SOLAR URJA PRIVATE LIMITED |  | 2200000360 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bhadla-III |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000407 | [6 empty] | Solar | 1000
|  | SR | Karnataka | Bidar PS |  | SPRNG GREEN ENERGY PRIVATE LIMITED |  | 2200000753 | [6 empty] | Wind | 100
|  | WR | Gujarat | Raghanesda PS |  | SPRNG OJAS PRIVATE LIMITED |  | 2200000614 | [6 empty] | Solar | 200
|  | WR | Gujarat | Raghanesda PS |  | SPRNG WIND ENERGY PRIVATE LIMITED |  | 2200001160 | [6 empty] | Hybrid (RHGS) | 164
|  | WR | Gujarat | Raghanesda PS |  | SPRNG OJAS PRIVATE LIMITED |  | 2200000651 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Ramgarh |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000499 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Ramgarh |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000550 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Ramgarh |  | MIGOS HYBREN PRIVATE LIMITED |  | 2200000618 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Ramgarh |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000598 | [6 empty] | Solar | 500
|  | NR | Rajasthan | Ramgarh |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000599 | [6 empty] | Solar | 500
|  | NR | UP | Robertsganj |  | AVAADA WATERBATTERY PRIVATE LIMITED |  | 2200000553 | [6 empty] | Pump Storage | 1120
|  | NR | Rajasthan | Ramgarh |  | PRAVAT RENEWABLES INDIA PROJECT PRIVATE LIMITED |  | 2200000452 | [6 empty] | Solar | 300
|  | WR | Gujarat | Lakadiya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000511 | [6 empty] | Solar | 200
|  | WR | Gujarat | KPS-1 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000478 | [6 empty] | Hybrid (RHGS) | 650
|  | WR | Gujarat | KPS-1 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000479 | [6 empty] | Hybrid (RHGS) | 100
|  | WR | Gujarat | KPS-1 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000784 | [6 empty] | Wind | 60
|  | WR | Gujarat | KPS-3 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000476 | [6 empty] | Hybrid (RHGS) | 1250
|  | WR | Gujarat | KPS-3 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000477 | [6 empty] | Hybrid (RHGS) | 75
|  | WR | Gujarat | KPS-3 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000602 | [6 empty] | Hybrid (RHGS) | 65 MW (Solar: 50MW
|  | WR | Gujarat | KPS-3 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000603 | [6 empty] | Wind | 75
|  | WR | Gujarat | KPS-3 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000785 | [6 empty] | Wind | 100
|  | WR | Gujarat | KPS-3 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000786 | [6 empty] | Wind | 195
|  | WR | Gujarat | KPS-3 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000953 | [6 empty] | Hybrid (RHGS) | 1530
|  | SR | Karnataka | Bidar PS |  | SPRNG VAYU KIRAN PRIVATE LIMITED |  | 2200000751 | [6 empty] | Wind | 200
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200001062 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Barmer-II |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000636 | [6 empty] | Solar | 450
|  | NR | Rajasthan | Barmer-II |  | SPRNG URJA PRIVATE LIMITED |  | 2200000681 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Barmer-II |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000810 | [6 empty] | Solar | 717
|  | NR | Rajasthan | Barmer-II |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000906 | [6 empty] | Solar | 500
|  | NR | Rajasthan | Barmer-II |  | SPRNG RENEWABLE RESOURCES PRIVATE LIMITED |  | 2200000531 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Barmer-II |  | SPRNG URJA PRIVATE LIMITED |  | 2200000539 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Barmer-II |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000567 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-II |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000580 | [6 empty] | Solar | 500
|  | NR | Rajasthan | Barmer-II |  | AMARESHA RENAWABLES INDIA PROJECT PRIVATE LIMITED |  | 2200000715 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-II |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000778 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-II |  | ADANI RENEWABLE ENERGY TWO LIMITED |  | 2200000809 | [6 empty] | Wind | 595
|  | NR | Rajasthan | Barmer-II |  | ADANI RENEWABLE ENERGY TWO LIMITED |  | 2200000807 | [6 empty] | Wind | 600
|  | NR | Rajasthan | Bikaner-V |  | SAURYA URJA COMPANY OF RAJASTHAN LIMITED |  | 2200000475 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-V |  | IRAAX INTERNATIONAL (OPC) PRIVATE LIMITED |  | 2200000484 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-V |  | IRAAX INTERNATIONAL (OPC) PRIVATE LIMITED |  | 2200000540 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-V |  | AVAADA RJBIKANER PRIVATE LIMITED |  | 2200000561 | [6 empty] | Solar | 136
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ADITYA BIRLA RENEWABLES LIMITED |  | 2200001128 | [6 empty] | Hybrid (RHGS) | 100
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | SPRNG GREEN ENERGY 2 PRIVATE LIMITED |  | 2200000824 | [6 empty] | Solar | 600
|  | WR | Gujarat | Raghanesda PS |  | JSW Energy Utkal Limited |  | 2200000650 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Bhadla-IV |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000516 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000521 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Bhadla-IV |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000522 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | KANTIDA RENEWABLES INDIA PROJECT PRIVATE LIMITED |  | 2200000761 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000811 | [6 empty] | Solar | 765
|  | NR | Rajasthan | Bhadla-IV |  | DEMETER SUN POWER PRIVATE LIMITED |  | 2200000875 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001085 | [6 empty] | Solar | 700
|  | NR | Rajasthan | Bhadla-IV |  | AVAADA RJSUSTAINABLE PRIVATE LIMITED |  | 2200001316 | [6 empty] | Solar | 660
|  | NR | Rajasthan | Bhadla-IV |  | ARIGHT FOODS AND ENERGY PRIVATE LIMITED |  | 2200001404 | [6 empty] | Solar | 2000
|  | NR | Rajasthan | Bikaner-V |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000726 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-V |  | SA RENEWABLE INFRA PRIVATE LIMITED |  | 2200000755 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-V |  | VENA ENERGY VINDHYA WIND POWER PRIVATE LIMITED |  | 2200000796 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | SOLARCRAFT POWER INDIA 8 PRIVATE LIMITED |  | 2200000866 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200001021 | [6 empty] | Solar | 350
|  | NR | Rajasthan | Bikaner-V |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200001056 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-V |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001126 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Bikaner-V |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200001210 | [6 empty] | Solar | 130
|  | NR | Rajasthan | Bikaner-V |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200001261 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200001262 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | AVAADA SURYAENERGY PRIVATE LIMITED |  | 2200001254 | [6 empty] | Solar | 560
|  | NR | Rajasthan | Bikaner-V |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001353 | [6 empty] | Solar | 350
|  | NR | Rajasthan | Bikaner-V |  | AVAADA RJBIKANER PRIVATE LIMITED |  | 2200001326 | [6 empty] | Solar | 354
|  | NR | Rajasthan | Ramgarh |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000661 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Ramgarh |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000662 | [6 empty] | Solar | 284
|  | NR | Rajasthan | Ramgarh |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000672 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Ramgarh-II |  | ADANI RENEWABLE ENERGY PARK RAJASTHAN LIMITED |  | 2200000600 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Ramgarh-II |  | ADANI RENEWABLE ENERGY PARK RAJASTHAN LIMITED |  | 2200000601 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Ramgarh-II |  | JSW NEO ENERGY LIMITED |  | 2200000689 | [6 empty] | Solar | 700
|  | NR | Rajasthan | Ramgarh-II |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000777 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Ramgarh-II |  | RJS RENEWABLES PRIVATE LIMITED |  | 2200000782 | [6 empty] | Wind | 150
|  | NR | Rajasthan | Ramgarh-II |  | SHN GREEN POWER PRIVATE LIMITED |  | 2200001198 | [6 empty] | Wind | 297
|  | NR | Rajasthan | Ramgarh-II |  | JUNACHAY WIND ENERGY PRIVATE LIMITED |  | 2200001382 | [6 empty] | Wind | 100
|  | NR | Rajasthan | Ramgarh-II |  | DHARVI KALAN WIND ENERGY PRIVATE LIMITED |  | 2200001391 | [6 empty] | Wind | 100
|  | NR | Rajasthan | Ramgarh-II |  | DANGRI WIND ENERGY PRIVATE LIMITED |  | 2200001390 | [6 empty] | Wind | 100
|  | NR | Rajasthan | Ramgarh-II |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200001523 | [6 empty] | Wind | 300
|  | NR | Rajasthan | Bhadla-IV |  | VISMAYA FOUR RENEWABLES PRIVATE LIMITED |  | 2200000910 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-II |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000973 | [6 empty] | Solar | 100
|  | SR | Karnataka | Bidar PS |  | SPRNG ENERGY PRIVATE LIMITED |  | 2200000767 | [6 empty] | Wind | 100
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000850 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000886 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000887 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000888 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000889 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000890 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Jalore |  | SPRNG VAAYU URJA PRIVATE LIMITED |  | 2200001006 | [6 empty] | Solar | 600
|  | WR | Gujarat | Raghanesda PS |  | SPRNG VAYU KIRAN PRIVATE LIMITED |  | 2200001161 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Sanchore |  | HR SARASWATI ENERGY PRIVATE LIMITED |  | 2200000946 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001026 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Barmer-III |  | TEQ GREEN POWER IX PRIVATE LIMITED |  | 2200001300 | [6 empty] | Solar | 208.5
|  | NR | Rajasthan | Barmer-III |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001352 | [6 empty] | Solar | 750
|  | NR | Rajasthan | Barmer-III |  | ACME GAMMA URJA PRIVATE LIMITED |  | 2200001366 | [6 empty] | Solar | 350
|  | NR | Rajasthan | Barmer-III |  | ENREN-IV ENERGY PRIVATE LIMITED |  | 2200001398 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001422 | [6 empty] | Solar | 800
|  | NR | Rajasthan | Barmer-III |  | POKHRAN WIND ENERGY PRIVATE LIMITED |  | 2200001440 | [6 empty] | Wind | 99
|  | NR | Rajasthan | Barmer-III |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001503 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | APRAAVA ENERGY PRIVATE LIMITED |  | 2200001557 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | UNIQUE HYTECH RENEWABLE ENERGY PRIVATE LIMITED |  | 2200001622 | [6 empty] | Hybrid (RHGS) | 1000
|  | NR | Rajasthan | Jalore |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200001087 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | VISMAYA FOUR RENEWABLES PRIVATE LIMITED |  | 2200001284 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Barmer-II |  | VISMAYA FIVE RENEWABLES PRIVATE LIMITED |  | 2200000954 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-II |  | VISMAYA FIVE RENEWABLES PRIVATE LIMITED |  | 2200001285 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Barmer-III |  | FOXTROT SOLAR RENEWABLES ENERGY PRIVATE LIMITED |  | 2200001057 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Barmer-III |  | GREEN INFRA RENEWABLE ENERGY FARMS PRIVATE LIMITED |  | 2200001141 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | GREEN INFRA RENEWABLE ENERGY FARMS PRIVATE LIMITED |  | 2200001194 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001188 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-III |  | FOXTROT SOLAR RENEWABLES ENERGY PRIVATE LIMITED |  | 2200001252 | [6 empty] | Solar | 74
|  | NR | Rajasthan | Merta-III |  | ENREN-III ENERGY PRIVATE LIMITED |  | 2200000860 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Pali |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200001089 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Pali |  | DIYOS THREE RENEWABLES PRIVATE LIMITED |  | 2200001100 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-V |  | SPRNG GREEN ENERGY 4 PRIVATE LIMITED |  | 2200001417 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bhadla-V |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001464 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Barmer-III |  | FOXTROT SOLAR RENEWABLES ENERGY PRIVATE LIMITED |  | 2200001088 | [6 empty] | Solar | 80
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000890 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Jalore |  | SPRNG VAAYU URJA PRIVATE LIMITED |  | 2200001006 | [6 empty] | Solar | 600
|  | WR | Gujarat | Raghanesda PS |  | SPRNG VAYU KIRAN PRIVATE LIMITED |  | 2200001161 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Sanchore |  | HR SARASWATI ENERGY PRIVATE LIMITED |  | 2200000946 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001026 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Barmer-III |  | TEQ GREEN POWER IX PRIVATE LIMITED |  | 2200001300 | [6 empty] | Solar | 208.5
|  | NR | Rajasthan | Barmer-III |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001352 | [6 empty] | Solar | 750
|  | NR | Rajasthan | Barmer-III |  | ACME GAMMA URJA PRIVATE LIMITED |  | 2200001366 | [6 empty] | Solar | 350
|  | NR | Rajasthan | Barmer-III |  | ENREN-IV ENERGY PRIVATE LIMITED |  | 2200001398 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001422 | [6 empty] | Solar | 800
|  | NR | Rajasthan | Barmer-III |  | ROHAT SOLAR PARK PRIVATE LIMITED |  | 2200001372 | [6 empty] | Solar | 350
|  | NR | Rajasthan | Barmer-III |  | UNIQUE HYTECH RENEWABLE ENERGY PRIVATE LIMITED |  | 2200001407 | [6 empty] | Wind | 150
|  | NR | Rajasthan | Barmer-III |  | POKHRAN WIND ENERGY PRIVATE LIMITED |  | 2200001440 | [6 empty] | Wind | 99
|  | NR | Rajasthan | Barmer-III |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001503 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | APRAAVA ENERGY PRIVATE LIMITED |  | 2200001557 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | UNIQUE HYTECH RENEWABLE ENERGY PRIVATE LIMITED |  | 2200001622 | [6 empty] | Hybrid (RHGS) | 1000
|  | NR | Rajasthan | Jalore |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200001087 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | VISMAYA FOUR RENEWABLES PRIVATE LIMITED |  | 2200001284 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Barmer-II |  | VISMAYA FIVE RENEWABLES PRIVATE LIMITED |  | 2200000954 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bikaner-V |  | ADYANT ENERSOL PRIVATE LIMITED |  | 2200001786 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Ramgarh-II |  | JIRE GREEN ENERGY PROJECT THREE LIMITED |  | 2200001717 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Ramgarh-II |  | WAAREE FOREVER ENERGIES PRIVATE LIMITED |  | 2200001735 | [6 empty] | Hybrid (RHGS) | 600
|  | NR | Rajasthan | Barmer-II |  | VISMAYA FIVE RENEWABLES PRIVATE LIMITED |  | 2200001285 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Barmer-III |  | FOXTROT SOLAR RENEWABLES ENERGY PRIVATE LIMITED |  | 2200001057 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Barmer-III |  | GREEN INFRA RENEWABLE ENERGY FARMS PRIVATE LIMITED |  | 2200001141 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | GREEN INFRA RENEWABLE ENERGY FARMS PRIVATE LIMITED |  | 2200001194 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001188 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-III |  | FOXTROT SOLAR RENEWABLES ENERGY PRIVATE LIMITED |  | 2200001252 | [6 empty] | Solar | 74
|  | NR | Rajasthan | Merta-III |  | ENREN-III ENERGY PRIVATE LIMITED |  | 2200000860 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Pali |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200001089 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Pali |  | DIYOS THREE RENEWABLES PRIVATE LIMITED |  | 2200001100 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-V |  | SPRNG GREEN ENERGY 4 PRIVATE LIMITED |  | 2200001417 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bhadla-V |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001464 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Pali |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001866 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sanchore |  | GODAVARI GREEN ENERGY PRIVATE LIMITED |  | 2200001810 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bhadla-V |  | AZURE POWER FIFTY ONE PRIVATE LIMITED |  | 2200001420 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Bhadla-V |  | TORRENT GREEN ENERGY PRIVATE LIMITED |  | 2200001642 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bhadla-V |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED |  | 2200001700 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-V |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001781 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Bhadla-V |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001864 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-V |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001865 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-V |  | VISMAYA FOUR RENEWABLES PRIVATE LIMITED |  | 2200001827 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sanchore |  | WAAREE FOREVER ENERGIES PRIVATE LIMITED |  | 2200001901 | [6 empty] | Solar | 300
|  | WR |  | 400/220kV Jam Khambhaliya (GIS) PS # | 22°08'41"N 69°40'38"E
|  | WR |  | 765/400/220kV Bhuj PS# | 23.45583333˚ N, 69.56235833˚ E
|  | WR |  | 765/400/220kV Bhuj-II PS# | Boundary Coordinates 23°22'29.92"N 69° 8'32.39"E 23°22'26.60"N 69° 8'55.06"E 23°22'6.44"N 69° 8'43.33"E 23°22'15.91"N 69° 8'24.01"E
|  | WR |  | 400/220kV Bhachau S/s | 23.20613889˚ N, 70.18733333˚ E
|  | WR |  | Khavda PS-I | Boundary Coordinates: 534252.00 m E 2665370.00 m N 534924.00 m E 2665328.00 m N 534892.00 m E 2664895.00 m N 534253.00 m E 2664935.00 m N
|  | WR |  | Khavda PS-II
|  | WR |  | Banaskantha (Radhanesda) PS [GIS] (Vav) | Boundary Coordinates: 24°20'33.9"N 71°29'08.3"E 24°20'40.4"N 71°29'13.5"E 24°20'35.5"N 71°29'20.6"E 24°20'29.0"N 71°29'15.3"E
|  | WR |  | 400/220kV Rajgarh (PG) (existing) S/s# | 22.68222222˚ N, 74.92444444˚ E
|  | WR |  | 400/220kV Indore (PG) (existing) S/s | 22°54'31.81"N, 75°53'58.87"E
|  | WR |  | Pachora PS# | 23.7177N 76.12333E
|  | WR |  | Neemuch PS
|  | WR |  | Khandwa S/s (PG) (existing S/s) | 21.83240889˚ N, 76.40401778˚ E
|  | WR |  | Raipur S/s (PG) (Existing S/s)# | 21˚ 14ʼ 00ˮN, 81˚ 29ʼ 00ˮE
|  | WR |  | Kallam PS# | 18°37'21.05"N, 75°52'17.08"E
|  | WR |  | 765/400/220kV Solapur (PG) (existing S/s)# | 17˚ 36ʼ 31.21ˮ N, 76˚ 2ʼ 59.98ˮE
|  | SR |  | 400/230 kV Tuticorin-II S/s | 9°3'02.1'' N 77°55'31.6''E
|  | SR |  | 400/230 kV Pugalur S/s | 10°57'42"N 77°55'22"E
|  | SR |  | 400/220 kV Palakkad S/s 10°46'22"N 76°45'36"E
|  | SR |  | 400/220 kV NP Kunta S/s | 14° 2'53.18"N, 78°25'43.01"E
|  | SR |  | 400/220 kV Pavagada S/s | 14.318579N 77.385479E
|  | SR |  | 400/220 kV Hiriyur S/s | 13°57'12.33"N 76°32'11.40"E
|  | SR |  | 765/400 kV Kurnool(new) S/s | 15°40'28.6" N 78°10'35.23" E
|  | SR |  | 400/220 kV Koppal S/s | 15°21'55.49"N 75°59'24.61"E
|  | SR |  | 400/230 kV Karur S/s | 10°50'34.10"N 77°39'32.91"E
|  | SR |  | 400/220 kV Gadag S/s | Boundary coordinates 15°47'13.673"N , 75°51'35.001" E 15°47'13.207" N, 75°51'22.707" E 15°46'58.257" N, 75°51'20.956" E 15°46'57.085" N, 75°51'34.122" E
|  | SR |  | 765/400/220kV Koppal- II PS
|  | SR |  | 400/220kV Gadag-II PS
|  | NR |  | 765/400/220kV Bhadla PS # | 27 25 10 N, 72 04 20E
|  | NR |  | 765/400/220kV Bikaner S/s # | 28 14 57 N, 73 22 55 E
|  | NR |  | 400kV Fatehgarh PS (TBCB) # | 26°51'8.48"N, 71°30'34.29"E
|  | NR |  | 765/400/220kV Bhadla- II PS # | Boundary Coordinates Point1:- 27.5047695, 72.4764157 Point2:- 27.5103991, 72.4844684 Point3:- 27.5160828, 72.4792790 Point4:- 27.5109950, 72.4713292
|  | NR |  | 765/400/220kV Fatehgarh-II PS # | Boundary Coordinates Point1:- N 26°42'13.3884", E 71°16'48.936 Point2:- N 26°42'13.5936", E 71°16'19.9956" Point3:- N 26°42'45.9396", E 71°16'19.8588" Point4:- N 26°42'45.6912", E 71°16'48.666"
|  | NR |  | 765/400/220kV Fatehgarh-III PS # | 26°21' 00" N, 71°06' 00" E
|  | NR |  | 400/220kV Bikaner-II PS# | 28°09'20"N, 73*00'23.4"E
|  | NR |  | 400/220kV Fatehgarh-IV PS# | Boundary Coordinates* Point1:- N 26°13'38.76", E 71°15'42.74" Point2:- N 26°13'59.62", E 71°15'53.12" Point3:- N 26°14'11.27", E 71°15'23.11" Point4:- N 26°13'50.22", E 71°15'12.67"
|  | NR |  | 765/400/220kV Bhadla- III PS# | Boundary Coordinates* Point1:- N 27°40'15.65", E 72°12'12.17" Point2:- N 27°40'2.8", E 72°12'20.84" Point3:- N 27°40'10.33", E 72°12'37.23" Point4:- N 27°40'23.54", E 72°12'29.23"
|  | NR |  | 765/400/220kV Ramgarh PS# | Boundary Coordinates* Point1:- N 27°26'39.53", E 70°28'33.75" Point2:- N 27°26'40.33", E 70°29'2.68" Point3:- N 27°27'5.74", E 70°28'52.85" Point4:- N 27°27'5.92", E 70°28'21.92"
|  | NR |  | 765/400/220kV Bikaner- III PS# | Location to be identified
Disclaimer :- # In addition space provision has been kept for future I/c or drawl arrangement. 1. Boundary coordinates indicates the periphery within which the Sub-station is located. 2. Bay numbers are indicative in nature and may be co-related with SLD issued by concerned ISTS Licensee. 3. *The co-ordinates are tentative in nature and subject to change as per availablity of land with in boundary limit. Boundary limit is 3 km radius of above plot (3 km from any of the corner).

## RE Potential
| Region | State | District | Complex | S/s | Location (Village/Tehsil) | Solar | Wind | Hybrid | Others (CTUIL) | RE Potential (GW) | Installed Capacity | U/c & granted Capacity | Transmission Scheme | Complex | Remarks
Data Scoure (Sl. No.(s)9, 10a, )

## Margin
| Sl.No. | State | Region | Pooling S/s | Timelines | RE Potential |  |  | Expected CoD of Pooling Station | Connectivity Granted/ Agreed |  |  | Connectivity Granted/ Agreed |  |  | Margin for Connectivity |  |  | Additional Margin for Connectivity requiring ICT Augmentation / additional Tr. System |  |  | Effectiveness of GNA for Capacity mentioned under "Margin for Connectivity
[6 empty] | RE Potential (MW) [A] | BESS (MW) [B] | S/s Evacuation Capacity (RE Potential - BESS [AB]) |  | 200 kV | 400 kV | Total (MW) | 200 kV | 400 kV | Total (MW) | 200 kV | 400 kV | Total (MW) | 200 kV | 400 kV | Total (MW)
Existing PS
| 1 | Rajasthan | WR | Bhadla Complex | Jul-25 to Dec-25 | 8430 | 0 | 8430 | Existing | 7475 | 2050 | 9525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5251.375MW: Existing 4273.625MW: Nov'25 onwards (Ph-II/Ph-III/Ph-IV) (upto Mar'27)
| 1a | Rajasthan | WR | Bhadla | Jan-26 to Jun-26 | 3380 | 0 | 3380 | Existing | 3580 | 0 | 3580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3580MW: Existing
| 1b | Rajasthan | WR | Bhadla-II | Jul-26 to Dec-31 | 5050 | 0 | 5050 | Existing | 3895 | 2050 | 5945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1671.375MW: Existing 4273.625MW: Nov'25 onwards (Ph-II/Ph-III/Ph-IV) (upto Mar'27)
| 2 | Rajasthan | WR | Fatehgarh-Barmer Complex | Beyond Dec-25 | 9600 | 0 | 9600 | Existing | 6940 | 3200 | 10140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7225.83MW: Existing 2914.17MW: Nov'25 onwards (Ph-II/Ph-III/Ph-IV) (upto Mar'27)
Data Scoure (Sl. No.(s)9) | 2a | Rajasthan | WR | Fatehgarh |  | 2200 | 0 | 2200 | Existing | 0 | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Existing Tr. System
| 2b | Rajasthan | WR | Fatehgarh-II |  | 5500 | 0 | 5500 | Existing | 4460 | 1000 | 5460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3525.83MW: Existing 1934.17MW: Nov'25 onwards (Ph-II/Ph-III/Ph-IV) (upto Mar'27)
| 2c | Rajasthan | WR | Fatehgarh-III (Section-I) |  | 1900 | 0 | 1900 | Existing | 2480 | 0 | 2480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500MW: Existing 480MW: Nov'25 (Ph-II) Including 2x250MW BESS granted at Fatehgarh-III (Section-I) 250MW: Existing 250MW: Mar'26
| 3 | Rajasthan | WR | Bikaner Complex |  | 5850 | 3000 | 8850 | Existing | 5695 | 3940 | 9635 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 2865MW: Existing 3360MW: Nov'25 onwards (Ph-II/Ph-IV/Ph-V) (upto Mar'27)
| 3a | Rajasthan | WR | Bikaner |  | 1850 | 0 | 1850 | Existing | 1235 | 2940 | 4175 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 2865MW: Existing 1360MW: Nov'25 onwards (Ph-II/Ph-IV/Ph-V) (Upto Mar'27)
| 3b | Rajasthan | WR | Bikaner-II |  | 4000 | 3000 | 7000 | Existing | 4460 | 1000 | 5460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5760MW:Nov'25 onwards (Upto Aug'26) (Ph-II/Ph-IV Part-I&II)
|  |  |  | Sub-Total (Existing) |  | 23880 | 3000 | 26880 |  | 20110 | 9190 | 29300 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0
B. Commissioning between Jul-25 to Dec-25
| 1 | Rajasthan | WR | (Bhadla Complex) Bhadla-III |  | 3500 | 0 | 3500 | Sep'25 | 2750 | 1000 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700MW : Feb'26 onwards (Upto Aug'26 (Ph-IV)): cumulative at Ramgarh & Bhadla-III: Raj. (Ph-III) Beyond 3700MW : Bhadla HVDC (Jan'29 Pole-1 & Jul'29 Pole-2) Out of 3750MW, 250MW connectvity of standalone BESS agreed for grant recently
| 2 | Rajasthan | WR | Fatehgarh-Barmer Complex |  | 7333 | 0 | 7333 |  | 4185 | 3450 | 7635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Dec'25 onwards (Ph-III) (Upto Mar' 27(Ph-IV/V) )
| 3 | Rajasthan | WR | (Ramgarh Complex) Ramgarh |  | 4000 | 0 | 4000 | Sep'25 | 1200 | 2784 | 3984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650W-3100MW : Bhadla HVDC (Jan'29 Pole-1 & Jul'29 Pole-2) Transmission system for evacuation of power (beyond 2.9GW and upto 4 GW) HVDC sys. is under planning (Exp Comm. up to Oct'30).
| 4 | Rajasthan | WR | (Bikaner Complex) Bikaner-III |  | 4000 | 3000 | 7000 | Dec'25 | 2267 | 2400 | 4667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000MW: Dec'25 (Ph-IV, Part-I&II) (Upto Aug'26) 667MW: with Bikaner-IV tr. System having schedule Nov'26
| Sub-Total (Jul'25 to Dec'25) |  |  |  |  | 18833 | 3000 | 21833 |  | 10402 | 9634 | 20036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Commissioning between Jan-26 to Jun-26
NIL
D. Commissioning between Jul-26 to Dec-31
| 1 | Rajasthan | WR | (Fatehgarh-Barmer Complex) Fatehgarh-IV (Section-II) |  | 5000 | 4000 | 9000 | Aug'26 | 3480 | 1500 | 4980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hybrid RE Potential : 9GW (Wind+Solar) along with BESS (4 GW), S/s Evacuation Capacity: 5GW For 4000MW (out of 5000MW): Nov'26 (Ph-IV, Part-II). For evacuation of balance 980MW : Dec'26 (Ph-IV, Part-IV).
| 2 | Rajasthan | WR | (Fatehgarh-Barmer Complex) Barmer-I |  | 4000 | 1500 | 5500 | Nov'26 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hybrid RE Potential: 5.5GW (Wind+Solar) along with BESS (1.5 GW), S/s Evacuation Capacity: 4GW. About 1.5GW: Nov'26 (Ph-IV, Part-II) For evacuation of >1.5GW (upto 4GW) : Upto Mar'27 (Ph-IV, Part-IV & Ph- V Part-1) For application of >4GW, connectvity will be provided at Barmer-II PS for which system is under approval (sch. Pole-I : Sep'29, Pole-2: Mar'30 ).
| 3 | Rajasthan | WR | (Fatehgarh-Barmer Complex) Barmer-II |  | 6000 | 0 | 6000 | Jan'30 to Jul'30 (HVDC) | 2080 | 3812 | 5892 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 0 | 108 | HVDC Corridor is recently approved for total 6 GW capacity (Expected Sch.Pole-1:Jan'30, Pole-2: Jul'30].
| 4 | Rajasthan | WR | (Fatehgarh-Barmer Complex) Barmer-III |  | 6000 | 0 | 6000 | Oct'30 to Apr'31 (HVDC) | 2462 | 3450 | 5912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 88 | HVDC Corridor is under planning for total 6 GW capacity (Expected Sch.Pole-1:Oct'30, Pole-2: Apr'31].
| 7 | Rajasthan | WR | (Bikaner Complex) Bikaner-V |  | 6000 | 0 | 6000 | Apr'30 to Oct'30 (HVDC) | 3490 | 2510 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Corridor is being planned for total 6 GW capacity (Expected Sch.Pole- 1:Apr'30, Pole-2: Oct'30].
|  | Rajasthan | WR | (Bikaner Complex) Bikaner-VI |  | 3548 | 0 | 3548 | Jun'31 to Dec'31 (HVDC) | 600 | 0 | 600 | 1750 | 600 | 2350 | 0 | 0 | 0 | 1850 | 1200 | 3050 | HVDC Transmission system (6GW) for evacuation of power from Bikaner- VI complexes is under planning (Exp. Comm. Schedule up to Dec'31).
| 8 | Rajasthan | WR | Sirohi |  | 2000 | 1000 | 3000 | Aug'26 | 1400 | 700 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Connectivity at Sirohi PS will be granted upto 2 GW only. Tr. System for evacuation of power from Sirohi PS is under implementation (sch. Mar'27). Beyond 2 GW in Sirohi complex, HVDC Transmission system for evacuation of power from Jalore complex (Jalore/Sanchore/Sirohi) for comined RE capacity of 6GW is under planning (HVDC) (Exp. Comm. Schedule up to Jun'31).
| 9 | Rajasthan | WR | Bhadla Complex (Bhadla-III Section linked to Bhadla HVDC station & system) |  | 3000 | 0 | 3000 | Jan'29 (Pole-1) to Jul'29 (Pole-2) | 1550 | 1450 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700MW : Jun'25 onwards (Upto Aug'26): cumulative at Ramgarh & Bhadla-III: Raj. (Ph-III) Beyond 3700MW : Bhadla HVDC (Jan'29 Pole-1 & Jul'29 Pole-2).
| 10 | Rajasthan | WR | Bhadla Complex (Bhadla-IV) |  | 2000 | 2000 | 5000 | Apr'30 to Oct'30 (HVDC) | 300 | 5525 | 5825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 175 | Transmission system for evacauation of power from Bhadla-IV PS is under planning (6GW HVDC) (Expected Sch.Pole-1:Apr'30, Pole-2: Oct'30]). Connectivity beyond 6 GW at Bhadla-IV PS to be processed at Bhadla-V (Bhadla complex) for which transmission system (HVDC) from Bhadla Complex to be evolved.
| 11 | Rajasthan | WR | Nagaur Complex (Merta-II) |  | 2000 | 0 | 2000 | Dec'26 | 2100 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tr. System for evacuation of power from Sirohi PS is under implementation (sch. Mar'27). Beyond 2 GW in Merta/Nagaur complex, Tr. system (HVDC) to be evolved
| 12 | Rajasthan | WR | Jalore Complex (Jalore) |  | 2000 | 1000 | 3000 | Dec'30 to Jun'31 (HVDC) | 1150 | 1000 | 2150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Transmission system for evacuation of power from Jalore complex (Jalore/Sanchore/Sirohi) for comined RE capacity of 6GW is under planning (HVDC) (Exp. Comm. Schedule up to Jun'31). At present 5220MW capacity granted/Agreed for grant at Sanchore & Jalore combindely. Balance capacity 780MW (6000-5220) is available for connectvity at Jalore/Sanchore/Sirohi-II PS
|  | Rajasthan | WR | Ramgarh Complex Ramgarh-III |  | 6000 | 0 | 6000 | Jun'31 to Dec'31 (HVDC) | 930 | 3282 | 4212 | 500 | 1177.33 | 1677 | 0 | 0 | 0 | 111 | 0 | 111 | HVDC Transmission system (6GW) for evacuation of power from Ramgarh-III complexes is under planning (Exp. Comm. Schedule up to Dec'31).
| 15 | Rajasthan | WR | Pali Complex (Pali) |  | 2000 | 1000 | 3000 | Dec'30 to Jun'31 (HVDC) | 1705 | 600 | 2305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Transmission system (6GW) for combined capacity 6GW RE from Nagaur(Merta) & Pali complexes is under planning (Exp. Comm. Schedule up to Jun'31). At present 3205MW capacity granted/agreed for grant at Pali and Merta-III combindely. Balance capacity 2795MW (6000-3205)( is available for connectvity at Pali/Merta-III PS
| 18 | Rajasthan | WR | Nagaur Complex (Merta-III) |  |  |  |  | Dec'30 to Jun'31 (HVDC) | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 900 | 1100 | Beyond 2 GW in Merta/Nagaur complex, HVDC Transmission system (6GW) for combined capacity 6GW RE from Nagaur(Merta) & Pali complexes is under planning (Exp. Comm. Schedule up to Jun'31). At present 3205MW capacity granted/agreed for grant at Pali and Merta-III combindely. Balance capacity 2795MW (6000-3205)( is available for connectvity at Pali/Merta-III PS
| 16 | Ladakh |  | Pang (Leh) |  | 13000 | 0 | 13000 | 2029-30 (VSC HVDC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | Leh - Ensviaged RE Capacity (13 GW) for connnectivity in Ladakh including Solar, Wind & BESS. However, net evacaution capacity of HVDC tr. system is 5000MW. Connectivity applications in Ladakh are yet to be received.
| 17 | Rajasthan | WR | Bhadla Complex (Bhadla-V) |  | 6000 | 0 | 6000 | Mar'31 to Sep'31 (HVDC) | 1300 | 4700 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Transmission system (6GW) for evacuation of power from Bhadla- V complexes is under planning (Exp. Comm. Schedule up to Sep'31).
|  | Rajasthan | WR | Bhadla Complex (Bhadla-VI) |  | 4830 | 0 | 4830 | Mar'32 to Sep'32 (HVDC) | 300 | 0 | 300 | 700 | 2100 | 2800 | 0 | 0 | 0 | 2000 | 900 | 2900 | HVDC Transmission system (6GW) for evacuation of power from Bhadla- VI complexes is under planning (Exp. Comm. Schedule up to Sep'32).
|  |  |  | Sub-Total NR (Beyond Dec'25) |  | 92378 | 14500 | 107878 |  | 34194 | 38802 | 72996 | 3675 | 4827 | 8502 | 0 | 13000 | 13000 | 6060 | 3263 | 9323
| Total (NR) |  |  |  |  | 111211 | 17500 | 129711 |  | 64706 | 57626 | 122332 | 3675 | 4827 | 8502 | 0 | 13050 | 13050 | 6060 | 3263 | 9323
Southern Region
A. Existing RE Pooling Stations
| 1 | Andhra Pradesh | SR | NP Kunta |  | 1500 | 0 | 1500 | Existing | 2200 | 0 | 2200 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 MW : Existing Tr. System 5th & 6th ICT (Dec'25) 7th ICT required for appplications beyond 2.5 GW
| 2 | Karnataka | SR | Pavagada |  | 2050 | 0 | 2050 | Existing | 2550 | 0 | 2550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050 MW : Existing Tr. System 500 MW : Dec'25: Narendra-Pune
| 5 | Tamil Nadu | SR | Karur PS (Phase-1) |  | 1000 | 0 | 1000 | Existing | 918 | 0 | 918 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 100 MW : Existing Tr. System 818 MW: Dec'25: Narendra-Pune
| 6 | Karnataka | SR | Gadag PS |  | 2500 | 0 | 2500 | Existing | 2243 | 0 | 2243 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 460 MW : Existing Tr. System 1923 MW: Dec'25: Narendra-Pune
| 7 | Andhra Pradesh | SR | Kurnool-III PS |  | 4500 | 0 | 4500 | Existing | 2250 | 1850 | 4100 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Kurnool-III PS commissioned, entire system expected by Sept'25 Kurnool-III PS has been closed for all purposes.
|  |  |  | Sub-Total (Existing) |  | 16550 | 0 | 16550 |  | 15762 | 1850 | 17612 | 800 | 0 | 800 | 52 | 0 | 52 | 0 | 0 | 0
C. Commissioning between Jul-25 to Dec-25
| 8 | Tamil Nadu | SR | Karur PS ( Phase-II) |  | 1500 | 0 | 1500 | Feb'26 | 1351 | 0 | 1351 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | Augmentation of ICTs and transmission line is required to accommodate under process applications Entire quantum of the under process applicatiuon cannot be accomadetd
| 9 | Karnataka | SR | Koppal-II/ Gadag-II Complex |  | 6000 | 2000 | 8000 |  | 6620 | 1800 | 8420 | 635 | 0 | 635 | 600 | 0 | 600 | 0 | 0 | 0
| 9a | Karnataka | SR | Koppal-II PS |  | 3000 | 1000 | 4000 | Dec'25 | 3305 | 0 | 3305 | 175 | 0 | 175 | 600 | 0 | 600 | 0 |  | 0 | Dec'25
| 9b | Karnataka | SR | Gadag-II PS |  | 3000 | 1000 | 4000 | Dec'25 | 3316 | 1800 | 5116 | 460 | 0 | 460 | 0 | 0 | 0 | 0 |  | 0 | Dec'25 PSP not considered for determination of margins.
| 10 | Andhra Pradesh | SR | Ananthapuram PS |  | 3500 | 0 | 3500 | Sept'25 | 1545 | 2484 | 4029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sept'25 Ananthapuram PS has been closed for all purposes
| 11 | Karnataka | SR | Pavagada (expansion with ICTs) |  | 0 | 0 | 0 | Sept'25 | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 MW : Sep'25 : 7th ICT
|  |  |  | Sub-Total SR (Jul'25- Dec'25) |  | 11000 | 2000 | 13000 |  | 10316 | 4284 | 14600 | 935 | 0 | 935 | 600 | 0 | 600 | 0 | 0 | 0
D. Commissioning beyond Dec'25
| 11 | Karnataka | SR | Davangere Complex |  | 7500 | 1000 | 8500 | Mar'27 | 7022 | 850 | 7872 | 2989 | 0 | 2989 | 0 | 0 | 0 | 0 | 0 | 0 | Mar'27 to Sep'27 (assuming SPV transfer by Mar'25)
| 11a | Karnataka | SR | Davangere |  | 3250 | 1000 | 4250 | Mar'27 | 3388 | 850 | 4238 | 724 | 0 | 724 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 MW :Mar'27 Balance tr. System under bidding All under process applications may not be accommodated.
| 11b | Karnataka | SR | Bellary |  | 4250 | 0 | 4250 | Sep'27 | 3634 | 0 | 3634 | 2265 | 0 | 2265 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 MW :Sep'27 Balance tr. System under bidding All under process applications may not be accommodated.
| 14 | Andhra Pradesh | SR | Ananthapuram/ Kurnool complex |  | 19500 | 0 | 19500 |  | 10410 | 7730 | 18140 | 0 | 1450 | 1763 | 180 | 0 | 180 | 0 | 0 | 0 | Progressivly from Mar'27 to Apr'27
| 14a | Andhra Pradesh | SR | Kurnool-III (Expansion with ICTs) |  | 4500 | 0 | 4500 | Mar'27 | 0 | 3500 | 3500 | 0 | 1450 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | • PSP not considered for determination of margins • Kurnool-III PS has been closed for all purposes. All under process applications may not be accommodated.
| 14b | Andhra Pradesh | SR | Ananthapuram PS-II |  | 7500 | 0 | 7500 | Mar'27 (Ph-I) Mar'28 (Ph-II) | 5420 | 1900 | 7320 | 0 | 0 | 313 | 0 | 0 | 0 | 0 | 0 | 0 | Mar'27 (Phase-1) Progressively from Sept'27 to Mar'28 (Phase-2) All under process applications may not be accommodated.
| 14c | Andhra Pradesh | SR | Kurnool-IV |  | 7500 | 0 | 7500 | Mar'27 (Ph-I) Mar'28 (Ph-II) | 4990 | 2330 | 7320 | 0 | 0 | 0 | 180 | 0 | 180 | 0 | 0 | 0 | Mar'27 (Phase-1) Progressively from Sept'27 to Mar'28 (Phase-2)
| 15 | Karnataka | SR | Tumkur-II |  | 3000 | 0 | 3000 | Sep'26 | 2100 | 0 | 2100 | 2450 | 0 | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 MW : Sep'26 All under process applications may not be accommodated.
| 16 | Telangana | SR | Nizamabad Complex |  | 5000 | 0 | 5000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 8500 | 0 | 8500 | Locations for RE potential declared in Telanagana under review by MNRE/SECI. Transmisison system put on-hold by NCT till finalization of same.
| 16a | Telangana | SR | Nizamabad-II |  | 2000 | 0 | 2000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 2500 |  | 2500 | Locations for RE potential declared in Telanagana under review by MNRE/SECI. Transmisison system put on-hold by NCT till finalization of same.
| 16b | Telangana | SR | Medak |  | 1500 | 0 | 1500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 3000 |  | 3000 | Locations for RE potential declared in Telanagana under review by MNRE/SECI. Transmisison system put on-hold by NCT till finalization of same.
| 16c | Telangana | SR | Rangareddy |  | 1500 | 0 | 1500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 3000 |  | 3000 | Locations for RE potential declared in Telanagana under review by MNRE/SECI. Transmisison system put on-hold by NCT till finalization of same.
| 17 | Tamil Nadu | SR | Avairakulam (Off shore) |  | 500 | 0 | 500 | Dec'30 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 4500 | 0 | 4500 | Mar'2030
| 18 | Karnataka | SR | Pavagada (expansion with ICTs) |  | 0 | 0 | 0 | May'26 | 1150 | 0 | 1150 | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 8th, 9th & 10th ICTs : May'26 Under process applications may not be accommodated.
| 19 | Andhra Pradesh | SR | Ananthapuram PS-III |  | 7500 | 0 | 7500 | Sep'28 | 3630 | 0 | 3630 | 1360 | 0 | 1360 | 2510 | 0 | 2510 | 0 | 0 | 0 | Ph-I (4.5 GW) Sep'28
| 20 | Andhra Pradesh | SR | Kurnool-V |  | 7500 | 0 | 7500 | Sep'28 | 1330 | 0 | 1330 | 570 | 0 | 570 | 5600 | 0 | 5600 | 0 | 0 | 0 | Ph-I (4.5 GW) Sep'28
| 21 | Andhra Pradesh | SR | Kadapa-II |  | 7500 | 0 | 7500 | Dec'28 | 600 | 0 | 600 | 0 | 0 | 0 | 1400 | 2500 | 3900 | 2000 | 1000 | 3000 | Dec'28
Western Region
A. Existing RE Pooling Stations
| 1 |  |  | Bhuj complex |  | 5500 |  | 5500 | Existing | 5559 | 0 | 5559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Existing Tr. System
| 1a | Gujarat | WR | Bhuj PS |  | 3500 |  | 3500 | Existing | 3500 |  | 3500 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | Existing Tr. System.
| 1b | Gujarat | WR | Bhuj-II PS |  | 2000 |  | 2000 | Existing | 2059 |  | 2059 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Existing Tr. System.
| 2 | Gujarat | WR | Radhanesda PS |  | 700 |  | 700 | Existing | 1250 |  | 1250 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | Existing Tr. System.
| 5 | Madhya Pradesh | WR | Pachora PS |  | 1500 |  | 1500 | Existing | 1398 |  | 1398 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 1.5GW: Commissioned
| 6 | Madhya Pradesh | WR | Neemuch PS |  | 1000 |  | 1000 | Existing | 950 |  | 950 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1GW: Commissioned
| 7 | Maharashtra | WR | Solapur S/s |  | 2000 |  | 2000 | Existing |  | 2000 | 2000 |  | 0 | 0 |  | 0 | 0 |  |  |  | Sep-24: Under Scope of applicant (ReNew). NO FURTHER MARGINS LEFT BEYOND 2GW. Application for 237MW needs to be deliberated. Connectivity of (100+76+48MW) of Renew has been revoked under non- compliance of 24.6 & the matter is presently subjudice.
| 8 | Gujarat | WR | Khavda I PS (Sec I) |  | 3000 |  | 3000 | Existing |  | 3000 | 3000 |  |  | 0 | 0 | 0 | 0 |  |  |  | 3GW: Commissioned
|  |  |  | Subtotal (Existing) |  | 16700 | 0 | 16700 |  | 12042 | 5000 | 17042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Commissioning by Jun'25
| 9 |  |  | Khavda complex |  | 10500 |  | 10500 |  | 0 | 10500 | 10500 | 0 | 0 | 0 | 0 | 0 | 0
| 9a | Gujarat | WR | Khavda I PS (Sec II) |  | 4500 |  | 4500 | Sec-II: Jan'25 |  | 4500 | 4500 |  |  | 0 | 0 | 0 | 0 |  |  |  | •Ph-1: 3GW - KPS1 (Comm) / KPS2: Jan'25(SCOD)/ Sep'25 (ACOD) •Ph-2: 5GW- Mar'25 (SCOD)/Nov'25 (ACOD) •Ph-3: 7GW- Dec'25 (SCOD)/ Jun'26 (ACOD)
| 9b | Gujarat | WR | Khavda II PS (Sec-I & II) |  | 3000 |  | 3000 | Sec-I & II: Jan'25 |  | 3000 | 3000 |  |  | 0 | 0 | 0 | 0
| 9c | Gujarat | WR | Khvada III PS (Sec-I) |  | 3000 |  | 3000 | Jan'25 |  | 3000 | 3000 |  |  | 0 | 0 | 0 | 0
| 10 | Madhya Pradesh | WR | Chhatarpur PS |  | 0 |  | 0 | Scheme dropped. | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | Scheme has been dropped as decided in NCT meeting & to be denotified by MoP.
| 11 | Maharashtra | WR | Kallam PS (Ph-II) |  | 1000 |  | 1000 | Dec-24 (1GW) | 835 | 1022 | 1856 | 0 | 200 | 200 | 150 | 78 | 228 |  |  |  | 1GW ICTs: Dec-24 & System for 2.25GW: Under Implementation-Oct-25 (exptd) 148.75MW Connectivity granted to Anupavan has been revoked under 11A. Further, 200MW connectivity of Serentica & 117MW of Renew(MHP) has been revoked under 24.6, however, matter is presently subjudice.
|  |  |  | Subtotal (By Jun'25) |  | 11500 | 0 | 11500 |  | 835 | 11522 | 12356 | 0 | 200 | 200 | 150 | 78 | 228
D. Commissioning between Jul-25 to Dec-25
| 12 |  |  | Khavda complex |  | 9000 |  | 9000 |  | 0 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | •Ph-1: 3GW - Completed in Feb-24. However, 2GW at KPS2 using Ph-I system would also require KPS2 S/s (Jan'25) •Ph-2: 5GW- Mar'25 (SCOD) •Ph-3: 7GW- Dec'25 (SCOD) •Ph-4: 7GW-Nov'26 (SCOD) •Ph-V: LCC Bipole-I:Nov'28) & LCC Bipole-II: May'29 (SCOD) / VSC 48 months from SPV transfer
| 12a | Gujarat | WR | Khavda I PS (Sec-I) |  | 1500 |  | 1500 | Sec-I ICT: Jul'25 |  | 1500 | 1500 |  |  | 0 | 0 | 0 | 0 |  |  |  | Total transformation capacity at Khavda complex (considering N-1 on each section): KPS1 - Sec-I: 4.5GW ; Sec-2: 6GW Total KPS1: 10.5GW KPS2 - Sec-I: 6GW ; Sec-2: 4.5GW Total KPS2: 10.5GW KPS3 - Sec-I: 4.5GW ; Sec-2: 4.5GW
| 12b | Gujarat | WR | Khavda II PS (Sec-I & II) |  | 6000 |  | 6000 | Sec-I & II ICTs : Feb'26 |  | 6000 | 6000 |  | 0 | 0 | 0 | 0 | 0
| 11 | Maharashtra | WR | Parli (New) S/s |  | 1000 |  | 1000 | Dec'25 (Bay) |  | 800 | 800 |  | 0 | 0 |  | 200 | 200 |  |  |  | 400kV bay under construction (suitable for 1000MW evacuation): Dec'25
|  |  |  | Sub-Total (WR) (Jul'25 to Dec'25) |  | 11500 | 0 | 11500 |  | 1414 | 9800 | 11214 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 0
E. Commissioning beyond Dec-25
| 15 |  |  | Khavda complex |  | 7500 |  | 7500 |  | 0 | 19390 | 19390 | 0 | 1600 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | •Ph-1: 3GW - Completed in Feb-24. However, 2GW at KPS2 using Ph-I system would also require KPS2 S/s (Jan'25) •Ph-2: 5GW- Mar'25 (SCOD) •Ph-3: 7GW- Dec'25 (SCOD) •Ph-4: 7GW-Nov'26 (SCOD) •Ph-V: LCC Bipole-I:Nov'28) & LCC Bipole-II: May'29 (SCOD) / VSC 48 months from SPV transfer
| 15a | Gujarat | WR | Khavda I PS (Sec-I) |  | 1500 |  | 1500 | Sec-I ICT: 2026-27 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total transformation capacity at Khavda complex (considering N-1 on each section): KPS1 - Sec-I: 6GW ; Sec-2: 4.5GW Total KPS1: 10.5GW KPS2 - Sec-I: 6GW ; Sec-2: 4.5GW Total KPS2: 10.5GW KPS3 - Sec-I: 4.5GW ; Sec-2: 4.5GW Total KPS3: 9GW Total (KPS1, KPS2 & KPS3): 30GW Under Process Application received for 1250MW at KPS2 is beyond Phase- VII system.
| 15b | Gujarat | WR | Khavda II PS (Sec-I & II) |  | 1500 |  | 1500 | Sec-I ICT: 2026-27 |  | 250 | 250 |  | 1250 | 1250 | 0 | 0 | 0 |  | 0 | 0
| 15c | Gujarat | WR | Khvada III PS (Sec-I & II) |  | 4500 |  | 4500 | Sec-II ICTs: Jun-26 (3x1500) & 2026-27 (1x1500) |  | 5140 | 5140 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 15d | Gujarat | WR | Khavda IV PS (Sec-I & II) |  | 8750 |  | 0 | 2027-28 |  | 8750 | 8750 |  | 0 | 0 | 0 | 0 | 0.0 | 0 | 0 | 0 | The Khavda Phase-I to Phase-VII shall be required for enabling evacuation of power upto 41.5GW from Khavda area out of which Phase-VI (5.5GW) & Phase-VII (6GW HVDC) are under approval stage.
| 15e | Gujarat | WR | Khavda V PS (Sec-I) |  | 3750 |  | 0 | 2027-28 |  | 3750 | 3750 |  | 350 | 350 | 0 | 0 | 0.0 | 0 | 0 | 0 | The Khavda Phase-I to Phase-VII shall be required for enabling evacuation of power upto 41.5GW from Khavda area out of which Phase-VI (5.5GW) & Phase-VII (6GW HVDC) are under approval stage. Under Process Application received for 350MW at KPS5 is beyond Phase- VII system.
| 16 | Maharashtra | WR | Solapur PS (1.5GW) |  | 1500 |  | 1500 | Mar-26 (exptd) | 2450.0 | 800.0 | 3250.0 |  | 2207 | 2207 | 0.0 | 0 | 0.0 | 0 | 0 | 0 | Solapur Ph-I (1.5GW): Mar-26: Under Implementation Solapur Ph-II (2GW): On hold pending potential declaration by MNRE For balance applications received at Solapur PS beyond 3.5GW, additional System / Pooling Station may be needed. 200MW margin is available at 400kV which will be allocated to applicants in order of priority of applications at Solapur PS.
| 17 | Madhya Pradesh | WR | Pachora PS |  | 2000 |  | 2000 | Feb-26 (exptd) | 2602 |  | 2602 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Rajgarh Ph-I(1.5GW): Commissioned, Ph-II (1GW): Under Implementation & Ph-III (1.5GW): Under Bidding NO FURTHER MARGINS ARE AVAILABLE (BEYOND 4000MW AT PACHORA PS).
| 20 | Gujarat | WR | Jamnagar |  | 1000 |  | 1000 | Sep-26 (extd). 400/220kV ICT Augmentation under planning | 1000 | 0 | 1000 | 956 | 0 | 956 | 0 | 0 | 0 | 0 | 0 | 0 | 765/400kV Jamnagar S/s is presently under tendering with time-line of 24 months from SPV transfer. ICT Augmentation shall be required for injection at 220kV level. Applications received beyond 1000MW would also require additional Tr. System to be planned.
| 21 | Gujarat | WR | Lakadia-I PS |  | 2000 |  | 2000 | Aug-26 (exptd) | 2550 | 0 | 2550 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | Total 3.5GW Capacity planned at Lakadia S/s and NO FURTHER MARGINS EXIST AT 220kV LEVEL OF LAKADIA S/s
| 22 | Gujarat | WR | Jam Khambhaliya-II / Kalyanpur |  | 2000 |  | 2000 | 2027-28 | 3500 | 1000 | 4500 |  | 450 | 450 | 0 | 0 | 0 |  |  | 0 | Substation is under planning for 4.5GW in first phase.
| 23 | Gujarat | WR | Raghanesda (GIS) |  | 3000 |  | 3000 | Oct-27 (SCOD) | 650 | 2800 | 3450 | 1105 | 5112 | 6217 |  | 0 | 0 |  |  | 0 | Substation is under implementation. NO FURTHER MARGINS ARE NOW AVAILABLE IN UNDER BIDDING SYSTEM. After 3.5GW, Augmentation shall be required for RE beyond 3.5GW at Raghanesda PS. Applications are received beyond Substation capacity.
| 24 | Gujarat | WR | Bhuj-II PS |  | 0 |  | 0 | 0.5GW: Nov'26 & 1.5GW: Dec'26 | 1442 |  | 1442 | 0 | 2759 | 2759 |  | 0 | 0 | 0 | 0 | 0 | NO FURTHER MARGINS ARE NOW AVAILABLE. For applications received beyond 2000MW, augmentation needs to be taken up. 500MW (350+50+100MW) Connectivity of Acme has been revoked based on applicants request. Further, 300MW Connectivity of Inox has been revoked under non-compliance of 24.6. The margin would be allocated to applicants after reallocation exercise in order of priority at Bhuj complex.
| 25 | Gujarat | WR | Jam Khambhaliya PS |  | 1000 |  | 1000 | May'26 | 1031 | 951 | 1982 | 0 | 0.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Augmentation of 400/220kV ICTs is required. Margins are shown considering 9th ICT at JK PS as confirmed by JKTL. NO FURTHER MARGINS ARE NOW AVAILABLE.
| 26 | MP | WR | Ishanagar |  | 0 |  | 0 | Feb'26 | 0 | 650 | 650 |  | 630 | 630 |  | 0 | 0 |  |  | 0 | Under Implementation. No further margins available at the substation.
| 27 | MP | WR | Kurawar |  | 0 |  | 0 | Sep'26 | 0 |  | 0 |  | 950.0 | 950 |  |  | 0 | 350 |  | 350 | Under Implementation
| 31 | MP | WR | Morena PS (Ph-I) |  | 2500 |  | 2500 | 2027-28 | 1550 | 750 | 2300 | 350 | 500 | 850 | 0 | 0 | 0 | 850 | 0 | 850 | Ph-I (2.5GW) under bidding stage. For applications beyond 2.5GW, additional transmission system is being planned.
| 32 | Gujarat | WR | Mahuva Offshore PS (Ph-I) |  | 500 |  | 500 | 2029 | 0 |  | 0 | 0 |  | 0 | 500 |  | 500 | 0 | 0 | 0 | Scheme under implementation by POWERGRID with SCOD of Mar-29
|  |  |  | Subtotal WR (Beyond Dec'25) |  | 27500 | 0 | 27500 |  | 27137 | 31461 | 58598 | 4656 | 17487 | 22143 | 500 | 0 | 500 | 1200 | 0 | 1200
|  |  |  | Total (WR) |  | 67200 | 0 | 67200 |  | 41427 | 57783 | 99210 | 4656 | 17687 | 22343 | 650 | 278 | 928 | 1200 | 0 | 1200
In WR, Tr. System has been planned w/o considering BESS capacity of 1.1GW in Maharashtra
North Eastern Region
A. Commissioning beyond Dec-25
| 1 Bokajan | Assam | NER |  |  | 1000 | 0 | 1000 | Dec-26 (exptd) | 0 | 750 | 750 | 0 | 0 | 0 | 0 | 250 | 250 | 1500 | 0 | 1500 | Under Implementation
| Subtotal NER (Beyond Dec'25) |  |  |  |  | 1000 | 0 | 1000 |  | 0 | 750 | 750 | 0 | 0 | 0 | 0 | 250 | 250 | 1500 | 0 | 1500
| Total (All India) |  |  |  |  | 255961 | 20500 | 292461 |  | 163764 | 130873 | 294637 | 24916 | 26264 | 51493 | 16492 | 16078 | 32570 | 23760 | 4263 | 28023

## Non RE proposed RE Integration
State | Name of Station | Capacity (MVA) | Capacity Allocated (MW) | Margin Existing 220kV (MW) | Margin Existing 400kV (MW) | Line Bays 220kV | Line Bays 400kV | Margin with ICT 220kV (MW) | Margin with ICT 400kV (MW) | Line Bays with ICT 220kV | Line Bays with ICT 400kV | No. of Transformers Required | Remarks
Gujarat | Navinal (GIS) 765/400kV | 6x1500MVA, 765/400kV | 1100 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | Applications beyond 300MW require additional System and are under deliberation | WR
Gujarat | Halvad/Surendranagar area |  | 1350 | [9 empty] | Applications for 820MW received in Halvad area & 530MW received in Surendranagar area which are under deliberations. | WR
Maharashtra | Aurangabad 765/400/220kV | 2x1500MVA, 765/400kV 2x315MVA, 400/220kV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overloading in 220kV downstream network. | WR
Maharashtra | Kolhapur 400kV | 400kV Switching Station | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Overloading observed in 400kV Kolhapur (PG)- Kolhapur(MSETCL) D/c line. | WR
Maharashtra | Parli (PG) 400/220kV | 2x500MVA, 400/220kV | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300MW capacity has been allocated at Parli (PG) S/s. Overloading in 220kV downstream & Parli 400kV network. | WR
Madhya Pradesh | Khandwa 400/220kV | 2x315+1x500MVA, 400/220kV | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300MW Stage-II connectivity & 300MW LTA from Masaya Solar at Khandwa has also been granted. Overloading in 220kV downstream network. | WR
Madhya Pradesh | Indore 765/400/220kV | 2x500MVA, 400/220kV + (1x500MVA with sectionalisation at 220kV for RE injection) | 1224.4 | 150.6 | 100 | 1 | 1 | 0 | 0 | 0 |  | 0 | 324.4MW LTA has been granted on 1x500MVA with sectionalisation at 220kV for RE injection & 900 MW (600+150+150) has been granted on 400kV bay. | WR
Madhya Pradesh | Jabalpur PS 765/400 | 2x1500MVA 765/400kV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765/400kV ICT overloading. | WR
Madhya Pradesh | Rajgarh 400/220kV | 2x315MVA, 400/220kV+ (2x500MVA with sectionalisation at 220kV for RE injection) | 892 | 356 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | Margins at 220kV bay of Srpng: 298.24MW has been granted / agreed for grant to M/s Sprng. Overloading in 220kV downstream network. Margins at 400/220kV ICT-III& IV: 593.6MW has been granted/agreed at extended 220kV bus of Rajgarh S/s through addl. 400/220kV, 500MVA ICT(s) for RE injection. | WR
Madhya Pradesh | Karera 765/400/220kV | 2x1500 MVA, 765/400 kV, 2x500 MVA, 400/220 kV S/s | 700 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | WR
Madhya Pradesh | Sidhi area | No ISTS Substation exists near Sidhi | 300 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Application received for 300MW (requested through LILO of Vindhyachal - Satna line). Studies are underway. | WR
Chhattisgarh | Dharamjaygarh 765/400kV | 2x1500MVA 765/400kV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765/400kV ICT overloading / Fault level issues
Chhattisgarh | Champa 765/400kV | 6x1500MVA 765/400kV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765/400kV ICT overloading / Fault level issues
Chhattisgarh | Bilaspur PS 765/400kV | 3x1500MVA 765/400kV | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 765/400kV ICT overloading / Fault level issues
Andhra Pradesh | Kurnool (New) 765/400kV | 2X1500 MVA, 765/400 kV | 2714 | 0 | 0 |  | 1 | 0 | 250 |  | 0 | 1 |  | SR
Karnataka | Hiriyur 400/220kV | 2x315 MVA, 400/220 kV + 1x500 MVA, 400/220 kV | 600.3 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | SR
Kerala | Palakkad (400/220kV) | 2x315 MVA, 400/220 kV + 1x500 MVA, 400/220 kV | 0 | 300 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 |  | SR
Tamil Nadu | Pugalur(Existing) 400/230kV | 2X315 MVA + 1X500 MVA, 400/230 kV | 655 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | Pugalur(Existing) has been closed for all purpose regarding grant of Connectivity. | SR
Tamil Nadu | Malekottaiyur(Kalivenda pattu) 400/230kV | 2X315 MVA + 1X500 MVA, 400/230 kV | NIL | 500 | 0 | 2 |  | 0 | 0 |  | 0 | 0 |  | SR
Tamil Nadu | Nagapattinam PS 765/400kV | Charged at 400 kV | NIL | 0 | 1000 |  | 2 | 0 | 0 |  | 0 | 0 |  | SR
Tamil Nadu | NLC TS-II | 2x250+1x315 | 160 | 0 | 0 | 0 | [6 empty] | Overloading at 230 kV network | SR
Rajasthan | Chittorgarh 765/400kV | 765/400kV : 2x1500MVA | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | WR
Rajasthan | Ajmer 765/400kV | 765/400kV : 2x1500MVA | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | WR
Rajasthan | Bassi | 400/220 kV : 2x315MVA +1x500MVA | NIL | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 220kV overloading | WR
Rajasthan | Bhiwadi | 400/220 kV : 3x315MVA | NIL | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 220kV overloading | WR
Rajasthan | Kankroli | 400/220 kV : 3x315MVA | NIL | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 220kV overloading | WR
Rajasthan | Kota | 400/220 kV : 2x315MVA | NIL | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 220kV overloading | WR
Rajasthan | Bhinmal | 400/220 kV : 2x315MVA+1x315 MVA UC | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220kV overloading | WR
Neemarana | Neemarana | 400/220 kV : 1x315MVA +1x500MVA | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220kV overloading
Neemarana | Sikar | 400/220 kV : 2x315MVA +1x500MVA | NIL | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 220kV overloading
Neemarana | Jaipur (South) | 400/220 kV : 2x500MVA | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Neemarana | Kotputli | 400/220 kV : 2x315MVA+1X500MVA (Planned) | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Haryana | Kaithal | 400/220 kV : 3X315MVA | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NR
Haryana | Bahadurgarh | 400/220 kV : 315MVA +500MVA+500MVA (UC) | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NR
Haryana | Manesar | 400/220 kV : 2X500MVA | NIL | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 400/220kv ICT over loading | NR
Uttar Pradesh | Kanpur(New) | 765/400 kV : 2x1500MVA+1x1500 | NIL | 0 | 500 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 220kV Not available | NR
Uttar Pradesh | Fatehpur | 765/400kV : 2x1500MVA; 400/220 kV : 2X315MVA | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NR
Uttar Pradesh | Lucknow (new) | 765/400 kV : 2x1500MVA | NIL | 0 | 500 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | NR
Uttar Pradesh | Balia | 765/400 kV : 2x1500MVA | NIL | 0 | 850 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 220kV Not available. | NR
Uttar Pradesh | Bareilly(New) | 765/400 kV : 2x1500MVA | NIL | 0 | 500 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | NR
Odisha | Jeypore | 400/220kV: 2x630MVA |  | 1500 | 0 | 5 | [7 empty] | ER
Odisha | Keonjhar | 400/220kV: 2x315MVA | 0 | 800 | 0 | 3 | [7 empty] | ER
Odisha | Pandiabil | 400/220kV: 3x500MVA | 0 | 0 | 0 | [8 empty] | ER
Odisha | Rengali | 400/220kV: 2x315MVA | 0 | 500 | 0 | 2 | [7 empty] | ER
Odisha | Angul | 765/400: 4x1500MVA | 0 | 0 | 0 | [8 empty] | ER
Odisha | Baripada | 400/220/132: 2x315MVA + 1x500MVA + 2x160MVA |  | 300 |  | 2 | [7 empty] | ER
Odisha | Bolangir | 400/220kV: 2x315MVA |  | 0 | [9 empty] | ER
Odisha | Indravati | 400/220kV: 1x315MVA |  | 0 | [9 empty] | ER
Odisha | Rourkela | 400/220kV: 4x315MVA |  | 0 | [9 empty] | ER
Paradeep | Paradeep | 765/400: 2x1500MVA |  |  | 3000 |  | 3
Paradeep | Gopalpur | 765/400: 2x1500MVA |  |  | 3000 |  | 3
Paradeep | Total |  | Total Od: | 3100 | 11000 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 14100
Jharkhand | Chaibasa | 400/220kV: 2x315MVA | 0 | 500 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 |  | ER
Jharkhand | Daltonganj | 400/220kV: 2x315MVA | 0 | 500 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 |  | ER
Jharkhand | Ranchi | 400/220kV: 2x315MVA + 1x500MVA |  | 800 |  | 3 |  | 0 | 0 | 0 |  | 0 |  | ER
Jharkhand | Ranchi (New) | 765/400kV: 2x1500MVA | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | ER
Jharkhand | Chandwa | 400kV switching |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | ER
Jharkhand | Dhanbad | 400/200kV: 2x500MVA |  | 500 |  | 2 | [7 empty] | ER
Jharkhand | Total |  | Total Jh: | 2300 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | ER
Bihar | Banka | 400/132kV: 2x200MVA + 1x315MVA 400/220kV: 2x500MVA | 0 | 600+700 | 0 | 5 | 0 | 400 | 0 | 0 | 0 | 0 | 100MW at 132kV level in the existing system and 400MW at 220kV level with the implementation of "Augmentation of 400/220kV, 2x500MVA ICT at Banka" Scheme expected by Oct 2024 | ER
Bihar | Lakhisarai | 400/132kV: 2x200MVA + 1x315MVA | 0 | 300 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 132kV level | ER
Bihar | Motihari | 400/132kV: 2x200MVA + 1x315MVA | 0 | 500 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 132kV level | ER
Bihar | Chandauti | 400/220kV: 3x500MVA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ER
Bihar | Muzaffarpur | 400/220kV: 2x315MVA + 2x500MVA | 0 | 800 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | line corridor available for 2 lines | ER
Bihar | Saharsa | 400/220kV: 2x500MVA | 0 | 700 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | ER
Bihar | Sitamarhi | 400/220kV: 2x500MVA | 0 | 800+200 | 0 | 4 | 0 | 0 | 0 |  |  |  |  | ER
Bihar | Gaya | 400/220kV: 2x500MVA + 1x315MVA |  | 2000+1000 |  | 10 | [7 empty] | ER
Bihar | Darbhanga | 400/220kV: 2x500MVA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ER
Bihar | Kishanganj | 400/220kV: 2x500MVA | 0 | 500 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | ER
Bihar | New Purnea | 400/220kV: 2x500MVA | 0 | 1000 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | ER
Patna | Patna | 400/220kV: 3x500MVA | 0 | 100 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Patna | Purnea | 220/132kV: 3x160MVA | 0 | 900 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Patna | Sasaram | 220/132kV: 3x160MVA | 0 | 600 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Patna | Total |  | Total Bh: | 10700 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 10700
West Bengal | Durgapur-B | 400/220kV: 3x315MVA | 0 | 0 | [8 empty] | 220kV overloaded in present case under N-1. | ER
West Bengal | Maithon-B | 400/220kV: 3x500MVA | 0 | 0 | [8 empty] | 220kV overloaded in Base case (Maithon B - Asansol). | ER
West Bengal | Subhasgram | 400/220kV: 2x315MVA + 1x500MVA | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 220kV overloaded in present case under N-1 (Subhasgram). | ER
West Bengal | Jeerat-New | 765/400: 2x1500MVA | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 400/220kV ICT overloaded in present case under N-1 | ER
West Bengal | Medinipur | 765/400: 2x1500MVA | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 400/220kV ICT overloaded in present case | ER
West Bengal | Alipurduar | 400/220kV: 2x315MVA | 0 | 0 | [9 empty] | ER
West Bengal | Baharampur | 400kV switching | 0 | 0 | [9 empty] | ER
West Bengal | Rajarhat | 400/220kV: 3x500MVA | 0 | 0 | [8 empty] | 220kV overloaded in present case under N-1 (Subhasgram). | ER
West Bengal | Birpara | 220/132kV: 2x160MVA | 0 | 0 | [9 empty] | ER
West Bengal | Dalkhola | 220kV switching | 0 | 0 | [9 empty] | ER
West Bengal | Durgapur-A | 400kV switching | 0 | 0 | [9 empty] | ER
West Bengal | Maithon-A | 400kV switching | 0 | 0 | [9 empty] | ER
West Bengal | Farakka TPS | 400/220kV: 2x315MVA | 0 | 0 | [9 empty] | ER
West Bengal | Malda | 400/220kV: 2x500MVA | 0 | 0 | [9 empty] | ER
West Bengal | New Siliguri (Binaguri) | 400/220kV: 3x315MVA | 0 | 0 | [8 empty] | 132kV overloaded in present case under N-1 (Siliguri). | ER
West Bengal | Siliguri | 220/132kV: 2x160MVA | 0 | 0 | [8 empty] | 132kV overloaded in present case under N-1 (Siliguri). | ER

## Transformation Capacity
| S.No. | Region | State | Substation | Existing | Under Implementation | Planned
| 1 | WR |  | 400/220kV Jam Khambhaliya (GIS) PS # | 400/220kV, 4X500MVA,
Data Scoure (Sl. No.(s)9) | 2 | WR |  | 765/400/220kV Bhuj PS# | 4x1500MVA, 765/400kV; 8X500MVA, 400/220kV
| 3 | WR |  | 765/400/220kV Bhuj-II PS# | 1x1500 MVA, 765/400 kV; 4X500 MVA, 400/220 KV | 1x1500 MVA, 765/400 kV;
| 4 | WR |  | 400/220kV Bhachau S/s | 2X315 MVA, 400/220 KV
| 6 | WR |  | Khavda PS-II |  | 2x1500MVA, 765/400kV | 0
| 7 | WR |  | Banaskantha (Radhanesda) PS [GIS] (Vav) | 2x500 MVA, 400/220 KV
| 8 | WR |  | 400/220kV Rajgarh (PG) (existing) S/s# | 2x315 MVA, 400/220 KV |  | 1x500 MVA, 400/220 kV (segregated from existing 220kV bus through bus section)
| 9 | WR |  | 400/220kV Indore (PG) (existing) S/s | 2x1500 MVA, 765/400 kV 3X500 MVA, 400/220 kV
| 10 | WR |  | Pachora PS# |  | 3x500MVA, 400/220kV
| 11 | WR |  | Neemuch PS |  | 2x500MVA, 400/220kV
| 12 | WR |  | Khandwa S/s (PG) (existing S/s) | 2x315MVA + 1x500MVA, 400/220kV
| 13 | WR |  | Raipur S/s (PG) (Existing S/s)# | 3x315MVA, 400/220kV
| 15 | WR |  | 765/400/220kV Solapur (PG) (existing S/s)# | 2x1500 MVA, 765/400 kV; 2X315 MVA, 400/220 kV; 1X500 MVA 400/220 KV
| 16 | SR |  | 400/230 kV Tuticorin-II S/s | 3x500 MVA, 400/230 KV | 2x500MVA, 400/230kV
| 17 | SR |  | 400/230 kV Pugalur S/s | 2x315 MVA, 400/230 kV 1x500 MVA, 400/230 KV | -
| 18 | SR |  | 400/220 kV Palakkad S/s 10°46'22"N 76°45'36"E | 2x315 MVA, 400/220 kV | 1x500 MVA, 400/220 kV
| 19 | SR |  | 400/220 kV NP Kunta S/s | 4x500 MVA, 400/220 kV | -
| 21 | SR |  | 400/220 kV Hiriyur S/s | 2x315 MVA, 400/220 kV | 1x500 MVA, 400/220 kV
| 22 | SR |  | 765/400 kV Kurnool(new) S/s | 2x1500 MVA, 765/400 kV
| 23 | SR |  | 400/220 kV Koppal S/s | - | 5x500 MVA, 400/220 kV
| 24 | SR |  | 400/230 kV Karur S/s | - | 5x500 MVA, 400/230 kV
| 25 | SR |  | 400/220 kV Gadag S/s | - | 5x500 MVA, 400/220 kV
| 27 | SR |  | 400/220kV Gadag-II PS |  |  | 4x500 MVA, 400/220 kV
| 29 | NR |  | 765/400/220kV Bikaner S/s # | 2x1500MVA, 765/400kV 2x500MVA, 400/220kV | 1x1500MVA, 765/400kV, 1x500MVA, 400/220kV | 1x1500MVA, 765/400kV
| 30 | NR |  | 400kV Fatehgarh PS (TBCB) # | - | - | -
| 31 | NR |  | 765/400/220kV Bhadla- II PS # | 2x1500MVA, 765/400kV 3X500MVA, 400/220kV | 2x1500MVA, 765/400kV 5X500MVA, 400/220kV | 1x1500MVA, 765/400kV
| 32 | NR |  | 765/400/220kV Fatehgarh-II PS # | 4x1500MVA, 765/400kV 5X500MVA, 400/220kV | 2x1500MVA, 765/400kV 4X500MVA, 400/220kV | 2x500MVA, 400/220kV
| 34 | NR |  | 400/220kV Bikaner-II PS# |  | 2x500MVA, 400/220kV | 5x500MVA, 400/220kV
| 35 | NR |  | 400/220kV Fatehgarh-IV PS# |  |  | 5x500MVA, 400/220kV
| 36 | NR |  | 765/400/220kV Bhadla- III PS# |  |  | 2x1500MVA, 765/400kV 10X500MVA, 400/220kV
| 37 | NR |  | 765/400/220kV Ramgarh PS# |  |  | 3x1500MVA, 765/400kV 2X500MVA, 400/220kV
| 38 | NR |  | 765/400/220kV Bikaner- III PS# |  |  | 6x1500MVA, 765/400kV 5X500MVA, 400/220kV

## Element Status
| Element Code | Inter/Intra Tx. Element | Transmission Scheme | Transmission Scope | MVA | Status | Approval of Elements in which NCT | Mode (TBCB/RTM) | Tender Issuing Authority | Date of tender issuance | Date of Bid Submission | Execution Timeline | Tentative SCOD | Awarded To | SPV Transfer Date | Physical Progress S/s of Tx. Line | [7 empty] | Physical Progress Substation |  |  | Original SCOD | Anticipated SCOD | Remarks
[16 empty] | Length | Location | Foundation | Erection | Stringing | Foundation (%) | Erection (%) | Stringing (%) | Civil Work (%) | Equipment Received (%) | Equipment Erected (%)
24
21
Data Scoure (Sl. No.(s)1, 2, 5, 6, 10b, 10c, 10d, 10e, 12)
Formulas:
Tentative SCOD = DATE(YEAR(TODAY()), MONTH(TODAY()+[Execution Timeline]), DAY(TODAY()))