## Data Sources
SN | Connectivity Application Status | Frequency
1 | CTU ¦ Central Transmission Utility of India Limited CMETS (Agenda and Minutes: Region wise) link:https://ctuil.in/ists-consultation-meeting | Daily
2 | CTU ¦ Central Transmission Utility of India Limited JCC (Region wise as per document release Agenda/Minutes) link https://ctuil.in/ists-joint-coordination-meeting | Daily
3 | Status of effectiveness of connectivity granted to RE generators (Effective date of connectivity wise) link | Daily
4 | CTU ¦ Central Transmission Utility of India Limited Re-allocation meetings (Agenda and Minutes: Region wise) link | Weekly
5 | CTU ¦ Central Transmission Utility of India Limited Bidding Calendar link | Weekly
6 | Transmission Reports - Central Electricity Authority TBCB report from CEA transmission (monthly comparison) link | Daily
7 | CTUIL (OPEN ACCESS) (Compliance of Land and Financial Closure) link | Daily
8 | Monitoring of Connectivity (all 3 Annexures and monthly document release comparison) link | Daily
SN | Substation and Transmission Tracking | Frequency
9 | (Status of allocation of bays at ISTS substations for connectivity grantees, Connectivity margins at existing ISTS (non RE) substations for future RE integration and Connectivity Margin in ISTS RE Substations available by Mar-2030) link | Weekly
10a | Potential RE Zones Report link | Weekly
10b | NCT (Agenda and Minutes Summary and Comparison of Scheme wise elements) link Link: https://cea.nic.in/comm-trans/national-committee-on-transmission/?lang=en | Daily
10c | Tender websites PFCCL and RECPDCL mentioned in NCT under TBCB and RTM (RFP and other tender documents in folders; Bidding Status: Bid Submission Date or Deadline, Commissioning Timeline and Expected SCOD) RECPDCL: https://www.recpdcl.in/rectpcltender PFCCL:https://www.pfcclindia.com/tender-new.php PFCCL Notice: https://www.pfcclindia.com/notice.php?AM1 | Daily
10d | CEA monthly transmission reports: (track status for tender elements timelines from 1) CEA Monthly report for actual physical progress of elements and 2) Actual COD from completion report) CEA https://cea.nic.in/transmission-reports/?lang=en | Daily
10e | Map of the above Section 2 data to be created for review and edit by users
11 | Bulk Consumers and Green Hydrogen link | Weekly
12 | CEA: transmission schemes, substations (transformation capacity) and transmission lines published each month on CEA monthly reports section under transmission. | Weekly
13 | Global Wind Atlas (India Map Visualization) | Weekly
14 | Open Infrastructure Map (India Map Visualization) | Weekly

## Data to be captured
[8 empty] | 1200002471 |  | 2200002280 | 40 |  | 12.09.2025 |  | Solar + BESS | 300 | 300 | 300 +240 |  |  |  |  | 300 |  |  |  |  | JCC | JCC | [6 empty] | Generating station(s), including REGS(s), without ESS | Cmets , JCC | CMETS
| Sr.no. | Region | State | Substation | Coordinates | Name of Developers | Group | GNA/ST II Application ID | LTA Application ID | Application ID under Enhancement 5.2 or revision | CMETS GNA Approved | CMETS LTA Approved | CMETS GNA Meeting Date | CMETS LTA Meeting Date | Type | Application Quantum (MW)(ST II) | Granted Quantum GNA/LTA(MW) | Installed/Break-up Capacity (MW) |  |  |  | Battery |  |  | PSP |  |  | Commissioned |  | Application/Submission Date | Mode(Criteria for applying) | Applied Start of Connectivity sought by developer date( start date of connectivity as per the application) | GNA Operationalization Date | GNA Operationalization (Yes/No) | Date from which additional capacity is to be added | Nature of Applicant | Status of application(Withdrawn / granted. Revoked.) | Voltage level | Bay No | CTS Element Unique Code | ATS Element Unique Code | DTL Element Code Unique | Date of Last Element Unique Code | In-principle Grant | Final Grant | In case of Land BG Conversion Date | Remarks
[18 empty] | Solar | Wind | Hybrid | Hydro | MWh | Injection (MW) | Drawl (MW) | MWh | Injection (MW) | Drawl (MW) | TGNA | GNA
| 1 | NR | Uttar Pradesh | Aligarh (PG) |  | THDC India Limited |  | 2200001981 |  |  | 43 |  | 2026-01-12 |  | Solar | 11 | 0 | 11 | [11 empty] | 2025-04-28 | Land BG route | 2025-06-15 |  |  |  | REGS with installed capacity of 5 MW & above applying for Connectivity through electrical system of a generating station already having Connectivity to ISTS | Withdrawn
| 2 | NR | Rajasthan | Bikaner-II |  | ACME Solar Holdings Limited |  | 1200003683 | 1200003829 | 2200002332 | 43 |  | 2026-01-12 |  | Solar+BESS | 300 | 300 | 490 |  |  |  |  | 250 | [6 empty] | 2025-08-14 |  |  | 2027-03-31 | No | 2026-12-31 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 3 | NR | Rajasthan | Bikaner-II |  | Juniper Green Cosmic Private Limited |  | 1200003740 | 412100008 | 2200002123 | 42 |  | 2025-11-11 |  | Solar+BESS | 100 | 100 | 100 |  |  |  |  | 16 | [6 empty] | 2025-06-05 |  |  | 2025-12-31 | Yes | 2025-12-31 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 4 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003827 | 412100010 | 2200002125 | 42 |  | 2025-11-11 |  | Hybrid+BESS | 150 | 150 | [5 empty] | 28.75 | [6 empty] | 2025-06-05 |  |  | 2026-04-30 | No | 2026-04-30 | Generating station(s), including REGS(s), with ESS | Granted | 220
Data Scoure (Sl. No.(s) 1,2,3,4,7,8,9,11) | 5 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003910 | 412100010 | 2200002125 | 42 | [25 empty] | Granted | 220
| 6 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003958 | 412100010 | 2200002125 | 42 | [25 empty] | Granted | 220
| 7 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 312100010 | 412100010 | 2200002125 | 42 | [25 empty] | Granted | 220
| 8 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 312100012 | 412100010 | 2200002125 | 42 | [25 empty] | Granted | 220
| 9 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 312100010 | 412100011 | 2200002126 | 42 |  | 2025-11-11 |  | Solar+BESS | 65 | 65 | 65 |  |  |  |  | 17.5 | [6 empty] | 2025-06-05 |  |  | 2026-06-30 | No | 2026-04-30 | (Generating station(s), including REGS(s), with ESS | Granted | 220
| 10 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 312100012 | 412100011 | 2200002126 | 42 | [25 empty] | Granted | 220
| 11 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003827 | 412100009 | 2200002127 | 42 |  | 2025-11-11 |  | Hybrid+BESS | 150 | 150 | [5 empty] | 11.25 | [6 empty] | 2025-06-05 |  |  | 2026-03-31 | No | 2026-03-31 | Generating station(s), including REGS(s), with ESS | Granted | 220
| 12 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003910 | 412100009 | 2200002127 | 42 | [25 empty] | Granted | 220
| 13 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003958 | 412100009 | 2200002127 | 42 | [25 empty] | Granted | 220
| 14 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 312100010 | 412100009 | 2200002127 | 42 | [25 empty] | Granted | 220
| 15 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 312100012 | 412100009 | 2200002127 | 42 | [25 empty] | Granted | 220
| 16 | NR | Rajasthan | Barmer-I |  | Enren-I Energy Private Limited |  | 2200000286 |  | 2200002140 | 42 |  | 2025-11-11 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 150 | [6 empty] | 2025-06-11 |  |  | 2027-03-31 | No | 2026-02-28 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 17 | NR | Rajasthan | Fatehgarh-III |  | Serentica Renewables India Private Limited |  | 212100034 |  | 2200002249 | 42 |  | 2025-11-11 |  | Hybrid | 300 | 300 | 300 | 200 | [10 empty] | 2025-07-15 |  |  |  |  | 2028-06-30 | Generating station(s), including REGS(s), without ESS | Withdrawn
| 18 | NR | Rajasthan | Fatehgarh-III |  | Serentica Renewables India Private Limited |  | 212100036 |  | 2200002250 | 42 |  | 2025-11-11 |  | Hybrid | 300 | 300 | 300 | 200 | [10 empty] | 2025-07-15 |  |  |  |  | 2028-06-30 | Generating station(s), including REGS(s), without ESS | Withdrawn
| 19 | NR | Rajasthan | Fatehgarh-III |  | Serentica Renewables India Private Limited |  | 2200000020 |  | 2200002251 | 42 |  | 2025-11-11 |  | Hybrid | 300 | 300 | 300 | 200 | [10 empty] | 2025-07-15 |  |  |  |  | 2028-06-30 | Generating station(s), including REGS(s), without ESS | Withdrawn
| 20 | NR | Rajasthan | Bhadla-II |  | ACME Heergarh Powertech Private Limited |  | 1200002471 |  | 2200002280 | 42 |  | 2025-11-11 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 300 | [6 empty] | 2025-07-22 |  |  | 2027-03-31 | No | 2027-01-01 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 21 | NR | Rajasthan | Bikaner-IV |  | AM Green Energy Private Limited |  | 2200000319 |  | 2200002294 | 42 |  | 2025-11-11 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 125 | [6 empty] | 2025-07-30 |  |  | 2027-12-31 | No | 2027-12-31 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 22 | NR | Rajasthan | Fatehgarh-III |  | Khaba Renewable Energy Private Limited |  | 1200003502 |  | 2200002307 | 42 |  | 2025-11-11 |  | Solar+BESS | 250 | 250 | 250 |  |  |  |  | 150 | [6 empty] | 2025-08-01 |  |  | 2026-12-31 | No | 2026-12-31 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 23 | NR | Rajasthan | Bikaner-II |  | Litsolaire Energy Private Limited |  | 1200003983 |  | 2200002312 | 42 |  | 2025-11-11 |  | BESS | 100 | 100 | [5 empty] | 50 | [6 empty] | 2025-08-05 |  |  | 2026-12-31 | No | 2026-12-31 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 24 | NR | Rajasthan | Fatehgarh-IV |  | Luceo Solar Private Limited |  | 212100032 |  | 2200002316 | 42 |  | 2025-11-11 |  | Solar+BESS | 200 | 200 | 200 |  |  |  |  | 150 | [6 empty] | 2025-08-05 |  |  | 2027-06-30 | No | 2027-06-30 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 25 | NR | Rajasthan | Bikaner-II |  | ACME Solar Holdings Limited |  | 1200003683 | 1200003829 | 2200002332 | 42 |  | 2025-11-11 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 190 | [6 empty] | 2025-08-14 |  |  |  |  | 2026-12-31 | Generating station(s), including REGS(s), without ESS | Applied | 220
| 26 | NR | Rajasthan | Bikaner-IV |  | Avaada RJBikaner Private Limited |  | 2200000254 |  | 2200002330 | 42 |  | 2025-11-11 |  | Solar+BESS | 600 | 600 | 600 |  |  |  |  | 590 | [6 empty] | 2025-08-18 |  |  | 2027-06-30 | No | 2027-06-30 | Generating station(s), including REGS(s), without ESS | Granted
| 27 | NR | Rajasthan | Bhadla-III |  | Solarcraft Power India 4 Private Limited |  | 2200001749 |  | 2200002345 | 42 |  | 2025-11-11 |  | Solar+BESS | 50 | 50 | 50 |  |  |  |  | 50 | [6 empty] | 2025-08-21 |  |  | 2029-07-20 | No | 2029-07-20 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 28 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 2200000063 |  | 2200002358 | 42 |  | 2025-11-11 |  | Hybrid+BESS | 300 | 300 | 300 | 170 |  |  |  | 150 | [6 empty] | 2025-08-27 |  |  | 2027-12-31 | No | 2027-12-31 | Renewable Power Park developer | Granted | 220
| 29 | NR | Rajasthan | Bhadla-II |  | Solarcraft Power India 4 Private Limited |  | 2200000152 |  | 2200002376 | 42 |  | 2025-11-11 |  | Solar+BESS | 150 | 150 | 150 |  |  |  |  | 150 | [6 empty] | 2025-08-31 |  |  | 2028-03-31 | No | 2028-03-31 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 30 | NR | Rajasthan | Bikaner-IV |  | Solarcraft Power India 17 Private Limited |  | 2200000210 |  | 2200002378 | 42 |  | 2025-11-11 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 300 | [6 empty] | 2025-09-02 |  |  | 2028-03-31 | No | 2028-03-31 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 31 | NR | Rajasthan | Fatehgarh-III |  | Altra Xergi Power Private Limited |  | 1200002637 | 1200002639 | 2200002382 | 42 |  | 2025-11-11 |  | Solar+BESS | 380 | 380 | 290 |  |  |  |  | 380 | [6 empty] | 2025-09-03 |  |  |  |  | 2027-03-31 | Generating station(s), including REGS(s), without ESS | Withdrawn | 220
| 32 | NR | Rajasthan | Barmer-II |  | Vismaya Five Renewables Private Limited |  | 2200000954 |  | 2200002392 | 42 |  | 2025-11-11 |  | Solar+BESS | 250 | 250 | 250 |  |  |  |  | 150 | [6 empty] | 2025-09-05 |  |  | 2030-12-31 | No | 2031-12-31 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 33 | NR | Rajasthan | Bhadla-IV |  | Vismaya Four Renewables Private Limited |  | 2200000910 |  | 2200002394 | 42 |  | 2025-11-11 |  | Solar+BESS | 250 | 250 | 250 |  |  |  |  | 240 | [6 empty] | 2025-09-05 |  |  |  |  | 2031-10-01 | Generating station(s), including REGS(s), without ESS | Granted | 400
| 34 | NR | Uttar Pradesh | Aligarh (PG) |  | THDC India Limited |  | 2200001981 |  |  | 40 |  | 2025-09-12 |  | Solar | 11 |  | 11 | [11 empty] | 2025-04-28 | Land BG route | 2025-06-15 |  |  |  | REGS with installed capacity of 5 MW & above applying for Connectivity through electrical system of a generating station already having Connectivity to ISTS | Applied
| 35 | NR | Rajasthan | Ramgarh-I |  | ACME Greentech Urja Private Limited |  | 2200002060 |  |  | 40 |  | 2025-09-12 |  | Solar | 2182 |  | 2182 | [11 empty] | 2025-05-20 | Land BG route | 2028-12-28 |  |  |  | Generating station, including REGS, without ESS | Applied
| 36 | NR | Rajasthan | Ramgarh-II |  | RJS Renewables Private Limited |  | 2200002062 |  |  | 40 |  | 2025-09-12 |  | Solar | 150 | 0 | 150 | [11 empty] | 2025-05-20 | Land Route | 2028-04-20 |  |  |  | Generating station, including REGS, without ESS | Applied
| 37 | NR | Rajasthan | Ramgarh-II |  | Ashoka Renewable Energy 1 Private Limited |  | 2200002130 |  |  | 40 |  | 2025-09-12 |  | Wind | 150 |  |  | 150 | [10 empty] | 2025-06-06 | Land BG Route | 2030-10-01 |  |  |  | Generating station, including REGS, without ESS | Applied
| 38 | NR | Rajasthan | Barmer-IV |  | Jindal Green Private Limited |  | 2200002136 |  |  | 40 |  | 2025-09-12 |  | Solar | 350 |  | 350 | [11 empty] | 2025-06-10 | Land BG Route | 2031-06-30 |  |  |  | Generating station, including REGS, without ESS | Applied
| 39 | NR | Rajasthan | Barmer-IV |  | Jindal Green Private Limited |  | 2200002150 |  |  | 40 |  | 2025-09-12 |  | Solar | 300 |  | 300 | [11 empty] | 2025-06-11 | Land BG Route | 2031-09-30 |  |  |  | Generating station, including REGS, without ESS | Applied
| 40 | NR | Rajasthan | Bhadla-V |  | ReNew Solar Power Private Limited |  | 2200002154 |  |  | 40 |  | 2025-09-12 |  | Solar | 300 |  | 300 | [11 empty] | 2025-06-11 | Land BG Route | 2028-03-31 |  |  |  | Generating station, including REGS, without ESS | Applied
| 41 | NR | Rajasthan | Bhadla-V |  | ReNew Solar Power Private Limited |  | 2200002153 |  |  | 40 |  | 2025-09-12 |  | Solar | 300 |  | 300 | [11 empty] | 2025-06-11 | Land BG Route | 2028-06-30 |  |  |  | Generating station, including REGS, without ESS | Applied
| 42 | NR | Rajasthan | Bhadla-V |  | ReNew Solar Power Private Limited |  | 2200002152 |  |  | 40 |  | 2025-09-12 |  | Solar | 300 |  | 300 | [11 empty] | 2025-06-11 | Land BG Route | 2028-09-30 |  |  |  | Generating station, including REGS, without ESS | Applied
| 43 | NR | Rajasthan | Bhadla -V |  | ReNew Solar Power Private Limited |  | 2200002151 |  |  | 40 |  | 2025-09-12 |  | Solar | 300 |  | 300 | [11 empty] | 2025-06-11 | Land BG Route | 2028-12-31 |  |  |  | Generating station, including REGS, without ESS | Applied
| 44 | NR | Rajasthan | Bhadla-V |  | Jorhat Solar Power Private Limited |  | 2200002155 |  |  | 40 |  | 2025-09-12 |  | Solar | 400 |  | 400 | [11 empty] | 2025-06-12 | Land Route | 2030-03-31 |  |  |  | Generating station, including REGS, without ESS | Applied
| 45 | NR | Rajasthan | Bhadla-V |  | ReNew Solar Power Private Limited |  | 2200002164 |  |  | 40 |  | 2025-09-12 |  | Solar | 300 |  | 300 | [11 empty] | 2025-06-13 | Land BG Route | 2029-03-31 |  |  |  | Generating station, including REGS, without ESS | Applied
| 46 | NR | Rajasthan | Bhadla-V |  | ReNew Solar Power Private Limited |  | 2200002166 |  |  | 40 |  | 2025-09-12 |  | Solar | 300 |  | 300 | [11 empty] | 2025-06-13 | Land BG Route | 2029-06-30 |  |  |  | Generating station, including REGS, without ESS | Applied
| 47 | NR | Rajasthan | Bhadla-V |  | ReNew Solar Power Private Limited |  | 2200002165 |  |  | 40 |  | 2025-09-12 |  | Solar | 200 |  | 200 | [11 empty] | 2025-06-13 | Land BG Route | 2029-09-30 |  |  |  | Generating station, including REGS, without ESS | Applied
| 48 | NR | Rajasthan | Barmer-IV |  | ReNew Solar Power Private Limited |  | 2200002162 |  |  | 40 |  | 2025-09-12 |  | Solar | 300 |  | 300 | [11 empty] | 2025-06-13 | Land BG Route | 2027-09-30 |  |  |  | Generating station, including REGS, without ESS | Applied
| 49 | NR | Rajasthan | Bhadla-V |  | ReNew Solar Power Private Limited |  | 2200002163 |  |  | 40 |  | 2025-09-12 |  | Solar | 100 |  | 100 | [11 empty] | 2025-06-13 | LOA or PPA | 2027-06-30 |  |  |  | Generating station, including REGS, without ESS | Applied
| 50 | NR | Rajasthan | Bhadla-V |  | Balasore Solar Power Private Limited |  | 2200002174 |  |  | 40 |  | 2025-09-12 |  | Solar | 300 |  | 300 | [11 empty] | 2025-06-18 | Land Route | 2030-03-31 |  |  |  | Generating station, including REGS, without ESS | Applied
| 51 | NR | Jammu and Kashmir | Kishtwar-I |  | NHPC Limited |  | 2200002181 |  |  | 40 |  | 2025-09-12 |  | Hydro | 260 |  |  |  |  | 260 | [8 empty] | 2025-06-20 | NA | 2029-05-31 |  |  |  | Generating station, including REGS, without ESS | Applied
| 52 | NR | Rajasthan | Barmer-IV |  | Vannur Solar Power Private Limited |  | 2200002194 |  |  | 40 |  | 2025-09-12 |  | Solar | 275 |  | 275 | [11 empty] | 2025-06-23 | Land Route | 2030-10-31 |  |  |  | Generating station, including REGS, without ESS | Applied
| 53 | NR | Jammu and Kashmir | Kishtwar-I |  | Chenab Valley Power Projects Limited |  | 2200002179 |  |  | 40 |  | 2025-09-12 |  | Hydro | 540 |  |  |  |  | 540 | [8 empty] | 2025-06-24 | NA | 2027-12-31 |  |  |  | Generating station, including REGS, without ESS | Applied
| 54 | NR | Rajasthan | Ramgarh-III |  | Tata Power Renewable Energy Limited |  | 2200002201 |  |  | 40 |  | 2025-09-12 |  | Solar | 1000 |  | 1000 | [11 empty] | 2025-06-27 | Land BG Route | 2030-03-31 |  |  |  | Generating station, including REGS, without ESS | Applied
| 55 | NR | Rajasthan | Ramgarh-III |  | Adani Renewable Energy Holding Twelve Limited |  | 2200002217 |  |  | 40 |  | 2025-09-12 |  | Solar | 173.33 |  | 173.33 | [11 empty] | 2025-06-30 | LOA or PPA | 2027-06-15 |  |  |  | Generating station, including REGS, without ESS through a lead generator | Applied
| 56 | NR | Rajasthan | Barmer-III |  | Unique Hybrid Renewable Energy 3 Private Limited |  | 2200002227 |  |  | 40 |  | 2025-09-12 |  | Solar | 300 |  | 300 | [11 empty] | 2025-07-07 | Land BG route | 2030-10-01 |  |  |  | Generating station, including REGS, without ESS | Applied
| 57 | NR | Rajasthan | Ramgarh-II |  | BN Dispatchable-5 Private Limited |  | 2200002238 |  |  | 40 |  | 2025-09-12 |  | Hybrid+BESS | 350 |  | 150 | 200 |  |  |  | 100 | [6 empty] | 2025-07-09 | Land BG route | 2028-06-30 |  |  |  | Generating station, including REGS, with ESS | Applied
| 58 | NR | Rajasthan | Bikaner-IV |  | Purvah Green Power Private Limited |  | 2200002243 |  |  | 40 |  | 2025-09-12 |  | Solar | 300 |  | 300 | [11 empty] | 2025-07-11 | Land BG route | 2029-01-01 |  |  |  | Generating station, including REGS, without ESS | Applied
| 59 | NR | Rajasthan | Bikaner-IV |  | Purvah Green Power Private Limited |  | 2200002248 |  |  | 40 |  | 2025-09-12 |  | Solar | 300 |  | 300 | [11 empty] | 2025-07-14 | Land BG route | 2029-07-01 |  |  |  | Generating station, including REGS, without ESS | Applied
| 60 | NR | Jammu and Kashmir | Amargarh-I |  | NHPC Limited (Uri-I Stage-II HEP) |  | 2200002295 |  |  | 40 |  | 2025-09-12 |  | Hydro | 240 |  |  |  |  | 240 | [8 empty] | 2025-07-30 | - | 2029-03-31 |  |  |  | Generating station, including REGS, without ESS | Applied
| 61 | NR | Rajasthan | Bikaner-II |  | Juniper Green Cosmic Private Limited |  | 1200003740 | 412100008 | 2200002123 | 40 |  | 2025-09-12 |  | Solar+BESS | 100 |  | 100 |  |  |  |  | 16 | [6 empty] | 2025-06-05 |  |  |  |  | 2025-12-31 | Generating station(s), including REGS(s), without ESS | Applied | 220
| 62 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003827 | 412100010 | 2200002125 | 40 |  | 2025-09-12 |  | Hybrid+BESS | 150 | [6 empty] | 28.75 | [6 empty] | 2025-06-05 |  |  |  |  | 2026-04-30 | Generating station(s), including REGS(s), with ESS | Applied | 220
| 63 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003910 | 412100010 | 2200002125 | [26 empty] | Applied | 220
| 64 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003958 | 412100010 | 2200002125 | [26 empty] | Applied | 220
| 65 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 312100010 | 412100010 | 2200002125 | [26 empty] | Applied | 220
| 66 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 312100012 | 412100010 | 2200002125 | [26 empty] | Applied | 220
| 67 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 312100010 | 412100011 | 2200002126 | 40 |  | 2025-09-12 |  | Solar+BESS | 65 |  | 65 |  |  |  |  | 17.5 | [6 empty] | 2025-06-05 |  |  |  |  | 2026-04-30 | (Generating station(s), including REGS(s), with ESS | Applied | 220
| 68 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 312100012 | 412100011 | 2200002126 | [26 empty] | Applied | 220
| 69 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003827 | 412100009 | 2200002127 | 40 |  | 2025-09-12 |  | Hybrid+BESS | 150 | [6 empty] | 11.25 | [6 empty] | 2025-06-05 |  |  |  |  | 2026-03-31 | Generating station(s), including REGS(s), with ESS | Applied | 220
| 70 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003910 | 412100009 | 2200002127 | [26 empty] | Applied | 220
| 71 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003958 | 412100009 | 2200002127 | [26 empty] | Applied | 220
| 72 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 312100010 | 412100009 | 2200002127 | [26 empty] | Applied | 220
| 73 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 312100012 | 412100009 | 2200002127 | [26 empty] | Applied | 220
| 74 | NR | Rajasthan | Barmer-I |  | Enren-I Energy Private Limited |  | 2200000286 |  | 2200002140 | 40 |  | 2025-09-12 |  | Solar+BESS | 300 |  | 300 |  |  |  |  | 150 | [6 empty] | 2025-06-11 |  |  |  |  | 2026-02-28 | Generating station(s), including REGS(s), without ESS | Applied | 220
| 75 | NR | Rajasthan | Fatehgarh-III |  | Serentica Renewables India Private Limited |  | 212100034 |  | 2200002249 | 40 |  | 2025-09-12 |  | Hybrid | 300 |  | 300 | 200 | [10 empty] | 2025-07-15 |  |  |  |  | 2028-06-30 | Generating station(s), including REGS(s), without ESS | Applied | 400
| 76 | NR | Rajasthan | Fatehgarh-III |  | Serentica Renewables India Private Limited |  | 212100036 |  | 2200002250 | 40 |  | 2025-09-12 |  | Hybrid | 300 |  | 300 | 200 | [10 empty] | 2025-07-15 |  |  |  |  | 2028-06-30 | Generating station(s), including REGS(s), without ESS | Applied | 400
| 77 | NR | Rajasthan | Fatehgarh-III |  | Serentica Renewables India Private Limited |  | 2200000020 |  | 2200002251 | 40 |  | 2025-09-12 |  | Hybrid | 300 |  | 300 | 200 | [10 empty] | 2025-07-15 |  |  |  |  | 2028-06-30 | Generating station(s), including REGS(s), without ESS | Applied | 400
| 78 | NR | Rajasthan | Bhadla-II |  | ACME Heergarh Powertech Private Limited |  | 1200002471 |  | 2200002280 | 40 |  | 2025-09-12 |  | Solar+BESS | 300 |  | 540 |  |  |  |  | 300 | [6 empty] | 2025-07-22 |  |  |  |  | 2027-01-01 | Generating station(s), including REGS(s), without ESS | Applied | 220
| 79 | NR | Rajasthan | Bikaner-IV |  | AM Green Energy Private Limited |  | 2200000319 |  | 2200002294 | 40 |  | 2025-09-12 |  | Solar+BESS | 300 |  | 400 |  |  |  |  | 125 | [6 empty] | 2025-07-30 |  |  |  |  | 2027-12-31 | Generating station(s), including REGS(s), without ESS | Applied | 220
| 80 | NR | Rajasthan | Merta-III |  | Hexa Climate Solutions Private Limited |  | 2200001701 |  |  | 39 |  | 2025-07-28 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 50 | [6 empty] | 2025-01-28 | Land BG Route | 2029-11-30 |  |  |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-72571, EL-F1D12, EL-0C9F0, EL-5EA00, EL-C89B9, EL-DC354, EL-A1D4E, EL-4B103 |  | EL-468EF, EL-A50EC
| 81 | NR | Rajasthan | Merta-III |  | Hexa Climate Solutions Private Limited |  | 2200001702 |  |  | 39 |  | 2025-07-28 |  | BESS | 300 | 300 | [5 empty] | 300 | [6 empty] | 2025-01-28 | Land BG Route | 2029-11-30 | 2031-06-30 | No |  | Standalone ESS | Granted | 220 |  | EL-72571, EL-F1D12, EL-0C9F0, EL-5EA00, EL-C89B9, EL-DC354, EL-A1D4E, EL-4B103 |  | EL-468EF, EL-A50EC
| 82 | NR | Rajasthan | Sanchore-I |  | Green Infra Renewable Energy Farms Private Limited |  | 2200001762 |  |  | 39 |  | 2025-07-28 |  | Solar | 300 | 300 | 300 | [11 empty] | 2025-02-13 | Land BG Route | 2028-12-15 |  |  |  | Generating station, including REGS, without ESS | Granted | 220 |  | EL-A5BEB, EL-48EFF, EL-7E7E2, EL-05218, EL-73A05, EL-A1D4E, EL-0FE43, EL-4B103, EL-071AA |  | EL-6B5A6, EL-4C729
| 83 | NR | Rajasthan | Sanchore-I |  | Green Infra Renewable Energy Farms Private Limited |  | 2200001771 |  |  | 39 |  | 2025-07-28 |  | Solar | 300 | 300 | 300 | [11 empty] | 2025-02-14 | Land BG Route | 2028-12-15 | 2031-06-30 | No |  | Generating station, including REGS, without ESS | Granted | 220 |  | EL-A5BEB, EL-48EFF, EL-7E7E2, EL-05218, EL-73A05, EL-A1D4E, EL-0FE43, EL-4B103, EL-071AA |  | EL-6B5A6, EL-4C729
| 84 | NR | Rajasthan | Pali-I |  | Waaree Forever Energies Private Limited |  | 2200001903 |  |  | 39 |  | 2025-07-28 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 150 | [6 empty] | 2025-03-31 | Land BG Route | 2032-03-31 | 2025-06-16 | Yes |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-5B721, EL-43445, EL-0C9F0, EL-C89B9, EL-DC354, EL-A1D4E, EL-DB837, EL-4B103, EL-00011 |  | EL-6095C, EL-86667
| 85 | NR | Rajasthan | Pali-I |  | Waaree Forever Energies Private Limited |  | 2200001904 |  |  | 39 |  | 2025-07-28 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 150 | [6 empty] | 2025-03-31 | Land BG Route | 2032-09-30 | 2032-09-30 | No |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-5B721, EL-43445, EL-0C9F0, EL-C89B9, EL-DC354, EL-A1D4E, EL-DB837, EL-4B103, EL-00011 |  | EL-6095C, EL-86667
| 86 | NR | Rajasthan | Pali-I |  | Terra Clean Limited |  | 2200001922 |  |  | 39 |  | 2025-07-28 |  | Solar | 155 | 155 | 155 | [11 empty] | 2025-04-05 | Land BG route | 2030-09-30 | 2031-06-30 | No |  | Generating station, including REGS, without ESS | Granted | 220 |  | EL-5B721, EL-43445, EL-0C9F0, EL-C89B9, EL-DC354, EL-A1D4E, EL-DB837, EL-4B103, EL-00011 |  | EL-970EB, EL-86667
| 87 | NR | Rajasthan | Bhadla-V |  | HR Saraswati Energy Private Limited |  | 2200001917 |  |  | 39 |  | 2025-07-28 |  | Solar | 300 | 300 | 300 | [11 empty] | 2025-04-07 | Land BG route | 2026-12-31 | 2031-09-30 | No |  | Generating station, including REGS, without ESS | Granted | 220 |  | EL-D6782, EL-A9814, EL-3CFCF, EL-911E3, EL-2B272, EL-75882, EL-6DFEE, EL-65D44, EL-C8513 |  | EL-D77E9, EL-23E4F
| 88 | NR | Rajasthan | Bikaner-VI |  | Enren Surya Urja Private Limited |  | 2200001936 |  |  | 39 |  | 2025-07-28 |  | Solar+BESS | 300 |  | 300 |  |  |  |  | 150 | [6 empty] | 2025-04-10 | Land BG route | 2027-12-31 |  |  |  | Generating station, including REGS, with ESS | Applied
| 89 | NR | Rajasthan | Ramgarh-III |  | Enren Solar Private Limited |  | 2200001937 |  |  | 39 |  | 2025-07-28 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 150 | [6 empty] | 2025-04-10 | Land BG route | 2027-10-31 | 2031-12-31 | No |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-351F9, EL-D397F, EL-3F657, EL-38782, EL-30734, EL-A1D4E, EL-6EB09, EL-4B103, EL-EAAE1 |  | EL-CF954, EL-A1FDB
| 90 | NR | Rajasthan | Barmer-IV |  | Vannur Solar Power Private Limited |  | 2200001940 |  |  | 39 |  | 2025-07-28 |  | Solar | 300 | 300 | 300 | [11 empty] | 2025-04-11 | Land route | 2030-06-30 | 2031-12-31 | No |  | Generating station, including REGS, without ESS | Granted | 220 |  | EL-F5025, EL-C2F66, EL-B1EED, EL-099D8, EL-30D5A, EL-2B272, EL-1D2C6, EL-6DFEE, EL-4B103, EL-7448F |  | EL-63D48, EL-63408
| 91 | NR | Rajasthan | Pali-I |  | Jindal Green Private Limited |  | 2200001945 |  |  | 39 |  | 2025-07-28 |  | Solar | 350 | 350 | 350 | [11 empty] | 2025-04-11 | Land BG route | 2030-06-30 | 2031-06-30 | No |  | Generating station, including REGS, without ESS | Granted | 220 |  | EL-5B721, EL-43445, EL-0C9F0, EL-C89B9, EL-DC354, EL-A1D4E, EL-DB837, EL-4B103, EL-00011 |  | EL-EEBBC, EL-86667
| 92 | NR | Rajasthan | Sanchore-I |  | Waaree Forever Energies Private Limited |  | 2200001955 |  |  | 39 |  | 2025-07-28 |  | Solar+BESS | 600 | 600 | 600 |  |  |  |  | 300 | [6 empty] | 2025-04-17 | Land BG route | 2030-12-31 | 2031-06-30 | No |  | Generating station, including REGS, with ESS | Granted | 400 |  | EL-A5BEB, EL-48EFF, EL-7E7E2, EL-05218, EL-73A05, EL-A1D4E, EL-0FE43, EL-4B103, EL-071AA |  | EL-CC9A2, EL-759C3
| 93 | NR | Rajasthan | Sanchore-I |  | Ampin Energy Utility Private Limited |  | 2200001964 |  |  | 39 |  | 2025-07-28 |  | Hybrid | 150 | 150 | 135 | 50.4 | [10 empty] | 2025-04-18 | LOA or PPA | 2027-12-31 | 2031-06-30 | No |  | Generating station, including REGS, without ESS | Granted | 220 |  | EL-A5BEB, EL-48EFF, EL-7E7E2, EL-05218, EL-73A05, EL-A1D4E, EL-0FE43, EL-4B103, EL-071AA |  | EL-6B862, EL-4C729
| 94 | NR | Uttar Pradesh | Aligarh (PG) |  | THDC India Limited |  | 2200001981 |  |  | 39 |  | 2025-07-28 |  | Solar | 11 |  | 11 | [11 empty] | 2025-04-28 | Land BG route | 2025-06-15 |  |  |  | REGS with installed capacity of 5 MW & above applying for Connectivity to ISTS through electrical system of a generating station already having Connectivity to ISTS | Applied
| 95 | NR | Rajasthan | Bhadla-III |  | Rajasthan BESS Private Limited |  | 2200001994 |  |  | 39 |  | 2025-07-28 |  | BESS | 250 | 250 | [5 empty] | 250 | [6 empty] | 2025-04-30 | Land Route | 2026-05-20 | 2027-04-30 | No |  | Standalone ESS | Granted | 220 |  | EL-C16AF, EL-BE37F, EL-DD8DD |  | EL-C06E3, EL-D4AAF
| 96 | NR | Rajasthan | Bhadla-V |  | Renew Solar Power Private Limited |  | 2200001997 |  |  | 39 |  | 2025-07-28 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 150 | [6 empty] | 2025-04-30 | LOA or PPA | 2027-05-31 | 2031-09-30 | No |  | Generating station, including REGS, with ESS | Granted | 400 |  | EL-D6782, EL-A9814, EL-3CFCF, EL-911E3, EL-2B272, EL-75882, EL-6DFEE, EL-65D44, EL-C8513 |  | EL-6A564, EL-85FD1
| 97 | NR | Rajasthan | Barmer-IV |  | Renew Solar Power Private Limited |  | 2200002000 |  |  | 39 |  | 2025-07-28 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 150 | [6 empty] | 2025-04-30 | LOA or PPA | 2027-05-31 | 2031-12-31 | No |  | Generating station, including REGS, with ESS | Granted | 400 |  | EL-F5025, EL-C2F66, EL-B1EED, EL-099D8, EL-30D5A, EL-2B272, EL-1D2C6, EL-6DFEE, EL-4B103, EL-7448F |  | EL-DFA86, EL-EF8E0
| 98 | NR | Rajasthan | Ramgarh-III |  | Adani Renewable Energy Holding Twelve Limited |  | 2200002006 |  |  | 39 |  | 2025-07-28 |  | Solar | 520 | 520 | 520 | [11 empty] | 2025-04-30 | LOA or PPA | 2026-12-31 | 2031-12-31 | No |  | Generating station, including REGS, without ESS | Granted | 400 |  | EL-351F9, EL-D397F, EL-3F657, EL-38782, EL-30734, EL-A1D4E, EL-6EB09, EL-4B103, EL-EAAE1 |  | EL-64276, EL-48FFB
| 99 | NR | Rajasthan | Ramgarh-III |  | Adani Renewable Energy Holding Twelve Limited |  | 2200002009 |  |  | 39 |  | 2025-07-28 |  | Solar | 400 | 400 | 400 | [11 empty] | 2025-04-30 | LOA or PPA | 2026-12-31 | 2031-12-31 | No |  | Generating station, including REGS, without ESS through a lead generator | Granted | 400 |  | EL-351F9, EL-D397F, EL-3F657, EL-38782, EL-30734, EL-A1D4E, EL-6EB09, EL-4B103, EL-EAAE1 |  | EL-6DEF0, EL-E24A2
| 100 | NR | Rajasthan | Ramgarh-III |  | Adani Renewable Energy Holding Nine Limited |  | 2200002010 |  |  | 39 |  | 2025-07-28 |  | Solar+BESS | 180 | 180 | 180 |  |  |  |  | 85 | [6 empty] | 2025-04-30 | LOA or PPA | 2026-12-31 |  |  |  | Generating station, including REGS, with ESS through a lead generator | Granted | 400 |  | EL-351F9, EL-D397F, EL-3F657, EL-38782, EL-30734, EL-A1D4E, EL-6EB09, EL-4B103, EL-EAAE1 |  | EL-64276, EL-48FFB
| 101 | NR | Rajasthan | Barmer-IV |  | Adani Renewable Energy Holding Nine Limited |  | 2200002028 |  |  | 39 |  | 2025-07-28 |  | Solar+BESS | 180 | 180 | 180 |  |  |  |  | 85 | [6 empty] | 2025-05-10 | LOA or PPA | 2026-12-31 | 2031-12-31 | No |  | Generating station, including REGS, with ESS through a lead generator | Granted | 400 |  | EL-F5025, EL-C2F66, EL-B1EED, EL-099D8, EL-30D5A, EL-2B272, EL-1D2C6, EL-6DFEE, EL-4B103, EL-7448F |  | EL-98DE8, EL-EF8E0
| 102 | NR | Rajasthan | Bikaner-VI |  | Solarcraft Power India 17 Private Limited |  | 2200002030 |  |  | 39 |  | 2025-07-28 |  | Solar+BESS | 300 |  | 300 |  |  |  |  | 300 | [6 empty] | 2025-05-12 | Land Route | 2028-06-30 |  |  |  | Generating station, including REGS, with ESS | Applied
| 103 | NR | Rajasthan | Ramgarh-III |  | Acme Greentech Urja Private Limited |  | 2200002060 |  |  | 39 |  | 2025-07-28 |  | Solar | 2182 | 2182 | 2182 | [11 empty] | 2025-05-20 | Land BG route | 2028-12-28 | 2031-12-31 | No |  | Generating station, including REGS, without ESS | Granted | 400 |  | EL-351F9, EL-D397F, EL-3F657, EL-38782, EL-30734, EL-A1D4E, EL-6EB09, EL-4B103, EL-EAAE1 |  | EL-3EA43, EL-9D405
| 104 | NR | Rajasthan | Ramgarh-II |  | RJS Renewables Private Limited |  | 2200002062 |  |  | 39 |  | 2025-07-28 |  | Solar | 150 | 0 | 150 | [11 empty] | 2025-05-20 | Land Route | 2028-04-20 |  |  |  | Generating station, including REGS, without ESS | Applied
| 105 | NR | Rajasthan | Bhadla-V |  | Renew Solar Power Private Limited |  | 2200002063 |  |  | 39 |  | 2025-07-28 |  | Solar | 300 | 300 | 300 | [11 empty] | 2025-05-20 | LOA or PPA | 2027-05-31 |  |  |  | Generating station, including REGS, without ESS | Granted | 400 |  | EL-D6782, EL-A9814, EL-3CFCF, EL-911E3, EL-2B272, EL-75882, EL-6DFEE, EL-65D44, EL-C8513 |  | EL-6A564, EL-85FD1
| 106 | NR | Rajasthan | Bhadla-V |  | Waaree Forever Energies Private Limited |  | 2200002066 |  |  | 39 |  | 2025-07-28 |  | Solar+BESS | 200 | 200 | 200 |  |  |  |  | 100 | [6 empty] | 2025-05-21 | Land BG route | 2032-09-30 | 2032-09-30 | No |  | Generating station, including REGS, with ESS | Granted | 400 |  | EL-D6782, EL-A9814, EL-3CFCF, EL-911E3, EL-2B272, EL-75882, EL-6DFEE, EL-65D44, EL-C8513 |  | EL-77A48, EL-28727
| 107 | NR | Rajasthan | Bhadla-V |  | Waaree Forever Energies Private Limited |  | 2200002071 |  |  | 39 |  | 2025-07-28 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 150 | [6 empty] | 2025-05-22 | Land BG route | 2032-12-31 | 2032-12-31 | No |  | Generating station, including REGS, with ESS | Granted | 400 |  | EL-D6782, EL-A9814, EL-3CFCF, EL-911E3, EL-2B272, EL-75882, EL-6DFEE, EL-65D44, EL-C8513 |  | EL-77A48, EL-28727
| 108 | NR | Rajasthan | Bhadla-V |  | Waaree Forever Energies Private Limited |  | 2200002072 |  |  | 39 |  | 2025-07-28 |  | Solar+BESS | 200 | 200 | 220 |  |  |  |  | 100 | [6 empty] | 2025-05-22 | Land BG route | 2032-12-31 | 2025-05-22 | Yes |  | Generating station, including REGS, with ESS | Granted | 400 |  | EL-D6782, EL-A9814, EL-3CFCF, EL-911E3, EL-2B272, EL-75882, EL-6DFEE, EL-65D44, EL-C8513 |  | EL-77A48, EL-28727
| 109 | NR | Rajasthan | Bhadla-VI |  | Waaree Forever Energies Private Limited |  | 2200002080 |  |  | 39 |  | 2025-07-28 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 150 | [6 empty] | 2025-05-23 | Land BG route | 2031-12-31 | 2032-06-30 | No |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-0F996, EL-DEBDE, EL-24C0A, EL-6FD3E, EL-88DFA, EL-2B272, EL-F92C8, EL-6DFEE, EL-A4E7D, EL-61F37 |  | EL-64DF7, EL-7BD8D
| 110 | NR | Rajasthan | Barmer-I |  | Hinduja Renewables Energy Private Limited |  | 2200002093 |  |  | 39 |  | 2025-07-28 |  | Solar | 50 | 50 | 50 | [11 empty] | 2025-05-28 | Land BG route | 2028-03-31 | 2028-03-31 | No |  | Generating station, including REGS, without ESS | Granted | 220 |  | EL-AB6F6, EL-04FBF, EL-E0593, EL-C16AF, EL-9DE74, EL-26050, EL-4777E, EL-0D0CA, EL-7AF76, EL-DA901, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-5996E, EL-32FE8, EL-A495D, EL-74937, EL-50132, EL-06311, EL-D0E44, EL-553D7, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-F20FC, EL-6F66E, EL-B6BDF, EL-C7A50 |  | EL-EB9F7, EL-9D9D5
| 111 | NR | Rajasthan | Pali-I |  | Vena Energy Konkan Wind Power Private Limited |  | 2200002097 |  |  | 39 |  | 2025-07-28 |  | BESS | 300 | 300 | [5 empty] | 300 | [6 empty] | 2025-05-28 | Land Route | 2030-12-31 | 2031-06-30 | No |  | Standalone ESS | Granted | 220 |  | EL-5B721, EL-43445, EL-0C9F0, EL-C89B9, EL-DC354, EL-A1D4E, EL-DB837, EL-4B103, EL-00011 |  | EL-3FB44, EL-86667
| 112 | NR | Rajasthan | Bikaner-V |  | SA Renewable Infra Private Limited |  | 2200002099 |  |  | 39 |  | 2025-07-28 |  | Solar | 20 | 20 | 20 | [11 empty] | 2025-05-29 | Land Route | 2030-03-31 | 2030-10-31 | No |  | Generating station, including REGS, without ESS | Granted | 220 |  | EL-D9A07, EL-85255, EL-26318, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-905E4, EL-35672 |  | EL-3466E, EL-C638D
| 113 | NR | Rajasthan | Sanchore-I |  | Reliance Nu Energies Private Limited |  | 2200002104 |  |  | 39 |  | 2025-07-28 |  | Solar+BESS | 350 | 350 | 350 |  |  |  |  | 175 | [6 empty] | 2025-05-30 | LOA or PPA | 2027-12-31 | 2031-06-30 | No |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-A5BEB, EL-48EFF, EL-7E7E2, EL-05218, EL-73A05, EL-A1D4E, EL-0FE43, EL-4B103, EL-071AA |  | EL-7A64F, EL-4C729
| 114 | NR | Rajasthan | Sanchore-I |  | Adani Renewable Energy Holding Twelve Limited |  | 2200002111 |  |  | 39 |  | 2025-07-28 |  | Solar | 520 | 520 | 520 | [11 empty] | 2025-05-31 | LOA or PPA | 2027-06-30 | 2031-06-30 | No |  | Generating station, including REGS, without ESS | Granted | 400 |  | EL-A5BEB, EL-48EFF, EL-7E7E2, EL-05218, EL-73A05, EL-A1D4E, EL-0FE43, EL-4B103, EL-071AA |  | EL-95C39, EL-759C3
| 115 | NR | Rajasthan | Bikaner-II |  | Serentica Renewables India Private Limited |  | 1200003838 | 412100014 | 2200001968 | 39 |  | 2025-07-28 |  | Solar+BESS | 180 | 180 | 321 |  |  |  |  | 140 | [6 empty] | 2025-04-22 |  |  | 2026-12-31 | No | 2026-12-31 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 116 | NR | Rajasthan | Bikaner-II |  | Juniper Green Cosmic Private Limited |  | 1200003740 | 412100008 | 2200001970 | 39 |  | 2025-07-28 |  | Solar+BESS | 100 | 100 | 100 |  |  |  |  | 25.39 | [6 empty] | 2025-04-24 |  |  | 2025-12-31 | Yes | 2025-12-31 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 117 | NR | Rajasthan | Bhadla-III |  | Solarcraft Power India 4 Private Limited |  | 2200000300 |  | 2200001984 | 39 |  | 2025-07-28 |  | Solar+BESS | 50 | 50 | 50 |  |  |  |  | 50 | [6 empty] | 2025-04-28 |  |  | 2028-09-01 | No | 2028-09-01 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 118 | NR | Rajasthan | Bhadla-III |  | Solarcraft Power India 4 Private Limited |  | 2200000192 |  | 2200001986 | 39 |  | 2025-07-28 |  | Solar+BESS | 110 | 110 | 110 |  |  |  |  | 110 | [6 empty] | 2025-04-28 |  |  | 2028-09-01 | No | 2028-09-01 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 119 | NR | Rajasthan | Bikaner-IV |  | Solarcraft Power India 17 Private Limited |  | 2200000210 |  | 2200001989 | 39 |  | 2025-07-28 |  | Solar+BESS | 300 |  | 300 |  |  |  |  | 300 | [6 empty] | 2025-04-28 |  |  | 2027-03-31 |  | 2027-03-31 | Generating station(s), including REGS(s), without ESS | Withdrawn | 220
| 120 | NR | Rajasthan | Bhadla-II |  | Solarcraft Power India 4 Private Limited |  | 2200000152 |  | 2200001991 | 39 |  | 2025-07-28 |  | Solar+BESS | 150 |  | 150 |  |  |  |  | 150 | [6 empty] | 2025-04-29 |  |  | 2027-03-31 |  | 2027-03-31 | Generating station(s), including REGS(s), without ESS | Withdrawn | 220
| 121 | NR | Rajasthan | Bikaner-V |  | Solarcraft Power India 8 Private Limited |  | 2200000866 |  | 2200001992 | 39 |  | 2025-07-28 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 300 | [6 empty] | 2025-04-29 |  |  | 2030-09-30 | No | 2030-09-30 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 122 | NR | Rajasthan | Fatehgarh-IV |  | BN Dispatchable-1 Private Limited |  | 2200000103 |  | 2200001995 | 39 |  | 2025-07-28 |  | Hybrid+BESS | 300 | 300 | 154 | 150 |  |  |  | 25 | [6 empty] | 2025-04-30 |  |  | 2027-03-31 | No | 2027-03-31 | Generating station(s), including REGS(s), without ESS | Granted | 220
| 123 | NR | Rajasthan | Bikaner-IV |  | AM Green Energy Private Limited |  | 2200000319 |  | 2200002047 | 39 |  | 2025-07-28 |  | Solar+BESS | 300 |  | 400 |  |  |  |  | 125 | [6 empty] | 2025-05-21 |  |  |  |  | 2026-11-11 | Generating station(s), including REGS(s), without ESS | Withdrawn | 220
| 124 | NR | Rajasthan | Bikaner-III |  | Juniper Green Cosmic Private Limited |  | 2200000073 |  | 2200002079 | 39 |  | 2025-07-28 |  | Solar+BESS | 150 | 150 | 150 |  |  |  |  | 150 | [6 empty] | 2025-05-23 |  |  | 2027-03-31 | No | 2027-03-31 | Generating station(s), including REGS(s), without ESS | Granted
| 125 | NR | Rajasthan | Barmer- I |  | Juniper Green Energy Private Limited |  | 2200000305 |  | 2200002083 | 39 |  | 2025-07-28 |  | Solar+BESS | 300 |  | 500 |  |  |  |  | 160 | [6 empty] | 2025-05-23 |  |  |  |  | 2028-12-31 | Generating station(s), including REGS(s), without ESS | Withdrawn | 220
| 126 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 2200000063 |  | 2200002087 | 39 |  | 2025-07-28 |  | Hybrid+BESS | 300 |  | 300 | 170 |  |  |  | 160 | [6 empty] | 2025-05-23 |  |  |  |  | 2027-12-31 | Renewable Power Park developer | Withdrawn | 220
| 127 | NR | Rajasthan | Bhadla-V |  | Azure Power Fifty One Private Limited |  | 2200001420 |  |  | 38 |  | 2025-05-28 |  | Solar | 600 | 600 | 300 | [11 empty] | 2024-10-30 | Land Route | 2029-12-31 | 2031-09-30 | No |  | Generating station, including REGS, without ESS | Granted | 400 |  | EL-D6782, EL-A9814, EL-3CFCF, EL-911E3, EL-2B272, EL-75882, EL-6DFEE, EL-65D44, EL-B4A45 |  | EL-E140C, EL-24C88
| 128 | NR | Rajasthan | Bikaner-VI |  | Jindal India RE Limited |  | 2200001629 |  |  | 38 |  | 2025-05-28 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 150 | [6 empty] | 2025-01-06 | Land BG Route | 2027-09-30 | 2031-12-31 | No |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-EAECB, EL-F66C7, EL-70C46, EL-8D787, EL-B96FE, EL-A1D4E, EL-11BA3, EL-6DFEE, EL-4B103, EL-0A96D |  | EL-85879, EL-5264E
| 129 | NR | Rajasthan | Barmer-IV |  | Renew Solar Power Private Limited |  | 2200001550 |  |  | 38 |  | 2025-05-28 |  | Solar | 300 | 300 | 300 | [11 empty] | 2025-01-10 | LoA or PPA | 2027-03-03 | 2031-12-31 | No |  | Generating station, including REGS, without ESS | Granted | 400 |  | EL-F5025, EL-C2F66, EL-B1EED, EL-099D8, EL-30D5A, EL-2B272, EL-1D2C6, EL-6DFEE, EL-4B103, EL-7448F |  | EL-EF289, EL-84DBB
| 130 | NR | Rajasthan | Bhadla-V |  | Torrent Green Energy Private Limited |  | 2200001642 |  |  | 38 |  | 2025-05-28 |  | Solar | 1000 | 1000 | 1000 | [11 empty] | 2025-01-11 | Land BG Route | 2029-12-31 | 2031-09-30 | No |  | Generating station, including REGS, without ESS | Granted | 400 |  | EL-D6782, EL-A9814, EL-3CFCF, EL-911E3, EL-2B272, EL-75882, EL-6DFEE, EL-65D44, EL-B4A45 |  | EL-B9C26, EL-80AC0
| 131 | NR | Rajasthan | Barmer-IV |  | JIRE Green Energy Project Two Limited |  | 2200001659 |  |  | 38 |  | 2025-05-28 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 150 | [6 empty] | 2025-01-15 | Land BG Route | 2028-12-30 | 2031-12-31 | No |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-F5025, EL-C2F66, EL-B1EED, EL-099D8, EL-30D5A, EL-2B272, EL-1D2C6, EL-6DFEE, EL-4B103, EL-7448F |  | EL-6D14B, EL-94ECD
| 132 | NR | Rajasthan | Barmer-IV |  | Renew Solar Power Private Limited |  | 2200001684 |  |  | 38 |  | 2025-05-28 |  | Solar+BESS | 200 | 200 | 200 |  |  |  |  | 70 | [6 empty] | 2025-01-23 | LoA or PPA | 2027-01-31 | 2031-12-31 | No |  | Generating station, including REGS, with ESS | Granted | 400 |  | EL-F5025, EL-C2F66, EL-B1EED, EL-099D8, EL-30D5A, EL-2B272, EL-1D2C6, EL-6DFEE, EL-4B103, EL-7448F |  | EL-EF289, EL-84DBB
| 133 | NR | Rajasthan | Barmer-IV |  | Renew Solar Power Private Limited |  | 2200001689 |  |  | 38 |  | 2025-05-28 |  | Solar | 300 | 300 | 300 | [11 empty] | 2025-01-24 | LoA or PPA | 2027-03-31 | 2031-12-31 | No |  | Generating station, including REGS, without ESS | Granted | 400 |  | EL-F5025, EL-C2F66, EL-B1EED, EL-099D8, EL-30D5A, EL-2B272, EL-1D2C6, EL-6DFEE, EL-4B103, EL-7448F |  | EL-EF289, EL-84DBB
| 134 | NR | Rajasthan | Merta-III |  | Hexa Climate Solutions Private Limited |  | 2200001701 |  |  | 38 |  | 2025-05-28 |  | Solar+BESS | 300 |  | 300 |  |  |  |  | 300 | [6 empty] | 2025-01-28 | Land BG Route | 2029-11-30 |  |  |  | Generating station, including REGS, with ESS | Applied | 220
| 135 | NR | Rajasthan | Bhadla-V |  | Hexa Climate Solutions Private Limited |  | 2200001700 |  |  | 38 |  | 2025-05-28 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 50 | [6 empty] | 2025-01-28 | Land BG Route | 2029-11-30 | 2031-09-30 | No |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-D6782, EL-A9814, EL-3CFCF, EL-911E3, EL-2B272, EL-75882, EL-6DFEE, EL-65D44, EL-B4A45 |  | EL-F29A2, EL-9BFCD
| 136 | NR | Rajasthan | Merta-III |  | Hexa Climate Solutions Private Limited |  | 2200001702 |  |  | 38 |  | 2025-05-28 |  | BESS | 300 | 300 | [5 empty] | 300 | [6 empty] | 2025-01-28 | Land BG Route | 2029-11-30 |  |  |  | Standalone ESS | Applied | 400
| 137 | NR | Rajasthan | Ramgarh-II |  | JIRE Green Energy Project Three Limited |  | 2200001717 |  |  | 38 |  | 2025-05-28 |  | Solar+BESS | 200 | 200 | 200 |  |  |  |  | 100 | [6 empty] | 2025-01-30 | Land BG Route | 2028-12-31 | 2030-10-31 | No |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-3DDDE, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-4B103, EL-C8D83 |  | EL-12A1E, EL-28506, EL-D4A9F
| 138 | NR | Rajasthan | Bikaner-IV |  | Tata Power Renewable Energy Limited |  | 2200001721 |  |  | 38 |  | 2025-05-28 |  | Solar | 300 | 300 | 300 | [11 empty] | 2025-01-31 | Land BG Route | 2027-03-31 | 2031-12-31 | No |  | Generating station, including REGS, without ESS | Granted | 220 |  | EL-EAECB, EL-F66C7, EL-70C46, EL-8D787, EL-B96FE, EL-A1D4E, EL-11BA3, EL-6DFEE, EL-4B103, EL-0A96D |  | EL-BD5C2, EL-5264E
| 139 | NR | Rajasthan | Fatehgarh-II |  | Tata Power Renewable Energy Limited |  | 2200001722 |  |  | 38 |  | 2025-05-28 |  | Solar | 300 | 0 | 300 | [11 empty] | 2025-01-31 | Land BG Route | 2027-03-31 |  |  |  | Generating station, including REGS, without ESS | Withdrawn
| 140 | NR | Rajasthan | Ramgarh-II |  | Waaree Forever Energies Private Limited |  | 2200001735 |  |  | 38 |  | 2025-05-28 |  | Hybrid | 600 | 600 | 300 | 300 | [10 empty] | 2025-02-04 | Land BG Route | 2030-07-31 | 2030-10-31 | No |  | Generating station, including REGS, without ESS | Granted | 400 |  | EL-3DDDE, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-4B103, EL-C8D83 |  | EL-89B68, EL-177EE
| 141 | NR | Rajasthan | Bhadla-III |  | Solarcraft Power India 4 Private Limited |  | 2200001749 |  |  | 38 |  | 2025-05-28 |  | Solar | 50 | 50 | 50 | [11 empty] | 2025-02-10 | Land Route | 2028-09-01 | 2029-07-20 | No |  | Generating station, including REGS, without ESS | Granted | 220 |  | EL-4D705 |  | EL-17567
| 142 | NR | Rajasthan | Sanchore-I |  | Green Infra Renewable Energy Farms Private Limited |  | 2200001762 |  |  | 38 |  | 2025-05-28 |  | Solar | 300 | 300 | 300 | [11 empty] | 2025-02-13 | Land BG Route | 2028-12-15 |  |  |  | Generating station, including REGS, without ESS | Granted | 220
| 143 | NR | Rajasthan | Ramgarh-III |  | BN Peak Power-3 Private Limited |  | 2200001769 |  |  | 38 |  | 2025-05-28 |  | Hybrid+BESS | 350 | 350 | 150 | 200 |  |  |  | 100 | [6 empty] | 2025-02-14 | Land BG Route | 2028-06-30 | 2031-12-31 | No |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-351F9, EL-D397F, EL-3F657, EL-38782, EL-30734, EL-A1D4E, EL-6EB09, EL-4B103, EL-EAAE1 |  | EL-0CB10, EL-31BA6
| 144 | NR | Rajasthan | Sanchore-I |  | Green Infra Renewable Energy Farms Private Limited |  | 2200001771 |  |  | 38 |  | 2025-05-28 |  | Solar | 300 |  | 300 | [11 empty] | 2025-02-14 | Land BG Route | 2028-12-15 |  |  |  | Generating station, including REGS, without ESS | Applied
| 145 | NR | Rajasthan | Bhadla-V |  | ReNew Solar Power Private Limited |  | 2200001781 |  |  | 38 |  | 2025-05-28 |  | Solar+BESS | 200 | 200 | 200 |  |  |  |  | 70 | [6 empty] | 2025-02-18 | LOA or PPA | 2027-03-31 | 2031-09-30 | No |  | Generating station, including REGS, with ESS | Granted | 400 |  | EL-D6782, EL-A9814, EL-3CFCF, EL-911E3, EL-2B272, EL-75882, EL-6DFEE, EL-65D44, EL-B4A45 |  | EL-C3549, EL-A658A
| 146 | NR | Rajasthan | Bikaner-V |  | Adyant Enersol Private Limited |  | 2200001786 |  |  | 38 |  | 2025-05-28 |  | Solar | 150 | 150 | 150 | [11 empty] | 2025-02-20 | LOA or PPA | 2027-04-30 | 2030-10-31 | No |  | Generating station, including REGS, without ESS | Granted | 220 |  | EL-D9A07, EL-85255, EL-26318, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-905E4, EL-35672 |  | EL-F0D41, EL-18947, EL-85CFA
| 147 | NR | Rajasthan | Bikaner-VI |  | ACME Taurus Urja Private Limited |  | 2200001797 |  |  | 38 |  | 2025-05-28 |  | Solar | 300 |  | 300 | [11 empty] | 2025-02-27 | Land Route | 2027-03-31 |  |  |  | Generating station, including REGS, without ESS | Applied
| 148 | NR | Rajasthan | Bikaner-VI |  | Apraava Energy Private Limited |  | 2200001798 |  |  | 38 |  | 2025-05-28 |  | Solar | 600 |  | 600 | [11 empty] | 2025-02-28 | Land BG Route | 2028-12-31 |  |  |  | Generating station, including REGS, without ESS | Applied
| 149 | NR | Rajasthan | Ramgarh-III |  | Mahanadi Renewable Energy Private Limited |  | 2200001807 |  |  | 38 |  | 2025-05-28 |  | Solar+BESS | 280 | 280 | 280 |  |  |  |  | 280 | [6 empty] | 2025-03-01 | Land BG Route | 2030-06-30 | 2031-12-31 | No |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-351F9, EL-D397F, EL-3F657, EL-38782, EL-30734, EL-A1D4E, EL-6EB09, EL-4B103, EL-EAAE1 |  | EL-C5410, EL-31BA6
| 150 | NR | Rajasthan | Sanchore-I |  | Godavari Green Energy Private Limited |  | 2200001810 |  |  | 38 |  | 2025-05-28 |  | Solar+BESS | 250 | 250 | 250 |  |  |  |  | 250 | [6 empty] | 2025-03-03 | Land BG Route | 2030-06-30 | 2031-06-30 | No |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-A5BEB, EL-48EFF, EL-7E7E2, EL-05218, EL-73A05, EL-A1D4E, EL-0FE43, EL-4B103, EL-F7B5C |  | EL-13290, EL-079D8
| 151 | NR | Rajasthan | Bhadla-V |  | Vismaya Four Renewables Private Limited |  | 2200001827 |  |  | 38 |  | 2025-05-28 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 60 | [6 empty] | 2025-03-07 | Land BG Route | 2031-10-01 | 2031-10-01 | No |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-D6782, EL-A9814, EL-3CFCF, EL-911E3, EL-2B272, EL-75882, EL-6DFEE, EL-65D44, EL-B4A45 |  | EL-9915B, EL-C5523
| 152 | NR | Rajasthan | Jalore-I |  | Sabarmati Green Energy Private Limited |  | 2200001862 |  |  | 38 |  | 2025-05-28 |  | Solar+BESS | 250 | 250 | 250 |  |  |  |  | 250 | [6 empty] | 2025-03-20 | Land BG Route | 2030-09-30 | 2031-06-30 | No |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-A5BEB, EL-48EFF, EL-7E7E2, EL-35A84, EL-90D75, EL-73A05, EL-A1D4E, EL-0FE43, EL-4B103, EL-77D24 |  | EL-0D2E2, EL-4C759
| 153 | NR | Rajasthan | Bhadla-V |  | Renew Solar Power Private Limited |  | 2200001864 |  |  | 38 |  | 2025-05-28 |  | Solar | 300 | 300 | 300 | [11 empty] | 2025-03-20 | LOA or PPA | 2027-04-30 | 2031-09-30 | No |  | Generating station, including REGS, without ESS | Granted | 400 |  | EL-D6782, EL-A9814, EL-3CFCF, EL-911E3, EL-2B272, EL-75882, EL-6DFEE, EL-65D44, EL-B4A45 |  | EL-C3549, EL-A658A
| 154 | NR | Rajasthan | Pali-I |  | Renew Solar Power Private Limited |  | 2200001866 |  |  | 38 |  | 2025-05-28 |  | Solar | 300 | 300 | 300 | [11 empty] | 2025-03-20 | LOA or PPA | 2027-04-30 | 2031-06-30 | No |  | Generating station, including REGS, without ESS | Granted | 220 |  | EL-AEB5A, EL-43445, EL-0C9F0, EL-C89B9, EL-DC354, EL-A1D4E, EL-DB837, EL-4B103, EL-00011 |  | EL-20781, EL-60909
| 155 | NR | Rajasthan | Bhadla-V |  | Renew Solar Power Private Limited |  | 2200001865 |  |  | 38 |  | 2025-05-28 |  | Solar | 300 | 300 | 300 | [11 empty] | 2025-03-20 | LOA or PPA | 2027-04-30 | 2031-09-30 | No |  | Generating station, including REGS, without ESS | Granted | 400 |  | EL-D6782, EL-A9814, EL-3CFCF, EL-911E3, EL-2B272, EL-75882, EL-6DFEE, EL-65D44, EL-B4A45 |  | EL-C3549, EL-A658A
| 156 | NR | Rajasthan | Bikaner-VI |  | Waaree Forever Energies Private Limited |  | 2200001900 |  |  | 38 |  | 2025-05-28 |  | Solar+BESS | 250 | 250 | 250 |  |  |  |  | 125 | [6 empty] | 2025-03-31 | Land BG Route | 2031-07-31 |  |  |  | Generating station, including REGS, with ESS | Granted
| 157 | NR | Rajasthan | Sanchore-I |  | Waaree Forever Energies Private Limited |  | 2200001901 |  |  | 38 |  | 2025-05-28 |  | Solar+BESS | 300 | 300 | 300 |  |  |  |  | 150 | [6 empty] | 2025-03-31 | Land BG Route | 2031-10-31 | 2031-10-31 | No |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-A5BEB, EL-48EFF, EL-7E7E2, EL-05218, EL-73A05, EL-A1D4E, EL-0FE43, EL-4B103, EL-F7B5C |  | EL-6B418, EL-079D8
| 158 | NR | Rajasthan | Pali-I |  | Waaree Forever Energies Private Limited |  | 2200001903 |  |  | 38 |  | 2025-05-28 |  | Solar+BESS | 300 |  | 300 |  |  |  |  | 150 | [6 empty] | 2025-03-31 | Land BG Route | 2032-03-31 |  |  |  | Generating station, including REGS, with ESS | Applied
| 159 | NR | Rajasthan | Pali-I |  | Waaree Forever Energies Private Limited |  | 2200001904 |  |  | 38 |  | 2025-05-28 |  | Solar+BESS | 300 |  | 300 |  |  |  |  | 150 | [6 empty] | 2025-03-31 | Land BG Route | 2032-09-30 |  |  |  | Generating station, including REGS, with ESS | Applied
| 160 | NR | Rajasthan | Barmer-IV |  | Adani Renewable Energy Holding Twelve Limited |  | 2200001907 |  |  | 38 |  | 2025-05-28 |  | Solar | 520 | 520 | 520 | [11 empty] | 2025-03-31 | LOA or PPA | 2026-12-31 | 2031-12-31 | No |  | Generating station, including REGS, without ESS | Granted | 400 |  | EL-F5025, EL-C2F66, EL-B1EED, EL-099D8, EL-30D5A, EL-2B272, EL-1D2C6, EL-6DFEE, EL-4B103, EL-7448F |  | EL-00F7B, EL-9C614
| 161 | NR | Rajasthan | Barmer-IV |  | Adani Renewable Energy Holding Twelve Limited |  | 2200001908 |  |  | 38 |  | 2025-05-28 |  | Solar | 303 | 303 | 303.33 | [11 empty] | 2025-03-31 | LOA or PPA | 2026-12-31 | 2031-12-31 | No |  | Generating station, including REGS, without ESS through a lead generator | Granted | 400 |  | EL-F5025, EL-C2F66, EL-B1EED, EL-099D8, EL-30D5A, EL-2B272, EL-1D2C6, EL-6DFEE, EL-4B103, EL-7448F |  | EL-00F7B, EL-9C614
| 162 | NR | Haryana | Bhiwani (Bbmb) |  | BBMB |  | 2200001987 |  |  | 38 |  | 2025-05-28 |  | Solar | 10 | 10 | 10 | [11 empty] | 2025-04-29 | Land Route | 2025-06-30 |  |  |  | Generating station, including REGS, without ESS | Granted | 132
| 163 | NR | Haryana | Hissar (Bbmb) |  | BBMB |  | 2200001993 |  |  | 38 |  | 2025-05-28 |  | Solar | 1.5 | 1.5 | 1.5 | [11 empty] | 2025-04-29 | Land Route | 2025-06-30 |  |  |  | Generating station, including REGS, without ESS | Granted | 33 |  | EL-04AC2, EL-EBDC5, EL-0C837, EL-4EBF7, EL-533DB, EL-BE348, EL-ACF06, EL-CA2EA, EL-EA57A, EL-CB5A3, EL-58072
| 164 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003827 | 412100009 | 2200001677 | 38 |  | 2025-05-28 |  | Hybrid | 150 | 150 | 50 | 50 | 127.5 |  |  | 27.5 | [6 empty] | 2025-01-21 |  |  | 2026-04-30 | No | 2026-04-30 | Generator (Hybrid) | Granted | 220
| 165 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003910 | 412100009 | 2200001677 | [26 empty] | Granted | 220
| 166 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003958 | 412100009 | 2200001677 | [26 empty] | Granted | 220
| 167 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 312100010 | 412100009 | 2200001677 | [26 empty] | Granted | 220
| 168 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 312100012 | 412100009 | 2200001677 | [26 empty] | Granted | 220
| 169 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003827 | 412100010 | 2200001678 | 38 |  | 2025-05-28 |  | Hybrid | 150 | 150 | 50 | 20 |  |  |  | 27.5 | [6 empty] | 2025-01-21 |  |  | 2026-04-30 | No | 2026-04-30 | Generator (Hybrid) | Granted | 220
| 170 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003910 | 412100010 | 2200001678 | [26 empty] | Granted | 220
| 171 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003958 | 412100010 | 2200001678 | [26 empty] | Granted | 220
| 172 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 312100010 | 412100010 | 2200001678 | [26 empty] | Granted | 220
| 173 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 312100012 | 412100010 | 2200001678 | [26 empty] | Granted | 220
| 174 | NR | Rajasthan | Fatehgarh-III |  | ABREL (RJ) Projects Limited |  | 2200000140 |  | 2200001828 | 38 |  | 2025-05-28 |  | Hybrid | 260 | 260 | 260 | 52.7 | [10 empty] | 2025-03-09 |  |  | 2025-05-31 | Yes | 2025-05-31 | Captive generating plant | Granted
| 175 | NR | Rajasthan | Bikaner-II |  | ACME Solar Holdings Limited |  | 1200003683 |  | 2200001843 | 38 |  | 2025-05-28 |  | Solar+BESS | 300 |  | 300 |  |  |  |  | 300 | [6 empty] | 2025-03-13 |  |  |  |  | 2027-03-31 | Generating station(s), including REGS(s), without ESS | Applied | 220
| 176 | NR | Rajasthan | Bikaner-III |  | ACME Cleantech Solutions Private Limited |  | 2200000008 |  | 2200001851 | 38 |  | 2025-05-28 |  | Solar+BESS | 300 |  | 300 |  |  |  |  | 300 | [6 empty] | 2025-03-18 |  |  |  |  | 2027-03-31 | Generating station(s), including REGS(s), without ESS | Withdrawn
| 177 | NR | Rajasthan | Barmer-III |  | Avaada Energy Private Limited |  | 2200001352 |  |  | 37 |  | 2025-03-27 |  | Solar | 750 | 750 | 750 | [11 empty] | 2024-10-14 | NHPC LOA | 2027-03-31 | 2030-09-30 | No |  | Generator | Granted | 400 |  | EL-5F6B8, EL-D0DE2, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-7F1CE
| 178 | NR | Rajasthan | Bhadla-V |  | Sprng Green Energy 4 Private Limited |  | 2200001417 |  |  | 37 |  | 2025-03-27 |  | Solar | 400 | 400 | 400 | [11 empty] | 2024-10-29 | Land BG Route | 2029-06-30 | 2031-06-30 | No |  | Generator | Granted | 220 |  | EL-D6782, EL-2F7DB, EL-A9814, EL-4AEF9, EL-911E3, EL-2B272, EL-75882, EL-6DFEE, EL-65D44 |  | EL-CB8FF
| 179 | NR | Rajasthan | Bhadla-V |  | Azure Power Fifty One Private Limited |  | 2200001420 |  |  | 37 |  | 2025-03-27 |  | Solar | 600 |  | 600 | [11 empty] | 2024-10-30 | Land Route | 2029-12-31 |  |  |  | Generator | Applied
| 180 | NR | Rajasthan | Barmer-III |  | Avaada Energy Private Limited |  | 2200001422 |  |  | 37 |  | 2025-03-27 |  | Solar+BESS | 800 | 800 | [12 empty] | 2024-10-30 | SJVN LOA | 2027-06-30 | 2030-09-30 | No |  | Generator | Granted | 400 |  | EL-5F6B8, EL-D0DE2, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-7F1CE
| 181 | NR | Rajasthan | Barmer-III |  | Pokhran Wind Energy Private Limited |  | 2200001440 |  |  | 37 |  | 2025-03-27 |  | Wind | 99 | 99 |  | 99 | [10 empty] | 2024-11-04 | Land BG Route | 2027-01-31 | 2030-09-30 | No |  | Generator | Granted | 220 |  | EL-5F6B8, EL-D0DE2, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-0D343, EL-4A753
| 182 | NR | Rajasthan | Bikaner-I |  | Hexa Climate Solutions Private Limited |  | 2200001441 |  |  | 37 |  | 2025-03-27 |  | Solar | 50 | 0 | 50 | [11 empty] | 2024-11-06 | Land BG Route | 2026-03-31 | 2027-03-31 |  |  | Generator | Withdrawn
| 183 | NR | Rajasthan | Barmer-III |  | Aditya Birla Renewables Limited |  | 2200001446 |  |  | 37 |  | 2025-03-27 |  | Hybrid | 50 | 50 | 25 | 25 | [10 empty] | 2024-11-07 | Land BG Route | 2027-06-15 | 2030-09-30 | No |  | Generator | Granted | 220 |  | EL-5F6B8, EL-D0DE2, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-0D343, EL-4A753
| 184 | NR | Rajasthan | Barmer-III |  | TEQ Green Power XIII Private Limited |  | 2200001449 |  |  | 37 |  | 2025-03-27 |  | Solar | 50 | 0 | 50 | [11 empty] | 2024-11-09 | REMCL LOA | 2026-11-30 |  |  |  | Generator | Withdrawn
| 185 | NR | Rajasthan | Bays At Bhadla-V |  | Avaada Energy Private Limited |  | 2200001464 |  |  | 37 |  | 2025-03-27 |  | Solar | 1000 | 1000 | 1000 | [11 empty] | 2024-11-12 | NHPC LOA | 2027-06-30 | 2031-06-30 | No |  | Generator | Granted | 400 |  | EL-D6782, EL-2F7DB, EL-A9814, EL-4AEF9, EL-911E3, EL-2B272, EL-75882, EL-6DFEE, EL-65D44 |  | EL-B2D1F
| 186 | NR | Rajasthan | Barmer-III |  | Renew Solar Power Private Limited |  | 2200001503 |  |  | 37 |  | 2025-03-27 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-11-22 | NTPC LOA | 2027-01-31 | 2030-09-30 | No |  | Generator | Granted | 400 |  | EL-5F6B8, EL-D0DE2, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-9C16A
| 187 | NR | Rajasthan | Ramgarh-II |  | Tata Power Renewable Energy Limited |  | 2200001523 |  |  | 37 |  | 2025-03-27 |  | Wind | 300 | 300 |  | 300 | [10 empty] | 2024-11-28 | Land BG Route | 2027-03-31 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-3DDDE, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-141F6, EL-A6B97 |  | EL-95044
| 188 | NR | Rajasthan | Barmer-III |  | Apraava Energy Private Limited |  | 2200001557 |  |  | 37 |  | 2025-03-27 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-12-10 | Land BG Route | 2027-12-31 | 2030-09-30 | No |  | Generator | Granted | 220 |  | EL-5F6B8, EL-D0DE2, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-0F451
| 189 | NR | Rajasthan | Barmer-III |  | Unique Hytech Renewable Energy Private Limited |  | 2200001622 |  |  | 37 |  | 2025-03-27 |  | Hybrid | 1000 | 1000 | 400 | 600 | [10 empty] | 2024-12-28 | Land BG Route | 2030-07-31 | 2030-09-30 | No |  | Generator | Granted | 400 |  | EL-5F6B8, EL-D0DE2, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-14522
| 190 | NR | Rajasthan | Barmer-III |  | TEQ Green Power IX Private Limited |  | 2200001300 |  |  | 36 |  | 2025-01-15 |  | Solar | 208.5 | 208.5 | 208.5 | [11 empty] | 2024-09-30 | LoA or PPA | 2027-06-15 | 2030-09-30 | No |  | Generator | Granted | 220 |  | EL-5F6B8, EL-B5AA8, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-A5E2F, EL-06A29
| 191 | NR | Rajasthan | Bikaner-V |  | Avaada Rjbikaner Private Limited |  | 2200001326 |  |  | 36 |  | 2025-01-15 |  | Solar | 940 | 354 | 354 | [11 empty] | 2024-10-03 | Land Route | 2026-12-31 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-D9A07, EL-E354F, EL-85255, EL-26318, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-E5FDE |  | EL-1F425
| 192 | NR | Rajasthan | Bhadla-IV |  | Avaada Rjsustainable Private Limited |  | 2200001316 |  |  | 36 |  | 2025-01-15 |  | Solar | 660 | 660 | 660 | [11 empty] | 2024-10-04 | Land Route | 2026-12-31 | 2030-03-31 | No |  | Generator | Granted | 400 |  | EL-5A0ED, EL-9267B, EL-26318, EL-CE849, EL-2B272, EL-A4C5F, EL-6DFEE, EL-65D44 |  | EL-16884
| 193 | NR | Rajasthan | Bikaner-V |  | Avaada Energy Private Limited |  | 2200001353 |  |  | 36 |  | 2025-01-15 |  | Solar | 350 | 350 | 350 | [11 empty] | 2024-10-14 | NHPC LOA | 2027-03-31 | 2030-03-31 | No |  | Generator | Granted | 400 |  | EL-D9A07, EL-E354F, EL-85255, EL-26318, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-E5FDE |  | EL-2B49F
| 194 | NR | Rajasthan | Barmer-II |  | Avaada Energy Private Limited |  | 2200001352 |  |  | 36 |  | 2025-01-15 |  | Solar | 750 |  | 750 | [11 empty] | 2024-10-14 | NHPC LOA | 2027-03-31 |  |  |  | Generator | Applied
| 195 | NR | Rajasthan | Barmer-III |  | Acme Gamma Urja Private Limited |  | 2200001366 |  |  | 36 |  | 2025-01-15 |  | Solar | 350 | 350 | 350 | [11 empty] | 2024-10-18 | Land Route | 2026-12-31 | 2030-09-30 | No |  | Generator | Granted | 220 |  | EL-5F6B8, EL-B5AA8, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-A6DAA
| 196 | NR | Rajasthan | Ramgarh-II |  | Junachay Wind Energy Private Limited |  | 2200001382 |  |  | 36 |  | 2025-01-15 |  | Wind | 100 | 100 |  | 100 | [10 empty] | 2024-10-22 | Land BG Route | 2027-04-01 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-3DDDE, EL-A6B97, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-141F6 |  | EL-145D8
| 197 | NR | Rajasthan | Ramgarh-II |  | Dharvi Kalan Wind Energy Private Limited |  | 2200001391 |  |  | 36 |  | 2025-01-15 |  | Wind | 100 | 100 |  | 100 | [10 empty] | 2024-10-22 | Land BG Route | 2027-04-01 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-3DDDE, EL-A6B97, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-141F6 |  | EL-3DB34
| 198 | NR | Rajasthan | Ramgarh-II |  | Dangri Wind Energy Private Limited |  | 2200001390 |  |  | 36 |  | 2025-01-15 |  | Wind | 100 | 100 |  | 100 | [10 empty] | 2024-10-22 | Land BG Route | 2027-04-01 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-3DDDE, EL-A6B97, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-141F6 |  | EL-145D8, EL-6A5A4
| 199 | NR | Rajasthan | Barmer-III |  | Rohat Solar Park Private Limited |  | 2200001372 |  |  | 36 |  | 2025-01-15 |  | Solar | 350 | 350 | 350 | [11 empty] | 2024-10-23 | Land Route | 2027-12-31 | 2030-09-30 | No |  | Renewable Power Park developer | Granted | 220 |  | EL-5F6B8, EL-B5AA8, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-1CC5F
| 200 | NR | Rajasthan | Barmer-I |  | Hexa Climate Solutions Private Limited |  | 2200001396 |  |  | 36 |  | 2025-01-15 |  | Solar+BESS | 50 | 50 | [12 empty] | 2024-10-24 | Land BG Route | 2026-10-31 | 2027-03-31 | No |  | Generating station, including REGS, with ESS | Granted | 220 |  | EL-AB6F6, EL-04FBF, EL-E0593, EL-C16AF, EL-9DE74, EL-26050, EL-4777E, EL-0D0CA, EL-7AF76, EL-DA901, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-50132, EL-06311, EL-D0E44, EL-553D7, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-F20FC, EL-6F66E, EL-B6BDF, EL-C7A50 |  | EL-6F9F6, EL-9EA33
| 201 | NR | Rajasthan | Barmer-III |  | Enren-IV Energy Private Limited |  | 2200001398 |  |  | 36 |  | 2025-01-15 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-10-24 | Land BG Route | 2027-08-30 | 2030-09-30 | No |  | Generator | Granted | 220 |  | EL-5F6B8, EL-B5AA8, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-BF27C
| 202 | NR | Rajasthan | Bhadla-IV |  | Aright Foods And Energy Private Limited |  | 2200001404 |  |  | 36 |  | 2025-01-15 |  | Solar | 2000 | 2000 | 2000 | [11 empty] | 2024-10-25 | Land Route | 2027-09-30 | 2030-03-31 | No |  | Renewable Power Park developer | Granted | 400 |  | EL-5A0ED, EL-9267B, EL-26318, EL-CE849, EL-2B272, EL-A4C5F, EL-6DFEE, EL-65D44 |  | EL-E4838
| 203 | NR | Rajasthan | Barmer-III |  | Unique Hytech Renewable Energy Private Limited |  | 2200001407 |  |  | 36 |  | 2025-01-15 |  | Wind | 150 | 150 |  | 150 | [10 empty] | 2024-10-26 | Land Route | 2029-10-31 | 2030-09-30 | No |  | Generator | Granted | 220 |  | EL-5F6B8, EL-B5AA8, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-A5E2F, EL-06A29
| 204 | NR | Rajasthan | Bhadla-IV |  | Sprng Green Energy 4 Private Limited |  | 2200001417 |  |  | 36 |  | 2025-01-15 |  | Solar | 400 |  | 400 | [11 empty] | 2024-10-29 | Land BG Route | 2029-06-30 |  |  |  | Generator | Applied
| 205 | NR | Rajasthan | Bhadla-IV |  | Azure Power Fifty One Private Limited |  | 2200001420 |  |  | 36 |  | 2025-01-15 |  | Solar | 600 |  | 600 | [11 empty] | 2024-10-30 | Land Route | 2029-12-31 |  |  |  | Generator | Applied
| 206 | NR | Rajasthan | Barmer-II |  | Avaada Energy Private Limited |  | 2200001422 |  |  | 36 |  | 2025-01-15 |  | Solar+BESS | 800 | [13 empty] | 2024-10-30 | SJVN LOA | 2027-06-30 |  |  |  | Generating station, including REGS, with ESS | Applied
| 207 | NR | Rajasthan | Fatehgarh-I |  | Acme Solar Holdings Limited |  | 1200001602 |  | 2200001376 | 36 |  | 2025-01-15 |  | BESS | 300 | 300 |  |  |  |  | 1200 | 300 | [6 empty] | 2024-10-18 |  |  | 2027-06-25 | No | 2026-12-31 | Standalone ESS | Granted | 400
| 208 | NR | Rajasthan | Fatehgarh-I |  | Acme Solar Holdings Limited |  | 1200001603 |  | 2200001377 | 36 |  | 2025-01-15 |  | BESS | 300 | 300 |  |  |  |  | 1200 | 300 | [6 empty] | 2024-10-18 |  |  | 2027-06-25 | No | 2026-12-31 | Standalone ESS | Granted | 400
| 209 | NR | Rajasthan | Fatehgarh-I |  | Acme Solar Holdings Limited |  | 1200001643 |  | 2200001378 | 36 |  | 2025-01-15 |  | BESS | 300 | 300 |  |  |  |  | 1200 | 300 | [6 empty] | 2024-10-18 |  |  | 2027-06-25 | No | 2026-12-31 | Standalone ESS | Granted | 400
| 210 | NR | Rajasthan | Fatehgarh-I |  | Acme Solar Holdings Limited |  | 1200001642 |  | 2200001379 | 36 |  | 2025-01-15 |  | BESS | 300 | 300 |  |  |  |  | 1200 | 300 | [6 empty] | 2024-10-18 |  |  | 2027-06-25 | No | 2026-12-31 | Standalone ESS | Granted | 400
| 211 | NR | Rajasthan | Bhadla-II |  | Acme Heergarh Powertech Pvt. Limited |  | 1200002471 |  | 2200001385 | 36 |  | 2025-01-15 |  | Solar+BESS | 300 |  | 300 |  |  |  | 1200 | 300 | [6 empty] | 2024-10-21 |  |  | 2027-06-25 |  | 2026-06-30 | Standalone ESS | Applied | 220
| 212 | NR | Rajasthan | Barmer-II |  | Vismaya Five Renewables Private Limited |  | 2200000954 |  |  | 35 |  | 2024-10-29 |  | Solar | 250 | 250 | 250 | [11 empty] | 2024-06-21 | Land BG Route | 2030-12-31 | 2030-12-31 | No |  | Generator | Granted | 220 |  | EL-14747, EL-AD084, EL-98E67, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-BFED7
| 213 | NR | Rajasthan | Barmer-II |  | NTPC Renewable Energy Limited |  | 2200000973 |  |  | 35 |  | 2024-10-29 |  | Solar | 100 | 100 | 100 | [11 empty] | 2024-06-24 | Land Route | 2027-03-31 | 2029-12-31 | No |  | Generator | Granted | 400 |  | EL-14747, EL-AD084, EL-98E67, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-D9D1E
| 214 | NR | Uttar Pradesh | Robertsganj-I |  | Avaada Waterbattery Private Limited |  | 2200001086 |  |  | 35 |  | 2024-10-29 |  | PSP | 596 | 596 | [8 empty] | 520 | 596 |  |  | 2024-08-05 | - | 2029-06-30 |  |  |  | Pumped Storage | Granted | 400 |  | EL-CF972, EL-EF788, EL-59C19, EL-7C9B8, EL-A9AB8, EL-F97E5, EL-23874, EL-FE4F8, EL-F339F, EL-ED63C, EL-36B72, EL-6B87E, EL-1989E, EL-73496, EL-AAE2C, EL-DEDF4, EL-16C00, EL-D7DF8, EL-CA7A7, EL-A8719, EL-4816A, EL-37BE5 |  | EL-82D7A
| 215 | NR | Rajasthan | Bikaner-V |  | NTPC Renewable Energy Limited |  | 2200001126 |  |  | 35 |  | 2024-10-29 |  | Solar | 600 | 600 | 600 | [11 empty] | 2024-08-07 | Land Route | 2026-12-30 | 2030-03-31 | No |  | Generator | Granted | 400 |  | EL-D9A07, EL-85255, EL-26318, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-905E4, EL-207DF |  | EL-DA776
| 216 | NR | Rajasthan | Barmer-II |  | Aditya Birla Renewables Limited |  | 2200001128 |  |  | 35 |  | 2024-10-29 |  | Hybrid | 100 | 100 |  |  | 100 | [9 empty] | 2024-08-08 | Land BG Route | 2026-06-15 | 2029-12-31 | No |  | Generator | Granted | 220 |  | EL-14747, EL-AD084, EL-98E67, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-DF178, EL-4A753
| 217 | NR | Rajasthan | Merta-III |  | Aditya Birla Renewables Limited |  | 2200001134 |  |  | 35 |  | 2024-10-29 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-08-08 | Land BG Route | 2027-06-15 | 2031-03-31 | No |  | Generator | Granted | 220 |  | EL-72571, EL-F1D12, EL-0C9F0, EL-5EA00, EL-C89B9, EL-DC354, EL-A1D4E, EL-DB837, EL-141F6 |  | EL-F31CC
| 218 | NR | Rajasthan | Barmer-III |  | TEQ Green Power XIII Private Limited |  | 2200001136 |  |  | 35 |  | 2024-10-29 |  | Solar | 120 | 0 | 120 | [11 empty] | 2024-08-09 | REMCL LOA | 2027-03-15 |  |  |  | Generator | Withdrawn
| 219 | NR | Rajasthan | Barmer-III |  | Green Infra Renewable Energy Farms Private Limited |  | 2200001141 |  |  | 35 |  | 2024-10-29 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-08-09 | Land BG Route | 2028-12-15 | 2030-12-31 | No |  | Generator | Granted | 220 |  | EL-226AA, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-C6A87
| 220 | NR | Rajasthan | Barmer-III |  | Green Infra Renewable Energy Farms Private Limited |  | 2200001194 |  |  | 35 |  | 2024-10-29 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-08-30 | Land BG Route | 2028-12-15 | 2030-12-31 | No |  | Generator | Granted | 220 |  | EL-226AA, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-C6A87
| 221 | NR | Rajasthan | Barmer-III |  | Renew Solar Power Private Limited |  | 2200001188 |  |  | 35 |  | 2024-10-29 |  | Solar | 250 | 250 | 250 | [11 empty] | 2024-08-30 | NHPC LOA | 2026-09-30 | 2030-12-31 | No |  | Generator | Granted | 220 |  | EL-226AA, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-4428E
| 222 | NR | Rajasthan | Ramgarh-II |  | SHN Green Power Private Limited |  | 2200001198 |  |  | 35 |  | 2024-10-29 |  | Wind | 297 | 297 |  | 297 | [10 empty] | 2024-09-03 | Land BG Route | 2029-09-01 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-3DDDE, EL-A6B97, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-141F6 |  | EL-D2CF8
| 223 | NR | Rajasthan | Bikaner-V |  | Juniper Green Energy Private Limited |  | 2200001210 |  |  | 35 |  | 2024-10-29 |  | Solar | 130 | 130 | 130 | [11 empty] | 2024-09-09 | LOA NTPC | 2026-09-30 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-D9A07, EL-85255, EL-26318, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-905E4, EL-207DF |  | EL-BC130
| 224 | NR | Rajasthan | Barmer-III |  | Foxtrot Solar Renewables Energy Private Limited |  | 2200001252 |  |  | 35 |  | 2024-10-29 |  | Solar | 74 | 74 | 74 | [11 empty] | 2024-09-18 | Land Route | 2029-12-31 | 2030-12-31 | No |  | Generator | Granted | 220 |  | EL-226AA, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-BC07B
| 225 | NR | Rajasthan | Bikaner-V |  | Purvah Green Power Private Limited |  | 2200001261 |  |  | 35 |  | 2024-10-29 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-09-21 | Land BG Route | 2029-03-31 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-D9A07, EL-85255, EL-26318, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-905E4, EL-207DF |  | EL-ED8D0
| 226 | NR | Rajasthan | Bikaner-V |  | Purvah Green Power Private Limited |  | 2200001262 |  |  | 35 |  | 2024-10-29 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-09-21 | Land BG Route | 2029-09-01 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-D9A07, EL-85255, EL-26318, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-905E4, EL-207DF |  | EL-ED8D0
| 227 | NR | Rajasthan | Bikaner-V |  | Avaada Suryaenergy Private Limited |  | 2200001254 |  |  | 35 |  | 2024-10-29 |  | Solar | 560 | 560 | 560 | [11 empty] | 2024-09-24 | Land Route | 2026-12-31 | 2030-03-31 | No |  | Generator | Granted | 400 |  | EL-D9A07, EL-85255, EL-26318, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-905E4, EL-207DF |  | EL-24D0D
| 228 | NR | Rajasthan | Bhadla-IV |  | Vismaya Four Renewables Private Limited |  | 2200001284 |  |  | 35 |  | 2024-10-29 |  | Solar | 50 | 50 | 50 | [11 empty] | 2024-09-26 | Land BG Route | 2030-10-01 | 2030-10-01 | No |  | Generator | Granted | 400 |  | EL-5A0ED, EL-9267B, EL-26318, EL-CE849, EL-2B272, EL-A4C5F, EL-6DFEE, EL-65D44 |  | EL-6573E
| 229 | NR | Rajasthan | Barmer-II |  | Vismaya Five Renewables Private Limited |  | 2200001285 |  |  | 35 |  | 2024-10-29 |  | Solar | 50 | 50 | 50 | [11 empty] | 2024-09-26 | Land BG Route | 2030-12-31 | 2030-12-31 | No |  | Generator | Granted | 220 |  | EL-14747, EL-AD084, EL-98E67, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-AA42A
| 230 | NR | Rajasthan | Barmer-III |  | TEQ Green Power IX Private Limited |  | 2200001300 |  |  | 35 |  | 2024-10-29 |  | Solar | 208.5 |  | 208.5 | [11 empty] | 2024-09-30 | LOA or PPA | 2027-06-15 |  |  |  | Generator | Applied
| 231 | NR | Rajasthan | Bikaner-II |  | Soltown Infra Private Limited |  | 1200003889 |  |  | 34 |  | 2024-09-20 |  |  | 200 | 200 | [14 empty] | 2025-12-31 | 2025-12-31 | Yes |  |  | Granted | 220 |  | EL-328D7, EL-B075D, EL-E173B, EL-95D93, EL-C2590, EL-91E7F, EL-E8A1F, EL-2453D, EL-EF0A0, EL-4535D, EL-92EB7, EL-CBFD4 |  | EL-F0027
| 232 | NR | Rajasthan | Bikaner-II |  | Soltown Infra Private Limited |  | 212100007 |  |  | 34 |  | 2024-09-20 |  |  | 350 | 350 | [14 empty] | 2025-10-31 | 2026-08-22 | No |  |  | Granted | 220 |  | EL-328D7, EL-B075D, EL-E173B, EL-95D93, EL-C2590, EL-91E7F, EL-E8A1F, EL-2453D, EL-EF0A0, EL-4535D, EL-92EB7, EL-CBFD4 |  | EL-F0027
| 233 | NR | Rajasthan | Bikaner-II |  | Soltown Infra Private Limited |  | 212100008 |  |  | 34 |  | 2024-09-20 |  |  | 125 | 125 | [14 empty] | 2025-12-31 | 2026-08-22 | No |  |  | Granted | 220 |  | EL-328D7, EL-B075D, EL-E173B, EL-95D93, EL-C2590, EL-91E7F, EL-E8A1F, EL-2453D, EL-EF0A0, EL-4535D, EL-92EB7, EL-CBFD4 |  | EL-F0027
| 234 | NR | Rajasthan | Sirohi-I |  | ACME Solar Holdings Limited (erstwhile ACME Solar Holdings |  | 2200000788 |  |  | 34 |  | 2024-09-20 |  | Solar | 300 | 0 | 300 | [11 empty] | 2024-05-07 | Land BG Route | 2027-03-31 |  |  |  | Generator | Withdrawn
| 235 | NR | Rajasthan | Sirohi-I |  | SAEL Industries Limited |  | 2200000793 |  |  | 34 |  | 2024-09-20 |  | Solar | 300 | 0 | 300 | [11 empty] | 2024-05-10 | Land BG Route | 2026-05-30 |  |  |  | Generator | Withdrawn
| 236 | NR | Rajasthan | Sirohi-I |  | SAEL Industries Limited |  | 2200000794 |  |  | 34 |  | 2024-09-20 |  | Solar | 300 | 0 | 300 | [11 empty] | 2024-05-10 | Land BG Route | 2026-05-30 |  |  |  | Generator | Withdrawn
| 237 | NR | Rajasthan | Sirohi-II |  | Amplus Centaur Solar Private Limited |  | 2200000827 |  |  | 34 |  | 2024-09-20 |  | Solar | 350 | 350 | 350 | [11 empty] | 2024-05-20 | Land BG Route | 2027-04-30 | 2030-09-30 | No |  | Generator | Granted | 220 |  | EL-A6A24, EL-C8E53, EL-A2220, EL-73A05, EL-A1D4E, EL-0FE43, EL-141F6 |  | EL-64346
| 238 | NR | Rajasthan | Merta-II |  | ACME Solar Holdings Limited (erstwhile ACME Solar Holdings Private Limited) |  | 2200000841 |  |  | 34 |  | 2024-09-20 |  | Solar | 100 | 0 | 100 | [11 empty] | 2024-05-31 | Land BG Route | 2027-03-31 |  |  |  | Generator | Withdrawn
| 239 | NR | Rajasthan | Rishabhdeo-I |  | Serentica Renewables India Private Limited |  | 2200000891 |  |  | 34 |  | 2024-09-20 |  | Solar | 400 | 0 | 400 | [11 empty] | 2024-05-31 | Land BG Route | 2026-06-30 |  |  |  | Generator | Withdrawn
| 240 | NR | Rajasthan | Merta-III |  | Enren-III Energy Private Limited |  | 2200000860 |  |  | 34 |  | 2024-09-20 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-05-31 | Land BG Route | 2027-01-31 | 2031-03-31 | No |  | Generator | Granted | 220 |  | EL-72571, EL-F1D12, EL-0C9F0, EL-5EA00, EL-C89B9, EL-DC354, EL-A1D4E, EL-DB837, EL-141F6 |  | EL-41D01
| 241 | NR | Rajasthan | Merta-III |  | Sindhari Solar Power Private Limited |  | 2200000894 |  |  | 34 |  | 2024-09-20 |  | Solar | 300 | 0 | 300 | [11 empty] | 2024-05-31 | Land BG Route | 2027-06-30 |  |  |  | Renewable Power Park developer | Withdrawn
| 242 | NR | Rajasthan | Merta-III |  | Prespa Solar Private Limited |  | 2200000832 |  |  | 34 |  | 2024-09-20 |  | Solar | 250 | 250 | 250 | [11 empty] | 2024-06-04 | Land BG Route | 2026-12-31 | 2031-03-31 | No |  | Renewable Power Park developer | Granted | 220 |  | EL-72571, EL-F1D12, EL-0C9F0, EL-5EA00, EL-C89B9, EL-DC354, EL-A1D4E, EL-DB837, EL-141F6 |  | EL-12429
| 243 | NR | Rajasthan | Bikaner-V |  | Sunsure Solarpark RJ One Private Limited |  | 2200001021 |  |  | 34 |  | 2024-09-20 |  | Solar | 350 | 350 | 350 | [11 empty] | 2024-07-05 | Land BG Route | 2029-03-31 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-D9A07, EL-207DF, EL-85255, EL-26318, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-905E4 |  | EL-15D03
| 244 | NR | Rajasthan | Ramgarh-II |  | Sunbreeze Renewables Seven Private Limited |  | 2200000983 |  |  | 34 |  | 2024-09-20 |  | Solar | 400 | 400 | 400 | [11 empty] | 2024-07-05 | Land Route | 2026-03-31 | 2030-03-31 | No |  | Renewable Power Park developer | Granted | 220 |  | EL-3DDDE, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-141F6, EL-A6B97 |  | EL-E81E2
| 245 | NR | Rajasthan | Bikaner-V |  | Juniper Green Energy Private Limited |  | 2200001056 |  |  | 34 |  | 2024-09-20 |  | Solar | 400 | 400 | 400 | [11 empty] | 2024-07-16 | Land BG Route | 2029-06-30 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-D9A07, EL-207DF, EL-85255, EL-26318, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-905E4 |  | EL-D1B6F
| 246 | NR | Rajasthan | Barmer-III |  | Foxtrot Solar Renewables Energy Private Limited |  | 2200001057 |  |  | 34 |  | 2024-09-20 |  | Solar | 100 | 100 | 100 | [11 empty] | 2024-07-17 | Land Route | 2030-12-31 | 2030-12-31 | No |  | Generator | Granted | 220 |  | EL-226AA, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-C3BC4
| 247 | NR | Rajasthan | Fatehgarh-II |  | ACME Cleantech Solutions Private Limited |  | 2200001065 |  |  | 34 |  | 2024-09-20 |  | Solar | 150 | 150 | 150 | [11 empty] | 2024-07-17 | Land BG Route | 2026-10-31 | 2027-03-31 | No |  | Generator | Granted | 400 |  | EL-ADC60, EL-57AA1, EL-72AA1, EL-39439, EL-3877B, EL-1BF5F, EL-B6BDF, EL-C7A50 |  | EL-7263A
| 248 | NR | Rajasthan | Barmer-III |  | Renew Solar Power Private Limited |  | 2200001026 |  |  | 34 |  | 2024-09-20 |  | Solar | 200 | 200 | 200 | [11 empty] | 2024-07-19 | REMCL LOA | 2026-09-30 | 2030-09-30 | No |  | Generator | Granted | 220 |  | EL-226AA, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-3AEEC
| 249 | NR | Rajasthan | Bhadla-II |  | Adani Renewable Energy Holding Eighteen Limited |  | 2200001044 |  |  | 34 |  | 2024-09-20 |  | Solar | 50 | 50 | 50 | [11 empty] | 2024-07-24 | Land Route | 2025-06-15 | 2027-03-31 | No |  | Generator | Granted | 400 |  | EL-46A03, EL-57AA1, EL-72AA1, EL-39439, EL-3877B, EL-1BF5F, EL-B6BDF, EL-C7A50 |  | EL-6B998, EL-B8BAA
| 250 | NR | Rajasthan | Pali-I |  | TEQ Green Power XV Private Limited |  | 2200001089 |  |  | 34 |  | 2024-09-20 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-07-26 | Land BG Route | 2027-06-15 | 2031-03-31 | No |  | Renewable Power Park developer | Granted | 220 |  | EL-75464, EL-43445, EL-0C9F0, EL-C89B9, EL-DC354, EL-A1D4E, EL-DB837, EL-141F6 |  | EL-89EA0
| 251 | NR | Rajasthan | Jalore-I |  | TEQ Green Power XV Private Limited |  | 2200001087 |  |  | 34 |  | 2024-09-20 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-07-26 | Land BG Route | 2027-06-15 | 2030-09-30 | No |  | Renewable Power Park developer | Granted | 220 |  | EL-77D24, EL-A5BEB, EL-C8E53, EL-A2220, EL-35A84, EL-860DB, EL-73A05, EL-A1D4E, EL-0FE43, EL-141F6 |  | EL-E93BC
| 252 | NR | Rajasthan | Barmer-III |  | Foxtrot Solar Renewables Energy Private Limited |  | 2200001088 |  |  | 34 |  | 2024-09-20 |  | Solar | 80 | 80 | 80 | [11 empty] | 2024-07-26 | Land Route | 2031-12-31 | 2031-12-31 | No |  | Generator | Granted | 220 |  | EL-226AA, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-C3BC4
| 253 | NR | Rajasthan | Bhadla-IV |  | Avaada Energy Private Limited |  | 2200001085 |  |  | 34 |  | 2024-09-20 |  | Solar | 700 | 700 | 700 | [11 empty] | 2024-07-26 | NHPC LOA | 2026-04-30 | 2030-03-31 | No |  | Generator | Granted | 400 |  | EL-0ECFA, EL-9267B, EL-26318, EL-CE849, EL-2B272, EL-A4C5F, EL-6DFEE, EL-65D44, EL-7BBDE |  | EL-DBBE6
| 254 | NR | Rajasthan | Pali-I |  | Diyos Three Renewables Private Limited |  | 2200001100 |  |  | 34 |  | 2024-09-20 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-07-31 | Land BG Route | 2031-04-01 | 2031-04-01 | No |  | Renewable Power Park developer | Granted | 220 |  | EL-75464, EL-43445, EL-0C9F0, EL-C89B9, EL-DC354, EL-A1D4E, EL-DB837, EL-141F6 |  | EL-83715
| 255 | NR | Rajasthan | Bhadla-III |  | Renew Solar Power Private Limited |  | 2200000516 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 |  | 300 | [11 empty] | 2024-01-25 | SECI LOA | 2026-09-30 | 2030-03-31 |  |  | Generator | Applied
| 256 | NR | Rajasthan | Bhadla-IV |  | Renew Solar Power Private Limited |  | 2200000521 |  |  | 33 |  | 2024-08-05 |  | Solar | 200 |  | 200 | [11 empty] | 2024-01-25 | SJVN LOA | 2026-05-31 | 2026-09-30 |  |  | Generator with ESS | Applied
| 257 | NR | Rajasthan | Bhadla-IV |  | Renew Solar Power Private Limited |  | 2200000522 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-01-25 | SJVN LOA | 2026-05-31 | 2030-03-31 | No |  | Generator | Granted | 400 |  | EL-5A0ED, EL-9267B, EL-26318, EL-CE849, EL-2B272, EL-A4C5F, EL-6DFEE, EL-65D44, EL-7BBDE |  | EL-62002
| 258 | NR | Rajasthan | Barmer-II |  | NTPC Renewable Energy Limited |  | 2200000567 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-03-01 | Land Route | 2026-03-31 | 2029-12-31 | No |  | Generator | Granted | 400 |  | EL-14747, EL-AD084, EL-98E67, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-BBDA4
| 259 | NR | Rajasthan | Barmer-II |  | Avaada Energy Private Limited |  | 2200000580 |  |  | 33 |  | 2024-08-05 |  | Solar | 200 | 200 | 200 | [11 empty] | 2024-03-02 | NTPC LOA | 2026-03-26 | 2029-12-31 | No |  | Generator | Granted | 220 |  | EL-14747, EL-AD084, EL-98E67, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-CDE18
| 260 | NR | Rajasthan | Bikaner-V |  | Jade Hybren Private Limited |  | 2200000616 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 0 | 300 | [11 empty] | 2024-03-06 | Land BG Route | 2026-06-30 |  |  |  | Generator | Withdrawn
| 261 | NR | Rajasthan | Ramgarh-I |  | Migos Hybren Private Limited |  | 2200000618 |  |  | 33 |  | 2024-08-05 |  | Solar | 600 | 600 | 600 | [11 empty] | 2024-03-06 | Land BG Route | 2026-12-31 | 2028-12-31 | No |  | Generator | Granted | 220 |  | EL-2E45B, EL-065D3, EL-31139, EL-CE816, EL-DD8DD, EL-BE37F, EL-90F2A, EL-B8CEB, EL-C2310, EL-CD00C, EL-547E5, EL-BBD19, EL-69266, EL-95995 |  | EL-844B3
| 262 | NR | Rajasthan | Bhadla-III |  | Kyros Hybren Private Limited |  | 2200000624 |  |  | 33 |  | 2024-08-05 |  | Solar | 100 | 0 | 100 | [11 empty] | 2024-03-07 | Land BG Route | 2025-06-30 |  |  |  | Generator | Withdrawn
| 263 | NR | Rajasthan | Bhadla-IV |  | Aravalli Surya (Project 1) Private Limited |  | 2200000605 |  |  | 33 |  | 2024-08-05 |  | Solar | 335 | 335 | 335 | [11 empty] | 2024-03-07 | Land Route | 2027-12-31 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-5A0ED, EL-9267B, EL-26318, EL-CE849, EL-2B272, EL-A4C5F, EL-6DFEE, EL-65D44, EL-7BBDE |  | EL-5C930
| 264 | NR | Rajasthan | Ramgarh-I |  | Adani Renewable Energy Holding Four Limited |  | 2200000598 |  |  | 33 |  | 2024-08-05 |  | Solar | 500 | 500 | 500 | [11 empty] | 2024-03-13 | Land Route | 2025-06-15 | 2028-12-31 | No |  | Generator | Granted | 400 |  | EL-2E45B, EL-065D3, EL-31139, EL-CE816, EL-DD8DD, EL-BE37F, EL-90F2A, EL-B8CEB, EL-C2310, EL-CD00C, EL-547E5, EL-BBD19, EL-69266, EL-95995 |  | EL-D3904
| 265 | NR | Rajasthan | Ramgarh-I |  | Adani Renewable Energy Holding Four Limited |  | 2200000599 |  |  | 33 |  | 2024-08-05 |  | Solar | 500 | 500 | 500 | [11 empty] | 2024-03-13 | Land Route | 2025-06-15 | 2028-12-31 | No |  | Generator | Granted | 400 |  | EL-2E45B, EL-065D3, EL-31139, EL-CE816, EL-DD8DD, EL-BE37F, EL-90F2A, EL-B8CEB, EL-C2310, EL-CD00C, EL-547E5, EL-BBD19, EL-69266, EL-95995 |  | EL-D3904
| 266 | NR | Rajasthan | Sirohi-I |  | Serentica Renewables India Private Limited |  | 2200000644 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-03-14 | Land BG Route | 2026-06-30 | 2027-03-31 | No |  | Generator | Granted | 220 |  | EL-C16AF, EL-26050, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-544F8, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-B6BDF, EL-C7A50, EL-3CE98 |  | EL-3B6C3
| 267 | NR | Rajasthan | Ramgarh-II |  | Adani Renewable Energy Park Rajasthan Limited |  | 2200000600 |  |  | 33 |  | 2024-08-05 |  | Solar | 1000 | 1000 | 1000 | [11 empty] | 2024-03-14 | Land Route | 2025-06-15 | 2030-03-31 | No |  | Renewable Power Park developer | Granted | 400 |  | EL-3DDDE, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-141F6, EL-A6B97 |  | EL-9ADBC
| 268 | NR | Rajasthan | Ramgarh-II |  | Adani Renewable Energy Park Rajasthan Limited |  | 2200000601 |  |  | 33 |  | 2024-08-05 |  | Solar | 1000 | 1000 | 1000 | [11 empty] | 2024-03-14 | Land Route | 2025-06-15 | 2030-03-31 | No |  | Renewable Power Park developer | Granted | 400 |  | EL-3DDDE, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-141F6, EL-A6B97 |  | EL-B5F9A
| 269 | NR | Rajasthan | Sirohi-I |  | Illuminate Hybren Private Limited |  | 2200000646 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-03-15 | Land BG Route | 2026-06-30 | 2027-03-31 | No |  | Generator | Granted | 220 |  | EL-C16AF, EL-26050, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-544F8, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-B6BDF, EL-C7A50, EL-3CE98 |  | EL-7F39F
| 270 | NR | Rajasthan | Barmer-II |  | Avaada Energy Private Limited |  | 2200000636 |  |  | 33 |  | 2024-08-05 |  | Solar | 450 | 450 | 450 | [11 empty] | 2024-03-19 | SJVN LOA | 2026-09-30 | 2029-12-31 | No |  | Generator | Granted | 220 |  | EL-14747, EL-AD084, EL-98E67, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-CDE18
| 271 | NR | Rajasthan | Barmer-II |  | Green Infra Wind Energy Limited |  | 2200000654 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-03-27 | SJVN LOA | 2027-06-30 |  |  |  | Generator | Granted | 220
| 272 | NR | Rajasthan | Ramgarh-I |  | Adani Renewable Energy Holding Four Limited |  | 2200000661 |  |  | 33 |  | 2024-08-05 |  | Solar | 250 | 250 | 250 | [11 empty] | 2024-03-28 | SECI LOA | 2025-10-01 | 2028-12-31 | No |  | Generator | Granted | 400 |  | EL-2E45B, EL-065D3, EL-31139, EL-CE816, EL-DD8DD, EL-BE37F, EL-90F2A, EL-B8CEB, EL-C2310, EL-CD00C, EL-547E5, EL-BBD19, EL-69266, EL-95995 |  | EL-37646
| 273 | NR | Rajasthan | Ramgarh-I |  | Adani Renewable Energy Holding Four Limited |  | 2200000662 |  |  | 33 |  | 2024-08-05 |  | Solar | 284 | 284 | 284 | [11 empty] | 2024-03-28 | SECI LOA | 2026-10-01 | 2030-03-31 | No |  | Generator | Granted | 400 |  | EL-2E45B, EL-065D3, EL-31139, EL-CE816, EL-DD8DD, EL-BE37F, EL-90F2A, EL-B8CEB, EL-C2310, EL-CD00C, EL-547E5, EL-BBD19, EL-69266, EL-95995 |  | EL-3ABED
| 274 | NR | Rajasthan | Barmer-II |  | Juniper Green Energy Private Limited |  | 2200000668 |  |  | 33 |  | 2024-08-05 |  | Hybrid | 180 | 180 |  |  | 180 | [9 empty] | 2024-03-28 | SJVN LOA | 2026-06-30 | 2029-12-31 | No |  | Generator | Granted | 220 |  | EL-14747, EL-AD084, EL-98E67, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-703D7, EL-3FA83
| 275 | NR | Rajasthan | Ramgarh-I |  | Tata Power Renewable Energy Limited |  | 2200000672 |  |  | 33 |  | 2024-08-05 |  | Solar | 600 | 600 | 600 | [11 empty] | 2024-03-29 | Land BG Route | 2028-06-30 | 2030-03-31 | No |  | Generator | Granted | 400 |  | EL-3DDDE, EL-2E45B, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-141F6 |  | EL-F7376
| 276 | NR | Rajasthan | Barmer-II |  | Sprng Urja Private Limited |  | 2200000681 |  |  | 33 |  | 2024-08-05 |  | Solar | 1000 | 1000 | 1000 | [11 empty] | 2024-03-30 | Land BG Route | 2029-06-30 | 2029-12-31 | No |  | Renewable Power Park developer | Granted | 400 |  | EL-14747, EL-AD084, EL-98E67, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-E2AA3
| 277 | NR | Rajasthan | Ramgarh-II |  | JSW Neo Energy Limited |  | 2200000706 |  |  | 33 |  | 2024-08-05 |  | Solar | 700 | 700 | 700 | [11 empty] | 2024-04-12 | SJVN LOA | 2025-09-01 | 2030-03-31 | No |  | Generator | Granted | 400 |  | EL-3DDDE, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-141F6, EL-A6B97 |  | EL-7782E
| 278 | NR | Rajasthan | Ramgarh-II |  | JSW Neo Energy Limited |  | 2200000689 |  |  | 33 |  | 2024-08-05 |  | Solar | 700 | 700 | 700 | [11 empty] | 2024-04-12 | SJVN LOA | 2027-03-01 | 2030-03-31 | No |  | Generator | Granted | 400 |  | EL-3DDDE, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-141F6, EL-A6B97 |  | EL-36700
| 279 | NR | Rajasthan | Barmer-II |  | Amaresha Renawables India Project Private Limited |  | 2200000715 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-04-15 | Land BG Route | 2027-04-01 | 2029-12-31 | No |  | Renewable Power Park Developer | Granted | 220 |  | EL-14747, EL-AD084, EL-98E67, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-E67AA
| 280 | NR | Rajasthan | Bikaner-V |  | NTPC Renewable Energy Limited |  | 2200000726 |  |  | 33 |  | 2024-08-05 |  | Solar | 1000 | 1000 | 1000 | [11 empty] | 2024-04-23 | Land Route | 2026-12-31 | 2030-03-31 | No |  | Generator | Granted | 400 |  | EL-D9A07, EL-85255, EL-26318, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-A331D, EL-207DF |  | EL-8A87E
| 281 | NR | Rajasthan | Ramgarh-II |  | Juniper Green Energy Private Limited |  | 2200000756 |  |  | 33 |  | 2024-08-05 |  | Hybrid | 360 | 360 |  |  | 360 | [9 empty] | 2024-04-25 | NTPC LOA | 2026-06-30 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-3DDDE, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-141F6, EL-A6B97 |  | EL-AA42F
| 282 | NR | Rajasthan | Sirohi-I |  | Vayuna Renewables India Project Private Limited |  | 2200000758 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-04-25 | Land BG | 2027-04-01 | 2027-04-01 | No |  | Renewable Power Park Developer | Granted | 220 |  | EL-C16AF, EL-26050, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-544F8, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-B6BDF, EL-C7A50, EL-3CE98 |  | EL-47D10
| 283 | NR | Rajasthan | Bhadla-IV |  | Kantida Renewables India Project Private Limited |  | 2200000761 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-04-25 | Land BG Route | 2028-04-01 | 2030-03-31 | No |  | Renewable Power Park Developer | Granted | 400 |  | EL-5A0ED, EL-9267B, EL-26318, EL-CE849, EL-2B272, EL-A4C5F, EL-6DFEE, EL-65D44, EL-7BBDE |  | EL-9AF8D
| 284 | NR | Rajasthan | Sirohi-I |  | Izhma Solar Private Limited |  | 2200000743 |  |  | 33 |  | 2024-08-05 |  | Solar | 200 | 200 | 200 | [11 empty] | 2024-04-26 | Land BG Route | 2028-03-31 | 2028-03-31 | No |  | Generator | Granted | 220 |  | EL-C16AF, EL-26050, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-544F8, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-B6BDF, EL-C7A50, EL-3CE98 |  | EL-5A444
| 285 | NR | Rajasthan | Ramgarh-II |  | Renew Solar Power Private Limited |  | 2200000777 |  |  | 33 |  | 2024-08-05 |  | Solar | 400 | 400 | 400 | [11 empty] | 2024-04-30 | NTPC LOA | 2027-06-30 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-3DDDE, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-141F6, EL-A6B97 |  | EL-F8B67
| 286 | NR | Rajasthan | Barmer-II |  | Renew Solar Power Private Limited |  | 2200000778 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-04-30 | SECI LOA | 2026-12-31 | 2029-12-31 | No |  | Generator | Granted | 220 |  | EL-14747, EL-AD084, EL-98E67, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-65D5C
| 287 | NR | Rajasthan | Sirohi-I |  | Renew Solar Power Private Limited |  | 2200000779 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-04-30 | NTPC LOA | 2027-06-30 | 2027-06-30 | No |  | Generator | Granted | 400 |  | EL-C16AF, EL-26050, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-544F8, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-B6BDF, EL-C7A50, EL-3CE98 |  | EL-6423F
| 288 | NR | Rajasthan | Bikaner-V |  | SA Renewable Infra Private Limited |  | 2200000755 |  |  | 33 |  | 2024-08-05 |  | Solar | 100 | 100 | 100 | [11 empty] | 2024-05-04 | Land Route | 2026-03-31 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-D9A07, EL-85255, EL-26318, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-A331D, EL-207DF |  | EL-12C20, EL-13D4F
| 289 | NR | Rajasthan | Bikaner-V |  | Vena Energy Vindhya Wind Power Private Limited |  | 2200000796 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-05-06 | Land BG Route | 2027-10-01 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-D9A07, EL-85255, EL-26318, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-A331D, EL-207DF |  | EL-D2426
| 290 | NR | Rajasthan | Sirohi-I |  | ACME Solar Holdings Private Limited |  | 2200000788 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-07 | Land BG Route | 2027-03-31 |  |  |  | Generator | Applied
| 291 | NR | Rajasthan | Sirohi-I |  | SAEL Industries Limited |  | 2200000793 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-10 | Land BG Route | 2026-05-30 |  |  |  | Generator | Applied
| 292 | NR | Rajasthan | Sirohi-I |  | SAEL Industries Limited |  | 2200000794 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-10 | Land BG Route | 2026-05-30 |  |  |  | Generator | Applied
| 293 | NR | Rajasthan | Bhadla-IV |  | Adani Renewable Energy Holding Four Limited |  | 2200000811 |  |  | 33 |  | 2024-08-05 |  | Solar | 765 | 765 | 765 | [11 empty] | 2024-05-10 | SECI LOA | 2025-03-31 | 2030-03-31 | No |  | Generator | Granted | 400 |  | EL-5A0ED, EL-9267B, EL-26318, EL-CE849, EL-2B272, EL-A4C5F, EL-6DFEE, EL-65D44, EL-7BBDE |  | EL-72545
| 294 | NR | Rajasthan | Barmer-II |  | Adani Renewable Energy Holding Four Limited |  | 2200000810 |  |  | 33 |  | 2024-08-05 |  | Solar | 717 | 717 | 717 | [11 empty] | 2024-05-10 | SECI LOA | 2025-03-31 | 2029-12-31 | No |  | Generator | Granted | 400 |  | EL-14747, EL-AD084, EL-98E67, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-2FEF3
| 295 | NR | Rajasthan | Ramgarh-II |  | RJS Renewables Private Limited |  | 2200000782 |  |  | 33 |  | 2024-08-05 |  | Wind | 150 | 150 |  | 150 | [10 empty] | 2024-05-12 | Land Route | 2028-04-20 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-3DDDE, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-141F6, EL-A6B97 |  | EL-10FC4
| 296 | NR | Rajasthan | Ramgarh-II |  | JSW Neo Energy Limited |  | 2200000797 |  |  | 33 |  | 2024-08-05 |  | Solar | 700 | 700 | 700 | [11 empty] | 2024-05-13 | NTPC LOA | 2027-05-01 | 2030-03-31 | No |  | Generator | Granted | 400 |  | EL-3DDDE, EL-3BFE1, EL-6ACC9, EL-DB586, EL-11BD7, EL-A1D4E, EL-6EB09, EL-141F6, EL-A6B97 |  | EL-36700
| 297 | NR | Rajasthan | Nagaur-I |  | Green Infra Wind Energy Private Limited |  | 2200000812 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-14 | Land BG Route | 2027-05-31 |  |  |  | Generator | Applied
| 298 | NR | Rajasthan | Merta-II |  | Green Infra Wind Energy Private Limited |  | 2200000813 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-05-14 | Land BG Route | 2027-05-31 | 2027-05-31 | No |  | Generator | Granted | 220 |  | EL-50132, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-82F00, EL-6F66E, EL-B6BDF, EL-C7A50 |  | EL-9FD2A
| 299 | NR | Rajasthan | Merta-II |  | Banyan Energy Private Limited |  | 2200000823 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-05-18 | Land BG Route | 2026-06-30 | 2027-03-31 | No |  | Generator | Granted | 220 |  | EL-50132, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-82F00, EL-6F66E, EL-B6BDF, EL-C7A50 |  | EL-E5409
| 300 | NR | Rajasthan | Sirohi-I |  | Amplus Centaur Solar Private Limited |  | 2200000827 |  |  | 33 |  | 2024-08-05 |  | Solar | 350 |  | 350 | [11 empty] | 2024-05-20 | Land BG Route | 2027-04-30 |  |  |  | Generator | Applied
| 301 | NR | Rajasthan | Barmer-II |  | Adani Renewable Energy Two Limited |  | 2200000807 |  |  | 33 |  | 2024-08-05 |  | Wind | 600 | 600 |  | 600 | [10 empty] | 2024-05-21 | Land Route | 2025-03-31 | 2029-12-31 | No |  | Generator (Wind | Granted | 400 |  | EL-E1797
| 302 | NR | Rajasthan | Barmer-II |  | Adani Renewable Energy Two Limited |  | 2200000809 |  |  | 33 |  | 2024-08-05 |  | Wind | 595 | 595 |  | 595 | [10 empty] | 2024-05-21 | Land Route | 2025-03-31 | 2029-12-31 | No |  | Generator | Granted | 400 |  | EL-14747, EL-AD084, EL-98E67, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-2FEF3
| 303 | NR | Rajasthan | Merta-II |  | Acme Solar Holdings Private Limited |  | 2200000840 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-05-25 | Land BG Route | 2027-03-31 | 2027-03-31 | No |  | Generator | Granted | 220 |  | EL-50132, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-82F00, EL-6F66E, EL-B6BDF, EL-C7A50 |  | EL-9D5D3
| 304 | NR | Rajasthan | Merta-II |  | Purvah Green Power Private Limited |  | 2200000842 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-05-25 | Land BG Route | 2027-06-01 | 2027-06-01 | No |  | Generator | Granted | 220 |  | EL-50132, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-82F00, EL-6F66E, EL-B6BDF, EL-C7A50 |  | EL-FE938
| 305 | NR | Rajasthan | Merta-II |  | Hexa Climate Solutions Private Limited |  | 2200000848 |  |  | 33 |  | 2024-08-05 |  | Solar+BESS | 300 | 300 | [12 empty] | 2024-05-25 | Land BG Route | 2027-03-31 | 2027-03-31 | No |  | Generator | Granted | 220 |  | EL-50132, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-82F00, EL-6F66E, EL-B6BDF, EL-C7A50 |  | EL-10327
| 306 | NR | Rajasthan | Jalore-I |  | Renew Solar Power Private Limited |  | 2200000850 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-05-27 | NTPC LOA | 2026-11-30 | 2030-06-30 | No |  | Generator | Granted | 400 |  | EL-A5BEB, EL-48EFF, EL-7E7E2, EL-35A84, EL-90D75, EL-73A05, EL-A1D4E, EL-0FE43, EL-141F6, EL-77D24 |  | EL-8ACC2
| 307 | NR | Rajasthan | Bikaner-I |  | Hexa Climate Solutions Private Limited |  | 2200000854 |  |  | 33 |  | 2024-08-05 |  | Solar+BESS | 50 | 50 | [12 empty] | 2024-05-27 | Land BG Route | 2025-06-30 | 2027-03-31 | No |  | Generator | Granted | 400 |  | EL-B075D, EL-D92F2, EL-C2590, EL-91E7F, EL-E8A1F, EL-95D93, EL-2453D, EL-EF0A0, EL-4535D, EL-92EB7, EL-CBFD4, EL-80EC9, EL-5DAFB, EL-8F19A, EL-B6BDF, EL-C7A50 |  | EL-894BD, EL-BE974, EL-12818
| 308 | NR | Rajasthan | Barmer-II |  | Serentica Renewables India 11 Private Limited |  | 2200000856 |  |  | 33 |  | 2024-08-05 |  | Solar+BESS | 250 | 250 | [12 empty] | 2024-05-28 | NTPC LOA | 2027-12-31 | 2029-12-31 | No |  | Generator | Granted | 220 |  | EL-14747, EL-AD084, EL-98E67, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-F697A
| 309 | NR | Rajasthan | Bikaner-V |  | Solarcraft Power India 8 Private Limited |  | 2200000866 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-05-30 | LOA or PPA | 2026-06-29 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-D9A07, EL-85255, EL-26318, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-A331D, EL-207DF |  | EL-023ED
| 310 | NR | Rajasthan | Bhadla-IV |  | Demeter Sun Power Private Limited |  | 2200000875 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-05-30 | Land Route | 2027-12-31 | 2030-03-31 | No |  | Generator | Granted | 220 |  | EL-5A0ED, EL-9267B, EL-26318, EL-CE849, EL-2B272, EL-A4C5F, EL-6DFEE, EL-65D44, EL-7BBDE |  | EL-A6870
| 311 | NR | Rajasthan | Merta-II |  | Juniper Green Energy Private Limited |  | 2200000879 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-05-30 | Land BG Route | 2027-12-31 | 2027-12-31 | No |  | Generator | Granted | 220 |  | EL-50132, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-82F00, EL-6F66E, EL-B6BDF, EL-C7A50 |  | EL-4BF62
| 312 | NR | Rajasthan | Nagaur (Merta-II) |  | Acme Solar Holdings Private Limited |  | 2200000841 |  |  | 33 |  | 2024-08-05 |  | Solar | 100 |  | 100 | [11 empty] | 2024-05-31 | Land BG Route | 2027-03-31 |  |  |  | Generator | Applied
| 313 | NR | Rajasthan | Rishabhdeo-I |  | Serentica Renewables India Private Limited |  | 2200000891 |  |  | 33 |  | 2024-08-05 |  | Solar | 400 |  | 400 | [11 empty] | 2024-05-31 | Land BG Route | 2026-06-30 |  |  |  | Generator | Applied
| 314 | NR | Rajasthan | Jalore-I |  | Renew Solar Power Private Limited |  | 2200000886 |  |  | 33 |  | 2024-08-05 |  | Solar | 100 |  | 100 | [11 empty] | 2024-05-31 | Land BG Route | 2027-12-31 |  |  |  | Generator | Applied
| 315 | NR | Rajasthan | Jalore-I |  | Renew Solar Power Private Limited |  | 2200000887 |  |  | 33 |  | 2024-08-05 |  | Solar | 200 |  | 200 | [11 empty] | 2024-05-31 | Land BG Route | 2027-07-31 |  |  |  | Generator | Applied
| 316 | NR | Rajasthan | Jalore-I |  | Renew Solar Power Private Limited |  | 2200000888 |  |  | 33 |  | 2024-08-05 |  | Solar | 200 |  | 200 | [11 empty] | 2024-05-31 | Land BG Route | 2027-09-30 |  |  |  | Generator | Applied
| 317 | NR | Rajasthan | Jalore-I |  | Renew Solar Power Private Limited |  | 2200000889 |  |  | 33 |  | 2024-08-05 |  | Solar | 100 |  | 100 | [11 empty] | 2024-05-31 | Land BG Route | 2027-10-31 |  |  |  | Generator | Applied
| 318 | NR | Rajasthan | Jalore-I |  | Renew Solar Power Private Limited |  | 2200000890 |  |  | 33 |  | 2024-08-05 |  | Solar | 100 | 100 | 100 | [11 empty] | 2024-05-31 | Land BG Route | 2027-11-30 | 2030-06-30 | No |  | Generator | Granted | 400 |  | EL-A5BEB, EL-48EFF, EL-7E7E2, EL-35A84, EL-90D75, EL-73A05, EL-A1D4E, EL-0FE43, EL-141F6, EL-77D24 |  | EL-B97CE
| 319 | NR | Rajasthan | Nagaur Complex (Merta-II) |  | Enren-III Energy Private Limited |  | 2200000860 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-31 | Land BG Route | 2027-01-31 |  |  |  | Generator | Applied
| 320 | NR | Rajasthan | Nagaur-I |  | Sindhari Solar Power Private Limited |  | 2200000894 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-31 | Land BG Route | 2027-06-30 |  |  |  | Renewable Power Park developer | Applied
| 321 | NR | Rajasthan | Nagaur Complex (Merta-II) |  | Prespa Solar Private Limited |  | 2200000832 |  |  | 33 |  | 2024-08-05 |  | Solar | 250 |  | 250 | [11 empty] | 2024-06-04 | Land BG Route | 2026-12-31 |  |  |  | Renewable Power Park developer | Applied
| 322 | NR | Rajasthan | Bhadla-IV |  | Vismaya Four Renewables Private Limited |  | 2200000910 |  |  | 33 |  | 2024-08-05 |  | Solar | 250 | 250 | 250 | [11 empty] | 2024-06-06 | Land BG Route | 2030-04-01 | 2030-04-01 | No |  | Generator | Granted | 400 |  | EL-5A0ED, EL-9267B, EL-26318, EL-CE849, EL-2B272, EL-A4C5F, EL-6DFEE, EL-65D44, EL-7BBDE |  | EL-3276C
| 323 | NR | Rajasthan | Jalore-I |  | Sunsure Solarpark RJ One Private Limited |  | 2200000943 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-06-18 | Land BG Route | 2027-12-31 | 2030-06-30 | No |  | Generator | Granted | 220 |  | EL-A5BEB, EL-48EFF, EL-7E7E2, EL-35A84, EL-90D75, EL-73A05, EL-A1D4E, EL-0FE43, EL-141F6, EL-77D24 |  | EL-5B6A8
| 324 | NR | Rajasthan | Barmer-II |  | NTPC Renewable Energy Limited |  | 2200000906 |  |  | 33 |  | 2024-08-05 |  | Solar | 500 | 500 | 500 | [11 empty] | 2024-06-19 | Land Route | 2026-10-30 | 2030-06-30 | No |  | Generator | Granted | 400 |  | EL-14747, EL-AD084, EL-98E67, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-2785C
| 325 | NR | Rajasthan | Jalore-I |  | HR Saraswati Energy Private Limited |  | 2200000945 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 0 | 300 | [11 empty] | 2024-06-20 | Land BG Route | 2027-07-30 |  |  |  | Generator | Withdrawn
| 326 | NR | Rajasthan | Barmer-III |  | Vismaya Five Renewables Private Limited |  | 2200000954 |  |  | 33 |  | 2024-08-05 |  | Solar | 250 | 250 | 250 | [11 empty] | 2024-06-21 | Land BG Route | 2030-10-31 | 2030-10-31 | No |  | Generator | Granted | 220 |  | EL-226AA, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-ED97C
| 327 | NR | Rajasthan | Jalore-I |  | Acme Solar Holdings Private Limited |  | 2200000955 |  |  | 33 |  | 2024-08-05 |  | Solar | 500 | 0 | 500 | [11 empty] | 2024-06-21 | Land BG Route | 2027-03-31 |  |  |  | Generator | Withdrawn
| 328 | NR | Rajasthan | Sanchore-I |  | HR Saraswati Energy Private Limited |  | 2200000946 |  |  | 33 |  | 2024-08-05 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-06-22 | Land BG Route | 2026-06-30 | 2030-06-30 | No |  | Generator | Granted | 220 |  | EL-A5BEB, EL-48EFF, EL-7E7E2, EL-05218, EL-73A05, EL-A1D4E, EL-0FE43, EL-141F6, EL-F7B5C |  | EL-724C2
| 329 | NR | Rajasthan | Barmer-III |  | NTPC Renewable Energy Limited |  | 2200000973 |  |  | 33 |  | 2024-08-05 |  | Solar | 100 | 100 | 100 | [11 empty] | 2024-06-24 | Land Route | 2027-03-31 | 2030-06-30 | No |  | Generator | Granted | 220 |  | EL-226AA, EL-9AAB9, EL-2A125, EL-A1D4E, EL-CFCC2, EL-141F6 |  | EL-D78BE
| 330 | NR | Rajasthan | Jalore-I |  | Sprng Vaayu Urja Private Limited |  | 2200001006 |  |  | 33 |  | 2024-08-05 |  | Solar | 600 | 600 | 600 | [11 empty] | 2024-06-29 | Land BG Route | 2029-12-31 | 2030-06-30 | No |  | Renewable Power Park developer | Granted | 220 |  | EL-A5BEB, EL-48EFF, EL-7E7E2, EL-35A84, EL-90D75, EL-73A05, EL-A1D4E, EL-0FE43, EL-141F6, EL-77D24 |  | EL-B6A41
| 331 | NR | Uttarakhand | Mori-I |  | Sunflag Power Limited |  | 2200000357 |  |  | 31 |  | 2024-06-27 |  | Hydro | 60 |  |  |  |  | 60 | [8 empty] | 2023-11-15 | LOA or PPA | 2028-09-25 |  |  |  | Generating station, including REGS, without ESS | Applied
| 332 | NR | Uttar Pradesh | VIndhyachal Pooling Station-I |  | NTPC Limited |  | 2200000400 |  |  | 31 |  | 2024-06-27 |  | Thermal | 1600 | [13 empty] | 2023-12-11 | - | 2028-03-01 |  |  |  | Generator | Applied
| 333 | NR | Rajasthan | At Shree Cement Generation Plant-I |  | Shree Cement Limited |  | 2200000494 |  |  | 31 |  | 2024-06-27 |  | Thermal | 44 | 44 | [12 empty] | 2024-01-22 | - | 2024-03-31 | 2024-09-30 | Yes |  | Generator | Granted | 400 |  | EL-97075, EL-2BDBE |  | EL-2BDBE
| 334 | NR | Uttar Pradesh | - |  | Greenko UP01 IREP Private Limited |  | 2200000527 |  |  | 31 |  | 2024-06-27 |  | PSP | 672 | 672 | [8 empty] | 610 | 672 |  |  | 2024-01-25 | - | 2027-07-01 | 2027-07-01 | No |  | Pumped Storage | Granted | 400 |  | EL-CF906, EL-73496, EL-EF788, EL-AAE2C, EL-DEDF4, EL-7C9B8, EL-A9AB8, EL-041C4, EL-FE4F8, EL-F339F |  | EL-CF906
| 335 | NR | Uttar Pradesh |  |  | Greenko UP01 IREP Private Limited |  | 2200000529 |  |  | 31 |  | 2024-06-27 |  | PSP | 672 | 672 | [8 empty] | 610 | 672 |  |  | 2024-02-05 | - | 2027-12-16 | 2027-12-16 | No |  | Pumped Storage | Granted | 400 |  | EL-73496, EL-EF788, EL-AAE2C, EL-DEDF4, EL-7C9B8, EL-A9AB8, EL-041C4, EL-FE4F8, EL-3AD7A |  | EL-6CA5E
| 336 | NR | Uttar Pradesh |  |  | Greenko UP01 IREP Private Limited |  | 2200000524 |  |  | 31 |  | 2024-06-27 |  | PSP | 672 | 672 | [8 empty] | 610 | 672 |  |  | 2024-02-05 | - | 2026-11-16 | 2026-11-16 | No |  | Pumped Storage | Granted | 400 |  | EL-73496, EL-EF788, EL-AAE2C, EL-DEDF4, EL-7C9B8, EL-A9AB8, EL-041C4, EL-FE4F8, EL-F339F |  | EL-6CA5E
| 337 | NR | Uttar Pradesh |  |  | Greenko UP01 IREP Private Limited |  | 2200000525 |  |  | 31 |  | 2024-06-27 |  | PSP | 672 | 672 | [8 empty] | 610 | 672 |  |  | 2024-02-05 | - | 2027-02-01 | 2027-02-01 | No |  | Pumped Storage | Granted | 400 |  | EL-73496, EL-EF788, EL-AAE2C, EL-DEDF4, EL-7C9B8, EL-A9AB8, EL-041C4, EL-FE4F8, EL-F339F |  | EL-6CA5E
| 338 | NR | Uttar Pradesh |  |  | Greenko UP01 IREP Private Limited |  | 2200000526 |  |  | 31 |  | 2024-06-27 |  | PSP | 672 | 672 | [8 empty] | 610 | 672 |  |  | 2024-02-05 | - | 2027-04-16 | 2027-04-16 | No |  | Pumped Storage | Granted | 400 |  | EL-73496, EL-EF788, EL-AAE2C, EL-DEDF4, EL-7C9B8, EL-A9AB8, EL-041C4, EL-FE4F8, EL-F339F |  | EL-6CA5E
| 339 | NR | Uttar Pradesh |  |  | Greenko UP01 IREP Private Limited |  | 2200000528 |  |  | 31 |  | 2024-06-27 |  | PSP | 672 | 672 | [8 empty] | 610 | 672 |  |  | 2024-02-05 | - | 2027-04-16 | 2027-04-16 | No |  | Pumped Storage | Granted | 400 |  | EL-73496, EL-EF788, EL-AAE2C, EL-DEDF4, EL-7C9B8, EL-A9AB8, EL-041C4, EL-FE4F8, EL-F339F |  | EL-6CA5E
| 340 | NR | Uttar Pradesh |  |  | Avaada Waterbattery Private Limited |  | 2200000553 |  |  | 31 |  | 2024-06-27 |  | PSP | 1120 | 1120 | [8 empty] | 900 | 1120 |  |  | 2024-02-06 | - | 2028-03-31 | 2028-12-31 | No |  | Pumped Storage | Granted | 400 |  | EL-73496, EL-EF788, EL-AAE2C, EL-DEDF4, EL-7C9B8, EL-A9AB8, EL-23874, EL-FE4F8, EL-F339F |  | EL-6B87E
| 341 | NR | Jammu and Kashmir | Kishtwar Pooling Station-I |  | Chenab Valley Power Projects Private Limited |  | 2200000496 |  |  | 31 |  | 2024-06-27 |  | Hydro | 624 | 624 |  |  |  | 624 | [8 empty] | 2024-02-06 | - | 2025-11-01 | 2026-12-31 | No |  | Generator | Granted | 400 |  | EL-0B24F |  | EL-3AE0E, EL-2BFBD, EL-90627, EL-0F136
| 342 | NR | Rajasthan | Fatehgarh-II |  | Acme Cleantech Solutions Private Limited |  | 2200000387 |  |  | 31 |  | 2024-06-27 |  | Solar | 600 |  | 600 | [11 empty] | 2023-11-29 | Land BG route | 2026-03-31 | 2026-07-31 |  |  | Generator | Applied
| 343 | NR | Rajasthan | Fatehgarh-II |  | Acme Cleantech Solutions Private Limited |  | 2200000396 |  |  | 31 |  | 2024-06-27 |  | Hybrid | 250 | 250 |  |  | 250 | [9 empty] | 2023-11-30 | LOA (SJVN) | 2026-03-31 | 2026-07-31 | No |  | Generator | Granted | 400 |  | EL-ADC60, EL-D94DF, EL-57AA1, EL-72AA1, EL-39439, EL-3877B, EL-1BF5F, EL-951CC, EL-8F19A |  | EL-3DE89
| 344 | NR | Rajasthan | Barmer-I |  | Enfinity Global Surya Kiran Private Limited |  | 2200000411 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-12-08 | Land Route | 2026-06-30 | 2026-11-30 | No |  | Renewable Power Park developer | Granted | 220 |  | EL-AB6F6, EL-04FBF, EL-E0593, EL-C16AF, EL-9DE74, EL-26050, EL-4777E, EL-0D0CA, EL-7AF76, EL-DA901, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-50132, EL-06311, EL-D0E44, EL-553D7, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-F20FC, EL-6F66E |  | EL-81053
| 345 | NR | Rajasthan | Barmer-I |  | EG Mega Urja Private Limited (erstwhile Andhra Pradesh Resco Rooftop Solar Private Limited) |  | 2200000412 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-12-08 | Land Route | 2026-06-30 | 2026-11-30 | No |  | Renewable Power Park developer | Granted | 220 |  | EL-AB6F6, EL-04FBF, EL-E0593, EL-C16AF, EL-9DE74, EL-26050, EL-4777E, EL-0D0CA, EL-7AF76, EL-DA901, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-50132, EL-06311, EL-D0E44, EL-553D7, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-F20FC, EL-6F66E |  | EL-27C14
| 346 | NR | Rajasthan | Bays At Bikaner-IV |  | SJVN Green Energy Limited |  | 2200000423 |  |  | 31 |  | 2024-06-27 |  | Solar | 1000 | 1000 | 1000 | [11 empty] | 2023-12-15 | PPA PSPCL | 2025-02-13 | 2026-09-30 | No |  | Generator | Granted | 220 |  | EL-1713C, EL-FFEB8, EL-1990B, EL-A856A, EL-AC827, EL-CAA1E, EL-8F215, EL-C3D72, EL-81725, EL-95F93, EL-3535F, EL-4C59F, EL-8F19A, EL-32D0B |  | EL-FE432
| 347 | NR | Rajasthan | Bhadla-III |  | Renew Solar (Shakti Six) Private Limited |  | 2200000426 |  |  | 31 |  | 2024-06-27 |  | Solar | 15 |  | 15 | [11 empty] | 2023-12-16 | Land Route | 2026-06-30 |  |  |  | Generator | Applied
| 348 | NR | Rajasthan | Next-I |  | Green Infra Wind Energy Limited |  | 2200000436 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-12-17 | LOA NHPC | 2026-06-01 |  |  |  | Generator | Granted
| 349 | NR | Rajasthan | Barmer-I |  | Hinduja Renewables Energy Private Limited |  | 2200000425 |  |  | 31 |  | 2024-06-27 |  | Solar | 250 | 250 | 250 | [11 empty] | 2023-12-18 | LOA NHPC | 2026-03-07 | 2026-11-30 | No |  | Generator | Granted | 220 |  | EL-AB6F6, EL-04FBF, EL-E0593, EL-C16AF, EL-9DE74, EL-26050, EL-4777E, EL-0D0CA, EL-7AF76, EL-DA901, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-50132, EL-06311, EL-D0E44, EL-553D7, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-F20FC, EL-6F66E |  | EL-1DD32
| 350 | NR | Rajasthan | Bhadla-II |  | Green Infra Clean Wind Limited |  | 2200000437 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-12-18 | Land Route | 2027-06-01 | 2027-06-01 | No |  | Generator | Granted | 400 |  | EL-94DEC, EL-80AE9, EL-57AA1, EL-72AA1, EL-39439, EL-3877B, EL-00650, EL-8F19A |  | EL-AE35C, EL-D9DCD
| 351 | NR | Rajasthan | Barmer-I |  | Green Infra Clean Solar Farms Limited |  | 2200000408 |  |  | 31 |  | 2024-06-27 |  | Solar | 130 | 130 | 130 | [11 empty] | 2023-12-18 | Land Route | 2027-06-01 | 2029-12-31 | No |  | Generator | Granted | 220 |  | EL-14747, EL-AD084, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-B9274
| 352 | NR | Rajasthan | Bays At Barmer-I |  | Green Infra Renewable Projects Limited |  | 2200000410 |  |  | 31 |  | 2024-06-27 |  | Solar | 683 | 683 | 683 | [11 empty] | 2023-12-19 | Land Route | 2027-06-01 | 2027-06-01 | No |  | Generator | Granted | 220 |  | EL-AB6F6, EL-04FBF, EL-E0593, EL-C16AF, EL-9DE74, EL-26050, EL-4777E, EL-0D0CA, EL-7AF76, EL-DA901, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-50132, EL-06311, EL-D0E44, EL-553D7, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-F20FC, EL-6F66E |  | EL-E4767
| 353 | NR | Rajasthan | Bikaner-IV |  | Furies Solren Private Limited |  | 2200000419 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-12-21 | Land BG Route | 2026-01-31 | 2026-09-30 | No |  | Generator | Granted | 220 |  | EL-1713C, EL-FFEB8, EL-1990B, EL-A856A, EL-AC827, EL-CAA1E, EL-8F215, EL-C3D72, EL-81725, EL-95F93, EL-3535F, EL-4C59F, EL-8F19A, EL-32D0B |  | EL-09D53
| 354 | NR | Rajasthan | Bhadla-IV |  | Avaada Energy Private Limited |  | 2200000407 |  |  | 31 |  | 2024-06-27 |  | Solar | 1000 | 1000 | 1000 | [11 empty] | 2023-12-21 | LOA NHPC | 2025-12-31 | 2028-12-31 | No |  | Generator | Granted | 220 |  | EL-5A0ED, EL-9267B, EL-CE849, EL-2B272, EL-A4C5F, EL-6DFEE, EL-65D44, EL-7BBDE |  | EL-F5E74
| 355 | NR | Rajasthan | Bikaner-V |  | NTPC Renewable Energy Limited |  | 2200000420 |  |  | 31 |  | 2024-06-27 |  | Solar | 1000 | 1000 | 1000 | [11 empty] | 2023-12-22 | Land Route | 2026-06-30 | 2026-09-30 | No |  | Generator | Granted | 400 |  | EL-1713C, EL-FFEB8, EL-1990B, EL-A856A, EL-AC827, EL-CAA1E, EL-8F215, EL-C3D72, EL-81725, EL-95F93, EL-3535F, EL-4C59F, EL-8F19A, EL-32D0B |  | EL-C5579
| 356 | NR | Rajasthan | Ramgarh-I |  | Pravat Renewables India Project Private Limited |  | 2200000452 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-12-27 | Land BG Route | 2028-05-01 | 2029-01-31 | No |  | Renewable Power Park developer | Granted | 220 |  | EL-3CB80, EL-065D3, EL-31139, EL-CE816, EL-DD8DD, EL-BE37F, EL-90F2A, EL-B8CEB, EL-C2310, EL-CD00C, EL-547E5, EL-BBD19, EL-69266, EL-35C79 |  | EL-2EE71
| 357 | NR | Rajasthan | Barmer-II |  | Apraava Energy Private Limited |  | 2200000459 |  |  | 31 |  | 2024-06-27 |  | Solar | 250 | 250 | 250 | [11 empty] | 2023-12-29 | LOA NHPC | 2026-03-31 | 2029-12-31 | No |  | Generator | Granted | 220 |  | EL-14747, EL-AD084, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-A0D4D
| 358 | NR | Rajasthan | Barmer-I |  | Serentica Renewables India 11 Private Limited |  | 2200000469 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2023-12-30 | Land BG Route | 2026-05-31 |  |  |  | Generator | Applied
| 359 | NR | Rajasthan | Bikaner-III |  | Juniper Green Energy Private Limited |  | 2200000482 |  |  | 31 |  | 2024-06-27 |  | Solar | 200 |  | 200 | [11 empty] | 2023-12-30 | Land BG Route | 2027-09-30 |  |  |  | Generator | Applied
| 360 | NR | Rajasthan | Bikaner-V |  | Saurya Urja Company of Rajasthan Limited |  | 2200000475 |  |  | 31 |  | 2024-06-27 |  | Solar | 400 | 400 | 400 | [11 empty] | 2023-12-30 | Land BG Route | 2025-12-31 | 2029-12-31 | No |  | Renewable Power Park developer | Granted | 220 |  | EL-D9A07, EL-85255, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-905E4, EL-207DF |  | EL-56771
| 361 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Energy Private Limited |  | 2200000485 |  |  | 31 |  | 2024-06-27 |  | Solar | 50 |  | 50 | [11 empty] | 2023-12-31 | Land BG Route | 2027-12-31 | 2027-12-31 |  |  | Generator | Applied
| 362 | NR | Rajasthan | Bikaner-V |  | Iraax International (OPC) Private Limited |  | 2200000484 |  |  | 31 |  | 2024-06-27 |  | Solar | 100 | 100 | 100 | [11 empty] | 2024-01-10 | Land Route | 2026-03-31 | 2029-12-31 | No |  | Generator | Granted | 220 |  | EL-D9A07, EL-85255, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-905E4, EL-207DF |  | EL-59A52
| 363 | NR | Rajasthan | Barmer-II |  | Juniper Green Energy Private Limited |  | 2200000495 |  |  | 31 |  | 2024-06-27 |  | Hybrid | 230 | 230 | 150 | 80 | [10 empty] | 2024-01-11 | NTPC LOA | 2026-03-31 | 2029-12-31 | No |  | Generator | Granted | 220 |  | EL-14747, EL-AD084, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-733B4
| 364 | NR | Rajasthan | Ramgarh-I |  | Juniper Green Energy Private Limited |  | 2200000499 |  |  | 31 |  | 2024-06-27 |  | Solar | 150 | 150 | 150 | [11 empty] | 2024-01-11 | Land BG route | 2028-06-30 | 2028-12-31 | No |  | Generator | Granted | 220 |  | EL-3CB80, EL-065D3, EL-31139, EL-CE816, EL-DD8DD, EL-BE37F, EL-90F2A, EL-B8CEB, EL-C2310, EL-CD00C, EL-547E5, EL-BBD19, EL-69266, EL-35C79 |  | EL-6B099
| 365 | NR | Rajasthan | Barmer-I |  | Anboto Solar Private Limited |  | 2200000492 |  |  | 31 |  | 2024-06-27 |  | Solar | 50 | 50 | 50 | [11 empty] | 2024-01-18 | Land Route | 2025-11-30 | 2026-11-30 | No |  | Generator | Granted | 220 |  | EL-AB6F6, EL-04FBF, EL-E0593, EL-C16AF, EL-9DE74, EL-26050, EL-4777E, EL-0D0CA, EL-7AF76, EL-DA901, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-50132, EL-06311, EL-D0E44, EL-553D7, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-F20FC, EL-6F66E |  | EL-139DB
| 366 | NR | Rajasthan | Barmer-II |  | Solalite Power Private Limited |  | 2200000507 |  |  | 31 |  | 2024-06-27 |  | Solar | 250 | 0 | 250 | [11 empty] | 2024-01-19 | NTPC LOA | 2026-03-31 |  |  |  | Generator | Withdrawn
| 367 | NR | Rajasthan | Bhadla-IV |  | Renew Solar Power Private Limited |  | 2200000516 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-01-25 | SECI LOA | 2026-09-30 |  |  |  | Generator | Granted | 400
| 368 | NR | Rajasthan | Bhadla-IV |  | Renew Solar Power Private Limited |  | 2200000521 |  |  | 31 |  | 2024-06-27 |  | Solar | 200 | 200 | 200 | [11 empty] | 2024-01-25 | SJVN LOA | 2026-05-31 |  |  |  | Generator with ESS | Granted | 400
| 369 | NR | Rajasthan | Bhadla-IV |  | Renew Solar Power Private Limited |  | 2200000522 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-01-25 | SJVN LOA | 2026-05-31 |  |  |  | Generator | Granted | 400
| 370 | NR | Rajasthan | Barmer-II |  | Sprng Renewable Resources Private Limited |  | 2200000531 |  |  | 31 |  | 2024-06-27 |  | Solar | 200 | 200 | 200 | [11 empty] | 2024-01-25 | Land BG route | 2027-06-30 | 2029-12-31 | No |  | Generator | Granted | 220 |  | EL-14747, EL-AD084, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-A1757
| 371 | NR | Rajasthan | Barmer-II |  | Sprng Urja Private Limited |  | 2200000539 |  |  | 31 |  | 2024-06-27 |  | Solar | 200 | 200 | 200 | [11 empty] | 2024-01-30 | Land BG route | 2029-06-30 | 2029-12-31 | No |  | Generator | Granted | 220 |  | EL-14747, EL-AD084, EL-F9AF9, EL-AE2D7, EL-3B268, EL-92100, EL-E191F, EL-3F9F2 |  | EL-A1757
| 372 | NR | Rajasthan | Barmer-II |  | Green Infra Wind Energy Limited |  | 2200000541 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-01-30 | SECI LOA | 2027-06-01 |  |  |  | Generator | Granted | 220
| 373 | NR | Rajasthan | Fatehgarh-II |  | Axis Energy Ventures India Private Limited |  | 2200000510 |  |  | 31 |  | 2024-06-27 |  | Solar | 320 | 0 | 320 | [11 empty] | 2024-01-31 | Land Route | 2025-06-30 |  |  |  | Generator | Withdrawn
| 374 | NR | Rajasthan | Sirohi-I |  | CESC Ltd. |  | 2200000518 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 | 300 | 300 | [11 empty] | 2024-02-01 | Land BG Route | 2026-02-01 | 2027-03-31 | No |  | Generator | Granted | 220 |  | EL-C16AF, EL-3CE98, EL-26050, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-544F8, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-B6BDF, EL-C7A50 |  | EL-E2C4A
| 375 | NR | Rajasthan | Ramgarh-I |  | Juniper Green Energy Private Limited |  | 2200000550 |  |  | 31 |  | 2024-06-27 |  | Solar | 150 | 150 | 150 | [11 empty] | 2024-02-05 | Land BG Route | 2028-12-31 | 2028-12-31 | No |  | Generator | Granted | 220 |  | EL-3CB80, EL-065D3, EL-31139, EL-CE816, EL-DD8DD, EL-BE37F, EL-90F2A, EL-B8CEB, EL-C2310, EL-CD00C, EL-547E5, EL-BBD19, EL-69266, EL-35C79 |  | EL-6B099
| 376 | NR | Rajasthan | Sirohi-I |  | Renew Solar Power Private Limited |  | 2200000551 |  |  | 31 |  | 2024-06-27 |  | Solar | 400 | 400 | 400 | [11 empty] | 2024-02-05 | NTPC LOA | 2026-08-01 | 2027-03-31 | No |  | Generator | Granted | 220 |  | EL-C16AF, EL-3CE98, EL-26050, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-544F8, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-B6BDF, EL-C7A50 |  | EL-9EFA0
| 377 | NR | Rajasthan | Bikaner-V |  | Iraax International (Opc) Private Limited |  | 2200000540 |  |  | 31 |  | 2024-06-27 |  | Solar | 150 | 150 | 150 | [11 empty] | 2024-02-08 | Land Route | 2026-03-31 | 2029-12-31 | No |  | Generator | Granted | 220 |  | EL-D9A07, EL-85255, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-905E4, EL-207DF |  | EL-59A52
| 378 | NR | Rajasthan | Bikaner-V |  | Avaada RJBikaner Private Limited |  | 2200000561 |  |  | 31 |  | 2024-06-27 |  | Solar | 136 | 136 | 136 | [11 empty] | 2024-02-13 | Land Route | 2025-03-31 | 2029-12-31 | No |  | Generator | Granted | 220 |  | EL-D9A07, EL-85255, EL-326E0, EL-BDCD9, EL-23675, EL-75F9E, EL-745F8, EL-37199, EL-905E4, EL-207DF |  | EL-91598
| 379 | NR | Rajasthan | Based On Total Connectivity Quantum At Barmer-II |  | NTPC Renewable Energy Limited |  | 2200000564 |  |  | 31 |  | 2024-06-27 |  | Solar | 200 | 200 | 200 | [11 empty] | 2024-02-15 | SECI LOA | 2026-04-16 |  |  |  | Generator | Granted | 220
| 380 | NR | Rajasthan | Fatehgarh-IV |  | NTPC Renewable Energy Limited |  | 2200000567 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-03-01 | Land Route | 2026-03-31 |  |  |  | Generator | Applied
| 381 | NR | Rajasthan | Barmer-I |  | Avaada Energy Private Limited |  | 2200000580 |  |  | 31 |  | 2024-06-27 |  | Solar | 200 |  | 200 | [11 empty] | 2024-03-02 | NTPC LOA | 2026-03-26 |  |  |  | Generator | Applied
| 382 | NR | Rajasthan | Bikaner-IV |  | Jade Hybren Private Limited |  | 2200000616 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-03-06 | Land BG Route | 2026-06-30 |  |  |  | Generator | Applied
| 383 | NR | Rajasthan | Ramgarh-I |  | Migos Hybren Private Limited |  | 2200000618 |  |  | 31 |  | 2024-06-27 |  | Solar | 600 |  | 600 | [11 empty] | 2024-03-06 | Land BG Route | 2026-12-31 |  |  |  | Generator | Applied
| 384 | NR | Rajasthan | Bhadla-II |  | Kyros Hybren Private Limited |  | 2200000624 |  |  | 31 |  | 2024-06-27 |  | Solar | 100 |  | 100 | [11 empty] | 2024-03-07 | Land BG Route | 2025-06-30 |  |  |  | Generator | Applied
| 385 | NR | Rajasthan | Bhadla-II |  | Aravalli Surya (Project 1) Private Limited |  | 2200000605 |  |  | 31 |  | 2024-06-27 |  | Solar | 335 |  | 335 | [11 empty] | 2024-03-07 | Land Route | 2027-12-31 |  |  |  | Generator | Applied
| 386 | NR | Rajasthan | Ramgarh-I |  | Adani Renewable Energy Holding Four Limited |  | 2200000598 |  |  | 31 |  | 2024-06-27 |  | Solar | 500 |  | 500 | [11 empty] | 2024-03-13 | Land Route | 2025-06-15 |  |  |  | Generator | Applied
| 387 | NR | Rajasthan | Ramgarh-I |  | Adani Renewable Energy Holding Four Limited |  | 2200000599 |  |  | 31 |  | 2024-06-27 |  | Solar | 500 |  | 500 | [11 empty] | 2024-03-13 | Land Route | 2025-06-15 |  |  |  | Generator | Applied
| 388 | NR | Rajasthan | Sirohi-I |  | Serentica Renewables India Private Limited |  | 2200000644 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-03-14 | Land BG Route | 2026-06-30 |  |  |  | Generator | Applied
| 389 | NR | Rajasthan | Ramgarh-I |  | Adani Renewable Energy Park Rajasthan Limited |  | 2200000600 |  |  | 31 |  | 2024-06-27 |  | Solar | 1000 |  | 1000 | [11 empty] | 2024-03-14 | Land Route | 2025-06-15 |  |  |  | Renewable Power Park developer | Applied
| 390 | NR | Rajasthan | Ramgarh-I |  | Adani Renewable Energy Park Rajasthan Limited |  | 2200000601 |  |  | 31 |  | 2024-06-27 |  | Solar | 1000 |  | 1000 | [11 empty] | 2024-03-14 | Land Route | 2025-06-15 |  |  |  | Renewable Power Park developer | Applied
| 391 | NR | Rajasthan | Sirohi-I |  | Illuminate Hybren Private Limited |  | 2200000646 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-03-15 | Land BG Route | 2026-06-30 |  |  |  | Generator | Applied
| 392 | NR | Rajasthan | Barmer-I |  | Avaada Energy |  | 2200000636 |  |  | 31 |  | 2024-06-27 |  | Solar | 450 |  | 450 | [11 empty] | 2024-03-19 | SJVN LOA | 2026-09-30 |  |  |  | Generator | Applied
| 393 | NR | Rajasthan | Barmer-I |  | Green Infra Wind Energy Limited |  | 2200000654 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-03-27 | SJVN LOA | 2027-06-30 |  |  |  | Generator | Applied
| 394 | NR | Rajasthan | Ramgarh-I |  | Adani Renewable Energy Holding Four Limited |  | 2200000661 |  |  | 31 |  | 2024-06-27 |  | Solar | 250 |  | 250 | [11 empty] | 2024-03-28 | SECI LOA | 2025-10-01 |  |  |  | Generator | Applied
| 395 | NR | Rajasthan | Ramgarh-I |  | Adani Renewable Energy Holding Four Limited |  | 2200000662 |  |  | 31 |  | 2024-06-27 |  | Solar | 284 |  | 284 | [11 empty] | 2024-03-28 | SECI LOA | 2026-10-01 |  |  |  | Generator | Applied
| 396 | NR | Rajasthan | Barmer-I |  | Juniper Green Energy Private Limited |  | 2200000668 |  |  | 31 |  | 2024-06-27 |  | Hybrid | 180 |  |  |  | 180 | [9 empty] | 2024-03-28 | SJVN LOA | 2026-06-30 |  |  |  | Generator | Applied
| 397 | NR | Rajasthan | Ramgarh-I |  | Tata Power Renewable Energy Limited |  | 2200000672 |  |  | 31 |  | 2024-06-27 |  | Solar | 600 |  | 600 | [11 empty] | 2024-03-29 | Land BG Route | 2028-06-30 |  |  |  | Generator | Applied
| 398 | NR | Rajasthan | Barmer-I |  | Sprng Urja Private Limited |  | 2200000681 |  |  | 31 |  | 2024-06-27 |  | Solar | 1000 |  | 1000 | [11 empty] | 2024-03-30 | Land BG Route | 2029-06-30 |  |  |  | Renewable Power Park developer | Applied
| 399 | NR | Rajasthan | Ramgarh-I |  | JSW Neo Energy Limited |  | 2200000706 |  |  | 31 |  | 2024-06-27 |  | Solar | 700 |  | 700 | [11 empty] | 2024-04-12 | SJVN LOA | 2025-09-01 |  |  |  | Generator | Applied
| 400 | NR | Rajasthan | Ramgarh-I |  | JSW Neo Energy Limited |  | 2200000689 |  |  | 31 |  | 2024-06-27 |  | Solar | 700 |  | 700 | [11 empty] | 2024-04-12 | SJVN LOA | 2027-03-01 |  |  |  | Generator | Applied
| 401 | NR | Rajasthan | Barmer-I |  | Amaresha Renawables India Project Private Limited |  | 2200000715 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-04-15 | Land BG Route | 2027-04-01 |  |  |  | Renewable Power Park Developer | Applied
| 402 | NR | Rajasthan | Bikaner-IV |  | NTPC Renewable Energy Limited |  | 2200000726 |  |  | 31 |  | 2024-06-27 |  | Solar | 1000 |  | 1000 | [11 empty] | 2024-04-23 | Land Route | 2026-12-31 |  |  |  | Generator | Applied
| 403 | NR | Rajasthan | Ramgarh-I |  | Juniper Green Energy Private Limited |  | 2200000756 |  |  | 31 |  | 2024-06-27 |  | Hybrid | 360 |  |  |  | 360 | [9 empty] | 2024-04-25 | NTPC LOA | 2026-06-30 |  |  |  | Generator | Applied
| 404 | NR | Rajasthan | Sirohi-I |  | Vayuna Renewables India Project Private Limited |  | 2200000758 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-04-25 | Land BG | 2027-04-01 |  |  |  | Renewable Power Park Developer | Applied
| 405 | NR | Rajasthan | Bhadla-IV |  | Kantida Renewables India Project Private Limited |  | 2200000761 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-04-25 | Land BG Route | 2028-04-01 |  |  |  | Renewable Power Park Developer | Applied
| 406 | NR | Rajasthan | Sirohi-I |  | Izhma Solar Private Limited |  | 2200000743 |  |  | 31 |  | 2024-06-27 |  | Solar | 200 |  | 200 | [11 empty] | 2024-04-26 | Land BG Route | 2028-03-31 |  |  |  | Generator | Applied
| 407 | NR | Rajasthan | Ramgarh-I |  | Renew Solar Power Private Limited |  | 2200000777 |  |  | 31 |  | 2024-06-27 |  | Solar | 400 |  | 400 | [11 empty] | 2024-04-30 | NTPC LOA | 2027-06-30 |  |  |  | Generator | Applied
| 408 | NR | Rajasthan | Barmer-I |  | Renew Solar Power Private Limited |  | 2200000778 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-04-30 | SECI LOA | 2026-12-31 |  |  |  | Generator | Applied
| 409 | NR | Rajasthan | Sirohi-I |  | Renew Solar Power Private Limited |  | 2200000779 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-04-30 | NTPC LOA | 2027-06-30 |  |  |  | Generator | Applied
| 410 | NR | Rajasthan | Bikaner-III |  | SA Renewable Infra Private Limited |  | 2200000755 |  |  | 31 |  | 2024-06-27 |  | Solar | 100 |  | 100 | [11 empty] | 2024-05-04 | Land Route | 2026-03-31 |  |  |  | Generator | Applied
| 411 | NR | Rajasthan | Bikaner-IV |  | Vena Energy Vindhya Wind Power Private Limited |  | 2200000796 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-06 | Land BG Route | 2027-10-01 |  |  |  | Generator | Applied
| 412 | NR | Rajasthan | Sirohi-I |  | ACME Solar Holdings Private Limited |  | 2200000788 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-07 | Land BG Route | 2027-03-31 |  |  |  | Generator | Applied
| 413 | NR | Rajasthan | Sirohi-I |  | SAEL Industries Limited |  | 2200000793 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-10 | Land BG Route | 2026-05-30 |  |  |  | Generator | Applied
| 414 | NR | Rajasthan | Sirohi-I |  | SAEL Industries Limited |  | 2200000794 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-10 | Land BG Route | 2026-05-30 |  |  |  | Generator | Applied
| 415 | NR | Rajasthan | Bhadla-II |  | Adani Renewable Energy Holding Four Limited |  | 2200000811 |  |  | 31 |  | 2024-06-27 |  | Solar | 765 |  | 765 | [11 empty] | 2024-05-10 | SECI LOA | 2025-03-31 |  |  |  | Generator | Applied
| 416 | NR | Rajasthan | Fatehgarh-III |  | Adani Renewable Energy Holding Four Limited |  | 2200000810 |  |  | 31 |  | 2024-06-27 |  | Solar | 717 |  | 717 | [11 empty] | 2024-05-10 | SECI LOA | 2025-03-31 |  |  |  | Generator | Applied
| 417 | NR | Rajasthan | Ramgarh-I |  | RJS Renewables Private Limited |  | 2200000782 |  |  | 31 |  | 2024-06-27 |  | Wind | 150 |  |  | 150 | [10 empty] | 2024-05-12 | Land Route | 2028-04-20 |  |  |  | Generator | Applied
| 418 | NR | Rajasthan | Ramgarh-I |  | JSW Neo Energy Limited |  | 2200000797 |  |  | 31 |  | 2024-06-27 |  | Solar | 700 |  | 700 | [11 empty] | 2024-05-13 | NTPC LOA | 2027-05-01 |  |  |  | Generator | Applied
| 419 | NR | Rajasthan | Nagaur-I |  | Green Infra Wind Energy Private Limited |  | 2200000812 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-14 | Land BG Route | 2027-05-31 |  |  |  | Generator | Applied
| 420 | NR | Rajasthan | Nagaur-I |  | Green Infra Wind Energy Private Limited |  | 2200000813 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-14 | Land BG Route | 2027-05-31 |  |  |  | Generator | Applied
| 421 | NR | Rajasthan | Merta-I |  | Banyan Energy Private Limited |  | 2200000823 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-18 | Land BG Route | 2026-06-30 |  |  |  | Generator | Applied
| 422 | NR | Rajasthan | Sirohi-I |  | Amplus Centaur Solar Private Limited |  | 2200000827 |  |  | 31 |  | 2024-06-27 |  | Solar | 350 |  | 350 | [11 empty] | 2024-05-20 | Land BG Route | 2027-04-30 |  |  |  | Generator | Applied
| 423 | NR | Rajasthan | Barmer-I |  | Adani Renewable Energy Two Limited |  | 2200000807 |  |  | 31 |  | 2024-06-27 |  | Wind | 600 |  |  | 600 | [10 empty] | 2024-05-21 | Land Route | 2025-03-31 |  |  |  | Generator (Wind | Applied
| 424 | NR | Rajasthan | Barmer-I |  | Adani Renewable Energy Two Limited |  | 2200000809 |  |  | 31 |  | 2024-06-27 |  | Wind | 595 |  |  | 595 | [10 empty] | 2024-05-21 | Land Route | 2025-03-31 |  |  |  | Generator | Applied
| 425 | NR | Rajasthan | Nagaur (Merta-II) |  | Acme Solar Holdings Private Limited |  | 2200000840 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-25 | Land BG Route | 2027-03-31 |  |  |  | Generator | Applied
| 426 | NR | Rajasthan | Nagaur-I |  | Purvah Green Power Private Limited |  | 2200000842 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-25 | Land BG Route | 2027-06-01 |  |  |  | Generator | Applied
| 427 | NR | Rajasthan | Merta-II |  | Hexa Climate Solutions Private Limited |  | 2200000848 |  |  | 31 |  | 2024-06-27 |  | Solar+BESS | 300 | [13 empty] | 2024-05-25 | Land BG Route | 2027-03-31 |  |  |  | Generator | Applied
| 428 | NR | Rajasthan | Jalore-I |  | Renew Solar Power Private Limited |  | 2200000850 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-27 | NTPC LOA | 2026-11-30 |  |  |  | Generator | Applied
| 429 | NR | Rajasthan | Bikaner-I |  | Hexa Climate Solutions Private Limited |  | 2200000854 |  |  | 31 |  | 2024-06-27 |  | Solar+BESS | 50 | [13 empty] | 2024-05-27 | Land BG Route | 2025-06-30 |  |  |  | Generator | Applied
| 430 | NR | Rajasthan | Barmer-I |  | Serentica Renewables India 11 Private Limited |  | 2200000856 |  |  | 31 |  | 2024-06-27 |  | Solar+BESS | 250 | [13 empty] | 2024-05-28 | NTPC LOA | 2027-12-31 |  |  |  | Generator | Applied
| 431 | NR | Rajasthan | Bikaner-I |  | Solarcraft Power India 8 Private Limited |  | 2200000866 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-30 | LOA or PPA | 2026-06-29 |  |  |  | Generator | Applied
| 432 | NR | Rajasthan | Bhadla-IV |  | Demeter Sun Power Private Limited |  | 2200000875 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-30 | Land Route | 2027-12-31 |  |  |  | Generator | Applied
| 433 | NR | Rajasthan | Merta-II |  | Juniper Green Energy Private Limited |  | 2200000879 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-30 | Land BG Route | 2027-12-31 |  |  |  | Generator | Applied
| 434 | NR | Rajasthan | Nagaur (Merta-II) |  | Acme Solar Holdings Private Limited |  | 2200000841 |  |  | 31 |  | 2024-06-27 |  | Solar | 100 |  | 100 | [11 empty] | 2024-05-31 | Land BG Route | 2027-03-31 |  |  |  | Generator | Applied
| 435 | NR | Rajasthan | Rishabhdeo-I |  | Serentica Renewables India Private Limited |  | 2200000891 |  |  | 31 |  | 2024-06-27 |  | Solar | 400 |  | 400 | [11 empty] | 2024-05-31 | Land BG Route | 2026-06-30 |  |  |  | Generator | Applied
| 436 | NR | Rajasthan | Jalore-I |  | Renew Solar Power Private Limited |  | 2200000886 |  |  | 31 |  | 2024-06-27 |  | Solar | 100 |  | 100 | [11 empty] | 2024-05-31 | Land BG Route | 2027-12-31 |  |  |  | Generator | Applied
| 437 | NR | Rajasthan | Jalore-I |  | Renew Solar Power Private Limited |  | 2200000887 |  |  | 31 |  | 2024-06-27 |  | Solar | 200 |  | 200 | [11 empty] | 2024-05-31 | Land BG Route | 2027-07-31 |  |  |  | Generator | Applied
| 438 | NR | Rajasthan | Jalore-I |  | Renew Solar Power Private Limited |  | 2200000888 |  |  | 31 |  | 2024-06-27 |  | Solar | 200 |  | 200 | [11 empty] | 2024-05-31 | Land BG Route | 2027-09-30 |  |  |  | Generator | Applied
| 439 | NR | Rajasthan | Jalore-I |  | Renew Solar Power Private Limited |  | 2200000889 |  |  | 31 |  | 2024-06-27 |  | Solar | 100 |  | 100 | [11 empty] | 2024-05-31 | Land BG Route | 2027-10-31 |  |  |  | Generator | Applied
| 440 | NR | Rajasthan | Jalore-I |  | Renew Solar Power Private Limited |  | 2200000890 |  |  | 31 |  | 2024-06-27 |  | Solar | 100 |  | 100 | [11 empty] | 2024-05-31 | Land BG Route | 2027-11-30 |  |  |  | Generator | Applied
| 441 | NR | Rajasthan | Nagaur (Merta-II) |  | Enren-III Energy Private Limited |  | 2200000860 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-31 | Land BG Route | 2027-01-31 |  |  |  | Generator | Applied
| 442 | NR | Rajasthan | Nagaur-I |  | Sindhari Solar Power Private Limited |  | 2200000894 |  |  | 31 |  | 2024-06-27 |  | Solar | 300 |  | 300 | [11 empty] | 2024-05-31 | Land BG Route | 2027-06-30 |  |  |  | Renewable Power Park developer | Applied
| 443 | NR | Rajasthan | Bikaner-III |  | Avaada RJbikaner Private Limited |  | 2200000254 |  |  | 27 |  | 2024-01-10 |  | Solar | 600 |  | 600 | [11 empty] | 2023-10-03 | Land Route | 2025-03-31 |  |  |  | Generator | Applied
| 444 | NR | Rajasthan | Bhadla-III |  | Renew Solar (Shakti Six) Private Limited |  | 2200000275 |  |  | 27 |  | 2024-01-10 |  | Solar | 400 | 400 | 400 | [11 empty] | 2023-10-05 | Land Route | 2026-06-30 | 2028-09-01 | No |  | Generator | Granted | 400 |  | EL-BDC29, EL-CE816, EL-90F2A, EL-B8CEB, EL-0A99D, EL-DD8DD, EL-BE37F, EL-547E5, EL-BBD19, EL-69266 |  | EL-74588
| 445 | NR | Rajasthan | Barmer-I |  | Anboto Solar Private Limited |  | 2200000281 |  |  | 27 |  | 2024-01-10 |  | Solar | 250 | 250 | 250 | [11 empty] | 2023-10-06 | Land BG Route | 2025-11-30 | 2026-09-01 | No |  | Generator | Granted | 220 |  | EL-04FBF, EL-ED937, EL-E0593, EL-C16AF, EL-9DE74, EL-26050, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-DBCF2, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-6B356, EL-06311, EL-D0E44, EL-553D7, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-82F00, EL-6F66E |  | EL-CFE69
| 446 | NR | Rajasthan | At Bhadla-III |  | Malur Renewables Private Limited |  | 2200000266 |  |  | 27 |  | 2024-01-10 |  | Solar | 650 | 650 | 650 | [11 empty] | 2023-10-06 | Land Route | 2025-05-30 | 2028-09-01 | No |  | Renewable Power Park Developer | Granted | 400 |  | EL-BDC29, EL-CE816, EL-90F2A, EL-B8CEB, EL-E1B3D, EL-DD8DD, EL-BE37F, EL-547E5, EL-BBD19, EL-69266 |  | EL-C1D16
| 447 | NR | Rajasthan | Bhadla-III |  | Solarcraft Power India 4 Private Limited |  | 2200000300 |  |  | 27 |  | 2024-01-10 |  | Solar | 50 | 50 | 50 | [11 empty] | 2023-10-08 | Land Route | 2025-06-16 | 2028-08-31 | No |  | Generator | Granted | 220 |  | EL-09900, EL-97F77, EL-CE816, EL-90F2A, EL-B8CEB, EL-E1B3D, EL-DD8DD, EL-BE37F, EL-547E5, EL-BBD19, EL-69266 |  | EL-039DF
| 448 | NR | Rajasthan | Barmer-I |  | Juniper Green Energy Private Limited |  | 2200000305 |  |  | 27 |  | 2024-01-10 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-10-11 | Land BG Route | 2027-03-31 | 2027-03-31 | No |  | Generator | Granted | 220 |  | EL-38FD7, EL-04FBF, EL-E0593, EL-C16AF, EL-9DE74, EL-26050, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-544F8, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-6B356, EL-06311, EL-D0E44, EL-553D7, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-82F00, EL-6F66E |  | EL-8E167
| 449 | NR | Rajasthan | Bikaner-IV |  | Avaada Energy Private Limited |  | 2200000289 |  |  | 27 |  | 2024-01-10 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-10-12 | Land BG Route | 2025-11-30 | 2026-09-01 | No |  | Generator | Granted | 400 |  | EL-BF006, EL-57324, EL-FFEB8, EL-1990B, EL-A856A, EL-AC827, EL-CAA1E, EL-8F215, EL-C3D72, EL-81725, EL-95F93, EL-3535F, EL-83858, EL-8F19A |  | EL-C91CC
| 450 | NR | Rajasthan | Bhadla-III |  | Renew Solar (Shakti Six) Private Limited |  | 2200000309 |  |  | 27 |  | 2024-01-10 |  | Solar | 585 | 585 | 585 | [11 empty] | 2023-10-13 | Land Route | 2026-06-30 | 2028-09-01 | No |  | Generator | Granted | 400 |  | EL-BDC29, EL-CE816, EL-90F2A, EL-B8CEB, EL-E1B3D, EL-DD8DD, EL-BE37F, EL-547E5, EL-BBD19, EL-69266 |  | EL-AA9CE
| 451 | NR | Rajasthan | Bikaner-I (Bikaner (PG) |  | AK Renewable Infra Private Limited |  | 2200000284 |  |  | 27 |  | 2024-01-10 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-10-13 | Land Route | 2025-06-30 | 2026-03-01 | Yes |  | Generator | Granted | 400 |  | EL-B075D, EL-D92F2, EL-C2590, EL-91E7F, EL-E8A1F, EL-05C8E, EL-2453D, EL-EF0A0, EL-4535D, EL-92EB7, EL-CBFD4, EL-80EC9, EL-5DAFB, EL-82E5F, EL-8F19A |  | EL-62CF6
| 452 | NR | Rajasthan | Barmer-I |  | Auxo Sunlight Private Limited |  | 2200000312 |  |  | 27 |  | 2024-01-10 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-10-14 | Land BG Route | 2026-09-30 | 2026-09-30 | No |  | Generator | Granted | 220 |  | EL-244EB, EL-04FBF, EL-E0593, EL-C16AF, EL-9DE74, EL-26050, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-544F8, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-EA9C1, EL-A495D, EL-74937, EL-6B356, EL-06311, EL-D0E44, EL-553D7, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-82F00, EL-6F66E |  | EL-B3E52
| 453 | NR | Rajasthan | Barmer-I |  | Avaada Energy Private Limited |  | 2200000290 |  |  | 27 |  | 2024-01-10 |  | Hybrid | 250 | 250 |  |  | 250 | [9 empty] | 2023-10-17 | Land BG Route | 2025-09-30 | 2026-09-01 | No |  | Generator | Granted | 220 |  | EL-AB6F6, EL-04FBF, EL-E0593, EL-C16AF, EL-9DE74, EL-26050, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-544F8, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-6A951, EL-32FE8, EL-A495D, EL-74937, EL-6B356, EL-06311, EL-D0E44, EL-553D7, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-82F00, EL-6F66E |  | EL-31CD6
| 454 | NR | Rajasthan | Barmer-I |  | Renew Sun Power Private Limited |  | 2200000316 |  |  | 27 |  | 2024-01-10 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-10-17 | Land BG Route | 2026-09-30 | 2026-09-30 | No |  | Generator | Granted | 220 |  | EL-AB6F6, EL-04FBF, EL-E0593, EL-C16AF, EL-9DE74, EL-26050, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-544F8, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-F278C, EL-74937, EL-6B356, EL-06311, EL-D0E44, EL-553D7, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-82F00, EL-6F66E |  | EL-CAB21
| 455 | NR | Rajasthan | Ramgarh-I |  | Hazel Hybren Private Limited |  | 2200000327 |  |  | 27 |  | 2024-01-10 |  | Solar | 300 | 0 | 300 | [11 empty] | 2023-10-20 | Land BG Route | 2026-01-31 |  |  |  | Generator | Withdrawn
| 456 | NR | Rajasthan | Bikaner-IV |  | Shudh Solar Power Private Limited |  | 2200000306 |  |  | 27 |  | 2024-01-10 |  | Solar | 250 | 250 | 250 | [11 empty] | 2023-10-21 | Land Route | 2025-05-31 | 2026-09-01 | No |  | Generator | Granted | 220 |  | EL-1713C, EL-FFEB8, EL-1990B, EL-A856A, EL-AC827, EL-CAA1E, EL-8F215, EL-C3D72, EL-E8A3E, EL-95F93, EL-3535F, EL-4C59F, EL-82E5F, EL-8F19A |  | EL-84756
| 457 | NR | Rajasthan | Bikaner-IV |  | NTPC Renewable Energy Limited |  | 2200000308 |  |  | 27 |  | 2024-01-10 |  | Solar | 700 | 700 | 700 | [11 empty] | 2023-10-21 | Land Route | 2026-03-31 | 2026-09-01 | No |  | Generator | Granted | 400 |  | EL-57324, EL-FFEB8, EL-1990B, EL-A856A, EL-AC827, EL-CAA1E, EL-8F215, EL-C3D72, EL-81725, EL-95F93, EL-3535F, EL-4C59F, EL-82E5F, EL-8F19A |  | EL-90BC8
| 458 | NR | Rajasthan | Bikaner-IV |  | Hazel Hybren Private Limited |  | 2200000334 |  |  | 27 |  | 2024-01-10 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-10-23 | Land BG Route | 2026-01-31 | 2026-09-01 | No |  | Generator | Granted | 220 |  | EL-5C94B, EL-1713C, EL-3A4DE, EL-1990B, EL-A856A, EL-AC827, EL-CAA1E, EL-8F215, EL-C3D72, EL-81725, EL-95F93, EL-3535F, EL-4C59F, EL-82E5F, EL-8F19A |  | EL-A6B39
| 459 | NR | Rajasthan | Bikaner-IV |  | AM Green Energy Private Limited |  | 2200000319 |  |  | 27 |  | 2024-01-10 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-10-23 | Land BG Route | 2025-05-31 | 2026-09-01 | No |  | Generator | Granted | 220 |  | EL-1713C, EL-FFEB8, EL-1990B, EL-A856A, EL-AC827, EL-CAA1E, EL-8F215, EL-C3D72, EL-81725, EL-95F93, EL-988D2, EL-4C59F, EL-82E5F, EL-8F19A |  | EL-18207
| 460 | NR | Rajasthan | Bikaner-IV |  | Furies Solren Private Limited |  | 2200000333 |  |  | 27 |  | 2024-01-10 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-10-27 | Land BG Route | 2026-01-31 | 2026-09-01 | No |  | Generator | Granted | 220 |  | EL-1A1E8, EL-1713C, EL-FFEB8, EL-1990B, EL-A856A, EL-AC827, EL-CAA1E, EL-8F215, EL-C3D72, EL-81725, EL-95F93, EL-3535F, EL-83858, EL-8F19A, EL-0B255 |  | EL-FB49D
| 461 | NR | Rajasthan | Barmer-I |  | Gamma Renewables India Project One Private Limited |  | 2200000355 |  |  | 27 |  | 2024-01-10 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-10-31 | Land BG Route | 2026-06-01 | 2026-09-01 | No |  | Renewable Power Park Developer | Granted | 400 |  | EL-AB6F6, EL-04FBF, EL-E0593, EL-C16AF, EL-9DE74, EL-26050, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-544F8, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-6B356, EL-06311, EL-D0E44, EL-553D7, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-82F00, EL-6F66E |  | EL-CC73C
| 462 | NR | Rajasthan | Bikaner-IV |  | Iraax International (Opc) Private Limited |  | 2200000343 |  |  | 27 |  | 2024-01-10 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-11-09 | Land Route | 2026-03-31 | 2026-09-01 | No |  | Renewable Power Park developer | Granted | 220 |  | EL-BE4F7, EL-1713C, EL-8B247, EL-1990B, EL-A856A, EL-AC827, EL-CAA1E, EL-8F215, EL-C3D72, EL-81725, EL-95F93, EL-3535F, EL-4C59F, EL-82E5F, EL-8F19A |  | EL-63399
| 463 | NR | Rajasthan | Line Bay At Fatehgarh-IV |  | NTPC Renewable Energy Limited |  | 2200000348 |  |  | 27 |  | 2024-01-10 |  | Solar | 900 | 900 | 900 | [11 empty] | 2023-11-09 | Land BG Route | 2026-03-31 | 2026-09-01 | No |  | Generator | Granted | 400 |  | EL-4EA41, EL-04FBF, EL-C1BDA, EL-6EB5E, EL-E0593, EL-C16AF, EL-9DE74, EL-26050, EL-1677A, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-544F8, EL-8F19A, EL-0B255, EL-AE31B, EL-18361, EL-A83CD, EL-417DD, EL-32FE8, EL-A495D, EL-74937, EL-6B356, EL-BE8DC, EL-06311, EL-D0E44, EL-553D7, EL-D7C90, EL-F4EEC, EL-80081, EL-90C55, EL-C99C8, EL-82F00, EL-682A8 |  | EL-BA03C
| 464 | NR | Rajasthan | Bikaner-I |  | Clean Max Gamma Private Limited |  | 2200000344 |  |  | 27 |  | 2024-01-10 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-11-09 | Land Route | 2025-06-28 | 2026-09-01 | No |  | Renewable Power Park developer | Granted | 220 |  | EL-1713C, EL-FFEB8, EL-1990B, EL-A856A, EL-AC827, EL-CAA1E, EL-8F215, EL-C3D72, EL-81725, EL-95F93, EL-3535F, EL-4C59F, EL-82E5F, EL-8F19A |  | EL-2ED08
| 465 | NR | Uttar Pradesh | Line Bay (Gis) At Orai |  | Bundelkhand Saur Urja Limited |  | 2200000345 |  |  | 27 |  | 2024-01-10 |  | Solar | 1200 | 1200 | 1200 | [11 empty] | 2023-11-11 | Land Route | 2025-10-02 | 2026-12-31 | No |  | Renewable Power Park developer | Granted | 400 |  | EL-92873 |  | EL-D8B0A
| 466 | NR | Rajasthan | Ntpcrel At Bikaner-IV |  | NTPC Renewable Energy Limited |  | 2200000373 |  |  | 27 |  | 2024-01-10 |  | Solar | 400 | 400 | 400 | [11 empty] | 2023-11-17 | Land Route | 2026-03-31 | 2026-09-01 | No |  | Generator | Granted | 400 |  | EL-57324, EL-FFEB8, EL-1990B, EL-A856A, EL-AC827, EL-CAA1E, EL-8F215, EL-C3D72, EL-81725, EL-95F93, EL-3535F, EL-4C59F, EL-649B8, EL-8F19A |  | EL-7C392
| 467 | NR | Rajasthan | Line Bay At Bhadla-IV |  | Prerak Solar Urja Private Limited |  | 2200000360 |  |  | 27 |  | 2024-01-10 |  | Solar | 400 | 400 | 400 | [11 empty] | 2023-11-17 | Land Route | 2025-05-31 | 2029-04-01 | No |  | Renewable Power Park developer | Granted | 220 |  | EL-3FCFD, EL-8FDAD, EL-E8969, EL-F7FAC, EL-141A2, EL-10110, EL-B8CEB, EL-7ECBC |  | EL-BC27D
| 468 | NR | Rajasthan | Ntpcrel At Bikaner-IV |  | NTPC Renewable Energy Limited |  | 2200000358 |  |  | 27 |  | 2024-01-10 |  | Solar | 250 | 250 | 250 | [11 empty] | 2023-11-22 | Land Route | 2026-06-30 | 2026-09-01 | No |  | Generator | Granted | 400 |  | EL-57324, EL-FFEB8, EL-1990B, EL-A856A, EL-AC827, EL-CAA1E, EL-8F215, EL-C3D72, EL-81725, EL-95F93, EL-3535F, EL-4C59F, EL-82E5F, EL-8F19A |  | EL-BBDD5
| 469 | NR | Rajasthan | Fatehgarh-II |  | Acme Cleantech Solutions Private Limited |  | 2200000387 |  |  | 27 |  | 2024-01-10 |  | Solar | 600 |  | 600 | [11 empty] | 2023-11-29 | Land BG route | 2026-03-31 |  |  |  | Generator | Applied
| 470 | NR | Rajasthan | Fatehgarh-II |  | Acme Cleantech Solutions Private Limited |  | 2200000396 |  |  | 27 |  | 2024-01-10 |  | Hybrid | 250 |  |  |  | 250 | [9 empty] | 2023-11-30 | LOA (SJVN) | 2026-03-31 |  |  |  | Generator | Applied
| 471 | NR | Rajasthan | Bikaner-III |  | Avaada RJbikaner Private Limited |  | 2200000254 |  |  | 26 |  | 2023-12-01 |  | Solar | 600 |  | 600 | [11 empty] | 2023-10-03 | Land Route | 2025-03-31 |  |  |  | Generator | Applied
| 472 | NR | Rajasthan | Bhadla-III |  | Renew Solar (Shakti Six) Private Limited |  | 2200000275 |  |  | 26 |  | 2023-12-01 |  | Solar | 400 |  | 400 | [11 empty] | 2023-10-05 | Land Route | 2026-06-30 |  |  |  | Generator | Applied
| 473 | NR | Rajasthan | Barmer-I |  | Anboto Solar Private Limited |  | 2200000281 |  |  | 26 |  | 2023-12-01 |  | Solar | 250 |  | 250 | [11 empty] | 2023-10-06 | Land BG Route | 2025-11-30 |  |  |  | Generator | Applied
| 474 | NR | Rajasthan | Bhadla-III |  | Malur Renewables Private Limited |  | 2200000266 |  |  | 26 |  | 2023-12-01 |  | Solar | 650 |  | 650 | [11 empty] | 2023-10-06 | Land Route | 2025-05-30 |  |  |  | Renewable Power Park Developer | Applied
| 475 | NR | Rajasthan | Bhadla-III |  | Solarcraft Power India 4 Private Limited |  | 2200000300 |  |  | 26 |  | 2023-12-01 |  | Solar | 50 |  | 50 | [11 empty] | 2023-10-08 | Land Route | 2025-06-16 |  |  |  | Generator | Applied
| 476 | NR | Rajasthan | Barmer-I |  | Juniper Green Energy Private Limited |  | 2200000305 |  |  | 26 |  | 2023-12-01 |  | Solar | 300 |  | 300 | [11 empty] | 2023-10-11 | Land BG Route | 2027-03-31 |  |  |  | Generator | Applied
| 477 | NR | Rajasthan | Bhadla-III |  | Avaada Energy Private Limited |  | 2200000289 |  |  | 26 |  | 2023-12-01 |  | Solar | 300 |  | 300 | [11 empty] | 2023-10-12 | Land BG Route | 2025-11-30 |  |  |  | Generator | Applied
| 478 | NR | Rajasthan | Bhadla-III |  | Renew Solar (Shakti Six) Private Limited |  | 2200000309 |  |  | 26 |  | 2023-12-01 |  | Solar | 585 |  | 585 | [11 empty] | 2023-10-13 | Land Route | 2026-06-30 |  |  |  | Generator | Applied
| 479 | NR | Rajasthan | Bikaner-I |  | AK Renewable Infra Private Limited |  | 2200000284 |  |  | 26 |  | 2023-12-01 |  | Solar | 300 |  | 300 | [11 empty] | 2023-10-13 | Land Route | 2025-06-30 |  |  |  | Generator | Applied
| 480 | NR | Rajasthan | Barmer-I |  | Auxo Sunlight Private Limited |  | 2200000312 |  |  | 26 |  | 2023-12-01 |  | Solar | 300 |  | 300 | [11 empty] | 2023-10-14 | Land BG Route | 2026-09-30 |  |  |  | Generator | Applied
| 481 | NR | Rajasthan | Fatehgarh-IV |  | Avaada Energy Private Limited |  | 2200000290 |  |  | 26 |  | 2023-12-01 |  | Hybrid | 250 |  |  |  | 250 | [9 empty] | 2023-10-17 | Land BG Route | 2025-09-30 |  |  |  | Generator | Applied
| 482 | NR | Rajasthan | Barmer-I |  | Renew Sun Power Private Limited |  | 2200000316 |  |  | 26 |  | 2023-12-01 |  | Solar | 300 |  | 300 | [11 empty] | 2023-10-17 | Land BG Route | 2026-09-30 |  |  |  | Generator | Applied
| 483 | NR | Rajasthan | Ramgarh-I |  | Hazel Hybren Private Limited |  | 2200000327 |  |  | 26 |  | 2023-12-01 |  | Solar | 300 |  | 300 | [11 empty] | 2023-10-20 | Land BG Route | 2026-01-31 |  |  |  | Generator | Applied
| 484 | NR | Rajasthan | Bikaner-III |  | Shudh Solar Power Private Limited |  | 2200000306 |  |  | 26 |  | 2023-12-01 |  | Solar | 250 |  | 250 | [11 empty] | 2023-10-21 | Land Route | 2025-05-31 |  |  |  | Generator | Applied
| 485 | NR | Rajasthan | Bikaner-III |  | NTPC Renewable Energy Limited |  | 2200000308 |  |  | 26 |  | 2023-12-01 |  | Solar | 700 |  | 700 | [11 empty] | 2023-10-21 | Land Route | 2026-03-31 |  |  |  | Generator | Applied
| 486 | NR | Rajasthan | Bikaner-III |  | Hazel Hybren Private Limited |  | 2200000334 |  |  | 26 |  | 2023-12-01 |  | Solar | 300 |  | 300 | [11 empty] | 2023-10-23 | Land BG Route | 2026-01-31 |  |  |  | Generator | Applied
| 487 | NR | Rajasthan | Bikaner-II |  | AM Green Energy Private Limited |  | 2200000319 |  |  | 26 |  | 2023-12-01 |  | Solar | 300 |  | 300 | [11 empty] | 2023-10-23 | Land BG Route | 2025-05-31 |  |  |  | Generator | Applied
| 488 | NR | Rajasthan | Ramgarh-I |  | Furies Solren Private Limited |  | 2200000333 |  |  | 26 |  | 2023-12-01 |  | Solar | 300 |  | 300 | [11 empty] | 2023-10-27 | Land BG Route | 2026-01-31 |  |  |  | Generator | Applied
| 489 | NR | Rajasthan | Barmer-I |  | Gamma Renewables India Project One Private Limited |  | 2200000355 |  |  | 26 |  | 2023-12-01 |  | Solar | 300 |  | 300 | [11 empty] | 2023-10-31 | Land BG Route | 2026-06-01 |  |  |  | Renewable Power Park Developer | Applied
| 490 | NR | Rajasthan | Bhadla-III |  | Solarcraft Power India 4 Private Limited |  | 2200000152 |  |  | 25 |  | 2023-10-31 |  | Solar | 150 | 150 | 150 | [11 empty] | 2023-07-18 | Land Route | 2025-06-16 | 2028-06-30 | No |  | Generator | Granted | 220 |  | EL-CDD2B, EL-BDC29, EL-CE816, EL-90F2A, EL-B8CEB, EL-E1B3D, EL-DD8DD, EL-BE37F, EL-547E5, EL-BBD19, EL-69266
| 491 | NR | Rajasthan | Fatehgarh-IV |  | Renew Solar Power Private Limited |  | 2200000186 |  |  | 25 |  | 2023-10-31 |  | Solar | 300 |  | 300 | [11 empty] | 2023-08-02 | SECI LOA | 2025-06-30 |  |  |  | Generator | Applied
| 492 | NR | Rajasthan | Fatehgarh-IV |  | Renew Solar Power Private Limited |  | 2200000187 |  |  | 25 |  | 2023-10-31 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-08-02 | SECI LOA | 2025-06-30 | 2026-02-28 | Yes |  | Generator | Granted | 400 |  | EL-923E9, EL-A63E4, EL-6EB5E, EL-C1084, EL-0B255, EL-C16AF, EL-5DC81, EL-26050, EL-19650, EL-E0593, EL-9DE74, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-544F8, EL-AE31B, EL-18361, EL-A83CD, EL-32FE8, EL-417DD, EL-A495D, EL-8D20D |  | EL-5C02D
| 493 | NR | Rajasthan | Bikaner-IV |  | NTPC Renewable Energy Limited |  | 2200000179 |  |  | 25 |  | 2023-10-31 |  | Solar | 500 | 500 | 500 | [11 empty] | 2023-08-02 | REMCL LOA | 2025-06-28 | 2026-06-30 | No |  | Generator | Granted | 400 |  | EL-57324, EL-365F9, EL-6DFEE, EL-A1F2C, EL-D487C, EL-E2ECB, EL-16C93, EL-51E8F, EL-32392, EL-73F58, EL-82E5F, EL-8F19A |  | EL-1627C
| 494 | NR | Rajasthan | Barmer-I |  | Eden Renewable Cadet Private Limited |  | 2200000181 |  |  | 25 |  | 2023-10-31 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-08-11 | SECI LOA | 2025-04-26 | 2026-02-28 | Yes |  | Generator | Granted | 220 |  | EL-F1B66, EL-836ED, EL-E0593, EL-C16AF, EL-9DE74, EL-26050, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-544F8, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-EF09B, EL-417DD, EL-A495D, EL-74937 |  | EL-64979
| 495 | NR | Rajasthan | Bikaner-IV |  | Deshraj Solar Energy Private Limited |  | 2200000184 |  |  | 25 |  | 2023-10-31 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-08-11 | Land Route | 2025-06-25 | 2026-06-30 | No |  | Generator | Granted | 220 |  | EL-23514, EL-365F9, EL-6DFEE, EL-A1F2C, EL-D487C, EL-E2ECB, EL-16C93, EL-A475F, EL-32392, EL-73F58, EL-82E5F, EL-8F19A |  | EL-A10F2
| 496 | NR | Rajasthan | Bhadla-III |  | Acme Heergarh Powertech Private Limited |  | 2200000185 |  |  | 25 |  | 2023-10-31 |  | Solar | 50 | 0 | 50 | [11 empty] | 2023-08-14 | Land Route | 2025-06-16 | 2028-06-30 |  |  | Generator | Withdrawn
| 497 | NR | Rajasthan | Bhadla-III |  | Solarcraft Power India 4 Private Limited |  | 2200000192 |  |  | 25 |  | 2023-10-31 |  | Solar | 110 | 110 | 110 | [11 empty] | 2023-08-16 | Land Route | 2025-06-16 | 2028-06-30 | No |  | Generator | Granted | 220 |  | EL-F525F, EL-BDC29, EL-CE816, EL-90F2A, EL-B8CEB, EL-E1B3D, EL-DD8DD, EL-BE37F, EL-547E5, EL-BBD19, EL-69266 |  | EL-8995D
| 498 | NR | Uttar Pradesh | Varanasi-I |  | ACME Urja Two Private Limited |  | 2200000196 |  |  | 25 |  | 2023-10-31 |  | PSP | 600 | 600 | [12 empty] | 2023-08-23 | -- | 2027-01-01 |  |  |  | Pumped Storage | Granted | 400 |  | EL-250F9, EL-7BE5E |  | EL-250F9, EL-7BE5E
| 499 | NR | Rajasthan | Barmer-I |  | Radiant Star Solar Park Private Limited |  | 2200000212 |  |  | 25 |  | 2023-10-31 |  | Solar | 100 | 100 | 100 | [11 empty] | 2023-08-28 | Land Route | 2025-12-31 | 2026-02-28 | Yes |  | Renewable Power Park Developer | Granted | 220 |  | EL-836ED, EL-F1B66, EL-E0593, EL-C16AF, EL-9DE74, EL-26050, EL-0B6FA, EL-0D0CA, EL-7AF76, EL-544F8, EL-8F19A, EL-AE31B, EL-18361, EL-A83CD, EL-32FE8, EL-417DD, EL-A495D, EL-74937 |  | EL-A7D91
| 500 | NR |  | Nallagarh (PG) |  | AD Hydro HEP |  |  |  |  | 24 |  | 2023-09-20 |  |  | 192 | 192 | [14 empty] | Immediately | 2023-10-01 | Yes |  |  | Granted | 220
| 501 | NR | Rajasthan | Bhadla-III |  | Prerak Greentech Solar Private Limited |  | 212100003 | 1671216520154 |  | 23 |  | 2023-08-29 |  |  | 400 | 400 | [14 empty] | 31-Jan-25 | 30-Sep-25 (Interim) |  |  |  | Granted | 220 |  | EL-B3765, EL-BE37F, EL-DD8DD, EL-72AA1, EL-39439, EL-E4EB8, EL-1BF5F |  | EL-C567C
| 502 | NR | Rajasthan | Bikaner-II |  | Amplus Ages Private Limited |  | 1200003624 | 1671556542236 |  | 23 |  | 2023-08-29 |  |  | 62 | 62 | [14 empty] | 31-Oct-23 | 08-Dec-24 |  |  |  | Granted | 220 |  | EL-10D9C, EL-B075D, EL-E173B, EL-95D93, EL-C2590, EL-91E7F, EL-E8A1F, EL-2453D, EL-EF0A0, EL-4535D, EL-92EB7, EL-CBFD4, EL-4C95B, EL-08044, EL-EA661 |  | EL-28995, EL-101A7
| 503 | NR | Rajasthan | Bhadla-III |  | Tepsol Sun Sparkle Private Limited |  | 212100030 | 1672319027575 |  | 23 |  | 2023-08-29 |  |  | 300 | 300 | [14 empty] | 01-Oct-25 | 01-Oct-25 (Interim) |  |  |  | Granted | 220 |  | EL-6FD9F, EL-BE37F, EL-DD8DD, EL-72AA1, EL-39439, EL-E4EB8, EL-1BF5F |  | EL-1DCA8
| 504 | NR |  | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003827 | 200003910 |  | 23 |  | 2023-08-29 |  |  | 150 | 150 | [14 empty] | 30-Jun-25 | 30-Jun-25 (Interim) |  |  |  | Granted | 400 |  | EL-B3765, EL-BE37F, EL-DD8DD, EL-72AA1, EL-39439, EL-E4EB8, EL-1BF5F |  | EL-C567C
| 505 | NR |  | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 1200003910 | 200003958 |  | 23 |  | 2023-08-29 |  |  | 150 | 150 | [14 empty] | 30-Jun-26 (Revised to 31- Mar-26) | 31-Mar-26 (Interim) |  |  |  | Granted | 400 |  | EL-B3765, EL-BE37F, EL-DD8DD, EL-72AA1, EL-39439, EL-E4EB8, EL-1BF5F |  | EL-C567C
| 506 | NR | Rajasthan | Bhadla-III |  | Juniper Green Beta Pvt Ltd |  | 212100027 | 412100012 |  | 23 |  | 2023-08-29 |  |  | 150 | 150 | [14 empty] | 30-Jun-25 | 30-Sep-25 (Interim) |  |  |  | Granted | 220 |  | EL-81C54, EL-BE37F, EL-DD8DD, EL-72AA1, EL-39439, EL-E4EB8, EL-1BF5F |  | EL-7B912
| 507 | NR | Rajasthan | Bhadla-III |  | Juniper Green Beta Pvt Ltd |  | 312100013 | 412100013 |  | 23 |  | 2023-08-29 |  |  | 100 | 100 | [14 empty] | 31-Dec-25 | 31-Dec-25 (Interim) |  |  |  | Granted | 220 |  | EL-81C54, EL-BE37F, EL-DD8DD, EL-72AA1, EL-39439, EL-E4EB8, EL-1BF5F |  | EL-7B912
| 508 | NR |  | Fatehgarh-III |  | Azure Power India Pvt. Ltd. |  | 1200002814 | 1200003681 |  | 22 |  | 2023-08-21 |  |  | 333 | 0 | [19 empty] | Withdrawn
| 509 | NR |  | Fatehgarh-II |  | Azure Power India Pvt. Ltd. |  | 1200002400 | 1200003677 |  | 22 |  | 2023-08-21 |  |  | 500 | 0 | [19 empty] | Withdrawn
| 510 | NR |  |  |  | Renew Surya Roshni Pvt. Ltd. |  | 412100023 | 412100023 |  | 22 |  | 2023-08-21 |  |  |  | 0 | [19 empty] | Withdrawn
| 511 | NR |  |  |  | ReNew Surya Aayan Pvt. Ltd. |  | 412100022 | 412100022 |  | 22 |  | 2023-08-21 |  |  |  | 0 | [19 empty] | Withdrawn
| 512 | NR |  |  |  | ReNew Surya Vihaan Pvt. Ltd. |  | 412100021 | 412100021 |  | 22 |  | 2023-08-21 |  |  |  | 0 | [19 empty] | Withdrawn
| 513 | NR |  |  |  | Tata Power Trading Company Ltd. MTOA Application No. 0513600001 |  |  |  |  | 22 |  | 2023-08-21 |  |  |  | 0 | [19 empty] | Withdrawn
| 514 | NR |  |  |  | Sprng Nirjara Energy Pvt. Ltd. |  | 312100011 | 312100011 |  | 22 |  | 2023-08-21 |  |  | 50 | 0 | [19 empty] | Withdrawn
| 515 | NR |  |  |  | Sprng Nirjara Energy Pvt. Ltd. |  | 1670102829414 |  |  | 22 |  | 2023-08-21 |  |  | 50 | 0 | [19 empty] | Withdrawn
| 516 | NR |  |  |  | Rajasthan Solar Park Development Company Ltd. |  | 1200002151 | 1200000913 |  | 22 |  | 2023-08-21 |  |  | 925 | 925 | [15 empty] | 2023-10-01 | Yes |  |  | Granted
| 517 | NR |  |  |  | Adani Renewable Energy Park Rajasthan Ltd |  | 1200000287 | 1200003348 |  | 22 |  | 2023-08-21 |  |  | 704 | 704 | [15 empty] | 2023-10-01 | Yes |  |  | Granted
| 518 | NR |  | Fatehgarh-III |  | Renew Surya Vihaan Pvt. Ltd. |  | 1200002590 | 1200002567 |  | 22 |  | 2023-08-21 |  |  | 200 | 200 | [14 empty] | 2022-03-31 | 2023-10-01 | Yes |  |  | Granted | 220
| 519 | NR |  | Fatehgarh-III |  | Altra Xergi Power Private Limited |  | 1200002637 | 1200002639 |  | 22 |  | 2023-08-21 |  |  | 380 | 380 | [14 empty] | 2022-06-01 | 2023-10-01 | Yes |  |  | Granted | 220
| 520 | NR |  | Fatehgarh-II |  | Adani Renewable Energy Holding Sixteen Pvt. Ltd. |  | 1200002450 | 1200002656 |  | 22 |  | 2023-08-21 |  |  | 180 | 180 | [14 empty] | 2022-02-17 | 2023-10-01 | Yes |  |  | Granted | 220
| 521 | NR |  | Fatehgarh-III |  | Adani Renewable Energy Holding Seventeen Private Limited |  | 1200002635 | 1200002789 |  | 22 |  | 2023-08-21 |  |  | 600 | 600 | [14 empty] | 2022-06-01 | 2023-10-01 | Yes |  |  | Granted | 220
| 522 | NR | Rajasthan | Bikaner-I |  | Tata Power Green Energy Ltd. |  | 1200002728 | 1200002804 |  | 22 |  | 2023-08-21 |  |  | 225 | 225 | [14 empty] | 2023-07-26 | 2023-10-01 | Yes |  |  | Granted | 220
| 523 | NR |  | Fatehgarh-III |  | ReNew Surya Vihaan Private Limited |  | 1200002695 | 1200002783 |  | 22 |  | 2023-08-21 |  |  | 100 | 100 | [14 empty] | 2022-07-30 | 2023-10-01 | Yes |  |  | Granted | 220
| 524 | NR |  | Fatehgarh-III |  | ReNew Surya Aayan Private Limited |  | 1200002692 | 1200002782 |  | 22 |  | 2023-08-21 |  |  | 300 | 300 | [14 empty] | 2022-07-30 | 2023-10-01 | Yes |  |  | Granted | 220
| 525 | NR | Rajasthan | Bikaner-I |  | Avikiran Surya India Private Limited |  | 1200002642 | 1200002883 |  | 22 |  | 2023-08-21 |  |  | 100 | 100 | [14 empty] | 2023-07-26 | 2023-10-01 | Yes |  |  | Granted | 220
| 526 | NR |  | Fatehgarh-II |  | Eden Renewable Passy Private Limited |  | 1200002629 | 1200002890 |  | 22 |  | 2023-08-21 |  |  | 300 | 300 | [14 empty] | 2022-05-28 | 2023-10-01 | Yes |  |  | Granted | 220
| 527 | NR |  | Fatehgarh-II |  | NTPC Ltd. |  | 1200002339 | 1200002903 |  | 22 |  | 2023-08-21 |  |  | 105.83 | 105.83 | [14 empty] | 2022-07-29 | 2023-10-01 | Yes |  |  | Granted | 220 |  | EL-4C6E2
| 528 | NR | Rajasthan | Bhadla-II |  | NTPC Ltd. |  | 1200002340 | 1200002904 |  | 22 |  | 2023-08-21 |  |  | 176.375 | 176.375 | [14 empty] | 2021-12-29 | 2023-10-01 | Yes |  |  | Granted | 400
| 529 | NR | Rajasthan | Bikaner-I |  | Avaada Energy Private Limited |  | 1200002775 | 1200002941 |  | 22 |  | 2023-08-21 |  |  | 240 | 240 | [14 empty] | 2022-04-05 | 2023-10-01 | Yes |  |  | Granted
| 530 | NR | Rajasthan | Bhadla-II |  | Avaada Energy Pvt. Ltd. |  | 1200002636 | 1200002962 |  | 22 |  | 2023-08-21 |  |  | 320 | 320 | [14 empty] | 2022-07-19 | 2023-10-01 | Yes |  |  | Granted | 220
| 531 | NR |  | Fatehgarh-III |  | ABC Renewable Energy Pvt. Ltd. |  | 1200002699 | 1200003096 |  | 22 |  | 2023-08-21 |  |  | 400 | 400 | [14 empty] | 2022-04-04 | 2023-10-01 | Yes |  |  | Granted | 220
| 532 | NR | Rajasthan | Bhadla-II |  | NTPC Ltd. |  | 1200002501 | 1200003110 |  | 22 |  | 2023-08-21 |  |  | 211.65 | 211.65 | [14 empty] | 2022-05-28 | 2023-10-01 | Yes |  |  | Granted | 220
| 533 | NR | Rajasthan | Bhadla-II |  | NTPC Ltd. |  | 1200002483 | 1200003109 |  | 22 |  | 2023-08-21 |  |  | 211.65 | 211.65 | [14 empty] | 2022-07-27 | 2023-10-01 | Yes |  |  | Granted | 400
| 534 | NR | Rajasthan | Bhadla-II |  | NTPC Ltd. |  | 1200002483 | 1200003120 |  | 22 |  | 2023-08-21 |  |  | 88.35 | 88.35 | [14 empty] | 2021-09-01 | 2023-10-01 | Yes |  |  | Granted | 400
| 535 | NR | Rajasthan | Bhadla-II |  | NTPC Ltd. |  | 1200002340 | 1200003122 |  | 22 |  | 2023-08-21 |  |  | 73.625 | 73.625 | [14 empty] | 2022-05-28 | 2023-10-01 | Yes |  |  | Granted | 400
| 536 | NR | Rajasthan | Bhadla-II |  | NTPC Ltd. |  | 1200002501 | 1200003121 |  | 22 |  | 2023-08-21 |  |  | 88.35 | 88.35 | [14 empty] | 2022-05-28 | 2023-10-01 | Yes |  |  | Granted | 220
| 537 | NR |  | Fatehgarh-II |  | NTPC Ltd. |  | 1200002339 | 1200003124 |  | 22 |  | 2023-08-21 |  |  | 44.17 | 44.17 | [14 empty] | 2022-07-29 | 2023-10-01 | Yes |  |  | Granted | 220 |  | EL-4C6E2
| 538 | NR |  | Fatehgarh-II |  | NTPC Ltd. |  | 1200002497 | 1200003248 |  | 22 |  | 2023-08-21 |  |  | 63.5 | 63.5 | [14 empty] | 2022-02-19 | 2023-10-01 | Yes |  |  | Granted | 220
| 539 | NR |  | Fatehgarh-III |  | Renew Surya Roshni Private Limited |  | 1200002628 | 1200003269 |  | 22 |  | 2023-08-21 |  |  | 400 | 400 | [14 empty] | 2022-12-31 | 2023-10-01 | Yes |  |  | Granted | 220
| 540 | NR |  | Fatehgarh-II |  | NTPC Ltd. |  | 1200002497 | 1200003314 |  | 22 |  | 2023-08-21 |  |  | 26.5 | 26.5 | [14 empty] | 2022-02-19 | 2023-10-01 | Yes |  |  | Granted | 220
| 541 | NR | Rajasthan | Bhadla-II |  | ABC Solar (India) Private Limited |  | 1200002359 | 1200003357 |  | 22 |  | 2023-08-21 |  |  | 300 | 300 | [14 empty] | 2022-04-15 | 2023-10-01 | Yes |  |  | Granted | 220
| 542 | NR |  | Fatehgarh-IV |  | AMP Energy Green Pvt. Ltd. |  | 1200003022 | 1200003416 |  | 22 |  | 2023-08-21 |  |  | 130 | 130 | [14 empty] | 2023-01-19 | 2023-10-01 | Yes |  |  | Granted | 220
| 543 | NR | Rajasthan | Bhadla-II |  | ACME Solar Holdings Private Limited |  | 1200002471 | 1200003505 |  | 22 |  | 2023-08-21 |  |  | 300 | 300 | [14 empty] | 2022-04-15 | 2023-10-01 | Yes |  |  | Granted | 220
| 544 | NR |  | Fatehgarh-IV |  | ABC Renewable Energy Private Limited |  | 1200003002 | 1200003531 |  | 22 |  | 2023-08-21 |  |  | 380 | 380 | [14 empty] | 2023-11-30 | 2025-03-31 | Yes |  |  | Granted | 220
| 545 | NR | Rajasthan | Bikaner-I |  | The Tata Power Company Limited |  | 1200003027 | 1200003583 |  | 22 |  | 2023-08-21 |  |  | 110 | 110 | [14 empty] | 2023-11-11 | 2024-03-31 | Yes |  |  | Granted | 220
| 546 | NR | Rajasthan | Bhadla-II |  | Azure Power India Private Limited |  | 1200002401 | 1200003586 |  | 22 |  | 2023-08-21 |  |  | 267 | 267 | [14 empty] | 2023-12-31 | 2024-09-30 | Yes |  |  | Granted | 400
| 547 | NR | Rajasthan | Bhadla-II |  | Azure Power India Private Limited |  | 1200002401 | 200002403 |  | 22 |  | 2023-08-21 |  |  | 333 | 333 | [14 empty] | 2023-12-31 | 2024-09-30 | Yes |  |  | Granted | 400
| 548 | NR | Rajasthan | Bikaner-I |  | Avikiran Surya India Private Limited |  | 1200002642 | 1200003651 |  | 22 |  | 2023-08-21 |  |  | 200 | 200 | [14 empty] | 2023-07-26 | 2023-10-01 | Yes |  |  | Granted | 220
| 549 | NR | Rajasthan | Ramgarh-I |  | Adani Renewable Energy Holding Four Ltd. |  | 1200002432 | 1200003689 |  | 22 |  | 2023-08-21 |  |  | 500 | 500 | [14 empty] | 2023-10-13 | 2025-03-31 | Yes |  |  | Granted | 400
| 550 | NR |  | Fatehgarh-II |  | Adani Renewable Energy Holding Four Limited |  | 1200002430 | 1200003684 |  | 22 |  | 2023-08-21 |  |  | 500 | 500 | [14 empty] | 2024-12-01 | 2024-09-30 | Yes |  |  | Granted | 220
| 551 | NR | Rajasthan | Bhadla-II |  | Adani Renewable Energy Holding Four Ltd. |  | 1200002428 | 1200003685 |  | 22 |  | 2023-08-21 |  |  | 500 | 500 | [14 empty] | 2024-12-01 | 2024-09-30 | Yes |  |  | Granted | 400
| 552 | NR | Rajasthan | Bikaner-II |  | ACME Solar Holdings Private Limited |  | 1200003683 | 1200003829 |  | 22 |  | 2023-08-21 |  |  | 300 | 300 | [14 empty] | 2024-05-15 | 2024-05-15 | Yes |  |  | Granted | 220
| 553 | NR | Rajasthan | Bhadla-II |  | Azure Power India Private Limited |  | 1200002403 | 1200003843 |  | 22 |  | 2023-08-21 |  |  | 50 | 50 | [14 empty] | 2024-03-31 | 2024-09-30 | Yes |  |  | Granted | 400
| 554 | NR |  | Fatehgarh-III |  | ReNew Dinkar Jyoti Private Limited |  | 1200003813 | 1200003879 |  | 22 |  | 2023-08-21 |  |  | 100 | 100 | [14 empty] | 2024-06-30 | L St-II:1200003813 (100 MW) TA:1200003879 (100 MW) S ISTS : 400 kV(1 no.). chedule: ISTS bay to be taken up for implementation. Schedule to be informed by Renew in view of Reallocation at 400 kV bay at Fatehgarh-III PS(Sec-2) |  |  |  | Granted | 400
| 555 | NR | Rajasthan | Bhadla-II |  | AMP Energy Green Private Limited |  | 1200002676 | 1200003882 |  | 22 |  | 2023-08-21 |  |  | 100 | 100 | [14 empty] | 2024-03-31 | 2024-09-30 | Yes |  |  | Granted | 220
| 556 | NR |  | Fatehgarh-III |  | IB Vogt Solar Seven Private Limited |  | 1200002700 | 1200003931 |  | 22 |  | 2023-08-21 |  |  | 300 | 300 | [14 empty] | 2024-06-30 | 2025-03-31 | Yes |  |  | Granted | 220
| 557 | NR | Rajasthan | Bikaner-I |  | Ayana Renewable Power Three Private Limited |  | 1200002986 | 1200003933 |  | 22 |  | 2023-08-21 |  |  | 300 | 300 | [14 empty] | 2024-05-15 | 2024-05-15 | Yes |  |  | Granted
| 558 | NR | Rajasthan | Bikaner-II |  | SJVN Limited |  | 1200003559 | 1200003937 |  | 22 |  | 2023-08-21 |  |  | 1000 | 1000 | [14 empty] | 2024-05-15 | 2024-05-15 | Yes |  |  | Granted | 400
| 559 | NR | Rajasthan | Bikaner-II |  | ReNew Dinkar Urja Pvt. Ltd. |  | 1200003380 | 1200003935 |  | 22 |  | 2023-08-21 |  |  | 200 | 200 | [14 empty] | 2024-05-15 | 2024-05-15 | Yes |  |  | Granted | 220
| 560 | NR |  | Fatehgarh-II |  | Eden Renewable Bercy Private Limited |  | 1200002688 | 1200003947 |  | 22 |  | 2023-08-21 |  |  | 300 | 300 | [14 empty] | 2024-03-31 | 2024-09-30 | Yes |  |  | Granted | 220
| 561 | NR |  | Fatehgarh-III |  | Azure Power India Private Limited |  | 1200003532 | 412100002 |  | 22 |  | 2023-08-21 |  |  | 100 | 100 | [14 empty] | 2024-12-31 | 2025-03-31 | Yes |  |  | Granted
| 562 | NR | Rajasthan | Bikaner-II |  | Onevolt Energy Private Limited |  | 1200003626 | 412100004 |  | 22 |  | 2023-08-21 |  |  | 62 | 62 | [14 empty] | 2024-05-15 | 2024-05-15 | Yes |  |  | Granted | 220
| 563 | NR | Rajasthan | Bikaner-II |  | NHPC Ltd. |  | 1200003915 | 412100006 |  | 22 |  | 2023-08-21 |  |  | 300 | 300 | [14 empty] | 2024-05-15 | 2024-05-15 | Yes |  |  | Granted | 220
| 564 | NR |  | Fatehgarh-III |  | XL Xergi Power Pvt. Ltd. |  | 1200002847 | 412100007 |  | 22 |  | 2023-08-21 |  |  | 200 | 200 | [14 empty] | 2024-12-31 | 2025-03-31 | Yes |  |  | Granted | 220
| 565 | NR | Rajasthan | Bikaner-II |  | Juniper Green Cosmic Private Limited |  | 1200003740 | 412100008 |  | 22 |  | 2023-08-21 |  |  | 100 | 100 | [14 empty] | 2025-01-31 | 2025-01-31 | Yes |  |  | Granted | 220
| 566 | NR | Rajasthan | Bikaner-II |  | Grian Energy Private Limited |  | 1200003625 |  |  | 22 |  | 2023-08-21 |  |  | 100 | 100 | [14 empty] | 2024-12-08 | 2024-12-08 | Yes |  |  | Granted | 220
| 567 | NR |  | Fatehgarh-IV |  | Juniper Green Stellar Pvt. Ltd. |  | 312100010 | 12100012 |  | 22 |  | 2023-08-21 |  |  | 65 | 65 | [14 empty] | 2027-06-30 | 3 L St-II: 312100010 (45 MW) (5 MW out of 45 MW) 12100012 (60 MW) TA:412100011 (65 MW) B E ISTS : 220 kV(1 no.). ay is part of Ph-III (Part-A1 scheme) xpected: Feb’25 |  |  |  | Granted | 220
| 568 | NR | Rajasthan | Fatehgarh-IV |  | BN Hybrid Power-1 Private Limited |  | 2200000102 |  |  | 21 |  | 2023-07-31 |  | Hybrid | 180.8 |  | 180.8 | 70.8 | [10 empty] | 2023-06-01 | Land BG Route | 2025-06-30 |  |  |  | Generator | Applied
| 569 | NR | Rajasthan | Fatehgarh-IV |  | BN Dispatchable-1 Private Limited |  | 2200000103 |  |  | 21 |  | 2023-07-31 |  | Hybrid | 300 |  | 150 | 150 | [10 empty] | 2023-06-01 | Land BG Route | 2025-06-30 |  |  |  | Generator | Applied
| 570 | NR | Rajasthan | Fatehgarh-IV |  | Avaada Energy Private Limited |  | 2200000077 |  |  | 21 |  | 2023-07-31 |  | Hybrid | 50 |  | 25 | 25 | [10 empty] | 2023-06-05 | Land BG Route | 2025-09-30 |  |  |  | Generator | Applied
| 571 | NR | Rajasthan | Bhadla-III |  | Sprng Energy Private Limited |  | 2200000112 |  |  | 21 |  | 2023-07-31 |  | Solar | 200 |  | 200 | [11 empty] | 2023-06-13 | Land BG Route | 2025-06-30 |  |  |  | Generator | Applied
| 572 | NR | Rajasthan | Bikaner-III |  | MRS Buildvision Private Limited |  | 2200000098 |  |  | 21 |  | 2023-07-31 |  | Solar | 1000 |  | 1000 | [11 empty] | 2023-06-14 | Land Route | 2025-06-30 |  |  |  | Renewable Power Park developer | Applied
| 573 | NR | Rajasthan | Fatehgarh-IV |  | Sprng Energy Private Limited |  | 2200000116 |  |  | 21 |  | 2023-07-31 |  | Solar | 400 |  | 400 | [11 empty] | 2023-06-16 | Land BG Route | 2025-12-31 |  |  |  | Renewable Power Park developer | Applied
| 574 | NR | Rajasthan | Bikaner-III |  | Sunbreeze Renewables Nine Private Limited |  | 2200000111 |  |  | 21 |  | 2023-07-31 |  | Solar | 400 |  | 400 | [11 empty] | 2023-06-22 | Land Route | 2025-05-01 |  |  |  | Renewable Power Park developer | Applied
| 575 | NR | Rajasthan | Bhadla-II |  | Renew Solar Power Private Limited |  | 2200000110 |  |  | 21 |  | 2023-07-31 |  | Solar | 400 |  | 400 | [11 empty] | 2023-06-25 | LOI | 2025-01-02 |  |  |  | Generator | Applied
| 576 | NR | Rajasthan | Fatehgarh-III |  | ABREL (RJ) Projects Limited |  | 2200000140 |  |  | 21 |  | 2023-07-31 |  | Solar | 260 |  | 260 | [11 empty] | 2023-06-29 | Land BG Route | 2025-05-31 |  |  |  | Captive generating plant | Applied
| 577 | NR | Rajasthan | Fatehgarh-IV |  | Helia Energy Park Private Limited |  | 2200000120 |  |  | 21 |  | 2023-07-31 |  | Solar | 100 |  | 100 | [11 empty] | 2023-06-30 | Land Route | 2025-12-31 |  |  |  | Renewable Power Park developer | Applied
| 578 | NR | Rajasthan | Fatehgarh-III |  | Teq Green Power XV Private Limited |  | 2200000123 |  |  | 21 |  | 2023-07-31 |  | Solar | 95 |  | 95 | [11 empty] | 2023-06-30 | Land BG Route | 2026-01-01 |  |  |  | Renewable Power Park developer | Applied
| 579 | NR | Rajasthan | Bhadla-III |  | Frugal Energy Private Limited |  | 2200000118 |  |  | 21 |  | 2023-07-31 |  | Solar | 250 |  | 250 | [11 empty] | 2023-06-30 | Land Route | 2025-06-15 |  |  |  | Renewable Power Park developer | Applied
| 580 | NR | Rajasthan | Fatehgarh-IV |  | Green Infra Clean Wind Technology Limited |  | 2200000054 |  |  | 20 |  | 2023-06-30 |  | Solar | 300 |  | 300 | [11 empty] | 2023-05-15 | Land Route | 2025-06-01 |  |  |  | Generator | Applied
| 581 | NR | Rajasthan | Fatehgarh-IV |  | Utkrrisht Solar Energy Private Limited |  | 2200000067 |  |  | 20 |  | 2023-06-30 |  | Solar | 300 |  | 300 | [11 empty] | 2023-05-26 | Land Route | 2026-04-01 |  |  |  | Renewable Power Park developer | Applied
| 582 | NR | Rajasthan | Bikaner-II |  | Juniper Green Cosmic Private Limited |  | 2200000073 |  |  | 20 |  | 2023-06-30 |  | Solar | 150 |  | 150 | [11 empty] | 2023-05-24 | Land Route | 2025-01-31 |  |  |  | Generator | Applied
| 583 | NR | Rajasthan | Fatehgarh-IV |  | Sprng Pavana Urja Private Limited |  | 2200000034 |  |  | 20 |  | 2023-06-30 |  | Solar | 150 |  | 150 | [11 empty] | 2023-05-04 | Land Route | 2026-12-31 |  |  |  | Generator | Applied
| 584 | NR | Rajasthan | Bhadla-III |  | Project Nine Renewable Power Private Limited |  | 2200000037 |  |  | 20 |  | 2023-06-30 |  | Solar | 450 |  | 450 | [11 empty] | 2023-05-05 | Land BG Route | 2025-06-11 |  |  |  | Generator | Applied
| 585 | NR | Rajasthan | Bhadla-III |  | Juniper Green India Six Private Limited |  | 2200000062 |  |  | 20 |  | 2023-06-30 |  | Solar | 300 |  | 300 | [11 empty] | 2023-05-22 | Land BG Route | 2027-12-31 |  |  |  | Renewable Power Park developer | Applied
| 586 | NR | Rajasthan | Fatehgarh-IV |  | Juniper Green Stellar Private Limited |  | 2200000063 |  |  | 20 |  | 2023-06-30 |  | Solar | 300 |  | 300 | [11 empty] | 2023-05-22 | Land BG Route | 2026-12-31 |  |  |  | Renewable Power Park developer | Applied
| 587 | NR | Rajasthan | Bhadla-III |  | Sprng Urja Private Limited |  | 2200000060 |  |  | 20 |  | 2023-06-30 |  | Solar | 200 |  | 200 | [11 empty] | 2023-05-10 | Land BG Route | 2027-12-31 |  |  |  | Generator | Applied
| 588 | NR | Rajasthan | Fatehgarh-IV |  | Sprng Akshaya Urja Private Limited |  | 2200000065 |  |  | 20 |  | 2023-06-30 |  | Solar | 100 |  | 100 | [11 empty] | 2023-05-18 | LOA or PPA | 2025-06-30 |  |  |  | Generator | Applied
| 589 | NR | Rajasthan | Fatehgarh-IV |  | BN Hybrid Power-1 Private Limited |  | 2200000003 |  |  | 19 |  | 2023-05-31 |  | Hybrid | 119.2 |  | 40 | 79.2 | [10 empty] | 2023-04-14 | Land Route | 2025-06-30 |  |  |  | Generator | Applied
| 590 | NR | Rajasthan | Fatehgarh-IV |  | Sprng Power Private Limited |  | 2200000024 |  |  | 19 |  | 2023-05-31 |  | Solar | 400 |  | 400 | [11 empty] | 2023-04-17 | Land BG Route | 2025-12-31 |  |  |  | Generator | Applied
| 591 | NR | Rajasthan | Fatehgarh-III |  | Renew Surya Vihaan Private Limited (Enhancement) |  | 2200000027 |  |  | 19 |  | 2023-05-31 |  | Solar | 10 |  | 10 | [11 empty] | 2023-04-18 | Land Route | 2023-10-31 |  |  |  | Generator | Applied
| 592 | NR | Rajasthan | Bikaner-III |  | ACME Cleantech Solutions Private Limited |  | 2200000008 |  |  | 19 |  | 2023-05-31 |  | Solar | 300 |  | 300 | [11 empty] | 2023-04-18 | Land Route | 2025-05-31 |  |  |  | Generator | Applied
| 593 | NR | Rajasthan | Fatehgarh-IV |  | Sprng Pavana Urja Private Limited (Enhancement) |  | 2200000018 |  |  | 19 |  | 2023-05-31 |  | Solar | 100 |  | 100 | [11 empty] | 2023-04-26 | Land BG Route | 2025-12-31 |  |  |  | Generator | Applied
| 594 | NR | Rajasthan | Bikaner-III |  | Avaada RJBikaner Private Limited |  | 2200000013 |  |  | 19 |  | 2023-05-31 |  | Solar | 50 |  | 50 | [11 empty] | 2023-04-27 | Land Route | 2025-03-31 |  |  |  | Generator | Applied
| 595 | NR | Rajasthan | Fatehgarh-IV |  | Serentica Renewables India Private Limited |  | 2200000020 |  |  | 19 |  | 2023-05-31 |  | Solar | 300 |  | 300 | [11 empty] | 2023-04-29 | Land Route | 2025-03-31 |  |  |  | Generator | Applied
| 596 | NR | Rajasthan | Line Connectivity Is Planned To 220 |  | #Sprng Akshaya Urja Private Limited |  | 2200000040 |  |  | 19 |  | 2023-05-31 |  | Solar | 75 |  | 75 | [11 empty] | 2023-04-29 | LOA from REMCL | 2025-06-30 |  |  |  | Generator | Applied
| 597 | NR | Rajasthan | Bikaner-III |  | Proteus Energy Private Limited |  |  | 112100062 |  |  | 18 |  | 2023-04-28 | Solar | 300 |  | 300 | [11 empty] | 2023-03-10 |  | 2025-03-31 |  |  |  | Renewable Power Park Developer | Applied
| 598 | NR | Rajasthan | Bikaner-III |  | Proteus Energy Private Limited |  | 212100042 |  |  | 18 |  | 2023-04-28 |  | Solar | 217 |  | 217 | [11 empty] | 2023-03-10 |  | 2025-03-31 |  |  |  | Renewable Power Park Developer | Applied
| 599 | NR | Rajasthan | Fatehgarh-IV |  | Tepsol Saur Urja Private Limited |  | 212100043 |  |  | 18 |  | 2023-04-28 |  | Solar | 300 |  | 300 | [11 empty] | 2023-03-31 |  | 2025-12-31 |  |  |  | Renewable Power Park Developer | Applied
| 600 | NR | Rajasthan | Bikaner-III |  | Rajasthan Solarpark Development Company Limited |  |  | 112100068 |  |  | 18 |  | 2023-04-28 | Solar | 450 |  | 450 | [11 empty] | 2023-04-07 |  | 2024-03-30 |  |  |  | Renewable Power Park Developer | Applied
| 601 | NR | Rajasthan | Bikaner-III |  | Rajasthan Solarpark Development Company Limited |  |  | 112100070 |  |  | 18 |  | 2023-04-28 | Solar | 1000 |  | 1000 | [11 empty] | 2023-04-12 |  | 2024-02-23 |  |  |  | Renewable Power Park Developer | Applied
| 602 | NR | Rajasthan | Bhadla-III |  | Juniper Green Beta Private Limited |  | 312100021 |  |  | 18 |  | 2023-04-28 |  | Solar | 40 |  | 40 | [11 empty] | 2023-04-12 |  | 2025-06-30 |  |  |  | Generator | Applied
| 603 | NR | Rajasthan | Fatehgarh-IV |  | Cannice Renewables Energy Private Limited |  | 312100019 |  |  | 18 |  | 2023-04-28 |  | Hybrid | 90 |  | 70 | 20 | [10 empty] | 2023-04-12 |  | 2025-01-31 |  |  |  | Generator [Solar: 70MW, Wind: 20MW] | Applied
| 604 | NR | Rajasthan | Bikaner-II (Nr) |  | Serentica Renewables India Private Limited |  |  | 412100014 |  |  | 18 |  | 2023-04-28 |  | 31 | [13 empty] | 2023-03-17 |  | 2049-07-30 |  |  |  |  | Applied
| 605 | NR | Uttar Pradesh | Aligarh , Up (Nr) |  | THDC India Limited (Khurja STPP) |  |  | 413600001 |  |  | 18 |  | 2023-04-28 |  | 30 | [13 empty] | 2023-03-24 |  | 2049-04-29 |  |  |  |  | Applied
| 606 | NR | Rajasthan | Bhadla-III (Nr) |  | J uniper Green Beta Private Limited |  |  | 412100027 |  |  | 18 |  | 2023-04-28 |  | 31 | [13 empty] | 2023-04-12 |  | 2051-03-31 |  |  |  |  | Applied
| 607 | NR | Rajasthan | Fatehgarh -III |  | JSW Renew Energy Five Limited |  |  | 112100048 |  |  | 17 |  | 2023-03-31 | BESS | 250 | 250 | [5 empty] | 250 | [6 empty] | 2023-02-14 |  | 2024-10-15 | 2024-10-15 | Yes |  | Project based on Standalone Storage Source | Granted
| 608 | NR | Rajasthan | Fatehgarh -III |  | JSW Renew Energy Five Limited |  |  | 112100052 |  |  | 17 |  | 2023-03-31 | BESS | 250 | 250 | [5 empty] | 250 | [6 empty] | 2023-02-14 |  | 2024-10-15 | 2024-10-15 | Yes |  | Project based on Standalone Storage Source | Granted
| 609 | NR | Rajasthan | Bikaner -III |  | **MRS Buildvision Private Limited |  |  | 112100053 |  |  | 17 |  | 2023-03-31 | Solar | 1000 | 1000 | 1000 | [11 empty] | 2023-02-16 |  | 2025-03-31 | 2025-03-31 | Yes |  | Renewable Power Park Developer | Granted
| 610 | NR | Rajasthan | Fatehgarh -IV |  | *Radiant Star Solar Park Private Limited |  | 212100037 | 112100046 |  | 17 |  | 2023-03-31 |  | Solar | 200 | 200 | 200 | [11 empty] | 2023-02-13 |  | 2024-12-31 | 2024-12-31 | Yes |  | Renewable Power Park Developer | Granted
| 611 | NR | Rajasthan | Fatehgarh -IV |  | *Helia Energy Park Private Limited |  | 212100035 | 112100043 |  | 17 |  | 2023-03-31 |  | Solar | 200 | 200 | 200 | [11 empty] | 2023-02-13 |  | 2024-12-31 | 2024-12-31 | Yes |  | Renewable Power Park Developer | Granted
| 612 | NR | Rajasthan | Fatehgarh -III |  | ##JSW Renew Energy Five Limited |  | 212100039 | 112100048 |  | 17 |  | 2023-03-31 |  | BESS | 250 | 250 | [5 empty] | 250 | [6 empty] | 2023-02-14 |  | 2024-10-15 | 2024-10-15 | Yes |  | Project based on Standalone Storage Source | Granted
| 613 | NR | Rajasthan | Fatehgarh -III |  | ##JSW Renew Energy Five Limited |  | 212100040 | 112100052 |  | 17 |  | 2023-03-31 |  | BESS | 250 | 250 | [5 empty] | 250 | [6 empty] | 2023-02-14 |  | 2024-10-15 | 2024-10-15 | Yes |  | Project based on Standalone Storage Source | Granted
| 614 | NR | Rajasthan | Bikaner-II, Rajasthan |  | Prerak Greentech Private Limited |  | 1200003770 | 412100025 |  |  | 17 |  | 2023-03-31 |  | 226 | 226 | [12 empty] | 2023-02-28 |  | 2024-01-01 | 2024-01-01 | Yes |  |  | Granted
| 615 | NR | Rajasthan | Bikaner-II, Rajasthan |  | Amplus Ages Private Limited |  | 1200003624 | 1671556542236 |  |  | 17 |  | 2023-03-31 |  | 62 | 62 | [12 empty] | 2022-12-20 |  | 2023-10-31 | 2023-10-31 | Yes |  |  | Granted
| 616 | NR | Rajasthan | Bhadla-III, Rajasthan |  | Tepsol Sun Sparkle Private Limited |  | 212100030 | 1672319027575 |  |  | 17 |  | 2023-03-31 |  | 300 | 300 | [12 empty] | 2022-12-29 |  | 2025-10-01 | 2025-10-01 | Yes |  |  | Granted
| 617 | NR | Rajasthan | Fatehgarh-IV, Rajasthan |  | Juniper Green Stellar Private Limited |  | 1200003827 | 412100009 |  |  | 17 |  | 2023-03-31 |  | 150 | 150 | [12 empty] | 2022-12-30 |  | 2025-06-30 | 2025-06-30 | Yes |  |  | Granted
| 618 | NR | Rajasthan | Fatehgarh-IV, Rajasthan |  | Juniper Green Stellar Private Limited |  | 1200003910 | 412100010 |  |  | 17 |  | 2023-03-31 |  | 150 | 150 | [12 empty] | 2022-12-30 |  | 2026-06-30 | 2026-06-30 | No |  |  | Granted
| 619 | NR | Rajasthan | Bhadla-III, Rajasthan |  | Juniper Green Beta Private Limited |  | 212100027 | 412100012 |  |  | 17 |  | 2023-03-31 |  | 150 | 150 | [12 empty] | 2022-12-30 |  | 2025-06-30 | 2025-06-30 | Yes |  |  | Granted
| 620 | NR | Rajasthan | Fatehgarh-III, Rajasthan |  | Renew Surya Aayan Private Limited |  | 1200002692 | 412100022 |  |  | 17 |  | 2023-03-31 |  | 300 | 300 | [12 empty] | 2023-01-31 |  | 2023-09-30 | 2023-09-30 | Yes |  |  | Granted
| 621 | NR | Rajasthan | 100 (Firm) |  | Serentica Renewables India 4 Private Limited |  |  | 431400004 |  |  | 17 |  | 2023-03-31 | [15 empty] | 2023-01-19 |  | Hindustan Zinc Limited, Kankroli S/s, Rajasthan (NR) |  |  |  |  | Granted
| 622 | NR | Rajasthan | 100 (Firm) |  | Serentica Renewables India 4 Private Limited |  |  | 412100015 |  |  | 17 |  | 2023-03-31 | [15 empty] | 2023-01-19 |  | Hindustan Zinc Limited, Kankroli S/s, Rajasthan (NR) |  |  |  |  | Granted
| 623 | NR | Rajasthan | 75 (Ppa |  | Renew Solar Power Private Limited |  |  | 431400006 |  |  | 17 |  | 2023-03-31 | [15 empty] | 2023-02-13 |  | WBSEDCL, West Bengal/ER |  |  |  |  | Granted
| 624 | NR | Rajasthan | 75 Mw (Ppa |  | Renew Solar Power Pvt Ltd. |  |  | 451100014 |  |  | 17 |  | 2023-03-31 | [15 empty] | 2023-02-13 |  | • WBSEDCL(ER): 75 MW |  |  |  |  | Granted
| 625 | NR | Rajasthan | 75 Mw (Ppa |  | Renew Solar Power Pvt Ltd. |  |  | 451100015 |  |  | 17 |  | 2023-03-31 | [15 empty] | 2023-02-13 |  | • WBSEDCL(ER): 75 MW |  |  |  |  | Granted
| 626 | NR | Rajasthan | 100 Mw (Ppa |  | Renew Surya Ojas pvt Ltd. |  |  | 451100016 |  |  | 17 |  | 2023-03-31 | [15 empty] | 2023-02-13 |  | • HPPC (NR): 50 MW • Goa State (WR): 50 MW |  |  |  |  | Granted
| 627 | NR | Rajasthan | 25 (Firm) |  |  |  |  | 440100003 |  |  | 17 |  | 2023-03-31 | [15 empty] | East Central Railways 28-02-2023 |  | East Central Railway, Bihar (ER) – 20MW Delhi (NR) – 5MW |  |  |  |  | Granted
| 628 | NR | Rajasthan | Fatehgarh -IV |  | Serentica Renewables India Private Limited |  |  | 112100033 |  |  | 16 |  | 2023-02-28 | Solar | 500 | 500 | 500 | [11 empty] | 2023-01-11 |  | 2024-12-31 | 2024-12-31 | Yes |  | Generator | Granted
| 629 | NR | Rajasthan | Fatehgarh -IV |  | Serentica Renewables India Private Limited |  |  | 112100044 |  |  | 16 |  | 2023-02-28 | Solar | 500 | 500 | 500 | [11 empty] | 2023-01-30 |  | 2024-12-31 | 2024-12-31 | Yes |  | Generator | Granted
| 630 | NR | Rajasthan | Bikaner-III |  | Deshraj Solar Energy Private Limited |  |  | 112100038 |  |  | 16 |  | 2023-02-28 | Solar | 400 | 400 | 400 | [11 empty] | 2023-01-23 |  | 2025-01-31 | 2025-01-31 | Yes |  | Generator | Granted
| 631 | NR | Rajasthan | Fatehgarh -IV |  | Luceo Solar Private Limited |  |  | 112100039 |  |  | 16 |  | 2023-02-28 | Solar | 100 | 100 | 100 | [11 empty] | 2023-01-26 |  | 2024-12-31 | 2024-12-31 | Yes |  | Generator | Granted
| 632 | NR | Rajasthan | Fatehgarh -IV |  | Helia Energy Park Private Limited |  |  | 112100043 |  |  | 16 |  | 2023-02-28 | Solar | 300 | 300 | 300 | [11 empty] | 2023-01-30 |  | 2024-12-31 | 2024-12-31 | Yes |  | Renewable Power Park Developer | Granted
| 633 | NR | Rajasthan | Bikaner-III |  | Saimaa Solar Private Limited |  |  | 112100041 |  |  | 16 |  | 2023-02-28 | Solar | 400 | 400 | 400 | [11 empty] | 2023-01-31 |  | 2025-01-15 | 2025-01-15 | Yes |  | Generator | Granted
| 634 | NR | Rajasthan | Fatehgarh -IV |  | Radiant Star Solar Park Private Limited |  |  | 112100046 |  |  | 16 |  | 2023-02-28 | Solar | 300 | 300 | 300 | [11 empty] | 2023-01-31 |  | 2024-12-31 | 2024-12-31 | Yes |  | Renewable Power Park Developer | Granted
| 635 | NR | Rajasthan | Ramgarh-I |  | Adani Solar Energy AP Three Limited |  |  | 112100047 |  |  | 16 |  | 2023-02-28 | Solar | 150 | 150 | 150 | [11 empty] | 2023-01-31 |  | 2023-10-03 | 2023-10-03 | Yes |  | Generator | Granted
| 636 | NR | Rajasthan | Ramgarh-I |  | Resco Global Wind Services Private Limited |  |  | 112100040 |  |  | 16 |  | 2023-02-28 | Wind | 500 | 500 |  | 500 | [10 empty] | 2023-01-31 |  | 2025-02-01 | 2025-02-01 | Yes |  | Generator | Granted
| 637 | NR | Rajasthan | Fatehgarh -IV# |  | Khaba Renewable Energy Private Limited (Refer Note-1) |  | 312100017 | 1200003132 |  | 16 |  | 2023-02-28 |  | Solar | 50 | 50 | 50 | [11 empty] | 2023-01-02 |  | 2026-06-30 | 2026-06-30 | No |  | Generator | Granted
| 638 | NR | Rajasthan | Fatehgarh -IV# |  | Serentica Renewables India Private Limited |  | 212100034 | 112100033 |  | 16 |  | 2023-02-28 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-01-11 |  | 2024-12-31 | 2024-12-31 | Yes |  | Generator | Granted
| 639 | NR | Rajasthan | Fatehgarh -IV# |  | Serentica Renewables India Private Limited |  | 212100036 | 112100044 |  | 16 |  | 2023-02-28 |  | Solar | 300 | 300 | 300 | [11 empty] | 2023-01-30 |  | 2024-12-31 | 2024-12-31 | Yes |  | Generator | Granted
| 640 | NR | Rajasthan | Fatehgarh -IV# |  | Luceo Solar Private Limited |  | 312100018 | 112100039 |  | 16 |  | 2023-02-28 |  | Solar | 100 | 100 | 100 | [11 empty] | 2023-01-26 |  | 2024-12-31 | 2024-12-31 | Yes |  | Generator | Granted
| 641 | NR | Rajasthan | Ramgarh## |  | Adani Solar Energy AP Three Limited |  | 212100038 | 112100047 |  | 16 |  | 2023-02-28 |  | Solar | 150 | 150 | 150 | [11 empty] | 2023-01-31 |  | 2023-10-03 | 2023-10-03 | Yes |  | Generator | Granted
| 642 | NR | Rajasthan | Bhadla-III, Rajasthan |  | Prerak Greentech Solar Private Limited |  | 212100003 | 1671216520154 |  |  | 16 |  | 2023-02-28 |  | 400 | 400 | [12 empty] | 2022-12-17 |  | 2025-01-31 | 2025-01-31 | Yes |  |  | Granted
| 643 | NR | Rajasthan | Bikaner-II, Rajasthan |  | Amplus Ages Private Limited |  | 1200003624 | 1671556542236 |  |  | 16 |  | 2023-02-28 |  | 62 | 62 | [12 empty] | 2022-12-20 |  | 2023-10-31 | 2023-10-31 | Yes |  |  | Granted
| 644 | NR | Rajasthan | Bhadla-III, Rajasthan |  | Tepsol Sun Sparkle Private Limited |  | 212100030 | 1672319027575 |  |  | 16 |  | 2023-02-28 |  | 300 | 300 | [12 empty] | 2022-12-29 |  | 2025-10-01 | 2025-10-01 | Yes |  |  | Granted
| 645 | NR | Rajasthan | Fatehgarh-IV, Rajasthan |  | Juniper Green Stellar Private Limited |  | 1200003827 | 412100009 |  |  | 16 |  | 2023-02-28 |  | 150 | 150 | [12 empty] | 2022-12-30 |  | 2025-06-30 | 2025-06-30 | Yes |  |  | Granted
| 646 | NR | Rajasthan | Fatehgarh-IV, Rajasthan |  | Juniper Green Stellar Private Limited |  | 1200003910 | 412100010 |  |  | 16 |  | 2023-02-28 |  | 150 | 150 | [12 empty] | 2022-12-30 |  | 2026-06-30 | 2026-06-30 | No |  |  | Granted
| 647 | NR | Rajasthan | Bhadla-III, Rajasthan |  | Juniper Green Beta Private Limited |  | 212100027 | 412100012 |  |  | 16 |  | 2023-02-28 |  | 150 | 150 | [12 empty] | 2022-12-30 |  | 2025-06-30 | 2025-06-30 | Yes |  |  | Granted
| 648 | NR | Rajasthan | Bhadla-III, Rajasthan |  | Juniper Green Beta Private Limited |  | 312100013 | 412100013 |  |  | 16 |  | 2023-02-28 |  | 100 | 100 | [12 empty] | 2022-12-30 |  | 2026-12-31 | 2026-12-31 | No |  |  | Granted
| 649 | NR | Rajasthan | Bhadla-II, Rajasthan |  | Azure Power India Private Limited |  | 1200002403 | 412100018 |  |  | 16 |  | 2023-02-28 |  | 50 | 50 | [12 empty] | 2023-01-18 |  | 2024-07-20 | 2024-07-20 | Yes |  |  | Granted
| 650 | NR | Rajasthan | Fatehgarh-IV, Rajasthan |  | Amp Energy Green Private Limited |  | 312100005 | 412100019 |  |  | 16 |  | 2023-02-28 |  | 120 | 120 | [12 empty] | 2023-01-24 |  | 2025-01-11 | 2025-01-11 | Yes |  |  | Granted
| 651 | NR | Rajasthan | Fatehgarh-III, Rajasthan |  | Xl Xergi Power Private Limited |  | 1200002847 | 412100020 |  |  | 16 |  | 2023-02-28 |  | 200 | 200 | [12 empty] | 2023-01-25 |  | 2024-07-10 | 2024-07-10 | Yes |  |  | Granted
| 652 | NR | Rajasthan | Fatehgarh-III, Rajasthan |  | Renew Surya Vihaan Private Limited |  | 1200002695 | 412100021 |  |  | 16 |  | 2023-02-28 |  | 100 | 100 | [12 empty] | 2023-01-31 |  | 2023-09-30 | 2023-09-30 | Yes |  |  | Granted
| 653 | NR | Rajasthan | Fatehgarh-III, Rajasthan |  | Renew Surya Aayan Private Limited |  | 1200002692 | 412100022 |  |  | 16 |  | 2023-02-28 |  | 300 | 300 | [12 empty] | 2023-01-31 |  | 2023-09-30 | 2023-09-30 | Yes |  |  | Granted
| 654 | NR | Rajasthan | Fatehgarh-III, Rajasthan |  | Renew Surya Roshni Private Limited |  | 1200002628 | 412100023 |  |  | 16 |  | 2023-02-28 |  | 100 | 100 | [12 empty] | 2023-01-31 |  | 2023-09-30 | 2023-09-30 | Yes |  |  | Granted
| 655 | NR | Rajasthan | 1100 (Target) |  | Sarjan Realities Private Limited |  |  | 430700014 |  |  | 16 |  | 2023-02-28 | [15 empty] | 2023-01-12 |  | NR: 400 MW SR: 700 MW |  |  |  |  | Granted
| 656 | NR | Rajasthan | 1250 (Target) |  | Sarjan Realities Private Limited |  |  | 430700013 |  |  | 16 |  | 2023-02-28 | [15 empty] | 2023-01-12 |  | NR: 500 MW WR: 500 MW SR: 250 MW |  |  |  |  | Granted
| 657 | NR | Rajasthan | 1150 (Target) |  | Sarjan Realities Private Limited |  |  | 430700011 |  |  | 16 |  | 2023-02-28 | [15 empty] | 2023-01-12 |  | ER: 600 MW NR: 550 MW |  |  |  |  | Granted
| 658 | NR | Rajasthan | 100 (Firm) |  | Serentica Renewables India 4 Private Limited |  |  | 431400004 |  |  | 16 |  | 2023-02-28 | [15 empty] | 2023-01-19 |  | Hindustan Zinc Limited, Kankroli S/s, Rajasthan (NR) |  |  |  |  | Granted
| 659 | NR | Rajasthan | 100 (Firm) |  | Serentica Renewables India 4 Private Limited |  |  | 412100015 |  |  | 16 |  | 2023-02-28 | [15 empty] | 2023-01-19 |  | Hindustan Zinc Limited, Kankroli S/s, Rajasthan (NR) |  |  |  |  | Granted
| 660 | NR | Rajasthan | Fatehgarh -IV |  | Resco Global Wind Services Private Limited |  |  | 1671176748938 |  |  | 15 |  | 2023-02-27 | Wind | 500 | 500 |  | 500 | [10 empty] | 2022-12-26 |  | 2025-02-28 | 2025-02-28 | Yes |  | Generator | Granted
| 661 | NR | Rajasthan | Bikaner-II |  | Sprng Nirjara Energy Private Limited |  | 1670102829414 | 1200003622 |  | 15 |  | 2023-02-27 |  | Solar | 50 | 50 | 50 | [11 empty] | 2022-12-04 |  | 2026-01-31 | 2026-01-31 | Yes |  | Generator | Granted
| 662 | NR | Rajasthan | Bhadla-III |  | Juniper Green Beta Private Limited |  | 1670400777119 | 112100018 |  | 15 |  | 2023-02-27 |  | Solar | 70 | 70 | 70 | [11 empty] | 2022-12-13 |  | 2026-03-31 | 2026-03-31 | No |  | Generator | Granted
| 663 | NR | Rajasthan | Bikaner-II |  | Khidrat Renewable Energy Private Limited |  | 312100014 | 1200003368 |  | 15 |  | 2023-02-27 |  | Solar | 50 | 50 | 50 | [11 empty] | 2022-12-30 |  | 2025-12-31 | 2025-12-31 | Yes |  | Generator | Granted
| 664 | NR | Rajasthan | Fatehgarh-IV |  | Cannice Renewables Energy Private Limited |  | 1671600589106 | 112100009 |  | 15 |  | 2023-02-27 |  | Solar | 150 | 150 | 150 | [11 empty] | 2022-12-21 |  | 2025-01-31 | 2025-01-31 | Yes |  | Generator | Granted
| 665 | NR | Rajasthan | Fatehgarh-IV |  | Cannice Renewables Energy Private Limited |  | 212100004 | 112100009 |  | 15 |  | 2023-02-27 |  | Solar | 80 | 80 | 80 | [11 empty] | 2022-08-27 |  | 2025-01-31 | 2025-01-31 | Yes |  | Generator | Granted
| 666 | NR | Rajasthan | Bhadla-III, Rajasthan |  | Prerak Greentech Solar Private Limited |  | 212100003 | 1671216520154 |  |  | 15 |  | 2023-02-27 |  | 400 | 400 | [12 empty] | 2022-12-17 |  | 2025-01-31 | 2025-01-31 | Yes |  |  | Granted
| 667 | NR | Rajasthan | Bikaner-II, Rajasthan |  | Grian Energy Private Limited |  | 1200003625 | 1671544323119 |  |  | 15 |  | 2023-02-27 |  | 62 | 62 | [12 empty] | 2022-12-20 |  | 2023-08-31 | 2023-08-31 | Yes |  |  | Granted
| 668 | NR | Rajasthan | Bikaner-II, Rajasthan |  | Amplus Ages Private Limited |  | 1200003624 | 1671556542236 |  |  | 15 |  | 2023-02-27 |  | 62 | 62 | [12 empty] | 2022-12-20 |  | 2023-10-31 | 2023-10-31 | Yes |  |  | Granted
| 669 | NR | Rajasthan | Bhadla-III, Rajasthan |  | Tepsol Sun Sparkle Private Limited |  | 212100030 | 1672319027575 |  |  | 15 |  | 2023-02-27 |  | 300 | 300 | [12 empty] | 2022-12-29 |  | 2025-10-01 | 2025-10-01 | Yes |  |  | Granted
| 670 | NR | Rajasthan | Fatehgarh-IV, Rajasthan |  | Juniper Green Stellar Private Limited |  | 1200003827 | 412100009 |  |  | 15 |  | 2023-02-27 |  | 150 | 150 | [12 empty] | 2022-12-30 |  | 2025-06-30 | 2025-06-30 | Yes |  |  | Granted
| 671 | NR | Rajasthan | Fatehgarh-IV, Rajasthan |  | Juniper Green Stellar Private Limited |  | 1200003910 | 412100010 |  |  | 15 |  | 2023-02-27 |  | 150 | 150 | [12 empty] | 2022-12-30 |  | 2026-06-30 | 2026-06-30 | No |  |  | Granted
| 672 | NR | Rajasthan | Fatehgarh-IV, Rajasthan |  | Juniper Green Stellar Private Limited |  | 312100010 | 412100011 |  |  | 15 |  | 2023-02-27 |  | 65 | 65 | [12 empty] | 2022-12-30 |  | 2027-06-30 | 2027-06-30 | No |  |  | Granted
| 673 | NR | Rajasthan | Bhadla-III, Rajasthan |  | Juniper Green Beta Private Limited |  | 212100027 | 412100012 |  |  | 15 |  | 2023-02-27 |  | 150 | 150 | [12 empty] | 2022-12-30 |  | 2025-06-30 | 2025-06-30 | Yes |  |  | Granted
| 674 | NR | Rajasthan | Bhadla-III, Rajasthan |  | Juniper Green Beta Private Limited |  | 312100013 | 412100013 |  |  | 15 |  | 2023-02-27 |  | 100 | 100 | [12 empty] | 2022-12-30 |  | 2026-12-31 | 2026-12-31 | No |  |  | Granted
| 675 | NR | Rajasthan | Bhadla-III |  | Seven Renewable Power Private Limited |  |  | 112100011 |  |  | 14 |  | 2022-12-23 | Solar | 900 | 900 | 900 | [11 empty] | 2022-09-02 |  | 2024-06-30 | 2024-06-30 | Yes |  | Generator | Granted
| 676 | NR | Rajasthan | Bhadla-III |  | Tepsol Sun Sparkle Private Limited |  |  | 112100014 |  |  | 14 |  | 2022-12-23 | Solar | 1000 | 1000 | 1000 | [11 empty] | 2022-09-12 |  | 2025-03-31 | 2025-03-31 | Yes |  | Renewable Power Park Developer | Granted
| 677 | NR | Rajasthan | Bikaner-II |  | ReNew Dinkar Urja Private Limited |  |  | 112100013 |  |  | 14 |  | 2022-12-23 | Solar | 200 | 200 | 200 | [11 empty] | 2022-09-13 |  | 2023-10-01 | 2023-10-01 | Yes |  | Generator | Granted
| 678 | NR | Rajasthan | Fatehgarh -IV |  | Tepsol Saur Urja Private Limited |  |  | 112100017 |  |  | 14 |  | 2022-12-23 | Solar | 1000 | 1000 | 1000 | [11 empty] | 2022-09-20 |  | 2025-03-31 | 2025-03-31 | Yes |  | Renewable Power Park Developer | Granted
| 679 | NR | Rajasthan | Bhadla-III |  | Malur Renewables Pvt. Ltd. |  |  | 112100016 |  |  | 14 |  | 2022-12-23 | Solar | 900 | 900 | 900 | [11 empty] | 2022-09-27 |  | 2022-10-01 | 2022-10-01 | Yes |  | Renewable Power Park Developer | Granted
| 680 | NR | Rajasthan | Bhadla-III |  | Abu Renewables India Private Limited |  |  | 112100020 |  |  | 14 |  | 2022-12-23 | Solar | 350 | 350 | 350 | [11 empty] | 2022-09-30 |  | 2025-12-31 | 2025-12-31 | Yes |  | Generator | Granted
| 681 | NR | Rajasthan | Bhadla-III |  | Juniper Green Beta Private Limited |  |  | 112100018 |  |  | 14 |  | 2022-12-23 | Solar | 400 | 400 | 400 | [11 empty] | 2022-10-03 |  | 2025-03-31 | 2025-03-31 | Yes |  | Generator | Granted
| 682 | NR | Rajasthan | Bhadla-III |  | Frugal Energy Private Limited |  |  | 112100025 |  |  | 14 |  | 2022-12-23 | Solar | 300 | 300 | 300 | [11 empty] | 2022-10-29 |  | 2025-03-31 | 2025-03-31 | Yes |  | Renewable Power Park Developer | Granted
| 683 | NR | Rajasthan | Fatehgarh -IV |  | Luceo Solar Private Limited |  |  | 112100026 |  |  | 14 |  | 2022-12-23 | Solar | 200 | 200 | 200 | [11 empty] | 2022-10-30 |  | 2024-12-31 | 2024-12-31 | Yes |  | Generator | Granted
| 684 | NR | Rajasthan | Bhadla-III |  | Bhadla Three Skp Green Ventures Private Limited |  |  | 112100027 |  |  | 14 |  | 2022-12-23 | Solar | 300 | 300 | 300 | [11 empty] | 2022-10-30 |  | 2024-12-31 | 2024-12-31 | Yes |  | Renewable Power Park Developer | Granted
| 685 | NR | Rajasthan | Bhadla-III |  | ACME Solar Holdings Private Limited |  |  | 112100021 |  |  | 14 |  | 2022-12-23 | Solar | 300 | 300 | 300 | [11 empty] | 2022-11-04 |  | 2024-12-31 | 2024-12-31 | Yes |  | Generator | Granted
| 686 | NR | Rajasthan | Bhadla-III |  | ACME Solar Holdings Private Limited |  |  | 112100022 |  |  | 14 |  | 2022-12-23 | Solar | 300 | 300 | 300 | [11 empty] | 2022-11-04 |  | 2024-12-31 | 2024-12-31 | Yes |  | Generator | Granted
| 687 | NR | Rajasthan | Fatehgarh -IV |  | ACME Solar Holdings Private Limited |  |  | 112100023 |  |  | 14 |  | 2022-12-23 | Solar | 300 | 300 | 300 | [11 empty] | 2022-11-04 |  | 2025-03-31 | 2025-03-31 | Yes |  | Generator | Granted
| 688 | NR | Rajasthan | Bikaner-III |  | Sunsure Energy Private Limited |  |  | 112100028 |  |  | 14 |  | 2022-12-23 | Solar | 300 | 300 | 300 | [11 empty] | 2022-11-10 |  | 2024-12-31 | 2024-12-31 | Yes |  | Generator | Granted
| 689 | NR | Rajasthan | Bhadla-III |  | Juniper Green Beta Private Limited |  | 212100027 | 112100018 |  | 14 |  | 2022-12-23 |  | Solar | 150 | 150 | 150 | [11 empty] | 2022-10-03 |  | 2025-03-31 | 2025-03-31 | Yes |  | Generator | Granted
| 690 | NR | Rajasthan | Bhadla-III |  | Juniper Green Beta Private Limited |  | 312100013 | 112100018 |  | 14 |  | 2022-12-23 |  | Solar | 40 | 40 | 40 | [11 empty] | 2022-10-31 |  | 2025-03-31 | 2025-03-31 | Yes |  | Generator | Granted
| 691 | NR | Rajasthan | Fatehgarh -IV |  | Juniper Green Stellar Private Limited |  | 312100010 | 1200003672 |  | 14 |  | 2022-12-23 |  | Solar | 45 | 45 | 45 | [11 empty] | 2022-10-06 |  | 2025-01-31 | 2025-01-31 | Yes |  | Generator | Granted
| 692 | NR | Rajasthan | Fatehgarh -IV |  | Juniper Green Stellar Private Limited |  | 312100012 | 1200003672 |  | 14 |  | 2022-12-23 |  | Solar | 60 | 60 | 60 | [11 empty] | 2022-10-20 |  | 2025-01-31 | 2025-01-31 | Yes |  | Generator | Granted
| 693 | NR | Rajasthan | Bikaner-II |  | Sprng Nirjara Energy Private Limited |  | 312100011 | 1200003622 |  | 14 |  | 2022-12-23 |  | Solar | 50 | 50 | 50 | [11 empty] | 2022-10-10 |  | 2025-10-31 | 2025-10-31 | Yes |  | Generator | Granted
| 694 | NR | Rajasthan | Bhadla-III |  | Seven Renewable Power Private Limited |  | 212100028 | 112100011 |  | 14 |  | 2022-12-23 |  | Solar | 300 | 300 | 300 | [11 empty] | 2022-10-17 |  | 2024-06-30 | 2024-06-30 | Yes |  | Generator | Granted
| 695 | NR | Rajasthan | Bhadla-III |  | Tepsol Sun Sparkle Private Limited |  | 212100030 | 112100014 |  | 14 |  | 2022-12-23 |  | Solar | 300 | 300 | 300 | [11 empty] | 2022-10-25 |  | 2025-03-31 | 2025-03-31 | Yes |  | Renewable Power Park Developer | Granted
| 696 | NR | Rajasthan | Bhadla-III |  | Frugal Energy Private Limited |  | 212100031 | 112100025 |  | 14 |  | 2022-12-23 |  | Solar | 50 | 50 | 50 | [11 empty] | 2022-10-29 |  | 2025-03-31 | 2025-03-31 | Yes |  | Renewable Power Park Developer | Granted
| 697 | NR | Rajasthan | Fatehgarh -IV |  | Luceo Solar Private Limited |  | 212100032 | 112100026 |  | 14 |  | 2022-12-23 |  | Solar | 200 | 200 | 200 | [11 empty] | 2022-11-07 |  | 2024-12-31 | 2024-12-31 | Yes |  | Generator | Granted
| 698 | NR | Rajasthan | Bhadla-III |  | Bhadla Three SKP Green Ventures Private Limited |  | 212100033 | 112100027 |  | 14 |  | 2022-12-23 |  | Solar | 300 | 300 | 300 | [11 empty] | 2022-11-09 |  | 2024-12-31 | 2024-12-31 | Yes |  | Generator | Granted
| 699 | NR | Rajasthan | Fatehgarh -IV |  | Cannice Renewables Energy Private Limited |  | 212100004 | 112100009 |  | 14 |  | 2022-12-23 |  | Solar | 80 | 80 | 80 | [11 empty] | 2022-08-27 |  | 2025-01-31 | 2025-01-31 | Yes |  | Generator | Granted
| 700 | NR | Rajasthan | Fatehgarh-III, Rajasthan |  | XL Xergi Power Private Limited |  | 1200002847 | 412100007 |  |  | 14 |  | 2022-12-23 |  | 200 | 200 | [12 empty] | 2022-10-06 |  | 2024-01-18 | 2024-01-18 | Yes |  |  | Granted
| 701 | NR | Rajasthan | Bikaner-II, Rajasthan |  | Juniper Green Cosmic Private Limited |  | 1200003740 | 412100008 |  |  | 14 |  | 2022-12-23 |  | 100 | 100 | [12 empty] | 2022-10-29 |  | 2025-01-31 | 2025-01-31 | Yes |  |  | Granted

## Bulk Consumers
Sr.no. | Region | State | Substation | Name of Developers | Group | GNA Application ID | CMETS GNA Approved | CMETS GNA Meeting Date | GNA Type | Quantum (MW) | Quantum (MW) | Total Quantum (MW) | Nature of Applicant | Status of application (Applied/Withdrawn / Granted. Revoked.) | Start Date of GNA | End Date of GNA
[10 empty] | Within Region | Outside Region
1 | NR | Haryana | Jind (PG) | Panipat Green Hydrogen Private Limited |  | 2200002261 | 43 | 12.01.2026 |  | 0 | 99 | 99 | Bulk consumer (including Green Hydrogen / Green Ammonia) seeking to connect to ISTS directly | Applied | 25.08.2027 | 25.12.2052
2 | NR | Uttar Pradesh | Mainpuri (PG) Substation | Indian Railways |  | 2200002494 | 43 | 12.01.2026 |  | 0 | 50 | 50 | Bulk consumer seeking to connect to ISTS directly | Granted | 01.12.2025 | 31.12.2055
3 | NR | Rajasthan | Beawar-I | Hindustan Zinc Limited |  | 2200002025 | 42 | 11.11.2025 |  | 5 | 175 | 180 | Bulk consumer seeking to connect to ISTS directly | Granted | 01.02.2027 | 31.01.2052
4 | NR | Rajasthan |  | Hindustan Zinc Limited |  | 2200001595 | 41 | 10.10.2025 |  | 5 | 215 | 220 | Bulk consumer seeking to connect to ISTS directly | Granted | 30.06.2027 | 30.06.2052
5 | NR | Rajasthan | Beawar-I | Hindustan Zinc Limited |  | 2200002025 | 41 | 10.10.2025 |  | 5 | 175 | 180 | Bulk consumer seeking to connect to ISTS directly | Granted | 01.02.2027 | 31.01.2052
6 | NR | Uttar Pradesh | Sector 148 | STT Global Data Centres India Private Limited |  | 2200002213 | 41 | 10.10.2025 |  | 0 | 2 | 2 | Drawee entity connected to Intra State | Withdrawn | 01.07.2025 | 30.04.2050
7 | NR | Delhi | Vsnl-I | STT Global Data Centres India Private Limited |  | 2200002215 | 41 | 10.10.2025 |  | 0 | 7 | 7 | Drawee entity connected to Intra State | Withdrawn | 01.07.2025 | 31.03.2035
8 | NR | Haryana | Jind (PG) | Panipat Green Hydrogen Private Limited |  | 2200002261 | 41 | 10.10.2025 |  | 0 | 99 | 99 | Bulk consumer (including Green Hydrogen / Green Ammonia) seeking to connect to ISTS directly | Applied | 25.08.2027 | 25.12.2052
9 | NR | Rajasthan |  | Hindustan Zinc Limited |  | 2200001595 | 40 | 12.09.2025 |  | 5 | 215 | 220 | Bulk consumer seeking to connect to ISTS directly | Applied | 30.06.2027 | 30.06.2052
10 | NR | Rajasthan |  | Hindustan Zinc Limited |  | 2200002025 | 40 | 12.09.2025 |  | 5 | 175 | 180 | Bulk consumer seeking to connect to ISTS directly | Applied | 01.02.2027 | 31.01.2052
11 | NR | Rajasthan |  | STT Global Data Centres India Private Limited |  | 2200002213 | 40 | 12.09.2025 |  | 0 | 2 | 2 | Drawee entity connected to Intra State | Applied | 01.07.2025 | 30.04.2050
12 | NR | Rajasthan |  | STT Global Data Centres India Private Limited |  | 2200002215 | 40 | 12.09.2025 |  | 0 | 7 | 7 | Drawee entity connected to Intra State | Applied | 01.07.2025 | 31.03.2035
13 | NR | Punjab | Wadala Granthian-I | Panipat Green Hydrogen Private Limited |  | 2200002261 | 40 | 12.09.2025 |  | 0 | 99 | 99 | Bulk consumer (including Green Hydrogen / Green Ammonia) seeking to connect to ISTS directly | Applied | 25.08.2027 | 25.12.2052
14 | NR | Rajasthan |  | Vedanta Limited |  | 2200001695 | 39 | 28.07.2025 |  | 0 | 100 | 100 | Bulk consumer seeking to connect to ISTS directly | Withdrawn | 31.12.2027 | 31.12.2052
15 | NR | Rajasthan | Kankroli (PG) | Hindustan Zinc Limited |  | 2200001595 | 39 | 28.07.2025 |  | 5 | 215 | 220 | Bulk consumer seeking to connect to ISTS directly | Applied | 30.06.2027 | 30.06.2052
16 | NR | Delhi | Bses Yamuna Karkardooma-I | Aman Hospitality Private Limited |  | 2200001714 | 38 | 28.05.2025 |  | 2.5 | 0 | 2.5 | Drawee entity connected to Intra State Transmission System | Granted | 01.04.2025 | 31.03.2050
17 | NR | Delhi |  | Indian Railways |  | 2200001663 | 38 | 28.05.2025 |  | 0 | 5 | 5 | Drawee entity connected to Intra State Transmission System | Granted | 01.03.2025 | 30.09.2049
18 | NR | Uttar Pradesh | Allahabad (PG) | Indian Railways |  | 2200001656 | 38 | 28.05.2025 |  | 0 | 50 | 50 | Bulk consumer seeking to connect to ISTS directly | Granted | 01.02.2025 | 31.01.2055
19 | NR | Rajasthan | Barmer-I | Vedanta Limited |  | 2200001695 | 38 | 28.05.2025 |  | 0 | 100 | 100 | Bulk consumer seeking to connect to ISTS directly | Applied | 31.12.2027 | 31.12.2052
20 | NR | Rajasthan | Debari-I | Hindustan Zinc Limited |  | 2200001595 | 38 | 28.05.2025 |  | 5 | 215 | 220 | Bulk consumer seeking to connect to ISTS directly | Applied | 30.06.2027 | 30.06.2052
21 | NR | Uttar Pradesh | Gajraula Substation-I | Ingrevia Limited |  | 2200001564 | 37 | 27.03.2025 |  | 0 | 5.4 | 5.4 | Drawee entity connected to Intra State Transmission System | Granted | 15.05.2025 | 31.03.2050
22 | NR | Rajasthan | Barmer-I | Vedanta Limited |  | 2200001265 | 35 | 29.10.2024 |  | 0 | 25 | 25 | Drawee entity connected to Intra State Transmission System | Granted | 15.11.2024 | 30.06.2049
23 | NR | Punjab | Rajpura-I | Asian Fine Cements Private Limited |  | 2200001060 | 34 | 20.09.2024 |  | 0 | 4 | 4 | Drawee entity connected to Intra State Transmission System | Granted | 01.09.2024 | 31.03.2026
24 | NR | Punjab | Ropar-I | Ambuja Cements Limited |  | 2200001058 | 34 | 20.09.2024 |  | 0 | 10 | 10 | Drawee entity connected to Intra State Transmission System | Granted | 01.09.2024 | 31.03.2026
25 | NR | Punjab | Gndtp Bathinda-I | Ambuja Cements Limited |  | 2200001059 | 34 | 20.09.2024 |  | 0 | 3 | 3 | Drawee entity connected to Intra State Transmission System | Granted | 01.09.2024 | 31.03.2026
26 | NR | Uttar Pradesh | Gauriganj-I | ACC Limited |  | 2200001081 | 34 | 20.09.2024 |  | 0 | 4.5 | 4.5 | Drawee entity connected to Intra State Transmission System | Granted | 01.09.2024 | 31.03.2026
27 | NR | Uttarakhand | Raipur-I | Ambuja Cements Limited |  | 2200001101 | 34 | 20.09.2024 |  | 0 | 5.85 | 5.85 | Drawee entity connected to Intra State Transmission System | Granted | 01.09.2024 | 31.03.2026
28 | NR | Rajasthan |  | 2200000740 Ambuja Cements Limited |  | 2200000740 | 33 | 05.08.2024 |  | 0 | 25 | 25 | 03.05.2024 Drawee entity connected to Intra State Transmission System | Granted | 01.06.2024 (revised to 01.09.2024) | 30.06.2025 (revised to 31.03.2026)
29 | NR | Rajasthan |  | 2200000739 Ambuja Cements Limited |  | 2200000739 | 33 | 05.08.2024 |  | 0 | 7 | 7 | 03.05.2024 Drawee entity connected to Intra State Transmission System | Granted | 01.06.2024 | 30.06.2025
30 | NR | Himachal Pradesh | Chamakri Substation-I | 2200000770 Ambuja Cements Limited |  | 2200000770 | 33 | 05.08.2024 |  | 0 | 15 | 15 | 07.05.2024 Drawee entity connected to Intra State Transmission System | Granted | 01.06.2024 (revised to 01.09.2024) | 30.06.2025 (revised to 31.03.2026)
31 | NR | Rajasthan | Kangoo Substation-I | 2200000768 Ambuja Cements Limited |  | 2200000768 | 33 | 05.08.2024 |  | 0 | 8.5 | 8.5 | 07.05.2024 Drawee entity connected to Intra State Transmission System | Applied | 01.06.2024 (revised to 01.09.2024) | 30.06.2025 (revised to 31.03.2026)
32 | NR | Uttar Pradesh | Allahabad-I | Limited |  | 2200000627 | 32 | 10.07.2024 |  | 50 | 50 | 100 | Bulk consumer seeking to connect to ISTS | Applied | 01.04.2026 | 31.03.2061
33 | NR | Uttarakhand | Jhajra-I | Limited |  | 2200000691 | 32 | 10.07.2024 |  | 0 | 8 | 8 | Drawee entity connected to Intra State Transmission System | Granted | 16.07.2024 (revised to 01.01.2025) | 30.06.2039
34 | NR | Himachal Pradesh |  | 2 2200000721 Cosmos Hydro Power Private Limited |  | 2200000721 | 32 | 10.07.2024 |  | 19.53 | 0 | 19.53 | Injecting entity connected to intra-State transmission system | Applied | 01.07.2024 (Revised to 01.09.2024) | 19.09.2033
35 | NR | Rajasthan |  | 2200000740 Ambuja Cements Limited |  | 2200000740 | 32 | 10.07.2024 |  | 0 | 25 | 25 | Drawee entity connected to Intra State Transmission System | Applied |  | 01.06.2024 30.06.2025
36 | NR | Rajasthan |  | 2200000739 Ambuja Cements Limited |  | 2200000739 | 32 | 10.07.2024 |  | 0 | 7 | 7 | Drawee entity connected to Intra State Transmission System | Applied |  | 01.06.2024 30.06.2025
37 | NR | Himachal Pradesh | Kv Substation-I | 2200000770 Ambuja Cements Limited |  | 2200000770 | 32 | 10.07.2024 |  | 0 | 15 | 15 | Drawee entity connected to Intra State Transmission System | Applied |  | 01.06.2024 30.06.2025
38 | NR | Himachal Pradesh | Kangoo Substation-I | 2200000768 Ambuja Cements Limited |  | 2200000768 | 32 | 10.07.2024 |  | 0 | 8.5 | 8.5 | Drawee entity connected to Intra State Transmission System | Applied |  | 01.06.2024 30.06.2025
39 | NR | Himachal Pradesh | Nalagarh (PG) | 2200000769 Ambuja Cements Limited |  | 2200000769 | 32 | 10.07.2024 |  | 0 | 7.5 | 7.5 | Drawee entity connected to Intra State Transmission System | Withdrawn |  | 01.06.2024 30.06.2025
40 | NR | Uttar Pradesh |  | Noida Power Company Limited |  | 2200000829 | 32 | 10.07.2024 |  | 0 | 100 | 100 | Drawee entity connected to Intra State Transmission System | Granted | 01.06.2024 | 31.03.2026
41 | NR | Rajasthan |  | Company Limited |  | 1220000082 | 32 | 10.07.2024 |  | 0 | 100 | 100 | 21.05.2024 Drawee entity connected to Intra State Transmission System |  | 01.06.2024(revised to 30.07.2024) | 31.03.2026
42 | NR | Rajasthan | A Distance-I | HHP Two Pvt. Limited |  | 2200000272 | 31 | 27.06.2024 |  | 0 | 110 | 110 | Bulk consumer seeking to connect to ISTS at Sonipat (PG) | Withdrawn | 01.05.2026 | 01.05.2051
43 | NR | Rajasthan |  | Indian Railways |  | 1220000057 | 31 | 27.06.2024 |  |  | 15 | 15 | Drawee entity connected to Intra State Transmission System |  | 01.03.2024 | 23.11.2044
44 | NR | Rajasthan | Rvpn At Gulabpura-I | Limited |  | 2200000467 | 31 | 27.06.2024 |  | 5 | 65 | 70 | Bulk consumer seeking to connect to ISTS | Applied |  | 30.06.2026 29.06.2051
45 | NR | Rajasthan |  | Hindustan Zinc |  | 2200000457 | 31 | 27.06.2024 |  | 5 | 45 | 50 | Bulk consumer seeking | Granted | 30.06.2026 | 29.06.2051
46 | NR | Uttar Pradesh |  | Limited |  | 2200000453 | 31 | 27.06.2024 |  | 5 | 50 | 55 | Bulk consumer seeking to connect to ISTS | Applied |  | 30.06.2026 29.06.2051
47 | NR | Rajasthan |  | Hindustan Zinc Limited |  | 2220000046 | 31 | 27.06.2024 |  | 5 | 65 | 70 | Bulk consumer seeking to connect to ISTS |  | 30.06.2026 | 29.06.2051
48 | NR | Jammu and Kashmir | Dulhasti Substation-I | HHP Two Private Limited |  | 2200000272 | 26 | 01.12.2023 |  | 0 | 110 | 110 | Bulk consumer seeking to connect to ISTS at Sonipat (PG) | Granted | 01.05.2026 | 01.05.2051
49 | WR | Rajasthan | Chittorgarh Ists Station In Northern Region For Their Chanderiya Lead Zinc Smelter Plant From Chittorgarh-I | Hindustan Zinc Limited |  | 2200000059 | 20 | 30.06.2023 |  | 250 | 250 | 500 | Bulk consumer seeking to connect to ISTS | Applied | 31.03.2025 | 30.03.2050
50 | NR | Haryana | Jind (PG) | Renew Solar (Shakti Thirteen) Private Limited |  | 0010800002 | 17 | 31.03.2023 |  |  |  | 100 | Bulk Consumer | Granted | 01.06.2025
51 | NR | Rajasthan | Kankroli (PG) | Hindustan Zinc Limited |  | 0012100007 | 14 | 23.12.2022 |  |  |  | 200 | Bulk Consumer | Granted | 01.07.2024

## RE Potential
| Region | State | District | Complex | S/s | Location (Village/Tehsil) | Solar | Wind | Hybrid | Others (CTUIL) | RE Potential (GW) | Installed Capacity | U/c & granted Capacity | Transmission Scheme | Complex | Remarks
|  |  | Bikaner |  |  | Bikaner | 1.85
Data Scoure (Sl. No.(s)9, 10a, ) |  |  | Bikaner |  |  | Bikaner | 2.95
|  |  | Kurnool |  |  | Kurnool | 5.5
|  |  | Anantapur |  |  | Anantapur | 2.5
|  |  | Gadag |  |  | Gadag | 2.5
|  |  | Koppal |  |  | Koppal | 2.5
|  | Rajasthan |  |  |  |  | 15 | 1 |  |  | 60 |  |  |  |  | 45 GW (15 GW Wind & 30 GW solar in GIB Zone)
|  | Andhra Pradesh |  |  |  |  | 18 | 2 |  |  | 33
|  | Karnataka |  |  |  |  | 8 | 3 |  |  | 9
|  | Tamil Nadu |  |  |  |  | 5 | 4 |  |  | 5 |  |  |  |  | Offshore wind
|  | Telangana |  |  |  |  | 3 | 5 |  |  | 10
|  | Madhya Pradesh |  |  |  |  | 2 | 6 |  |  | 6
|  | Gujarat |  |  |  |  | 5 | 7 |  |  | 5 |  |  |  |  | Offshore wind
|  | Maharashtra |  |  |  |  | 2 | 8 |  |  | 5.5
|  | Rajasthan |  |  |  |  | 30 | 75
|  | Andhra Pradesh |  |  |  |  | 10 | 51 |  |  | 10
|  | Karnataka |  |  |  |  | 2 | 17 |  |  | 2
|  | Tamil Nadu |  |  |  |  | 5 | 5
|  | Telangana |  |  |  |  | 1 | 13 |  |  | 2.5
|  | Madhya Pradesh |  |  |  |  | 2 | 8
|  | Gujarat |  |  |  |  | 5 | 5
|  | Maharashtra |  |  |  |  | 1 | 7.5 |  |  | 1
|  | Rajasthan |  |  |  |  | 60 | 15 |  |  | 67.5
Gujarat
Maharashtra
|  | Maharashtra |  |  |  |  | 5.5 | 2 |  |  | 6.5 |  |  |  |  | 5.4
Madhya Pradesh
|  | Madhya Pradesh |  |  |  |  | 6 | 2 |  |  | 8
Andhra Pradesh
|  | Andhra Pradesh |  |  |  |  | 33 | 18 |  |  | 41
Karnataka
|  | Karnataka |  |  |  |  | 9 | 8 |  |  | 14
Telangana
|  | Telangana |  |  |  |  | 10 | 3 |  |  | 11.5 |  |  |  |  | 8.5
Tamil Nadu
|  | Telangana | Bikaner |  |  | Bikaner | 8 | 8.1 |  |  | 400
|  | Telangana | Bikaner |  |  | Bikaner | 400
|  | Telangana | Bikaner |  |  | Bikaner | 300
|  | Telangana | Bikaner |  |  | Bikaner | 9 | 8.1 |  |  | 400
|  | Telangana | Gadag |  |  | Gadag | 12 | 1000 |  |  | 400
|  | Telangana | Gadag |  |  | Gadag | 400
|  | Telangana | Koppal |  |  | Koppal | 13 | 2500 |  |  | 400
|  | Telangana | Koppal |  |  | Koppal | 400
|  | Telangana | Koppal |  |  | Koppal | 2
|  | Telangana | Gadag |  |  | Gadag | 11 | 1500 |  |  | 400
|  | Telangana | Kurnool |  |  | Kurnool | 1 | 2500 |  |  | 400
|  | Telangana | Kurnool |  |  | Kurnool | 400
|  | Telangana | Anantapur |  |  | Anantapur | 400
|  | Telangana | Kurnool |  |  | Kurnool | 3 | 3000 |  |  | 765
|  | Telangana | Kurnool |  |  | Kurnool | 765
|  | Rajasthan |  |  |  |  | 7 | 0 |  |  | 7
|  | Rajasthan |  |  |  |  | 6 | 6 |  |  | 12
|  | Rajasthan |  |  |  |  | 6 | 4 |  |  | 10
|  | Rajasthan |  |  |  |  | 3 | 0 |  |  | 3
|  | Rajasthan |  |  |  |  | 2 | 0 |  |  | 2
|  | Rajasthan |  |  |  |  | 3 | 2 |  |  | 5
|  | Rajasthan |  |  |  |  | 4 | 3 |  |  | 7
|  | Rajasthan |  |  |  |  | 6 | 0 |  |  | 6
|  | Rajasthan |  |  |  |  | 5 | 0 |  |  | 5
|  | Maharashtra |  |  |  |  | 1 | 0 |  |  | 1
|  | Maharashtra |  |  |  |  | 1 | 1 |  |  | 2
|  | Maharashtra |  |  |  |  | 2.5 | 2.5 |  |  | 0 |  |  |  |  | 2.5
|  | Gujarat |  |  |  |  | 5 | 5 |  |  | 2
|  | Telangana |  |  |  |  | 2.5 | 1 |  |  | 3.5
|  | Telangana |  |  |  |  | 2.5 | 0 |  |  | 2.5 |  |  |  |  | 0.5
|  | Karnataka |  |  |  |  | 2 | 2 |  |  | 4
|  | Karnataka |  |  |  |  | 0 | 2 |  |  | 2
|  | Karnataka |  |  |  |  | 1.5 | 0 |  |  | 1.5
|  | Tamil Nadu |  |  |  |  | 5 | 5 |  |  | 0
|  | Tamil Nadu |  | Bikaner-II | Bikaner-II |  | 7 | 0 |  | 0 | 7
|  | Tamil Nadu |  | Bikaner-III | Bikaner-III |  | 7 | 0 |  | 0 | 7
|  | Tamil Nadu |  | Fatehgarh-IV | Fatehgarh-IV |  | 6 | 6 |  | 2 | 12
|  | Tamil Nadu |  | Ramgarh | Ramgarh |  | 6 | 4 |  | 2 | 10
|  | Tamil Nadu |  | Jalore | Jalore |  | 3 | 0 |  | 0 | 3
|  | Tamil Nadu |  | Sanchore | Sanchore |  | 3 | 0 |  | 0 | 3
|  | Tamil Nadu |  | Sirohi | Sirohi |  | 3 | 0 |  | 0 | 3
|  | Tamil Nadu |  | Pali | Pali |  | 3 | 0 |  | 0 | 3
|  | Tamil Nadu |  | Ajmer | Ajmer |  | 2 | 0 |  | 0 | 2
|  | Tamil Nadu |  | Nagaur | Nagaur |  | 2 | 0 |  | 0 | 2
|  | Tamil Nadu |  | Bhadla-IV | Bhadla-IV |  | 3 | 2 |  | 0 | 5
|  | Tamil Nadu |  | Barmer-I | Barmer-I |  | 4 | 3 |  | 2 | 7
|  | Tamil Nadu |  | Barmer-II | Barmer-II |  | 6 | 0 |  | 0 | 6
|  | Tamil Nadu |  | Jaisalmer/ Jodhpur (Intra-State) | Jaisalmer/ Jodhpur (Intra-State) |  | 5 | 0 |  | 0 | 5
|  | Tamil Nadu |  | Total | Total |  | 60 | 15 |  | 6 | 75
|  | Tamil Nadu |  | Jaisalmer/ Jodhpur (Intra-State) | Jaisalmer/ Jodhpur (Intra-State) |  | 5 | 0 |  | 0 | 5
|  | Tamil Nadu |  | Jaisalmer/ Jodhpur (Intra-State) | Jaisalmer/ Jodhpur (Intra-State) |  | 5 | 0 |  | 0 | 5
|  | Tamil Nadu |  | Kurnool-IV | Kurnool-IV |  | 7.5 | 4 |  | 3 | 11.5
|  | Tamil Nadu |  | Kurnool-V | Kurnool-V |  | 7.5 | 4 |  | 3 | 11.5
|  | Tamil Nadu |  | Anantapur | Anantapur |  | 2 | 2 |  | 1 | 4
|  | Tamil Nadu |  | Anantapur-II | Anantapur-II |  | 8 | 8 |  | 4 | 16
|  | Tamil Nadu |  | Kadapa-II | Kadapa-II |  | 8 | 0 |  | 3 | 8
|  | Tamil Nadu |  | Total | Total |  | 33 | 18 |  | 14 | 51
|  | Tamil Nadu |  | Koppal-II | Koppal-II |  | 2 | 2 |  | 1 | 4
|  | Tamil Nadu |  | Gadag-II | Gadag-II |  | 2 | 2 |  | 1 | 4
|  | Tamil Nadu |  | Devanagere/ Chitragurga | Devanagere/ Chitragurga |  | 2 | 2 |  | 1 | 4
|  | Tamil Nadu |  | Bijapur | Bijapur |  | 0 | 2 |  | 0 | 2
|  | Tamil Nadu |  | Bellary | Bellary |  | 1.5 | 0 |  | 0 | 1.5
|  | Tamil Nadu |  | Tumkur-II | Tumkur-II |  | 1.5 | 0 |  | 0 | 1.5
|  | Tamil Nadu |  | Total | Total |  | 9 | 8 |  | 3 | 17
|  | Tamil Nadu |  | Nizamabad-II | Nizamabad-II |  | 2.5 | 1 |  | 1 | 3.5
|  | Tamil Nadu |  | Medak | Medak |  | 2.5 | 1 |  | 1 | 3.5
|  | Tamil Nadu |  | Rangareddy | Rangareddy |  | 2.5 | 1 |  | 1 | 3.5
|  | Tamil Nadu |  | Karimnagar | Karimnagar |  | 2.5 | 0 |  | 0 | 2.5
|  | Tamil Nadu |  | Total | Total |  | 10 | 3 |  | 3 | 13
|  | Tamil Nadu |  | Sl. No. | Sl. No.

## Margin
Sl.No. | State | Region | Pooling S/s | Additional Information of Pooling S/s | Timelines | RE Potential |  |  | Expected CoD of Pooling Station | Connectivity Granted/ Agreed |  |  | Connectivity Under Process |  |  | Margin for Connectivity |  |  | Additional Margin for Connectivity requiring ICT Augmentation / additional Tr. System |  |  | Effectiveness of GNA for Capacity mentioned under "Margin for Connectivity
[6 empty] | RE Potential (MW) [A] | BESS (MW) [B] | S/s Evacuation Capacity (RE Potential - BESS [AB]) |  | 200 kV | 400 kV | Total (MW) | 200 kV | 400 kV | Total (MW) | 200 kV | 400 kV | Total (MW) | 200 kV | 400 kV | Total (MW)
Existing PS
1 | Rajasthan | NR | Bhadla Complex |  | Existing | 8430 | 0 | 8430 | Existing | 7475 | 2050 | 9525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5251.375MW: Existing 4273.625MW: Nov'25 onwards (Ph-II/Ph-III/Ph-IV) (upto Mar'27)
1a | Rajasthan | NR | Bhadla |  | Existing | 3380 | 0 | 3380 | Existing | 3580 | 0 | 3580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3580MW: Existing
1b | Rajasthan | NR | Bhadla-II |  | Existing | 5050 | 0 | 5050 | Existing | 3895 | 2050 | 5945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1671.375MW: Existing 4273.625MW: Nov'25 onwards (Ph-II/Ph-III/Ph-IV) (upto Mar'27)
2 | Rajasthan | NR | Fatehgarh-Barmer Complex |  | Existing | 9600 | 0 | 9600 | Existing | 6940 | 3200 | 10140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7225.83MW: Existing 2914.17MW: Nov'25 onwards (Ph-II/Ph-III/Ph-IV) (upto Mar'27)
2a | Rajasthan | NR | Fatehgarh |  | Existing | 2200 | 0 | 2200 | Existing | 0 | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Existing Tr. System
2b | Rajasthan | NR | Fatehgarh-II |  | Existing | 5500 | 0 | 5500 | Existing | 4460 | 1000 | 5460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3525.83MW: Existing 1934.17MW: Nov'25 onwards (Ph-II/Ph-III/Ph-IV) (upto Mar'27)
2c | Rajasthan | NR | Fatehgarh-III | Section-I | Existing | 1900 | 0 | 1900 | Existing | 2480 | 0 | 2480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500MW: Existing 480MW: Nov'25 (Ph-II) Including 2x250MW BESS granted at Fatehgarh-III (Section-I) 250MW: Existing 250MW: Mar'26
3 | Rajasthan | NR | Bikaner Complex |  | Existing | 8850 | 3000 | 5850 | Existing | 5695 | 3940 | 9635 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 2865MW: Existing 3360MW: Nov'25 onwards (Ph-II/Ph-IV/Ph-V) (upto Mar'27)
3a | Rajasthan | NR | Bikaner |  | Existing | 1850 | 0 | 1850 | Existing | 1235 | 2940 | 4175 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 2865MW: Existing 1360MW: Nov'25 onwards (Ph-II/Ph-IV/Ph-V) (Upto Mar'27)
3b | Rajasthan | NR | Bikaner-II |  | Existing | 7000 | 3000 | 4000 | Existing | 4460 | 1000 | 5460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5760MW:Nov'25 onwards (Upto Aug'26) (Ph-II/Ph-IV Part-I&II)
4 | Rajasthan | NR | Bhadla-III |  | Between Jul-25 to Dec-25 | 3500 | 0 | 3500 | Sep'25 | 2750 | 1000 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700MW : Feb'26 onwards (Upto Aug'26 (Ph-IV)): cumulative at Ramgarh & Bhadla-III: Raj. (Ph-III) Beyond 3700MW : Bhadla HVDC (Jan'29 Pole-1 & Jul'29 Pole-2) Out of 3750MW, 250MW connectvity of standalone BESS agreed for grant recently
5 | Rajasthan | NR | Fatehgarh-Barmer Complex |  | Between Jul-25 to Dec-25 | 7333 | 0 | 7333 |  | 4185 | 3450 | 7635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Dec'25 onwards (Ph-III) (Upto Mar' 27(Ph-IV/V) )
5a | Rajasthan | NR | Fatehgarh-III | Section-II | Between Jul-25 to Dec-25 | 5233 | 0 | 5233 | Jul'25 onwards | 2160 | 3450 | 5610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Dec'25 onwards- (Ph-III) (Upto Mar'27 (Ph-IV/V) )
5b | Rajasthan | NR | Fatehgarh-IV | Section-I | Between Jul-25 to Dec-25 | 2100 | 0 | 2100 | Aug'25 | 2025 | 0 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Dec'25 onwards (Ph-III) (Upto Aug26)
6 | Rajasthan | NR | Ramgarh |  | Between Jul-25 to Dec-25 | 4000 | 0 | 4000 | Sep'25 | 1200 | 2784 | 3984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650W-3100MW : Bhadla HVDC (Jan'29 Pole-1 & Jul'29 Pole-2) Transmission system for evacuation of power (beyond 2.9GW and upto 4 GW) HVDC sys. is under planning (Exp Comm. up to Oct'30).
7 | Rajasthan | NR | Bikaner-III |  | Between Jul-25 to Dec-25 | 7000 | 3000 | 4000 | Dec'25 | 2267 | 2400 | 4667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000MW: Dec'25 (Ph-IV, Part-I&II) (Upto Aug'26) 667MW: with Bikaner-IV tr. System having schedule Nov'26
8 | Rajasthan | NR | Fatehgarh-IV | Section-II | Between Jul-26 to Dec-31 | 9000 | 4000 | 5000 | Aug'26 | 3480 | 1500 | 4980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hybrid RE Potential : 9GW (Wind+Solar) along with BESS (4 GW), S/s Evacuation Capacity: 5GW For 4000MW (out of 5000MW): Nov'26 (Ph-IV, Part-II). For evacuation of balance 980MW : Dec'26 (Ph-IV, Part-IV).
9 | Rajasthan | NR | Barmer-I |  | Between Jul-26 to Dec-31 | 5500 | 1500 | 4000 | Nov'26 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hybrid RE Potential: 5.5GW (Wind+Solar) along with BESS (1.5 GW), S/s Evacuation Capacity: 4GW. About 1.5GW: Nov'26 (Ph-IV, Part-II) For evacuation of >1.5GW (upto 4GW) : Upto Mar'27 (Ph-IV, Part-IV & Ph- V Part-1) For application of >4GW, connectvity will be provided at Barmer-II PS for which system is under approval (sch. Pole-I : Sep'29, Pole-2: Mar'30 ).
10 | Rajasthan | NR | Barmer-II |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Jan'30 to Jul'30 (HVDC) | 2080 | 3812 | 5892 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 0 | 108 | HVDC Corridor is recently approved for total 6 GW capacity (Expected Sch.Pole-1:Jan'30, Pole-2: Jul'30].
11 | Rajasthan | NR | Barmer-III |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Oct'30 to Apr'31 (HVDC) | 2462 | 3450 | 5912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 88 | HVDC Corridor is under planning for total 6 GW capacity (Expected Sch.Pole-1:Oct'30, Pole-2: Apr'31].
12 | Rajasthan | NR | Barmer-IV |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Jun'31 to Dec'31 (HVDC) | 600 | 2103 | 2703 | 575 | 950 | 1525 | 0 | 0 | 0 | 1772 | 0 | 1772 | HVDC Transmission system (6GW) for evacuation of power from Barmer- IV complexes is under planning (Exp. Comm. Schedule up to Dec'31).
13 | Rajasthan | NR | Bikaner-IV |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Nov'26 | 3150 | 2850 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Comprehensive Transmission scheme for Bikaner-IV PS (6GW) is under implementation (Sch. -Nov'26).
14 | Rajasthan | NR | Bikaner-V |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Apr'30 to Oct'30 (HVDC) | 3490 | 2510 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Corridor is being planned for total 6 GW capacity (Expected Sch.Pole- 1:Apr'30, Pole-2: Oct'30].
15 | Rajasthan | NR | Bikaner-VI |  | Between Jul-26 to Dec-31 | 3548 | 0 | 3548 | Jun'31 to Dec'31 (HVDC) | 600 | 0 | 600 | 1750 | 600 | 2350 | 0 | 0 | 0 | 1850 | 1200 | 3050 | HVDC Transmission system (6GW) for evacuation of power from Bikaner- VI complexes is under planning (Exp. Comm. Schedule up to Dec'31).
16 | Rajasthan | NR | Sirohi |  | Between Jul-26 to Dec-31 | 3000 | 1000 | 2000 | Aug'26 | 1400 | 700 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Connectivity at Sirohi PS will be granted upto 2 GW only. Tr. System for evacuation of power from Sirohi PS is under implementation (sch. Mar'27). Beyond 2 GW in Sirohi complex, HVDC Transmission system for evacuation of power from Jalore complex (Jalore/Sanchore/Sirohi) for comined RE capacity of 6GW is under planning (HVDC) (Exp. Comm. Schedule up to Jun'31).
17 | Rajasthan | NR | Bhadla-III | Section linked to Bhadla HVDC station & system | Between Jul-26 to Dec-31 | 3000 | 0 | 3000 | Jan'29 (Pole-1) to Jul'29 (Pole-2) | 1550 | 1450 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700MW : Jun'25 onwards (Upto Aug'26): cumulative at Ramgarh & Bhadla-III: Raj. (Ph-III) Beyond 3700MW : Bhadla HVDC (Jan'29 Pole-1 & Jul'29 Pole-2).
18 | Rajasthan | NR | Bhadla-IV |  | Between Jul-26 to Dec-31 | 5000 | 2000 | 2000 | Apr'30 to Oct'30 (HVDC) | 300 | 5525 | 5825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 175 | Transmission system for evacauation of power from Bhadla-IV PS is under planning (6GW HVDC) (Expected Sch.Pole-1:Apr'30, Pole-2: Oct'30]). Connectivity beyond 6 GW at Bhadla-IV PS to be processed at Bhadla-V (Bhadla complex) for which transmission system (HVDC) from Bhadla Complex to be evolved.
19 | Rajasthan | NR | Merta-II |  | Between Jul-26 to Dec-31 | 2000 | 0 | 2000 | Dec'26 | 2100 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tr. System for evacuation of power from Sirohi PS is under implementation (sch. Mar'27). Beyond 2 GW in Merta/Nagaur complex, Tr. system (HVDC) to be evolved
20 | Rajasthan | NR | Jalore |  | Between Jul-26 to Dec-31 | 3000 | 1000 | 2000 | Dec'30 to Jun'31 (HVDC) | 1150 | 1000 | 2150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Transmission system for evacuation of power from Jalore complex (Jalore/Sanchore/Sirohi) for comined RE capacity of 6GW is under planning (HVDC) (Exp. Comm. Schedule up to Jun'31). At present 5220MW capacity granted/Agreed for grant at Sanchore & Jalore combindely. Balance capacity 780MW (6000-5220) is available for connectvity at Jalore/Sanchore/Sirohi-II PS
21 | Rajasthan | NR | Sanchore |  | Between Jul-26 to Dec-31 | 3000 | 1000 | 2000 | Dec'30 to Jun'31 (HVDC) | 1050 | 2020 | 3070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Transmission system for evacuation of power from Jalore complex (Jalore/Sanchore/Sirohi) for comined RE capacity of 6GW is under planning (HVDC) (Exp. Comm. Schedule up to Jun'31). At present 5220MW capacity granted/agreed for grant at Sanchore & Jalore combindely. Balance capacity 780MW (6000-5220) is available for connectvity at Jalore/Sanchore/Sirohi-II PS
22 | Rajasthan | NR | Ramgarh-II |  | Between Jul-26 to Dec-31 | 8000 | 3000 | 5000 | Apr'30 to Oct'30 (HVDC) | 1647 | 3300 | 4947 | 150 | 0 | 150 | 0 | 0 | 0 | 19 | 0 | 19 | Hybrid RE Potential: 8GW (Wind+Solar) along with BESS (3 GW), S/s Evacuation Capacity: 5GW. HVDC Transmission system for evacuation of power from Ramgarh-II PS for evacuation of 6GW RE power (Ramgarh-I:0.9GW, Ramgarh-II:5.1 GW) is under planning (Exp Comm. Schedule up to Oct'30). Connectivity beyond 5.1 GW at Ramgarh-II PS to be processed at Ramgarh- III PS (Ramgarh complex) for which transmission system (HVDC) from Ramgarh Complex to be evolved.
23 | Rajasthan | NR | Ramgarh-III |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Jun'31 to Dec'31 (HVDC) | 930 | 3282 | 4212 | 500 | 1177.33 | 1677 | 0 | 0 | 0 | 111 | 0 | 111 | HVDC Transmission system (6GW) for evacuation of power from Ramgarh-III complexes is under planning (Exp. Comm. Schedule up to Dec'31).
24 | Rajasthan | NR | Pali |  | Between Jul-26 to Dec-31 | 3000 | 1000 | 2000 | Dec'30 to Jun'31 (HVDC) | 1705 | 600 | 2305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Transmission system (6GW) for combined capacity 6GW RE from Nagaur(Merta) & Pali complexes is under planning (Exp. Comm. Schedule up to Jun'31). At present 3205MW capacity granted/agreed for grant at Pali and Merta-III combindely. Balance capacity 2795MW (6000-3205)( is available for connectvity at Pali/Merta-III PS
25 | Rajasthan | NR | Merta-III |  | Between Jul-26 to Dec-31 |  |  |  | Dec'30 to Jun'31 (HVDC) | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 900 | 1100 | Beyond 2 GW in Merta/Nagaur complex, HVDC Transmission system (6GW) for combined capacity 6GW RE from Nagaur(Merta) & Pali complexes is under planning (Exp. Comm. Schedule up to Jun'31). At present 3205MW capacity granted/agreed for grant at Pali and Merta-III combindely. Balance capacity 2795MW (6000-3205)( is available for connectvity at Pali/Merta-III PS
26 | Ladakh | NR | Pang | Leh | Between Jul-26 to Dec-31 | 13000 | 0 | 13000 | 2029-30 (VSC HVDC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | Leh - Ensviaged RE Capacity (13 GW) for connnectivity in Ladakh including Solar, Wind & BESS. However, net evacaution capacity of HVDC tr. system is 5000MW. Connectivity applications in Ladakh are yet to be received.
27 | Rajasthan | NR | Bhadla-V |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Mar'31 to Sep'31 (HVDC) | 1300 | 4700 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Transmission system (6GW) for evacuation of power from Bhadla- V complexes is under planning (Exp. Comm. Schedule up to Sep'31).
28 | Rajasthan | NR | Bhadla-VI |  | Between Jul-26 to Dec-31 | 4830 | 0 | 4830 | Mar'32 to Sep'32 (HVDC) | 300 | 0 | 300 | 700 | 2100 | 2800 | 0 | 0 | 0 | 2000 | 900 | 2900 | HVDC Transmission system (6GW) for evacuation of power from Bhadla- VI complexes is under planning (Exp. Comm. Schedule up to Sep'32).
29 | Andhra Pradesh | SR | NP Kunta |  | Existing | 1500 | 0 | 1500 | Existing | 2200 | 0 | 2200 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 MW : Existing Tr. System 5th & 6th ICT (Dec'25) 7th ICT required for appplications beyond 2.5 GW
30 | Karnataka | SR | Pavagada |  | Existing | 2050 | 0 | 2050 | Existing | 2550 | 0 | 2550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050 MW : Existing Tr. System 500 MW : Dec'25: Narendra-Pune
31 | Tamil Nadu | SR | Tuticorin-II |  | Existing | 2500 | 0 | 2500 | Existing | 2848 | 0 | 2848 | 100 | 0 | 100 | 52 | 0 | 52 |  |  |  | 1870 MW : Existing Tr. System 640 MW: Dec'25: Narendra-Pune & 6th ICT 438 MW : Mar'27 : 7th ICT
32 | Karnataka | SR | Koppal |  | Existing | 2500 | 0 | 2500 | Existing | 2753 | 0 | 2753 | 300 | 0 | 300 | 0 | 0 | 0 |  |  |  | 1260 MW : Existing Tr. System 1493 MW:Dec'25: Narendra-Pune Koppal PS has been closed for all purposes and under process applications may not be accommodated.
33 | Tamil Nadu | SR | Karur | Phase-1 | Existing | 1000 | 0 | 1000 | Existing | 918 | 0 | 918 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 100 MW : Existing Tr. System 818 MW: Dec'25: Narendra-Pune
34 | Karnataka | SR | Gadag |  | Existing | 2500 | 0 | 2500 | Existing | 2243 | 0 | 2243 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 460 MW : Existing Tr. System 1923 MW: Dec'25: Narendra-Pune
35 | Andhra Pradesh | SR | Kurnool-III |  | Existing | 4500 | 0 | 4500 | Existing | 2250 | 1850 | 4100 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Kurnool-III PS commissioned, entire system expected by Sept'25 Kurnool-III PS has been closed for all purposes.
36 | Tamil Nadu | SR | Karur | Phase-II | Between Jul-25 to Dec-25 | 1500 | 0 | 1500 | Feb'26 | 1351 | 0 | 1351 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | Augmentation of ICTs and transmission line is required to accommodate under process applications Entire quantum of the under process applicatiuon cannot be accomadetd
37 | Karnataka | SR | Koppal-II/ Gadag-II Complex |  | Between Jul-25 to Dec-25 | 8000 | 2000 | 6000 |  | 6620 | 1800 | 8420 | 635 | 0 | 635 | 600 | 0 | 600 | 0 | 0 | 0
37a | Karnataka | SR | Koppal-II |  | Between Jul-25 to Dec-25 | 4000 | 1000 | 3000 | Dec'25 | 3305 | 0 | 3305 | 175 | 0 | 175 | 600 | 0 | 600 | 0 |  | 0 | Dec'25
37b | Karnataka | SR | Gadag-II |  | Between Jul-25 to Dec-25 | 4000 | 1000 | 3000 | Dec'25 | 3316 | 1800 | 5116 | 460 | 0 | 460 | 0 | 0 | 0 | 0 |  | 0 | Dec'25 PSP not considered for determination of margins.
38 | Andhra Pradesh | SR | Ananthapuram |  | Between Jul-25 to Dec-25 | 3500 | 0 | 3500 | Sept'25 | 1545 | 2484 | 4029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sept'25 Ananthapuram PS has been closed for all purposes
39 | Karnataka | SR | Pavagada | expansion with ICTs | Between Jul-25 to Dec-25 | 0 | 0 | 0 | Sept'25 | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 MW : Sep'25 : 7th ICT
40 | Karnataka | SR | Davangere Complex |  | Beyond Dec-25 | 8500 | 1000 | 7500 | Mar'27 | 7022 | 850 | 7872 | 2989 | 0 | 2989 | 0 | 0 | 0 | 0 | 0 | 0 | Mar'27 to Sep'27 (assuming SPV transfer by Mar'25)
40a | Karnataka | SR | Davangere |  | Beyond Dec-25 | 4250 | 1000 | 3250 | Mar'27 | 3388 | 850 | 4238 | 724 | 0 | 724 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 MW :Mar'27 Balance tr. System under bidding All under process applications may not be accommodated.
40b | Karnataka | SR | Bellary |  | Beyond Dec-25 | 4250 | 0 | 4250 | Sep'27 | 3634 | 0 | 3634 | 2265 | 0 | 2265 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 MW :Sep'27 Balance tr. System under bidding All under process applications may not be accommodated.
41 | Karnataka | SR | Bijapur |  | Beyond Dec-25 | 3500 | 0 | 3500 | Jan'27 | 1962 | 0 | 1962 | 4431 | 1200 | 5631 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 MW :Jan'27 All under process applications may not be accommodated.
42 | Karnataka | SR | Bidar |  | Beyond Dec-25 | 2500 | 0 | 2500 | Feb'26 | 3350 | 0 | 3350 | 1650 | 1100 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 MW : Feb'26 1000 MW: Feb'27 (Augmentation of 3x500 MVA ICTs (6th - 8th) & 1x1500 MVA ICT(4th)) Transmission system for application beyond 3.5 GW has been put-on hold by NCT
43 | Andhra Pradesh | SR | Ananthapuram/ Kurnool complex |  | Beyond Dec-25 | 19500 | 0 | 19500 |  | 10410 | 7730 | 18140 | 0 | 1450 | 1763 | 180 | 0 | 180 | 0 | 0 | 0 | Progressivly from Mar'27 to Apr'27
43a | Andhra Pradesh | SR | Kurnool-III | Expansion with ICTs | Beyond Dec-25 | 4500 | 0 | 4500 | Mar'27 | 0 | 3500 | 3500 | 0 | 1450 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | • PSP not considered for determination of margins • Kurnool-III PS has been closed for all purposes. All under process applications may not be accommodated.
43b | Andhra Pradesh | SR | Ananthapuram-II |  | Beyond Dec-25 | 7500 | 0 | 7500 | Mar'27 (Ph-I) Mar'28 (Ph-II) | 5420 | 1900 | 7320 | 0 | 0 | 313 | 0 | 0 | 0 | 0 | 0 | 0 | Mar'27 (Phase-1) Progressively from Sept'27 to Mar'28 (Phase-2) All under process applications may not be accommodated.
43c | Andhra Pradesh | SR | Kurnool-IV |  | Beyond Dec-25 | 7500 | 0 | 7500 | Mar'27 (Ph-I) Mar'28 (Ph-II) | 4990 | 2330 | 7320 | 0 | 0 | 0 | 180 | 0 | 180 | 0 | 0 | 0 | Mar'27 (Phase-1) Progressively from Sept'27 to Mar'28 (Phase-2)
44 | Karnataka | SR | Tumkur-II |  | Beyond Dec-25 | 3000 | 0 | 3000 | Sep'26 | 2100 | 0 | 2100 | 2450 | 0 | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 MW : Sep'26 All under process applications may not be accommodated.
45 | Telangana | SR | Nizamabad Complex |  | Beyond Dec-25 | 5000 | 0 | 5000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 8500 | 0 | 8500 | Locations for RE potential declared in Telanagana under review by MNRE/SECI. Transmisison system put on-hold by NCT till finalization of same.
45a | Telangana | SR | Nizamabad-II |  | Beyond Dec-25 | 2000 | 0 | 2000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 2500 |  | 2500 | Locations for RE potential declared in Telanagana under review by MNRE/SECI. Transmisison system put on-hold by NCT till finalization of same.
45b | Telangana | SR | Medak |  | Beyond Dec-25 | 1500 | 0 | 1500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 3000 |  | 3000 | Locations for RE potential declared in Telanagana under review by MNRE/SECI. Transmisison system put on-hold by NCT till finalization of same.
45c | Telangana | SR | Rangareddy |  | Beyond Dec-25 | 1500 | 0 | 1500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 3000 |  | 3000 | Locations for RE potential declared in Telanagana under review by MNRE/SECI. Transmisison system put on-hold by NCT till finalization of same.
46 | Tamil Nadu | SR | Avairakulam | Off shore | Beyond Dec-25 | 500 | 0 | 500 | Dec'30 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 4500 | 0 | 4500 | Mar'2030
47 | Karnataka | SR | Pavagada | expansion with ICTs | Beyond Dec-25 | 0 | 0 | 0 | May'26 | 1150 | 0 | 1150 | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 8th, 9th & 10th ICTs : May'26 Under process applications may not be accommodated.
48 | Andhra Pradesh | SR | Ananthapuram-III |  | Beyond Dec-25 | 7500 | 0 | 7500 | Sep'28 | 3630 | 0 | 3630 | 1360 | 0 | 1360 | 2510 | 0 | 2510 | 0 | 0 | 0 | Ph-I (4.5 GW) Sep'28
49 | Andhra Pradesh | SR | Kurnool-V |  | Beyond Dec-25 | 7500 | 0 | 7500 | Sep'28 | 1330 | 0 | 1330 | 570 | 0 | 570 | 5600 | 0 | 5600 | 0 | 0 | 0 | Ph-I (4.5 GW) Sep'28
50 | Andhra Pradesh | SR | Kadapa-II |  | Beyond Dec-25 | 7500 | 0 | 7500 | Dec'28 | 600 | 0 | 600 | 0 | 0 | 0 | 1400 | 2500 | 3900 | 2000 | 1000 | 3000 | Dec'28
51 | Gujarat | WR | Bhuj complex |  | Existing | 5500 |  | 5500 | Existing | 5559 | 0 | 5559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Existing Tr. System
51a | Gujarat | WR | Bhuj |  | Existing | 3500 |  | 3500 | Existing | 3500 |  | 3500 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | Existing Tr. System.
51b | Gujarat | WR | Bhuj-II |  | Existing | 2000 |  | 2000 | Existing | 2059 |  | 2059 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Existing Tr. System.
52 | Gujarat | WR | Radhanesda |  | Existing | 700 |  | 700 | Existing | 1250 |  | 1250 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | Existing Tr. System.
53 | Gujarat | WR | Jam Khambhaliya |  | Existing | 2000 |  | 2000 | Existing | 1969 | 0 | 1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Existing Tr. System.
54 | Maharashtra | WR | Kallam | Ph-I | Existing | 1000 |  | 1000 | Existing | 916 | 0 | 916 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1GW: Commissioned
55 | Madhya Pradesh | WR | Pachora |  | Existing | 1500 |  | 1500 | Existing | 1398 |  | 1398 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 1.5GW: Commissioned
56 | Madhya Pradesh | WR | Neemuch |  | Existing | 1000 |  | 1000 | Existing | 950 |  | 950 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1GW: Commissioned
57 | Maharashtra | WR | Solapur |  | Existing | 2000 |  | 2000 | Existing |  | 2000 | 2000 |  | 0 | 0 |  | 0 | 0 |  |  |  | Sep-24: Under Scope of applicant (ReNew). NO FURTHER MARGINS LEFT BEYOND 2GW. Application for 237MW needs to be deliberated. Connectivity of (100+76+48MW) of Renew has been revoked under non- compliance of 24.6 & the matter is presently subjudice.
58 | Gujarat | WR | Khavda I | Sec I | Existing | 3000 |  | 3000 | Existing |  | 3000 | 3000 |  |  | 0 | 0 | 0 | 0 |  |  |  | 3GW: Commissioned
59 | Gujarat | WR | Khavda complex |  | Between Jul-26 to Jun'25 | 10500 |  | 10500 |  | 0 | 10500 | 10500 | 0 | 0 | 0 | 0 | 0 | 0
59a | Gujarat | WR | Khavda I | Sec II | Between Jul-26 to Jun'25 | 4500 |  | 4500 | Sec-II: Jan'25 |  | 4500 | 4500 |  |  | 0 | 0 | 0 | 0 |  |  |  | •Ph-1: 3GW - KPS1 (Comm) / KPS2: Jan'25(SCOD)/ Sep'25 (ACOD) •Ph-2: 5GW- Mar'25 (SCOD)/Nov'25 (ACOD) •Ph-3: 7GW- Dec'25 (SCOD)/ Jun'26 (ACOD)
59b | Gujarat | WR | Khavda II | Sec-I & II | Between Jul-26 to Jun'25 | 3000 |  | 3000 | Sec-I & II: Jan'25 |  | 3000 | 3000 |  |  | 0 | 0 | 0 | 0
59c | Gujarat | WR | Khvada III | Sec-I | Between Jul-26 to Jun'25 | 3000 |  | 3000 | Jan'25 |  | 3000 | 3000 |  |  | 0 | 0 | 0 | 0
60 | Madhya Pradesh | WR | Chhatarpur |  | Between Jul-26 to Jun'25 | 0 |  | 0 | Scheme dropped. | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | Scheme has been dropped as decided in NCT meeting & to be denotified by MoP.
61 | Maharashtra | WR | Kallam | Ph-II | Between Jul-26 to Jun'25 | 1000 |  | 1000 | Dec-24 (1GW) | 835 | 1022 | 1856 | 0 | 200 | 200 | 150 | 78 | 228 |  |  |  | 1GW ICTs: Dec-24 & System for 2.25GW: Under Implementation-Oct-25 (exptd) 148.75MW Connectivity granted to Anupavan has been revoked under 11A. Further, 200MW connectivity of Serentica & 117MW of Renew(MHP) has been revoked under 24.6, however, matter is presently subjudice.
62 | Gujarat | WR | Khavda complex |  | Between Jul-25 to Dec-25 | 9000 |  | 9000 |  | 0 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | •Ph-1: 3GW - Completed in Feb-24. However, 2GW at KPS2 using Ph-I system would also require KPS2 S/s (Jan'25) •Ph-2: 5GW- Mar'25 (SCOD) •Ph-3: 7GW- Dec'25 (SCOD) •Ph-4: 7GW-Nov'26 (SCOD) •Ph-V: LCC Bipole-I:Nov'28) & LCC Bipole-II: May'29 (SCOD) / VSC 48 months from SPV transfer
62a | Gujarat | WR | Khavda I | Sec-I | Between Jul-25 to Dec-25 | 1500 |  | 1500 | Sec-I ICT: Jul'25 |  | 1500 | 1500 |  |  | 0 | 0 | 0 | 0 |  |  |  | Total transformation capacity at Khavda complex (considering N-1 on each section): KPS1 - Sec-I: 4.5GW ; Sec-2: 6GW Total KPS1: 10.5GW KPS2 - Sec-I: 6GW ; Sec-2: 4.5GW Total KPS2: 10.5GW KPS3 - Sec-I: 4.5GW ; Sec-2: 4.5GW
62b | Gujarat | WR | Khavda II | Sec-I & II | Between Jul-25 to Dec-25 | 6000 |  | 6000 | Sec-I & II ICTs : Feb'26 |  | 6000 | 6000 |  | 0 | 0 | 0 | 0 | 0
62c | Gujarat | WR | Khvada III | Sec-I | Between Jul-25 to Dec-25 | 1500 |  | 1500 | Sec-I ICT : Jul'25 |  | 1500 | 1500 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | Total KPS3: 9GW Total (KPS1, KPS2 & KPS3): 30GW
63 | Gujarat | WR | Bhuj |  | Between Jul-25 to Dec-25 | 500 |  | 500 | Jul'25 | 464 |  | 464 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 9th ICT at Bhuj PS shall be required for applications beyond 3500MW NO FURTHER MARGINS ARE NOW AVAILABLE. Applications reeived beyond margins.
64 | Gujarat | WR | Lakadia |  | Between Jul-25 to Dec-25 | 1000 |  | 1000 | Oct'25 | 950 | 0 | 950 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Oct-25: Under Implementation
65 | Maharashtra | WR | Parli |  | Between Jul-25 to Dec-25 | 1000 |  | 1000 | Dec'25 (Bay) |  | 800 | 800 |  | 0 | 0 |  | 200 | 200 |  |  |  | 400kV bay under construction (suitable for 1000MW evacuation): Dec'25
66 | Gujarat | WR | Khavda complex |  | Beyond Dec-25 | 7500 |  | 7500 |  | 0 | 19390 | 19390 | 0 | 1600 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | •Ph-1: 3GW - Completed in Feb-24. However, 2GW at KPS2 using Ph-I system would also require KPS2 S/s (Jan'25) •Ph-2: 5GW- Mar'25 (SCOD) •Ph-3: 7GW- Dec'25 (SCOD) •Ph-4: 7GW-Nov'26 (SCOD) •Ph-V: LCC Bipole-I:Nov'28) & LCC Bipole-II: May'29 (SCOD) / VSC 48 months from SPV transfer
66a | Gujarat | WR | Khavda I | Sec-I | Beyond Dec-25 | 1500 |  | 1500 | Sec-I ICT: 2026-27 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total transformation capacity at Khavda complex (considering N-1 on each section): KPS1 - Sec-I: 6GW ; Sec-2: 4.5GW Total KPS1: 10.5GW KPS2 - Sec-I: 6GW ; Sec-2: 4.5GW Total KPS2: 10.5GW KPS3 - Sec-I: 4.5GW ; Sec-2: 4.5GW Total KPS3: 9GW Total (KPS1, KPS2 & KPS3): 30GW Under Process Application received for 1250MW at KPS2 is beyond Phase- VII system.
66b | Gujarat | WR | Khavda II | Sec-I & II | Beyond Dec-25 | 1500 |  | 1500 | Sec-I ICT: 2026-27 |  | 250 | 250 |  | 1250 | 1250 | 0 | 0 | 0 |  | 0 | 0
66c | Gujarat | WR | Khvada III | Sec-I & II | Beyond Dec-25 | 4500 |  | 4500 | Sec-II ICTs: Jun-26 (4500) & 2026-27 (1500) |  | 5140 | 5140 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
66d | Gujarat | WR | Khavda IV | Sec-I & II | Beyond Dec-25 | 0 |  | 8750 | 2027-28 |  | 8750 | 8750 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The Khavda Phase-I to Phase-VII shall be required for enabling evacuation of power upto 41.5GW from Khavda area out of which Phase-VI (5.5GW) & Phase-VII (6GW HVDC) are under approval stage.
66e | Gujarat | WR | Khavda V | Sec-I | Beyond Dec-25 | 0 |  | 3750 | 2027-28 |  | 3750 | 3750 |  | 350 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | The Khavda Phase-I to Phase-VII shall be required for enabling evacuation of power upto 41.5GW from Khavda area out of which Phase-VI (5.5GW) & Phase-VII (6GW HVDC) are under approval stage. Under Process Application received for 350MW at KPS5 is beyond Phase- VII system.
67 | Maharashtra | WR | Solapur | 1.5GW | Beyond Dec-25 | 1500 |  | 1500 | Mar-26 (exptd) | 2450 | 800 | 3250 |  | 2207 | 2207 | 0 | 0 | 0 | 0 | 0 | 0 | Solapur Ph-I (1.5GW): Mar-26: Under Implementation Solapur Ph-II (2GW): On hold pending potential declaration by MNRE For balance applications received at Solapur PS beyond 3.5GW, additional System / Pooling Station may be needed. 200MW margin is available at 400kV which will be allocated to applicants in order of priority of applications at Solapur PS.
68 | Madhya Pradesh | WR | Pachora |  | Beyond Dec-25 | 2000 |  | 2000 | Feb-26 (exptd) | 2602 |  | 2602 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Rajgarh Ph-I(1.5GW): Commissioned, Ph-II (1GW): Under Implementation & Ph-III (1.5GW): Under Bidding NO FURTHER MARGINS ARE AVAILABLE (BEYOND 4000MW AT PACHORA PS).
69 | Madhya Pradesh | WR | Mandsaur |  | Beyond Dec-25 | 2000 |  | 2000 | Aug-26 (exptd) | 2998 | 1500 | 4498 |  | 2484 | 2484 | 0 | 0 | 0 | 0 | 0 | 0 | Aug-26 : Under Implementation With grant of connectivity under GNA to PSP at 400kV level (1512MW), it is considered at PSP shall not inject power under high RE period and hence not considered in given table ICT Augmentation (765/400kV as well as 400/220kV ICTs) shall be required at Mandsaur for under process applications, as applicable. NO FURTHER MARGINS ARE AVAILABLE (BEYOND 4500MW AT MANDSAUR PS). Applications received beyond 4500MW would need to be deliberated.
70 | Maharashtra | WR | Dhule |  | Beyond Dec-25 | 2000 |  | 2000 | Feb-26 (exptd) | 1976 |  | 1976 | 2245 |  | 2245 | 0 | 0 | 0 | 0 | 0 | 0 | Feb-26 (SCOD): Under Implementation. NO FURTHER MARGINS ARE AVAILABLE (BEYOND 2000MW. Applications received beyond 2000MW would require additional Tr. System to be planned.
71 | Gujarat | WR | Jamnagar |  | Beyond Dec-25 | 1000 |  | 1000 | Sep-26 (extd). 400/220kV ICT Augmentation under planning | 1000 | 0 | 1000 | 956 | 0 | 956 | 0 | 0 | 0 | 0 | 0 | 0 | 765/400kV Jamnagar S/s is presently under tendering with time-line of 24 months from SPV transfer. ICT Augmentation shall be required for injection at 220kV level. Applications received beyond 1000MW would also require additional Tr. System to be planned.
72 | Gujarat | WR | Lakadia-I |  | Beyond Dec-25 | 2000 |  | 2000 | Aug-26 (exptd) | 2550 | 0 | 2550 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | Total 3.5GW Capacity planned at Lakadia S/s and NO FURTHER MARGINS EXIST AT 220kV LEVEL OF LAKADIA S/s
73 | Gujarat | WR | Jam Khambhaliya-II / Kalyanpur |  | Beyond Dec-25 | 2000 |  | 2000 | 2027-28 | 3500 | 1000 | 4500 |  | 450 | 450 | 0 | 0 | 0 |  |  | 0 | Substation is under planning for 4.5GW in first phase.
74 | Gujarat | WR | Raghanesda | GIS | Beyond Dec-25 | 3000 |  | 3000 | Oct-27 (SCOD) | 650 | 2800 | 3450 | 1105 | 5112 | 6217 |  | 0 | 0 |  |  | 0 | Substation is under implementation. NO FURTHER MARGINS ARE NOW AVAILABLE IN UNDER BIDDING SYSTEM. After 3.5GW, Augmentation shall be required for RE beyond 3.5GW at Raghanesda PS. Applications are received beyond Substation capacity.
75 | Gujarat | WR | Bhuj-II |  | Beyond Dec-25 | 0 |  | 0 | 0.5GW: Nov'26 & 1.5GW: Dec'26 | 1442 |  | 1442 | 0 | 2759 | 2759 |  | 0 | 0 | 0 | 0 | 0 | NO FURTHER MARGINS ARE NOW AVAILABLE. For applications received beyond 2000MW, augmentation needs to be taken up. 500MW (350+50+100MW) Connectivity of Acme has been revoked based on applicants request. Further, 300MW Connectivity of Inox has been revoked under non-compliance of 24.6. The margin would be allocated to applicants after reallocation exercise in order of priority at Bhuj complex.
76 | Gujarat | WR | Jam Khambhaliya |  | Beyond Dec-25 | 1000 |  | 1000 | May'26 | 1031 | 951 | 1982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Augmentation of 400/220kV ICTs is required. Margins are shown considering 9th ICT at JK PS as confirmed by JKTL. NO FURTHER MARGINS ARE NOW AVAILABLE.
77 | Madhya Pradesh | WR | Ishanagar |  | Beyond Dec-25 | 0 |  | 0 | Feb'26 | 0 | 650 | 650 |  | 630 | 630 |  | 0 | 0 |  |  | 0 | Under Implementation. No further margins available at the substation.
78 | Madhya Pradesh | WR | Kurawar |  | Beyond Dec-25 | 0 |  | 0 | Sep'26 | 0 |  | 0 |  | 950 | 950 |  |  | 0 | 350 |  | 350 | Under Implementation
79 | Madhya Pradesh | WR | Neemuch |  | Beyond Dec-25 | 0 |  | 0 | 2027-28 | 1050 |  | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Neemuch Ph-I(1GW): Commissioned, Ph-II (1GW): Under Bidding. NO FURTHER MARGINS ARE AVAILABLE (BEYOND 2000MW AT NEEMUCH PS).
80 | Gujarat | WR | Lakadia-II | Near Chitrod | Beyond Dec-25 | 0 |  | 0 | 2027-28 | 3879 | 3621 | 7500 | 0 | 795 | 795 | 0 | 0 | 0 | 0 | 0 | 0 | Substation is uner planning for 7.5GW. Applications received beyond 7.5GW cannot be accomodated at this substation.
81 | Gujarat | WR | Bhuj |  | Beyond Dec-25 | 500 |  | 500 | 2026-27 | 460 |  | 460 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Margin of 76.4MW is being requested by pending applicants at Bhuj-II PS. Hence, no margin is left. Further, 93.5MW Connectivity of Netra & 2.1MW of Avikiran has been revoked under non-compliance of 24.6. The margin would be allocated to applicants in order of priority after reallocation exercise at Bhuj complex.
82 | Madhya Pradesh | WR | Morena | Ph-I | Beyond Dec-25 | 2500 |  | 2500 | 2027-28 | 1550 | 750 | 2300 | 350 | 500 | 850 | 0 | 0 | 0 | 850 | 0 | 850 | Ph-I (2.5GW) under bidding stage. For applications beyond 2.5GW, additional transmission system is being planned.
83 | Gujarat | WR | Mahuva Offshore | Ph-I | Beyond Dec-25 | 500 |  | 500 | 2029 | 0 |  | 0 | 0 |  | 0 | 500 |  | 500 | 0 | 0 | 0 | Scheme under implementation by POWERGRID with SCOD of Mar-29
84 | Assam | NER | Bokajan |  | Beyond Dec-25 | 1000 | 0 | 1000 | Dec-26 (exptd) | 0 | 750 | 750 | 0 | 0 | 0 | 0 | 250 | 250 | 1500 | 0 | 1500 | Under Implementation
85 | Rajasthan | NR | Bhadla Complex |  | Existing | 8430 | 0 | 8430 | Existing | 7475 | 2050 | 9525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5251.375MW: Existing 4273.625MW: Nov'25 onwards (Ph-II/Ph-III/Ph-IV) (upto Mar'27)
85a | Rajasthan | NR | Bhadla |  | Existing | 3380 | 0 | 3380 | Existing | 3580 | 0 | 3580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3580MW: Existing
85b | Rajasthan | NR | Bhadla-II |  | Existing | 5050 | 0 | 5050 | Existing | 3895 | 2050 | 5945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1671.375MW: Existing 4273.625MW: Nov'25 onwards (Ph-II/Ph-III/Ph-IV) (upto Mar'27)
86 | Rajasthan | NR | Fatehgarh-Barmer Complex |  | Existing | 9600 | 0 | 9600 | Existing | 6940 | 3200 | 10140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7225.83MW: Existing 2914.17MW: Nov'25 onwards (Ph-II/Ph-III/Ph-IV) (upto Mar'27)
86a | Rajasthan | NR | Fatehgarh |  | Existing | 2200 | 0 | 2200 | Existing | 0 | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Existing Tr. System
86b | Rajasthan | NR | Fatehgarh-II |  | Existing | 5500 | 0 | 5500 | Existing | 4460 | 1000 | 5460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3525.83MW: Existing 1934.17MW: Nov'25 onwards (Ph-II/Ph-III/Ph-IV) (upto Mar'27)
86c | Rajasthan | NR | Fatehgarh-III | Section-I | Existing | 1900 | 0 | 1900 | Existing | 2480 | 0 | 2480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500MW: Existing 480MW: Nov'25 (Ph-II) Including 2x250MW BESS granted at Fatehgarh-III (Section-I) 250MW: Existing 250MW: Mar'26
87 | Rajasthan | NR | Bikaner Complex |  | Existing | 8850 | 3000 | 5850 | Existing | 5695 | 3940 | 9635 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 2865MW: Existing 3360MW: Nov'25 onwards (Ph-II/Ph-IV/Ph-V) (upto Mar'27)
87a | Rajasthan | NR | Bikaner |  | Existing | 1850 | 0 | 1850 | Existing | 1235 | 2940 | 4175 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 2865MW: Existing 1360MW: Nov'25 onwards (Ph-II/Ph-IV/Ph-V) (Upto Mar'27)
87b | Rajasthan | NR | Bikaner-II |  | Existing | 7000 | 3000 | 4000 | Existing | 4460 | 1000 | 5460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5760MW:Nov'25 onwards (Upto Aug'26) (Ph-II/Ph-IV Part-I&II)
88 | Rajasthan | NR | Bhadla-III |  | Between Jul-25 to Dec-25 | 3500 | 0 | 3500 | Sep'25 | 2750 | 1000 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700MW : Feb'26 onwards (Upto Aug'26 (Ph-IV)): cumulative at Ramgarh & Bhadla-III: Raj. (Ph-III) Beyond 3700MW : Bhadla HVDC (Jan'29 Pole-1 & Jul'29 Pole-2) Out of 3750MW, 250MW connectvity of standalone BESS agreed for grant recently
89 | Rajasthan | NR | Fatehgarh-Barmer Complex |  | Between Jul-25 to Dec-25 | 7333 | 0 | 7333 |  | 4185 | 3450 | 7635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Dec'25 onwards (Ph-III) (Upto Mar' 27(Ph-IV/V) )
89a | Rajasthan | NR | Fatehgarh-III | Section-II | Between Jul-25 to Dec-25 | 5233 | 0 | 5233 | Jul'25 onwards | 2160 | 3450 | 5610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Dec'25 onwards- (Ph-III) (Upto Mar'27 (Ph-IV/V) )
89b | Rajasthan | NR | Fatehgarh-IV | Section-I | Between Jul-25 to Dec-25 | 2100 | 0 | 2100 | Aug'25 | 2025 | 0 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Dec'25 onwards (Ph-III) (Upto Aug26)
90 | Rajasthan | NR | Ramgarh |  | Between Jul-25 to Dec-25 | 4000 | 0 | 4000 | Sep'25 | 1200 | 2784 | 3984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650W-3100MW : Bhadla HVDC (Jan'29 Pole-1 & Jul'29 Pole-2) Transmission system for evacuation of power (beyond 2.9GW and upto 4 GW) HVDC sys. is under planning (Exp Comm. up to Oct'30).
91 | Rajasthan | NR | Bikaner-III |  | Between Jul-25 to Dec-25 | 7000 | 3000 | 4000 | Dec'25 | 2267 | 2400 | 4667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000MW: Dec'25 (Ph-IV, Part-I&II) (Upto Aug'26) 667MW: with Bikaner-IV tr. System having schedule Nov'26
92 | Rajasthan | NR | Fatehgarh-IV | Section-II | Between Jul-26 to Dec-31 | 9000 | 4000 | 5000 | Aug'26 | 3480 | 1500 | 4980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hybrid RE Potential : 9GW (Wind+Solar) along with BESS (4 GW), S/s Evacuation Capacity: 5GW For 4000MW (out of 5000MW): Nov'26 (Ph-IV, Part-II). For evacuation of balance 980MW : Dec'26 (Ph-IV, Part-IV).
93 | Rajasthan | NR | Barmer-I |  | Between Jul-26 to Dec-31 | 5500 | 1500 | 4000 | Nov'26 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hybrid RE Potential: 5.5GW (Wind+Solar) along with BESS (1.5 GW), S/s Evacuation Capacity: 4GW. About 1.5GW: Nov'26 (Ph-IV, Part-II) For evacuation of >1.5GW (upto 4GW) : Upto Mar'27 (Ph-IV, Part-IV & Ph- V Part-1) For application of >4GW, connectvity will be provided at Barmer-II PS for which system is under approval (sch. Pole-I : Sep'29, Pole-2: Mar'30 ).
94 | Rajasthan | NR | Barmer-II |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Jan'30 to Jul'30 (HVDC) | 2080 | 3812 | 5892 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 0 | 108 | HVDC Corridor is recently approved for total 6 GW capacity (Expected Sch.Pole-1:Jan'30, Pole-2: Jul'30].
95 | Rajasthan | NR | Barmer-III |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Oct'30 to Apr'31 (HVDC) | 2462 | 3450 | 5912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 88 | HVDC Corridor is under planning for total 6 GW capacity (Expected Sch.Pole-1:Oct'30, Pole-2: Apr'31].
96 | Rajasthan | NR | Barmer-IV |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Jun'31 to Dec'31 (HVDC) | 300 | 2103 | 2403 | 575 | 950 | 1525 | 0 | 0 | 0 | 2072 | 0 | 2072 | HVDC Transmission system (6GW) for evacuation of power from Barmer- IV complexes is under planning (Exp. Comm. Schedule up to Dec'31).
97 | Rajasthan | NR | Bikaner-IV |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Nov'26 | 3150 | 2850 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Comprehensive Transmission scheme for Bikaner-IV PS (6GW) is under implementation (Sch. -Nov'26).
98 | Rajasthan | NR | Bikaner-V |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Apr'30 to Oct'30 (HVDC) | 3490 | 2510 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Corridor is being planned for total 6 GW capacity (Expected Sch.Pole- 1:Apr'30, Pole-2: Oct'30].
99 | Rajasthan | NR | Bikaner-VI |  | Between Jul-26 to Dec-31 | 3548 | 0 | 3548 | Jun'31 to Dec'31 (HVDC) | 300 | 0 | 300 | 1750 | 600 | 2350 | 0 | 0 | 0 | 2150 | 1200 | 3350 | HVDC Transmission system (6GW) for evacuation of power from Bikaner- VI complexes is under planning (Exp. Comm. Schedule up to Dec'31).
100 | Rajasthan | NR | Sirohi |  | Between Jul-26 to Dec-31 | 3000 | 1000 | 2000 | Aug'26 | 1400 | 700 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Connectivity at Sirohi PS will be granted upto 2 GW only. Tr. System for evacuation of power from Sirohi PS is under implementation (sch. Mar'27). Beyond 2 GW in Sirohi complex, HVDC Transmission system for evacuation of power from Jalore complex (Jalore/Sanchore/Sirohi) for comined RE capacity of 6GW is under planning (HVDC) (Exp. Comm. Schedule up to Jun'31).
101 | Rajasthan | NR | Bhadla-III | Section linked to Bhadla HVDC station & system | Between Jul-26 to Dec-31 | 3000 | 0 | 3000 | Jan'29 (Pole-1) to Jul'29 (Pole-2) | 1550 | 1450 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700MW : Jun'25 onwards (Upto Aug'26): cumulative at Ramgarh & Bhadla-III: Raj. (Ph-III) Beyond 3700MW : Bhadla HVDC (Jan'29 Pole-1 & Jul'29 Pole-2).
102 | Rajasthan | NR | Bhadla-IV |  | Between Jul-26 to Dec-31 | 5000 | 2000 | 2000 | Apr'30 to Oct'30 (HVDC) | 300 | 5525 | 5825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 175 | Transmission system for evacauation of power from Bhadla-IV PS is under planning (6GW HVDC) (Expected Sch.Pole-1:Apr'30, Pole-2: Oct'30]). Connectivity beyond 6 GW at Bhadla-IV PS to be processed at Bhadla-V (Bhadla complex) for which transmission system (HVDC) from Bhadla Complex to be evolved.
103 | Rajasthan | NR | Merta-II |  | Between Jul-26 to Dec-31 | 2000 | 0 | 2000 | Dec'26 | 2100 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tr. System for evacuation of power from Sirohi PS is under implementation (sch. Mar'27). Beyond 2 GW in Merta/Nagaur complex, Tr. system (HVDC) to be evolved
104 | Rajasthan | NR | Jalore |  | Between Jul-26 to Dec-31 | 3000 | 1000 | 2000 | Dec'30 to Jun'31 (HVDC) | 1150 | 1000 | 2150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Transmission system for evacuation of power from Jalore complex (Jalore/Sanchore/Sirohi) for comined RE capacity of 6GW is under planning (HVDC) (Exp. Comm. Schedule up to Jun'31). At present 5220MW capacity granted/Agreed for grant at Sanchore & Jalore combindely. Balance capacity 780MW (6000-5220) is available for connectvity at Jalore/Sanchore/Sirohi-II PS
105 | Rajasthan | NR | Sanchore |  | Between Jul-26 to Dec-31 | 3000 | 1000 | 2000 | Dec'30 to Jun'31 (HVDC) | 1050 | 2020 | 3070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Transmission system for evacuation of power from Jalore complex (Jalore/Sanchore/Sirohi) for comined RE capacity of 6GW is under planning (HVDC) (Exp. Comm. Schedule up to Jun'31). At present 5220MW capacity granted/agreed for grant at Sanchore & Jalore combindely. Balance capacity 780MW (6000-5220) is available for connectvity at Jalore/Sanchore/Sirohi-II PS
106 | Rajasthan | NR | Ramgarh-II |  | Between Jul-26 to Dec-31 | 8000 | 3000 | 5000 | Apr'30 to Oct'30 (HVDC) | 1447 | 3300 | 4747 | 150 | 0 | 150 | 0 | 0 | 0 | 219 | 0 | 219 | Hybrid RE Potential: 8GW (Wind+Solar) along with BESS (3 GW), S/s Evacuation Capacity: 5GW. HVDC Transmission system for evacuation of power from Ramgarh-II PS for evacuation of 6GW RE power (Ramgarh-I:0.9GW, Ramgarh-II:5.1 GW) is under planning (Exp Comm. Schedule up to Oct'30). Connectivity beyond 5.1 GW at Ramgarh-II PS to be processed at Ramgarh- III PS (Ramgarh complex) for which transmission system (HVDC) from Ramgarh Complex to be evolved.
107 | Rajasthan | NR | Ramgarh-III |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Jun'31 to Dec'31 (HVDC) | 930 | 3282 | 4212 | 450 | 1177.33 | 1627 | 0 | 0 | 0 | 161 | 0 | 161 | HVDC Transmission system (6GW) for evacuation of power from Ramgarh-III complexes is under planning (Exp. Comm. Schedule up to Dec'31).
108 | Rajasthan | NR | Pali |  | Between Jul-26 to Dec-31 | 3000 | 1000 | 2000 | Dec'30 to Jun'31 (HVDC) | 1705 | 600 | 2305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Transmission system (6GW) for combined capacity 6GW RE from Nagaur(Merta) & Pali complexes is under planning (Exp. Comm. Schedule up to Jun'31). At present 3205MW capacity granted/agreed for grant at Pali and Merta-III combindely. Balance capacity 2795MW (6000-3205)( is available for connectvity at Pali/Merta-III PS
109 | Rajasthan | NR | Merta-III |  | Between Jul-26 to Dec-31 |  |  |  | Dec'30 to Jun'31 (HVDC) | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 900 | 1100 | Beyond 2 GW in Merta/Nagaur complex, HVDC Transmission system (6GW) for combined capacity 6GW RE from Nagaur(Merta) & Pali complexes is under planning (Exp. Comm. Schedule up to Jun'31). At present 3205MW capacity granted/agreed for grant at Pali and Merta-III combindely. Balance capacity 2795MW (6000-3205)( is available for connectvity at Pali/Merta-III PS
110 | Ladakh | NR | Pang | Leh | Between Jul-26 to Dec-31 | 13000 | 0 | 13000 | 2029-30 (VSC HVDC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | Leh - Ensviaged RE Capacity (13 GW) for connnectivity in Ladakh including Solar, Wind & BESS. However, net evacaution capacity of HVDC tr. system is 5000MW. Connectivity applications in Ladakh are yet to be received.
111 | Rajasthan | NR | Bhadla-V |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Mar'31 to Sep'31 (HVDC) | 1300 | 4700 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Transmission system (6GW) for evacuation of power from Bhadla- V complexes is under planning (Exp. Comm. Schedule up to Sep'31).
112 | Rajasthan | NR | Bhadla-VI |  | Between Jul-26 to Dec-31 | 4830 | 0 | 4830 | Mar'32 to Sep'32 (HVDC) | 300 | 0 | 300 | 700 | 2100 | 2800 | 0 | 0 | 0 | 2000 | 900 | 2900 | HVDC Transmission system (6GW) for evacuation of power from Bhadla- VI complexes is under planning (Exp. Comm. Schedule up to Sep'32).
113 | Andhra Pradesh | SR | NP Kunta |  | Existing | 1500 | 0 | 1500 | Existing | 2300 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 MW : Existing Tr. System 5th & 6th ICT (Dec'25) 7th ICT required for appplications beyond 2.5 GW
114 | Karnataka | SR | Pavagada |  | Existing | 2050 | 0 | 2050 | Existing | 2550 | 0 | 2550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050 MW : Existing Tr. System 500 MW : Dec'25: Narendra-Pune
115 | Tamil Nadu | SR | Tuticorin-II |  | Existing | 2500 | 0 | 2500 | Existing | 2948 | 0 | 2948 | 0 | 0 | 0 | 52 | 0 | 52 |  |  |  | 1870 MW : Existing Tr. System 640 MW: Dec'25: Narendra-Pune & 6th ICT 438 MW : Mar'27 : 7th ICT
116 | Karnataka | SR | Koppal |  | Existing | 2500 | 0 | 2500 | Existing | 2753 | 0 | 2753 | 300 | 0 | 300 | 0 | 0 | 0 |  |  |  | 1260 MW : Existing Tr. System 1493 MW:Dec'25: Narendra-Pune Koppal PS has been closed for all purposes and under process applications may not be accommodated.
117 | Tamil Nadu | SR | Karur | Phase-1 | Existing | 1000 | 0 | 1000 | Existing | 918 | 0 | 918 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 100 MW : Existing Tr. System 818 MW: Dec'25: Narendra-Pune
118 | Karnataka | SR | Gadag |  | Existing | 2500 | 0 | 2500 | Existing | 2243 | 0 | 2243 | 0 | 0 | 0 | 143 | 0 | 143 |  |  |  | 460 MW : Existing Tr. System 1923 MW: Dec'25: Narendra-Pune
119 | Andhra Pradesh | SR | Kurnool-III |  | Existing | 4500 | 0 | 4500 | Existing | 2250 | 1850 | 4100 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Kurnool-III PS commissioned, entire system expected by Sept'25 Kurnool-III PS has been closed for all purposes.
120 | Tamil Nadu | SR | Karur | Phase-II | Between Jul-25 to Dec-25 | 1500 | 0 | 1500 | Feb'26 | 1351 | 0 | 1351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Augmentation of ICTs and transmission line is required to accommodate under process applications Entire quantum of the under process applicatiuon cannot be accomadetd
121 | Karnataka | SR | Koppal-II/ Gadag-II Complex |  | Between Jul-25 to Dec-25 | 8000 | 2000 | 6000 |  | 6538 | 1800 | 8338 | 635 | 0 | 635 | 696 | 0 | 696 | 0 | 0 | 0
121a | Karnataka | SR | Koppal-II |  | Between Jul-25 to Dec-25 | 4000 | 1000 | 3000 | Dec'25 | 3305 | 0 | 3305 | 175 | 0 | 175 | 696 | 0 | 696 | 0 |  | 0 | Dec'25
121b | Karnataka | SR | Gadag-II |  | Between Jul-25 to Dec-25 | 4000 | 1000 | 3000 | Dec'25 | 3233 | 1800 | 5033 | 460 | 0 | 460 | 0 | 0 | 0 | 0 |  | 0 | Dec'25 PSP not considered for determination of margins.
122 | Andhra Pradesh | SR | Ananthapuram |  | Between Jul-25 to Dec-25 | 3500 | 0 | 3500 | Sept'25 | 1545 | 2484 | 4029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sept'25 Ananthapuram PS has been closed for all purposes
123 | Karnataka | SR | Pavagada | expansion with ICTs | Between Jul-25 to Dec-25 | 0 | 0 | 0 | Sept'25 | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 MW : Sep'25 : 7th ICT
124 | Karnataka | SR | Davangere Complex |  | Beyond Dec-25 | 8500 | 1000 | 7500 | Mar'27 | 7022 | 850 | 7872 | 2989 | 0 | 2989 | 0 | 0 | 0 | 0 | 0 | 0 | Mar'27 to Sep'27 (assuming SPV transfer by Mar'25)
124a | Karnataka | SR | Davangere |  | Beyond Dec-25 | 4250 | 1000 | 3250 | Mar'27 | 3388 | 850 | 4238 | 724 | 0 | 724 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 MW :Mar'27 Balance tr. System under bidding All under process applications may not be accommodated.
124b | Karnataka | SR | Bellary |  | Beyond Dec-25 | 4250 | 0 | 4250 | Sep'27 | 3634 | 0 | 3634 | 2265 | 0 | 2265 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 MW :Sep'27 Balance tr. System under bidding All under process applications may not be accommodated.
125 | Karnataka | SR | Bijapur |  | Beyond Dec-25 | 3500 | 0 | 3500 | Jan'27 | 1962 | 0 | 1962 | 4431 | 1200 | 5631 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 MW :Jan'27 All under process applications may not be accommodated.
126 | Karnataka | SR | Bidar |  | Beyond Dec-25 | 2500 | 0 | 2500 | Feb'26 | 3350 | 0 | 3350 | 1450 | 1100 | 2550 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 MW : Feb'26 1000 MW: Feb'27 (Augmentation of 3x500 MVA ICTs (6th - 8th) & 1x1500 MVA ICT(4th)) Transmission system for application beyond 3.5 GW has been put-on hold by NCT
127 | Andhra Pradesh | SR | Ananthapuram/ Kurnool complex |  | Beyond Dec-25 | 19500 | 0 | 19500 |  | 9910 | 7730 | 17640 | 13 | 1450 | 1463 | 860 | 0 | 860 | 0 | 0 | 0 | Progressivly from Mar'27 to Apr'27
127a | Andhra Pradesh | SR | Kurnool-III | Expansion with ICTs | Beyond Dec-25 | 4500 | 0 | 4500 | Mar'27 | 0 | 3500 | 3500 | 0 | 1450 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | • PSP not considered for determination of margins • Kurnool-III PS has been closed for all purposes. All under process applications may not be accommodated.
127b | Andhra Pradesh | SR | Ananthapuram-II |  | Beyond Dec-25 | 7500 | 0 | 7500 | Mar'27 (Ph-I) Mar'28 (Ph-II) | 5170 | 1900 | 7070 | 13 | 0 | 13 | 430 | 0 | 430 | 0 | 0 | 0 | Mar'27 (Phase-1) Progressively from Sept'27 to Mar'28 (Phase-2) All under process applications may not be accommodated.
127c | Andhra Pradesh | SR | Kurnool-IV |  | Beyond Dec-25 | 7500 | 0 | 7500 | Mar'27 (Ph-I) Mar'28 (Ph-II) | 4740 | 2330 | 7070 | 0 | 0 | 0 | 430 | 0 | 430 | 0 | 0 | 0 | Mar'27 (Phase-1) Progressively from Sept'27 to Mar'28 (Phase-2)
128 | Karnataka | SR | Tumkur-II |  | Beyond Dec-25 | 3000 | 0 | 3000 | Sep'26 | 2100 | 0 | 2100 | 2450 | 0 | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 MW : Sep'26 All under process applications may not be accommodated.
129 | Telangana | SR | Nizamabad Complex |  | Beyond Dec-25 | 5000 | 0 | 5000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 8500 | 0 | 8500 | Locations for RE potential declared in Telanagana under review by MNRE/SECI. Transmisison system put on-hold by NCT till finalization of same.
129a | Telangana | SR | Nizamabad-II |  | Beyond Dec-25 | 2000 | 0 | 2000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 2500 |  | 2500 | Locations for RE potential declared in Telanagana under review by MNRE/SECI. Transmisison system put on-hold by NCT till finalization of same.
129b | Telangana | SR | Medak |  | Beyond Dec-25 | 1500 | 0 | 1500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 3000 |  | 3000 | Locations for RE potential declared in Telanagana under review by MNRE/SECI. Transmisison system put on-hold by NCT till finalization of same.
129c | Telangana | SR | Rangareddy |  | Beyond Dec-25 | 1500 | 0 | 1500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 3000 |  | 3000 | Locations for RE potential declared in Telanagana under review by MNRE/SECI. Transmisison system put on-hold by NCT till finalization of same.
130 | Tamil Nadu | SR | Avairakulam | Off shore | Beyond Dec-25 | 500 | 0 | 500 | Dec'30 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 4500 | 0 | 4500 | Mar'2030
131 | Karnataka | SR | Pavagada | expansion with ICTs | Beyond Dec-25 | 0 | 0 | 0 | May'26 | 1150 | 0 | 1150 | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 8th, 9th & 10th ICTs : May'26 Under process applications may not be accommodated.
132 | Andhra Pradesh | SR | Ananthapuram-III |  | Beyond Dec-25 | 7500 | 0 | 7500 | Sep'28 | 4190 | 800 | 4990 | 1500 | 0 | 1500 | 1810 | 0 | 1810 | 0 | 0 | 0 | Ph-I (4.5 GW) Sep'28
133 | Andhra Pradesh | SR | Kurnool-V |  | Beyond Dec-25 | 7500 | 0 | 7500 | Sep'28 | 1380 | 0 | 1380 | 820 | 0 | 820 | 5300 | 0 | 5300 | 0 | 0 | 0 | Ph-I (4.5 GW) Sep'28
134 | Andhra Pradesh | SR | Kadapa-II |  | Beyond Dec-25 | 7500 | 0 | 7500 | Dec'28 | 300 | 0 | 300 | 950 | 0 | 950 | 750 | 2500 | 3250 | 2000 | 1000 | 3000 | Dec'28
135 | Gujarat | WR | Bhuj complex |  | Existing | 5500 |  | 5500 | Existing | 5559 | 0 | 5559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Existing Tr. System
135a | Gujarat | WR | Bhuj |  | Existing | 3500 |  | 3500 | Existing | 3500 |  | 3500 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | Existing Tr. System.
135b | Gujarat | WR | Bhuj-II |  | Existing | 2000 |  | 2000 | Existing | 2059 |  | 2059 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Existing Tr. System.
136 | Gujarat | WR | Radhanesda |  | Existing | 700 |  | 700 | Existing | 1250 |  | 1250 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | Existing Tr. System.
137 | Gujarat | WR | Jam Khambhaliya |  | Existing | 2000 |  | 2000 | Existing | 1969 | 0 | 1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Existing Tr. System.
138 | Maharashtra | WR | Kallam | Ph-I | Existing | 1000 |  | 1000 | Existing | 916 | 0 | 916 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1GW: Commissioned
139 | Madhya Pradesh | WR | Pachora |  | Existing | 1500 |  | 1500 | Existing | 1398 |  | 1398 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 1.5GW: Commissioned
140 | Madhya Pradesh | WR | Neemuch |  | Existing | 1000 |  | 1000 | Existing | 950 |  | 950 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1GW: Commissioned
141 | Maharashtra | WR | Solapur |  | Existing | 2000 |  | 2000 | Existing |  | 2000 | 2000 |  | 0 | 0 |  | 0 | 0 |  |  |  | Sep-24: Under Scope of applicant (ReNew). NO FURTHER MARGINS LEFT BEYOND 2GW. Application for 237MW needs to be deliberated. Connectivity of (100+76+48MW) of Renew has been revoked under non- compliance of 24.6 & the matter is presently subjudice.
142 | Gujarat | WR | Khavda complex |  | Existing | 13500 |  | 13500 |  | 0 | 13500 | 13500 | 0 | 0 | 0 | 0 | 0 | 0
142a | Gujarat | WR | Khavda I | Sec I | Existing | 3000 |  | 3000 | Existing |  | 3000 | 3000 |  |  | 0 | 0 | 0 | 0 |  |  |  | 3GW: Commissioned
142b | Gujarat | WR | Khavda I | Sec II | Existing | 4500 |  | 4500 | Existing |  | 4500 | 4500 |  |  | 0 | 0 | 0 | 0 |  |  |  | •Ph-1: 3GW - KPS1 (Comm) / KPS2: Jan'25(SCOD)/ Sep'25 (ACOD) •Ph-2: 5GW- Mar'25 (SCOD)/Nov'25 (ACOD) •Ph-3: 7GW- Dec'26 (Exp. COD)/ Jun'26 (ACOD)
142c | Gujarat | WR | Khavda II | Sec-I & II | Existing | 3000 |  | 3000 | 3000MVA ICTs charged |  | 3000 | 3000 |  |  | 0 | 0 | 0 | 0
142d | Gujarat | WR | Khvada III | Sec-I | Existing | 3000 |  | 3000 | Existing |  | 3000 | 3000 |  |  | 0 | 0 | 0 | 0
143 | Madhya Pradesh | WR | Chhatarpur |  | Existing | 0 |  | 0 | Scheme dropped. | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | Scheme has been dropped as decided in NCT meeting & to be denotified by MoP.
144 | Maharashtra | WR | Kallam | Ph-II | Existing | 1000 |  | 1000 | Existing | 685 | 1022 | 1706 | 0 | 200 | 200 | 300 | 78 | 378 |  |  |  | 1GW ICTs: Dec-24 & System for 2.25GW: Under Implementation-Oct-25 (exptd) 148.75MW Connectivity granted to Anupavan has been revoked under 11A. Further, 200MW connectivity of Serentica & 117MW of Renew(MHP) has been revoked under 24.6, however, matter is presently subjudice.
145 | Gujarat | WR | Khavda complex |  | Between Jul-25 to Dec-25 | 9000 |  | 9000 |  | 0 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | •Ph-1: 3GW - Completed in Feb-24. However, 2GW at KPS2 using Ph-I system would also require KPS2 S/s (Nov'25) •Ph-2: 5GW- Dec'25 (Exp. COD) •Ph-3: 7GW- Dec'26 (Exp. COD) •Ph-4: 7GW-Nov'26 (SCOD) •Ph-V: LCC Bipole-I:Nov'28) & LCC Bipole-II: May'29 (SCOD) / VSC 48 months from SPV transfer
145a | Gujarat | WR | Khavda I | Sec-I | Between Jul-25 to Dec-25 | 1500 |  | 1500 | Sec-I ICT:commissioned on 25.07.2025 |  | 1500 | 1500 |  |  | 0 | 0 | 0 | 0 |  |  |  | Total transformation capacity at Khavda complex (considering N-1 on each section): KPS1 - Sec-I: 4.5GW ; Sec-2: 6GW Total KPS1: 10.5GW KPS2 - Sec-I: 6GW ; Sec-2: 4.5GW Total KPS2: 10.5GW KPS3 - Sec-I: 4.5GW ; Sec-2: 4.5GW Total KPS3: 9GW Total (KPS1, KPS2 & KPS3): 30GW
145b | Gujarat | WR | Khavda II | Sec-I & II | Between Jul-25 to Dec-25 | 6000 |  | 6000 | Sec-I & II ICTs: 28.02.2025 (SCOD) Exp. COD: Jun'26 |  | 6000 | 6000 |  | 0 | 0 | 0 | 0 | 0
145c | Gujarat | WR | Khvada III | Sec-I | Between Jul-25 to Dec-25 | 1500 |  | 1500 | Sec-I ICT : 07.07.2025 (SCOD) Exp. COD: Mar-26 |  | 1500 | 1500 |  | 0 | 0 | 0 | 0 | 0
146 | Gujarat | WR | Bhuj |  | Between Jul-25 to Dec-25 | 500 |  | 500 | Jul'25 (SCOD) Jan-26 (Exp. COD) | 464 |  | 464 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 9th ICT at Bhuj PS shall be required for applications beyond 3500MW NO FURTHER MARGINS ARE NOW AVAILABLE. Applications reeived beyond margins.
147 | Gujarat | WR | Lakadia |  | Between Jul-25 to Dec-25 | 1000 |  | 1000 | Dec'25 | 950 | 0 | 950 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Dec-25: Under Implementation
148 | Maharashtra | WR | Parli |  | Between Jul-25 to Dec-25 | 1000 |  | 1000 | Dec'25 (Bay) |  | 800 | 800 |  | 0 | 0 |  | 200 | 200 |  |  |  | 400kV bay under construction (suitable for 1000MW evacuation): Dec'25
149 | Gujarat | WR | Khavda complex |  | Beyond Dec-25 | 7500 |  | 7500 |  | 0 | 19390 | 19390 | 0 | 1600 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | •Ph-1: 3GW - Completed in Feb-24. However, 2GW at KPS2 using Ph-I system would also require KPS2 S/s (Nov'25) •Ph-2: 5GW- Dec'25 (Exp. COD) •Ph-3: 7GW- Dec'26 (Exp. COD) •Ph-4: 7GW-Nov'26 (SCOD) •Ph-V: LCC Bipole-I:Nov'28) & LCC Bipole-II: May'29 (SCOD) / VSC 48 months from SPV transfer
149a | Gujarat | WR | Khavda I | Sec-I | Beyond Dec-25 | 1500 |  | 1500 | 18.02.2027 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total transformation capacity at Khavda complex (considering N-1 on each section): KPS1 - Sec-I: 6GW ; Sec-2: 4.5GW Total KPS1: 10.5GW KPS2 - Sec-I: 6GW ; Sec-2: 4.5GW Total KPS2: 10.5GW KPS3 - Sec-I: 4.5GW ; Sec-2: 4.5GW Total KPS3: 9GW Total (KPS1, KPS2 & KPS3): 30GW Under Process Application received for 1250MW at KPS2 is beyond Phase- VII system.
149b | Gujarat | WR | Khavda II | Sec-I & II | Beyond Dec-25 | 1500 |  | 1500 | 18.02.2027 |  | 250 | 250 |  | 1250 | 1250 | 0 | 0 | 0 |  | 0 | 0
149c | Gujarat | WR | Khvada III | Sec-I & II | Beyond Dec-25 | 4500 |  | 4500 | Sec-II ICTs: Jun-26 (4500) & 2026-27 (1500) |  | 5140 | 5140 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
149d | Gujarat | WR | Khavda IV | Sec-I & II | Beyond Dec-25 | 0 |  | 8750 | 2027-28 |  | 8750 | 8750 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The Khavda Phase-I to Phase-VII shall be required for enabling evacuation of power upto 41.5GW from Khavda area out of which Phase-VI (5.5GW) & Phase-VII (6GW HVDC) are under approval stage.
149e | Gujarat | WR | Khavda V | Sec-I | Beyond Dec-25 | 0 |  | 3750 | 2027-28 |  | 3750 | 3750 |  | 350 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | The Khavda Phase-I to Phase-VII shall be required for enabling evacuation of power upto 41.5GW from Khavda area out of which Phase-VI (5.5GW) & Phase-VII (6GW HVDC) are under approval stage. Under Process Application received for 350MW at KPS5 is beyond Phase- VII system.
150 | Maharashtra | WR | Solapur | 1.5GW | Beyond Dec-25 | 1500 |  | 1500 | Mar-26 (exptd) | 2450 | 800 | 3250 |  | 2207 | 2207 | 0 | 0 | 0 | 0 | 0 | 0 | Solapur Ph-I (1.5GW): Mar-26: Under Implementation Solapur Ph-II (2GW): On hold pending potential declaration by MNRE For balance applications received at Solapur PS beyond 3.5GW, additional System / Pooling Station may be needed. 200MW margin is available at 400kV which will be allocated to applicants in order of priority of applications at Solapur PS.
151 | Madhya Pradesh | WR | Pachora |  | Beyond Dec-25 | 2000 |  | 2000 | Feb-26 (exptd) | 2602 |  | 2602 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Rajgarh Ph-I(1.5GW): Commissioned, Ph-II (1GW): Under Implementation & Ph-III (1.5GW): Under Bidding NO FURTHER MARGINS ARE AVAILABLE (BEYOND 4000MW AT PACHORA PS).
152 | Madhya Pradesh | WR | Mandsaur |  | Beyond Dec-25 | 2000 |  | 2000 | Aug-26 (exptd) | 2998 | 1500 | 4498 |  | 2784 | 2784 | 0 | 0 | 0 | 0 | 0 | 0 | Aug-26 : Under Implementation With grant of connectivity under GNA to PSP at 400kV level (1512MW), it is considered at PSP shall not inject power under high RE period and hence not considered in given table ICT Augmentation (765/400kV as well as 400/220kV ICTs) shall be required at Mandsaur for under process applications, as applicable. NO FURTHER MARGINS ARE AVAILABLE (BEYOND 4500MW AT MANDSAUR PS). Applications received beyond 4500MW would need to be deliberated.
153 | Maharashtra | WR | Dhule |  | Beyond Dec-25 | 2000 |  | 2000 | Feb-26 (exptd) | 1976 |  | 1976 | 1945 |  | 1945 | 0 | 0 | 0 | 0 | 0 | 0 | Feb-26 (SCOD): Under Implementation. NO FURTHER MARGINS ARE AVAILABLE (BEYOND 2000MW. Applications received beyond 2000MW would require additional Tr. System to be planned.
154 | Gujarat | WR | Jamnagar |  | Beyond Dec-25 | 1000 |  | 1000 | Sep-26 (extd). 400/220kV ICT Augmentation under planning | 1000 | 0 | 1000 | 756 | 0 | 756 | 0 | 0 | 0 | 0 | 0 | 0 | 765/400kV Jamnagar S/s is presently under tendering with time-line of 24 months from SPV transfer. ICT Augmentation shall be required for injection at 220kV level. Applications received beyond 1000MW would also require additional Tr. System to be planned.
155 | Gujarat | WR | Lakadia-I |  | Beyond Dec-25 | 2000 |  | 2000 | Aug-26 (exptd) | 2550 | 0 | 2550 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | Total 3.5GW Capacity planned at Lakadia S/s and NO FURTHER MARGINS EXIST AT 220kV LEVEL OF LAKADIA S/s
156 | Gujarat | WR | Jam Khambhaliya-II / Kalyanpur |  | Beyond Dec-25 | 2000 |  | 2000 | 2027-28 | 3500 | 1000 | 4500 |  | 450 | 450 | 0 | 0 | 0 |  |  | 0 | Substation is under planning for 4.5GW in first phase.
157 | Gujarat | WR | Raghanesda | GIS | Beyond Dec-25 | 3000 |  | 3000 | Oct-27 (SCOD) | 650 | 2800 | 3450 | 1105 | 5112 | 6217 |  | 0 | 0 |  |  | 0 | Substation is under implementation. NO FURTHER MARGINS ARE NOW AVAILABLE IN UNDER BIDDING SYSTEM. After 3.5GW, Augmentation shall be required for RE beyond 3.5GW at Raghanesda PS. Applications are received beyond Substation capacity.
158 | Gujarat | WR | Bhuj-II |  | Beyond Dec-25 | 0 |  | 0 | 0.5GW: Nov'26 & 1.5GW: Dec'26 | 1442 |  | 1442 | 0 | 2759 | 2759 |  | 0 | 0 | 0 | 0 | 0 | NO FURTHER MARGINS ARE NOW AVAILABLE. For applications received beyond 2000MW, augmentation needs to be taken up. 500MW (350+50+100MW) Connectivity of Acme has been revoked based on applicants request. Further, 300MW Connectivity of Inox has been revoked under non-compliance of 24.6. The margin would be allocated to applicants after reallocation exercise in order of priority at Bhuj complex.
159 | Gujarat | WR | Jam Khambhaliya |  | Beyond Dec-25 | 1000 |  | 1000 | May'26 | 1031 | 951 | 1982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Augmentation of 400/220kV ICTs is required. Margins are shown considering 9th ICT at JK PS as confirmed by JKTL. NO FURTHER MARGINS ARE NOW AVAILABLE.
160 | Madhya Pradesh | WR | Ishanagar |  | Beyond Dec-25 | 0 |  | 0 | Feb'26 | 0 | 650 | 650 | 300 | 630 | 930 |  | 0 | 0 |  |  | 0 | Under Implementation. No further margins available at the substation.
161 | Madhya Pradesh | WR | Kurawar |  | Beyond Dec-25 | 0 |  | 0 | Sep'26 | 0 |  | 0 |  | 600 | 600 |  |  | 0 | 350 |  | 350 | Under Implementation
162 | Madhya Pradesh | WR | Neemuch |  | Beyond Dec-25 | 0 |  | 0 | 2027-28 | 1050 |  | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Neemuch Ph-I(1GW): Commissioned, Ph-II (1GW): Under Bidding. NO FURTHER MARGINS ARE AVAILABLE (BEYOND 2000MW AT NEEMUCH PS).
163 | Gujarat | WR | Lakadia-II | Near Chitrod | Beyond Dec-25 | 0 |  | 0 | 2027-28 | 3879 | 3621 | 7500 | 0 | 795 | 795 | 0 | 0 | 0 | 0 | 0 | 0 | Substation is uner planning for 7.5GW. Applications received beyond 7.5GW cannot be accomodated at this substation.
164 | Gujarat | WR | Bhuj |  | Beyond Dec-25 | 500 |  | 500 | 2026-27 | 460 |  | 460 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Margin of 76.4MW is being requested by pending applicants at Bhuj-II PS. Hence, no margin is left. Further, 93.5MW Connectivity of Netra & 2.1MW of Avikiran has been revoked under non-compliance of 24.6. The margin would be allocated to applicants in order of priority after reallocation exercise at Bhuj complex.
165 | Madhya Pradesh | WR | Morena | Ph-I | Beyond Dec-25 | 2500 |  | 2500 | 2027-28 | 1550 | 0 | 1550 | 350 | 500 | 850 | 0 | 0 | 0 | 1600 | 0 | 1600 | Ph-I (2.5GW) under bidding stage. For applications beyond 2.5GW, additional transmission system is being planned.
166 | Gujarat | WR | Mahuva Offshore | Ph-I | Beyond Dec-25 | 500 |  | 500 | 2029 | 0 |  | 0 | 0 |  | 0 | 500 |  | 500 | 0 | 0 | 0 | Scheme under implementation by POWERGRID with SCOD of Mar-29
167 | Assam | NER | Bokajan |  | Beyond Dec-25 | 1000 | 0 | 1000 | Dec-26 (exptd) | 0 | 750 | 750 | 0 | 0 | 0 | 0 | 250 | 250 | 1500 | 0 | 1500 | Under Implementation

## Non RE proposed RE Integration
State | Name of Station | Capacity (MVA) | Capacity Allocated (MW) | Margin Existing 220kV (MW) | Margin Existing 400kV (MW) | Line Bays 220kV | Line Bays 400kV | Margin with ICT 220kV (MW) | Margin with ICT 400kV (MW) | Line Bays with ICT 220kV | Line Bays with ICT 400kV | No. of Transformers Required | Remarks

## Transformation Capacity
| S.No. | Region | State | Substation | Voltage level (kV) | Existing Capacity (MVA) | Under Implementation Capacity (MVA) | Planned Capacity (MVA)
Data Scoure (Sl. No.(s)9)

## Element Status
| Element Code | Inter/Intra Tx. Element | Transmission Scheme | Transmission Scope | MVA | Status | Approval of Elements in which NCT | Mode (TBCB/RTM/NCT) | Tender Issuing Authority | Date of tender issuance | Date of Bid Submission | Execution Timeline | Tentative SCOD | Awarded To | SPV Transfer Date | Physical Progress S/s of Tx. Line | [7 empty] | Physical Progress Substation |  |  | Original SCOD | Anticipated SCOD | Remarks
[16 empty] | Length | Location | Foundation | Erection | Stringing | Foundation (%) | Erection (%) | Stringing (%) | Civil Work (%) | Equipment Received (%) | Equipment Erected (%)
24
21
Data Scoure (Sl. No.(s)1, 2, 5, 6, 10b, 10c, 10d, 10e, 12)
| EL-89310 | Rajasthan phase-II | Rajasthan phase-II Part G SPV Name | Khetri-Narela 765kV D/C Line |  |  |  | TBCB | [5 empty] | PGCIL | May-22 | 340 | 463 | 463 | 463 | 340 | 1 | 1 | 1 |  |  |  | Nov-23 | Dec - 25 | Forest Delhi (0.95 Ha, 3 locs, 82.58 Ckm): Stage I&II received.Tree felling permission received from Hon'ble Supreme court vide order dated 26.05.25.
| EL-5C100 | Rajasthan phase-II | Rajasthan phase-II Part G SPV Name | LILO of 765kV S/c Meerut – Bhiwani line at Narela |  |  |  | TBCB | [5 empty] | PGCIL | May-22 |  | 97 | 97 | 97 | 68 | 1 | 1 |  |  |  |  | Nov-23 | Oct - 25 | Line charged on 01.10.2025
| EL-DB924 | Rajasthan phase-II | Rajasthan phase-II Part G SPV Name | 3x1500MVA ,765/400kV GIS substation at Narela |  |  |  | TBCB | [5 empty] | PGCIL | May-22 | [8 empty] | 100.00% | 100.00% | 100.00% | Nov-23 | Dec - 25 | ICT-1&3 Charged on 01.10.2025 ICT-2 Charged on 02.10.2025 Bays commissioning matching with Tx. Line
| EL-44E32 | Rajasthan Phase-II | Rajasthan Phase-II Part E, Phase | Bhadla II - Sikar II 765 kV D/C line (2nd) |  |  |  | TBCB | [5 empty] | PGCIL | Mar-23 | 628 | 816 | 816 | 816 | 524.24 | 1 | 1 | 0.83 |  |  |  | Sep-24 | Dec - 25 | Stringing RoW (10 locs): Sikar Dist. (10) in Rajasthan
| EL-A523B | Khavda Phase II | Khavda Phase II Part B | 765kV D/C Lakadia PS-Ahmedabad Line |  |  |  | TBCB | [5 empty] | PGCIL | Mar-23 | 368 | 476 | 476 | 476 | 335.16 | 1 | 1 | 0.91 |  |  |  | Mar-25 | Dec - 25 | Work affected due to severe RoW Issue.
| EL-0E3A6 | Khavda Phase II | Khavda Phase II Part C | 765kV D/C Ahemdabad- New Navsari (South Gujrat) line |  |  |  | TBCB | [5 empty] | PGCIL | Mar-23 | 590 | 804 | 803 | 755 | 426.44 | 1 | 0.94 | 0.72 |  |  |  | Mar-25 | Dec - 25 | Forest (5.13 Ha):Stage-II received on 04.02.2025
| EL-730E3 | Khavda Phase II | Khavda Phase II Part C | 765/400kV 3x1500MVA Ahmedabad New S/s |  |  |  | TBCB | [5 empty] | PGCIL | Mar-23 | [8 empty] | 98.00% | 100.00% | 98.00% | Mar-25 | Dec - 25 | ICT-I & II charged on 06.09.2025. ICT-III charged on 14.11.2025.
| EL-CB900 | Khavda | Khavda | 765/400kV 4x1500MVA KPS2 New SS (GIS) | 1500 |  |  | TBCB | [5 empty] | PGCIL | Mar-23 | [8 empty] | 98.00% | 100.00% | 98.00% | Dec-24 | Dec - 25 | 330 MVAr 765kV BR-1 charged on 01.04.25. ICT-1 charged on 12.04.2025. ICT-2 charged on 25.07.2025. ICT-3 charged on 07.11.2025.
| EL-C077F | Kurnool | Kurnool | 7x500 MVA , 400/220 KV Ananthpuram S/s | 3500 |  |  | TBCB | [5 empty] | PGCIL | Sep-23 | [8 empty] | 90.00% | 85.00% | 30.00% | Sep-25 | Mar - 26 | Land (63.69 Acre) acquired
| EL-EE1F5 | Kurnool | Kurnool | Ananthpuram PS-Kurnool-III PS 400 kV (Quad moose) D/c Line |  |  |  | TBCB | [5 empty] | PGCIL | Sep-23 | 171 | 222 | 222 | 222 | 146 | 1 | 1 | 0.85 |  |  |  | Sep-25 | Dec - 25
| EL-E664A | Kurnool | Kurnool | Ananthpuram PS-Cuddapah-400kV (Quad moose) D/c Line |  |  |  | TBCB | [5 empty] | PGCIL | Sep-23 | 371 | 490 | 470 | 423 | 149.3 | 0.96 | 0.86 | 0.4 |  |  |  | Sep-25 | Mar - 26 | Foundation RoW (2 loc.): YSR kadapa (2) in Andhra pradesh.
| EL-D0625 | Rajasthan Phase-III | Rajasthan Phase-III part B1 | Bhadla-III PS – Sikar-II S/s 765 kV D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Sep-23 | 650 | 847 | 847 | 823 | 395.84 | 1 | 0.97 | 0.61 |  |  |  | Mar-25 | Dec - 25 | Stringing RoW Locs. (1 section): Didwana Kuchanamn (1) in Rajasthan. Forest :Rajasthan (24.32 Ha, 5 locs, 25 km ): Stage-I issued on 08.05.25. Stage-II issued on 08.09.2025.
| EL-34BDA | Rajasthan Phase-III | Rajasthan Phase-III part B1 | 2x1500MVA, 765/400KV & 3x500 MVA, 400/220 kV Bhadla III New S/s | 4500 |  |  | TBCB | [5 empty] | PGCIL | Sep-23 | [8 empty] | 100.00% | 99.00% | 98.00% | Mar-25 | Dec - 25
| EL-F5B43 | Rajasthan Phase-III | Rajasthan Phase-III Part C1 | 2x1500MVA, 765/400KV & 2X500MVA, 400/220 kV Ramgarh PS | 4000 |  |  | TBCB | [5 empty] | PGCIL | Oct-23 | [8 empty] | 99.00% | 100.00% | 99.00% | Apr-25 | Dec - 25 | 400kV ICT-1 Test charged from 33kV on 16.09.25. awaiting for readiness of Bhadla-3 Substation & B3S2 Line for evacuation of Power.
| EL-065D3 | Rajasthan Phase-III | Rajasthan Phase-III Part C1 | Ramgarh PS- Bhadla-III PS 765kV D/C line |  |  |  | TBCB | [5 empty] | PGCIL | Oct-23 | 372 | 467 | 467 | 467 | 372 | 1 | 1 | 1 |  |  |  | Apr-25 | Dec - 25 | Line is Ready for charging.
| EL-0A17F | Rajasthan Phase-III | Rajasthan Phase-III Part C1 | 2x300 MVAr Statcom with 4x125 MVAr MSC, 2x125 MVAr MSR at Ramgarh PS |  |  |  | TBCB | [5 empty] | PGCIL | Oct-23 | [8 empty] | 85.00% | 42.00% | 20.00% | Oct-25 | Mar - 26 | Work under progress
| EL-9B9C5 | Rajasthan Phase-III | Rajasthan Phase-III part H | Beawar-Dausa 765kV D/C line |  |  |  | TBCB | [5 empty] | PGCIL | Oct-23 | 474 | 634 | 626 | 572 | 219.86 | 0.99 | 0.9 | 0.46 |  |  |  | Apr-25 | Jan - 26 | Foundation RoW locs.(2): Ajmer Dist. (2) in Rajasthan. Erection RoW Locs. (7): Beawar (3), Ajmer (4) in Rajasthan. Forest: (5.58 Ha, 02 locs, 2 Ckm): Stage-II issued on 24.05.25.
| EL-FE0D9 | Rajasthan Phase-III | Rajasthan Phase-III part H | LILO of both circuits of Jaipur (Phagi)-Gwalior 765 kV D/c at Dausa |  |  |  | TBCB | [5 empty] | PGCIL | Oct-23 | 133 | 173 | 173 | 160 | 61.62 | 1 | 0.92 | 0.46 |  |  |  | Apr-25 | Dec - 25 | Under progress
| EL-16C55 | Rajasthan Phase-III | Rajasthan Phase-III part H | LILO of both circuits of Agra – Jaipur (south) 400kV D/c at Dausa |  |  |  | TBCB | [5 empty] | PGCIL | Oct-23 |  | 59 | 59 | 59 | 45 | 1 | 1 |  |  |  |  | Apr-25 | Jul - 25 | Line charged on 13.07.2025
| EL-AF357 | Rajasthan Phase-III | Rajasthan Phase-III part H | 2x1500MVA, 765/400KV Dausa S/s | 3000 |  |  | TBCB | [5 empty] | PGCIL | Oct-23 | [8 empty] | 100.00% | 100.00% | 99.00% | Apr-25 | Dec - 25 | Land (114.879 Acre): All Acquired
| EL-30947 | Koppal Phase-II | Koppal Phase-II | Establishment of 765/400 kV 2x1500 MVA, 400/220 kV, 2x500 MVA Koppal-II (Phase- A) | 4000 |  |  | TBCB | [5 empty] | PGCIL | Dec-23 | [8 empty] | 80.00% | 50.00% | 10.00% | Dec-25 | Mar - 26 | Pvt. Land (174.575 Acre): Registry of 132.125 out of 140 acres of consented land complete. advance possesion of remaining land has been given to POWERGRID by Dist. Administration on 18.12.24.
| EL-314FC | Koppal Phase-II | Koppal Phase-II | Establishment of 400/220 kV, 2x500 MVA Gadag-II (Phase -A) Pooling Station | 1000 |  |  | TBCB | [5 empty] | PGCIL | Dec-23 | [8 empty] | 85.00% | 95.00% | 20.00% | Dec-25 | Mar - 26 | Pvt. Land (50.97 Acre): All acquired
| EL-E95F4 | Koppal Phase-II | Koppal Phase-II | Koppal-II PS – Narendra (New) 765 kV D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Dec-23 | 238 | 310 | 257 | 134 |  | 0.83 | 0.43 | 0 |  |  |  | Dec-25 | Jun - 26 | Foundation RoW (36 loc.): Koppal (8), Vijaypura (24), Bagalkote (4) in Karnataka Forest,Karnataka, Koppal (0.657 Ha, Nil locs., 0.2 Ckm)- Stage-II awaited
| EL-036FE | Koppal Phase-II | Koppal Phase-II | Gadag-II PS – Koppal-II PS 400 kV (Quad Moose) D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Dec-23 | 77 | 104 | 70 | 44 |  | 0.67 | 0.42 | 0 |  |  |  | Dec-25 | Mar - 26 | Foundation RoW (42 loc.): Koppal Dist. (31), Gadag Dist. (11) in Karnataka
| EL-744C2 | Koppal Phase-II | Koppal Phase-II | Koppal-II PS – Raichur 765 kV D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Dec-23 | 293 | 375 | 346 | 209 | 31.38 | 0.92 | 0.56 | 0.11 |  |  |  | Dec-25 | Mar - 26 | Foundation RoW (12 loc.): Koppal Dist. (11), Raichur (1) in Karnataka Erection RoW (1 loc): Koppal Dist. (1) in Karnataka.
| EL-D257F | Koppal Phase-II | Koppal Phase-II | Augmentation by 2x1500 MVA, 765/400 kV ICTs at Koppal-II PS | 3000 |  |  | TBCB | [5 empty] | PGCIL | Dec-23 | [8 empty] | 80.00% | 50.00% | 10.00% | Dec-25 | Mar - 26 | Under progress
| EL-86FAE | Koppal Phase-II | Koppal Phase-II | Augmentation by 2x500 MVA, 400/220 kV ICTs at Koppal-II PS | 1000 |  |  | TBCB | [5 empty] | PGCIL | Dec-23 | [8 empty] | 80.00% | 50.00% | 10.00% | Dec-25 | Mar - 26 | Under progress
| EL-2F219 | Khavda RE Park Phase-III | Khavda RE Park Phase-III Part B | Establishment of 765 kV switching station near Vataman |  |  |  | TBCB | [5 empty] | PGCIL | Dec-23 | [8 empty] | 10.00% | 35.00% |  | Dec-25 | Dec - 26 | Land (154.36 Acre): Acquired
| EL-D027E | Khavda RE Park Phase-III | Khavda RE Park Phase-III Part B | Halvad – Vataman 765 kV D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Dec-23 | 254 | 336 | 143 | 14 |  | 0.43 | 0.04 | 0 |  |  |  | Dec-25 | Dec - 26 | Forest,Gujarat (2.717 Ha, 1 loc, 1.28Ckm) Stage-II issued on 20.10.2025.
| EL-4D37A | Khavda RE Park Phase-III | Khavda RE Park Phase-III Part B | LILO of Lakadia – Vadodara 765 kV D/c line at Vataman 765 kV switching station |  |  |  | TBCB | [5 empty] | PGCIL | Dec-23 | 56 | 82 | 54 |  |  | 0.66 | 0 | 0 |  |  |  | Dec-25 | Dec - 26 | Gujarat (0.5424 Ha, Nil locs, 0.16Ckm) Stage-II issued on 11.11.2025
| EL-CDF4C | Khavda RE Park Phase-III | Khavda RE Park Phase-III Part B | Vataman switching station – Navsari (New)(GIS) 765 kV D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Dec-23 | 495 | 690 | 353 | 46 |  | 0.51 | 0.07 | 0 |  |  |  | Dec-25 | Dec - 26 | Gujarat (15.2371 Ha, 2 locs, 4.54 Ckm )- Stage-II issued on 17.11.2025.
| EL-EA4AC | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV (Part-1) PART A | Establishment of 6x1500 MVA (along with one spare unit of 500 MVA), 765/400 kV & 5x500 MVA 400/220 kV Bikaner-III Pooling Station | 11500 |  |  | TBCB | [5 empty] | PGCIL | Dec-23 | [8 empty] | 90.00% | 70.00% | 30.00% | Dec-25 | Mar - 26 | Land (213.78 Acre): All Acquired.
| EL-91E7F | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV (Part-1) PART A | Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) |  |  |  | TBCB | [5 empty] | PGCIL | Dec-23 | 62 | 86 | 66 | 37 |  | 0.77 | 0.43 | 0 |  |  |  | Dec-25 | Mar - 26 | Stringing RoW (3 locs.): Bikaner (5) in Rajasthan Forest in Bikaner (0.442 Ha, Nil locs, 0.5km), Stage-II received on 24.11.25.
| EL-E8A1F | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV (Part-1) PART A | Bikaner-III - Neemrana-II 765 kV D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Dec-23 | 682 | 905 | 865 | 688 | 61.82 | 0.96 | 0.76 | 0.09 |  |  |  | Dec-25 | Jun - 26 | Foundation RoW (25 loc.): Churu (14), Jhunjhunu (8), Kotputli Behror (1) in Rajasthan, Mahendragarh (1) in Haryana Erection RoW (10 loc.):Mahendragarh (1) in Haryana, Bikaner (9) in Rajasthan Forest: i) Haryana (0.8361 Ha,6 loc, 1 km): Stage-II Awaited ii) Rajasthan (1.916 Ha, 3 loc, 0.5 km) : Stage-II Awaited.
| EL-68B7A | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV (Part-1) PART A | LILO of both circuits of 400 kV Bikaner (PG)-Bikaner-II D/c line at Bikaner-III PS |  |  |  | TBCB | [5 empty] | PGCIL | Dec-23 | 74 | 102 | 102 | 94 | 31.52 | 1 | 0.92 | 0.43 |  |  |  | Dec-25 | Mar - 26 | Stringing RoW (3 locs.): Bikaner (5) in Rajasthan
| EL-92EB7 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV (Part-1) PART D | Neemrana-II- Bareilly (PG) 765 kV D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Dec-23 | 666 | 863 | 837 | 732 | 257.4 | 0.97 | 0.85 | 0.39 |  |  |  | Dec-25 | Jun - 26 | i)Forest,Rajasthan, Alwar (16.054 Ha,6 loc, 3km) Division: Stage-II Awaited ii) Forest, Haryana (11.849 Ha,2 loc, 2 km): Stage-I awaited iii) Forest,Haryana, Palwal (2.37 Ha,19 loc, 24.2km): Stage-II obtained on 20.11.25. iv) Forest, Uttar Pradesh (2.44 Ha,24loc, 5.5km): Stage-II Awaited
| EL-5F015 | Bidar | Bidar | Bidar PS–Maheshwaram (PG) 765KV D/C line |  |  |  | TBCB | [5 empty] | PGCIL | Feb-24 | 479 | 628 | 606 | 506 | 133.3 | 0.96 | 0.81 | 0.28 |  |  |  | Feb-26 | Jun - 26 | Foundation RoW (22 loc.): Bidar District (2), Ranga Reddy District (20) in Telangana. Erection RoW (11 loc.): Ranga Reddy District (11) in Telangana.
| EL-03CCE | Bidar | Bidar | Establishement of Bidar PS 3x1500 MVA, 765/400 kV and 5x500 MVA, 400/220 kV ICTs | 7000 |  |  | TBCB | [5 empty] | PGCIL | Feb-24 | [8 empty] | 80.00% | 80.00% | 20.00% | Feb-26 | Jun - 26 | Pvt Land (162.07 Acre), Pending (8.87) Acre The pending land (8.87 acres) is being acquired through RFTLARR Act, 2013.
| EL-39439 | Rajasthan Phase-III | Rajasthan Phase-III Part D | Sikar-II –Narela 765 kV D/C line |  |  |  | TBCB | [5 empty] | PGCIL | Feb-24 | 473 | 630 | 482 | 386 | 99.5 | 0.77 | 0.61 | 0.21 |  |  |  | Aug-25 | Jun - 26 | Forest: i)Haryana (16.75 Ha, 0 loc, 6 km)- Stage-I Awaited. ii) Delhi (1.319 ha, 0 loc, 1.2 km): Stage-I awaited.
| EL-72AA1 | Rajasthan Phase-III | Rajasthan Phase-III Part D | Sikar-II –Khetri765 kV D/C line |  |  |  | TBCB | [5 empty] | PGCIL | Feb-24 | 144 | 198 | 173 | 150 | 33.7 | 0.87 | 0.76 | 0.23 |  |  |  | Aug-25 | Jun - 26 | Forest i)Rajasthan (29.97 Ha, 15 locs, 8km)- Stage-I Awaited Proposal submitted 22.07.24. Area modified to 29.9758 ha. Revised documents uploaded on 28.07.25. Proposal forwarded by NO to SG on 28.11.25.
| EL-7DDB5 | Khavda Phase-IV | Khavda Phase-IV Part E2 | Augmentaion of transformation capacity at KPS2 GIS by 2x1500 MVA, 765/400 kV ICT on Bus Section-I (5th & 6th) & 2x1500 MVA, 765/400 kV ICT on Bus Section-II (7th & 8th) | 6000 |  |  | TBCB | [5 empty] | PGCIL | May-24 | [8 empty] | 50.00% | 20.00% |  | Feb-26 | Jun - 26 | Work under progress.
| EL-6A0DE | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part C | Establishment of 3x1500 MVA, 765/400 kV and 5x500 MVA, 400/220 kV Mandsaur Pooling Station | 7000 |  |  | TBCB | [5 empty] | PGCIL | Aug-24 | [8 empty] | 58.00% | 22.00% | 2.00% | Aug-26 | Dec - 26 | Pvt. land (36.32 Acre): Pending (5.24 Acre). Registry of remaining land 5.24 acre is under process. Patta (16.8 Acre): Pending (16.8) Acre. Applied on 29.04.2024. Sale permission notification under process. Regular followup with DM is being made.
| EL-AE31B | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part C | Mandsaur PS - Indore (PG) 765 kV D/C Line |  |  |  | TBCB | [5 empty] | PGCIL | Aug-24 | 338 | 445 | 329 | 201 |  | 0.74 | 0.45 | 0 |  |  |  | Aug-26 | Aug - 26 | Foundation RoW (12 locs): Indore (8), Ujjain(4) in Madhya Pradesh.
| EL-4777E | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part E | Establishment of 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) |  |  |  | TBCB | [5 empty] | PGCIL | Aug-24 | [11 empty] | Aug-26 | Mar - 27 | Land (197.68 Acre): Pending (197.68) Acre *Govt . Land acquisition was completed, now acquired land has been converted to wet land. Subsequently two alternative sites has been identified.
| EL-0D0CA | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part E | Sirohi PS - Rishabdeo 765 kV D/C line |  |  |  | TBCB | [5 empty] | PGCIL | Aug-24 | 421 | 582 | 365 | 173 | 3.28 | 0.63 | 0.3 | 0.01 |  |  |  | Aug-26 | Mar - 27 | Foundation RoW (13 locs): Sirohi (9), Udaipur (4) in Rajasthan. Forest: Rajasthan (101.29 Ha, 46 locs, 15.15 km)- Stage-I Awaited
| EL-7AF76 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part E | Rishabdeo - Mandsaur PS 765 kV D/C line |  |  |  | TBCB | [5 empty] | PGCIL | Aug-24 | 250 | 327 | 247 | 141 |  | 0.76 | 0.43 | 0 |  |  |  | Aug-26 | Mar - 27 | Forest: Rajasthan (6.458 Ha, 3 locs, 3 km)- Stage-II received on 20.11.25.
| EL-544F8 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part E | LILO of one circuit of 765 kV Chittorgarh - Banaskanta D/C line at Rishabdeo S/S |  |  |  | TBCB | [5 empty] | PGCIL | Aug-24 | 25 | 34 | 5 |  |  | 0.15 | 0 | 0 |  |  |  | Aug-26 | Mar - 27 | Survey under progress
| EL-C16AF | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part B | Establishment of 2x1500MVA, 765/400 KV Substation at suitable location near Sirohi | 3000 |  |  | TBCB | [5 empty] | PGCIL | Aug-24 | [8 empty] | 20.00% | 15.00% |  | Aug-26 | Dec - 26 | Work under progress
| EL-5DC81 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part B | Fatehgarh-IV (Section-2) PS-Sirohi PS 765KV D/C Line |  |  |  | TBCB | [5 empty] | PGCIL | Aug-24 | 412 | 537 | 318 | 184 | 17.46 | 0.59 | 0.34 | 0.04 |  |  |  | Aug-26 | Dec - 26 | Foundation RoW (58 loc.): Balotra (41), Jalore (6), Barmer (11)in Rajasthan
| EL-6838B | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part B | Sirohi PS-Chhitorgarh (PG) 400KV D/C Line (Quad) |  |  |  | TBCB | [5 empty] | PGCIL | Aug-24 | 445 | 604 | 370 | 289 |  | 0.61 | 0.48 | 0 |  |  |  | Aug-26 | Dec - 26 | Foundation RoW (6 loc.): Sirohi (6) in Rajasthan i)Forest, Rajasthan (45.88 Ha, 34 locs, 9.97 km)- Stage-I Awaited Proposal submitted on 25.01.2025. SG forwarded proposal to IRO on 10.11.25.
| EL-0B255 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part D | Beawar-Mandsaur PS 765KV D/C line |  |  |  | TBCB | [5 empty] | PGCIL | Aug-24 | 553 | 742 | 535 | 245 |  | 0.72 | 0.33 | 0 |  |  |  | Aug-26 | Aug - 26 | Foundation RoW (40 loc.): Bhilwara (29), Beawar (11) in Rajasthan i)Rajasthan (49.81 Ha,20 loc, 8km)- Stage-II Awaited ii)Forest, Madhya Pradesh (14.08 Ha,6 loc, 2km)-Stage-II received on 27.11.25.
| EL-7FAF6 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part H1 | Establishment of 765/400/220/132kV at Kurawar S/s |  |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | [8 empty] | 5.00% | 1.00% |  | Oct-26 | Mar - 27 | Land (173.15 Acre): Pending (61.15) Acre Pvt. (149.68 Acre): Pending (37.68) Acre. Registration of 112 acres of land completed. Govt. (23.47 Acre): Pending (23.47). Proposal has been marked to SDM.
| EL-A9492 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part H1 | a) 765/400 kV (2x1500 MVA) Kurawar S/s | 3000 |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | [11 empty] | Oct-26 | Mar - 27 | Engg. Under Progress
| EL-31275 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part H1 | b) 400/220 kV (2x500 MVA) Kurawar S/s | 1000 |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | [11 empty] | Oct-26 | Mar - 27 | Engg. Under Progress
| EL-8FF0E | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part H1 | c) 220/132 kV (3x200 MVA) Kurawar S/s | 600 |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | [11 empty] | Oct-26 | Mar - 27 | Engg. Under Progress
| EL-EF0B9 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part H1 | Mandsaur – Kurawar 765 kV D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | 402 | 522 | 412 | 168 |  | 0.79 | 0.32 | 0 |  |  |  | Oct-26 | Mar - 27 | work under progress.
| EL-2C1F5 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part H1 | Kurawar – Ashta 400 kV D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | 112 | 159 | 9 |  |  | 0.06 | 0 | 0 |  |  |  | Oct-26 | Mar - 27 | work under progress.
| EL-A280A | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part H1 | Shujalpur – Kurawar 400 kV D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | 57 | 77 | 7 |  |  | 0.09 | 0 | 0 |  |  |  | Oct-26 | Mar - 27 | Engg. & survey Under Progress
| EL-C08FB | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part H1 | LILO of one circuit of Indore – Itarsi 400 kV D/c line at Ashta S/s |  |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | 112 | 154 |  |  |  | 0 | 0 | 0 |  |  |  | Oct-26 | Mar - 27 | Madhya Pradesh (31.97 Ha, 18 locs., 6.95 km )- Stage-I Awaited
| EL-8674E | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part H1 | LILO of one circuit of Indore – Bhopal 765 kV S/c line at Kurawar S/s |  |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | 53 | 69 | 35 |  |  | 0.51 | 0 | 0 |  |  |  | Oct-26 | Mar - 27 | work under progress.
| EL-1366C |  |  | Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 2x500MVA, 400/220kV ICT (5th and 6th) (terminated on New 220kV bus section-II) | 1000 |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | [8 empty] | 15.00% | 1.00% |  | Jul-26 | Jul - 26 | Work under progress
| EL-5E2E2 |  |  | Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 1x500MVA, 400/220kV ICT (7th) (terminated on New 220kV bus section- II) | 500 |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | [8 empty] | 15.00% | 1.00% |  | Jul-26 | Jul - 26 | Work under progress
| EL-A2048 |  |  | Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 1x500MVA, 400/220kV ICT (8th) (terminated on New 220kV bus section- III) | 500 |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | [8 empty] | 15.00% | 1.00% |  | Jul-26 | Jul - 26 | Work under progress
| EL-8CE01 |  |  | Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 1x500MVA, 400/220kV (9th) ICT terminated on New 220kV bus section-III | 500 |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | [8 empty] | 15.00% | 1.00% |  | Jul-26 | Jul - 26 | Work under progress
| EL-BF863 | KHAVDA PHASE-IV | KHAVDA PHASE-IV PART B | Establishment of 2x1500 MVA, 765/400 kV & 2x500 MVA, 400/220 kV GIS S/s at a suitable location in South Olpad (between Olpad and Ichhapore) | 4000 |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | [11 empty] | Oct-26 | Mar - 27 | Land (107 Acre): Pending (107) Acre Pvt. (107 Acre): Pending (107 ) Acre. Application for acquisition of land under LARR,2013 submitted on 27.11.2024. Negotiation with land owners failed. Joint Measurement of lands belonging to aggrieved land conducted on 14.11.25 under police protection.
| EL-851BC | KHAVDA PHASE-IV | KHAVDA PHASE-IV PART B | Vadodara (GIS) –South Olpad (GIS) 765 kV D/C line |  |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | 249 | 343 | 38 |  |  | 0.11 | 0 | 0 |  |  |  | Oct-26 | Mar - 27 | Foundation RoW (242 locs.): Vadodara (95), Bharuch (147) Forest, Gujarat (2.4897 ha, Nil Locs, 0.351 Km) : Stage-I Awaited
| EL-CBF31 | KHAVDA PHASE-IV | KHAVDA PHASE-IV PART B | LILO of Gandhar – Hazira 400 kV D/c line at South Olpad (GIS) |  |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | 8 | 12 | 0 |  |  | 0 | 0 | 0 |  |  |  | Oct-26 | Mar - 27 | Engg & Survey under Progress
| EL-9DF1E | KHAVDA PHASE-IV | KHAVDA PHASE-IV PART B | Ahmedabad – South Olpad (GIS) 765 kV D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Oct-24 | 455 | 607 | 144 | 8 |  | 0.24 | 0.01 | 0 |  |  |  | Oct-26 | Mar - 27 | Foundation RoW (75 locs.): Ahmedabad (15), Anand (8), Vadodara (7), Bharuch (45) in Gujarat Forest, Gujarat (28.5931 ha, Nil Locs, 4.268 Km) : Stage-I Awaited Proposal submitted online on 14.04.25 . Proposal recommended in PSC I on 12.06.25. MoM issued on 07.07.25 and proposal fowarded to DFOs for filling of Part-II.
| EL-42126 | Bhadla | Bhadla | Bhadla-III - Bikaner-III 765 kV D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Aug-24 | 254 | 328 | 106 | 10 |  | 0.32 | 0.03 | 0 |  |  |  | Aug-26 | Dec - 26 | Erection RoW Locs. (2): Bikaner District (2) in Rajasthan Forest, Rajasthan (6.8714 ha) : Stage-I Awaited Proposal submitted on 06.05.25. SG forwarded proposal to IRO on 20.11.25.
| EL-D09B9 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part F Part F1 & F2 | Establishment of 3x1500 MVA, 765/400 kV & 2x500 MVA, 400/220 kV Barmer-I Pooling Station | 5500 |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | [11 empty] | Nov-26 | Jun - 27 | Govt. (143.5 Acre): Pending (143.5 Acre). Demand note is under process, expected by 05.12.25
| EL-E0593 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part F Part F1 & F2 | Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) |  |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | 102 | 103 | 30 |  |  | 0.29 | 0 | 0 |  |  |  | Nov-26 | Jun - 27 | Foundation RoW (13 loc.): Barmer (13) in Rajasthan.
| EL-9DE74 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part F Part F1 & F2 | Barmer-I PS– Sirohi PS 765 kV D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | 419 | 543 | 329 | 22 |  | 0.61 | 0.04 | 0 |  |  |  | Nov-26 | Jun - 27 | Forest, Rajasthan (0.2412 ha) : Stage-II Awaited Proposaal submitted on 01.05.2025. Stage-I issued on 03.09.25. Compliance forwarded by NO to SG on 27.11.25..
| EL-1713C | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV PART A | Establishment of 6x1500 MVA, 765/400 kV & 6x500 MVA, 400/220 kV Bikaner-IV Pooling Station. | 12000 |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | [11 empty] | Nov-26 | Mar - 27 | Land (235.86 Acre): Land Acquisition process completed on 16.09.25.
| EL-741D9 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV PART A | LILO of both ckts of Bikaner II PS - Bikaner III PS (Quad) at Bikaner-IV PS |  |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | 65 | 68 | 0 |  |  | 0 | 0 | 0 |  |  |  | Nov-26 | Mar - 27 | Engg under progress
| EL-26CA8 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV PART A | Bikaner-IV PS – Siwani 765 kV D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | 481 | 622 | 298 | 29 |  | 0.48 | 0.05 | 0 |  |  |  | Nov-26 | Mar - 27 | Forest, Rajasthan (1.2609 ha): Stage-II Awaited Forest, Haryana (0.7817 ha): Stage-I Awaited
| EL-81725 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV PART A | Siwani– Fatehabad (PG) 400 kV D/c line (Quad) |  |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | 165 | 220 | 23 | 7 |  | 0.1 | 0.03 | 0 |  |  |  | Nov-26 | Mar - 27 | Forest, Haryana (3.448 ha, Nil locs, 0.0205 km): Stage-I Awaited. Proposal submitted on 16.02.25. PSC I raised queries. CA Land alotted by MP and detailed CA scheme forwarded to Region on 23.04.25. Revised proposal with reduced forest area submitted on 17.11.25.
| EL-C3D72 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV PART A | Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) |  |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | 281 | 377 | 39 | 6 |  | 0.1 | 0.02 | 0 |  |  |  | Nov-26 | Mar - 27 | i) Forest, Haryana (13.12 ha, Nil locs., 0.0323 Km) :Proposal submitted on 16.02.25. PSC I raised queries. CA Land alotted by MP and detailed CA scheme forwarded to Region on 23.04.25. ii)Forest, Punjab (2.43ha, Nil locs., 0.00597Km) : Proposal submitted on 15.02.25. Under process with DFOs for Part II.
| EL-E7C96 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV PART A | STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) at Bikaner-IV PS |  |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | [11 empty] | Nov-26 | Mar - 27 | Engg under progress
| EL-4352D | Khavda Phase-V | Khavda Phase-V Part A | Establishment of 6000 MW (4x1500 MW), ± 800 kV (HVDC) [LCC] at KPS2 and Nagpur terminal station (Bipole-1: 3000 MW) | 3000 |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | [8 empty] | 5.00% | 1.00% |  | Nov-28 | Nov - 28 | Land (405 Acre, All Pvt.): Pending (284) Acre
| EL-EFC49 | Khavda Phase-V | Khavda Phase-V Part A | Establishment of 6x1500 MVA, 765/400 kV ICTs at Nagpur S/s along with associated interconnections with HVDC Switchyard | 9000 |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | [11 empty] | Nov-28 | Nov - 28 | Engg. Under Progress
| EL-A6AD8 | Khavda Phase-V | Khavda Phase-V Part A | ±800 kV HVDC Bipole line (Hexa lapwing) between KPS2 (HVDC) and Nagpur (HVDC) |  |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | 2,409 | 3,152 | 64 | [8 empty] | Nov-28 | Nov - 28 | i)Forest, Gujarat (373.89 ha, 54.188 Km) : Proposal submitted on 03.06.25. Proposal recommended in PSC I on 12.06.25 & fowarded to DFOs for filling of Part- II. ii) WL- Wild Ass Sanctuary (26.4907 ha): Proposal submitted online on 03.06.25.Query raised by wildlife warden replied on 02.11.25. Site inspection to be done by wildlife warden. iii)Forest, Madhya Pradesh (156.936 ha) :Proposal submitted online on 28.08.25. Proposal discussed in PSC-I meeting on 08.09.25 and further forwarded to DFO for filling of Part-II on 09.09.25. iv)Forest, Maharashtra (57.71 ha) :Proposal submitted online on 21.10.25 & discussed in PSC-I meeting on 27.10.25. Proposal not accepted in PSC and it has been asked to confirm forest area from Amravati division.
| EL-238D3 | Khavda Phase-V | Khavda Phase-V Part A | LILO of Wardha – Raipur 765 kV one D/c line (out of 2xD/c lines) at Nagpur |  |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | 68 | 86 | 5 |  |  | 0.06 | 0 | 0 |  |  |  | Nov-28 | Nov - 28 | Engg. Under Progress
| EL-00D0C | Madhya Pradesh | Madhya Pradesh | ± 300 MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS1 400 kV Bus section-1 (GIS) |  |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | [11 empty] | Nov-26 | Nov - 26 | Land : Govt. Land (7.41 Acres): Pending (7.41 Acres): Proposal is has been marked to Secretariat , Gandhinagar by DM. Sectratariat has sent file to DM kutch for valuation of land.
| EL-92361 | Madhya Pradesh | Madhya Pradesh | ± 300 MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS1 400 kV Bus section-2 (GIS) |  |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | [11 empty] | Nov-26 | Nov - 26 | Land : Govt. Land (7.41 Acres): Pending (7.41 Acres): Proposal is has been marked to Secretariat , Gandhinagar by DM. Sectratariat has sent file to DM kutch for valuation of land.
| EL-FECE5 | Madhya Pradesh | Madhya Pradesh | ± 300 MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS3 400 kV Bus section-1 (GIS) |  |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | [8 empty] | 10.00% | 1.00% |  | Nov-26 | Nov - 26 | Work under progress
| EL-AC827 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part B | Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) | 9000 |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | [8 empty] | 3.00% | 1.00% |  | Nov-26 | Mar - 27 | Land (139 Acre): Pending (Nil) Acre
| EL-05F0B | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part B | Bikaner-IV PS – Siwani 765 kV D/C (2nd) line |  |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | 480 | 625 | 400 | 84 |  | 0.64 | 0.13 | 0 |  |  |  | Nov-26 | Mar - 27 | Forest, Rajasthan (1.2462 ha): Stage-II Awaited. Proposal submitted on 18.05.25. Stage-I issued on 01.10.25. Demand for compensatory levies approved by NO on 07.10.25.Payment deposited on 13.11.25. Forest, Haryana (0.5504 ha): Stage-I Awaited. Proposal submitted on 18.06.25. Proposal with revised forest area submitted on 22.11.25.
| EL-95F93 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part B | Siwani – Sonipat (PG) 400 kV D/C line (Quad) |  |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | 273 | 378 | 1 |  |  | 0 | 0 | 0 |  |  |  | Nov-26 | Mar - 27 | Forest, Haryana (9.5307 ha): Stage-I Awaited. Route alignment approved on 08.04.25. Proposal submitted on 20.06.25. Proposal discussed in PSC I meeting on 16.07.25. Proposal returned to UA on 22.07.25. Main query is pertaining to CA land in other States. Request letter given to ACS (Forest), MP for allotment of DFL land on 23.07.25. Reply submitted to MS(PSC-I) on 07.11.25.
| EL-CFD88 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part B | Siwani – Jind (PG) 400 kV D/C line (Quad) (93.69 km). |  |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | 187 | 258 |  |  |  | 0 | 0 | 0 |  |  |  | Nov-26 | Mar - 27 | Forest, Haryana (4.2216 ha): Stage-I Awaited. Proposal submitted online on 28.10.2025. DFO raised query regarding DFL land on 29.10.25.Query replied back on 12.11.25
| EL-894EE | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part B | STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) and MSR (2x125 MVAr) at Siwani S/s. |  |  |  | TBCB | [5 empty] | PGCIL | Nov-24 | [11 empty] | Nov-26 | Mar - 27 | Engg under progress
| EL-10073 | Rajasthan REZ Phase III | Rajasthan REZ Phase III | Augmentation of 2x500 MVA (4th & 5th)., 400/220 KV ICTs at Bhadla- III PS | 1000 |  |  | TBCB | [5 empty] | PGCIL | Aug-24 | [8 empty] | 50.00% | 25.00% | 10.00% | Feb-26 | Mar - 26 | work under progress
| EL-178D3 | Rajasthan REZ Phase III | Rajasthan REZ Phase III | Augmentation of 1x1500 MVA 765/400 KV (3rd) ICT at Bhadla-III PS | 1500 |  |  | TBCB | [5 empty] | PGCIL | Aug-24 | [8 empty] | 50.00% | 25.00% | 10.00% | Feb-26 | Mar - 26 | work under progress
| EL-1EBBE | Rajasthan REZ Phase III | Rajasthan REZ Phase III | Augmentation of 1x1500 MVA 765/400KV (4th) ICT at Bhadla-III PS | 1500 |  |  | TBCB | [5 empty] | PGCIL | Aug-24 | [8 empty] | 40.00% | 20.00% | 10.00% | Dec-25 | Mar - 26 | work under progress
| EL-6DFEE | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part A | Establishment of 765/400kV, 2x1500 MVA S/s at Ghiror (Distt. Mainpuri) (UP) | 3000 |  |  | TBCB | [5 empty] | PGCIL | Dec-24 | [8 empty] | 1.00% | 2.00% |  | Dec-26 | Mar - 27 | Pvt. (146.50 Acre): Pending (16.7) Acre. Proposal submitted to DM on 25.11.2024 , for purchase of land on tripartite mode. Registry of 129.8 acres land completed & remaining is under process.
| EL-284D2 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part A | Augmentation by 765/400 kV, 2x1500 MVA Transformer (4th& 5th) at Barmer-I PS. | 3000 |  |  | TBCB | [5 empty] | PGCIL | Dec-24 | [11 empty] | Dec-26 | Mar - 27 | Engg Under Progress
| EL-DC77E | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part A | Augmentation by 5x500 MVA (5th to 9th), 400/220 kV ICTs at Barmer-I PS. | 2500 |  |  | TBCB | [5 empty] | PGCIL | Dec-24 | [11 empty] | Dec-26 | Mar - 27 | Engg Under Progress
| EL-DC8F9 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part A | Fatehgarh-IV PS (Sec-2) – Barmer-I PS 400kV D/c line. |  |  |  | TBCB | [5 empty] | PGCIL | Dec-24 | 74 | 108 | 2 |  |  | 0.02 | 0 | 0 |  |  |  | Dec-26 | Mar - 27 | Foundation RoW (13 loc.): Barmer (13) in Rajasthan. Forest, Rajasthan (0.1656 ha, ): Stage-II Awaited. Proposal submitted on 06.05.25. Stage-I issued on 14.09.25. Stage-I compliance forwarded to NO on 26.11.25. NO forwarded to SG on 27.11.25.
| EL-90C55 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part A | Dausa - Ghiror 765 kV D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Dec-24 | 545 | 714 | 234 | 50 |  | 0.33 | 0.07 | 0 |  |  |  | Dec-26 | Mar - 27 | Forest, Uttar Pradesh (15.77 ha, ): Stage-I Awaited Forest, Rajasthan (16.2877 ha, ): Stage-I Awaited
| EL-C99C8 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part A | LILO of both ckt of 765 kV Aligarh (PG) - Orai (PG) D/c line at Ghiror S/s |  |  |  | TBCB | [5 empty] | PGCIL | Dec-24 | 49 | 70 | 19 | 4 |  | 0.27 | 0.06 | 0 |  |  |  | Dec-26 | Mar - 27 | Forest, Uttar Pradesh (2.689 ha, ): Stage-II Awaited
| EL-D7B2A | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part A | LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 2xS/c line at Ghiror S/s |  |  |  | TBCB | [5 empty] | PGCIL | Dec-24 | 50 | 66 | 21 | 1 |  | 0.32 | 0.02 | 0 |  |  |  | Dec-26 | Mar - 27 | Forest, Uttar Pradesh (0.410 ha, ): Stage-II Awaited
| EL-81FAC | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part A | 400kV Ghiror-Firozabad (UPPTCL) D/c line. |  |  |  | TBCB | [5 empty] | PGCIL | Dec-24 | 97 | 132 | 40 |  |  | 0.3 | 0 | 0 |  |  |  | Dec-26 | Mar - 27 | Forest, Uttar Pradesh (22.8045 ha, ): Stage-I Awaited
| EL-44E89 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part A | STATCOM (2X±300 MVAr) along with MSC (4X125 MVAr) and MSR (2X125 MVAr) at Barmer-I PS |  |  |  | TBCB | [6 empty] | Dec-24 | [11 empty] | Dec-26 | Mar - 27
| EL-2D433 |  |  | Kudankulam Nuclear Power Plant (3&4) – Tuticorin-II GIS PS 400 kV (quad) D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Jan-25 | 208 | 278 | 90 | 31 |  | 0.32 | 0.11 | 0 |  |  |  | Dec-26 | Dec - 26 | Foundation RoW (11 loc.): Tirunelveli District (11) in Tamilnadu.
| EL-8A3C9 | Koppal | Koppal | Gadag-II PS – Koppal-II PS 400 kV (Quad) 2nd D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Jan-25 | 77 | 102 | 7 |  |  | 0.07 | 0 | 0 |  |  |  | Jan-27 | Jan - 27 | Work under progress.
| EL-15EF5 | Koppal | Koppal | Augmentation by 3x1500 MVA (5th, 6th & 7th), 765/400kV ICTs at Koppal-II PS | 4500 |  |  | TBCB | [5 empty] | PGCIL | Jan-25 | [8 empty] | 10.00% |  |  | Dec-25 | Aug - 26 | Work under progress.
| EL-0B9FE | Koppal | Koppal | Augmentation by 5x500 MVA, 400/220kV ICTs (5th, 6th, 7th, 8th & 9th) at Koppal-II PS | 2500 |  |  | TBCB | [5 empty] | PGCIL | Jan-25 | [8 empty] | 10.00% |  |  | Dec-25 | Aug - 26 | Work under progress.
| EL-F6E3D | Koppal | Koppal | Augmentation by 7x500 MVA, 400/220kV ICTs (3rd, 4th, 5th, 6th, 7th, 8th & 9th) at Gadag-II PS | 3500 |  |  | TBCB | [5 empty] | PGCIL | Jan-25 | [8 empty] | 2.00% |  |  | Jan-27 | Jan - 27
| EL-AD555 | Bidar | Bidar | Augmentation by 1x1500 MVA (4th), 765/400kV ICT at Bidar PS | 1500 |  |  | TBCB | [5 empty] | PGCIL | Feb-25 | [8 empty] | 2.00% |  |  | Feb-27 | Feb - 27 | Work under progress.
| EL-AD7CE | Bidar | Bidar | Augmentation by 3x500 MVA, 400/220kV ICTs (6th, 7th, & 8th) at Bidar PS | 1500 |  |  | TBCB | [5 empty] | PGCIL | Feb-25 | [8 empty] | 2.00% |  |  | Feb-27 | Feb - 27 | Work under progress.
| EL-2CFEB | KPS Phase V | KPS Phase V Part B1 & B2 | Augmentation by 1x1500 MVA (9th), 765/400kV ICT at KPS1(GIS) on Bus section-II | 1500 |  |  | TBCB | [5 empty] | PGCIL | Feb-25 | [11 empty] | Feb-27 | Feb - 27 | Engg under progress
| EL-8851B | KPS Phase V | KPS Phase V Part B1 & B2 | Augmentation by 1x1500 MVA (9th), 765/400kV ICT at KPS2(GIS) on Bus section-I | 1500 |  |  | TBCB | [5 empty] | PGCIL | Feb-25 | [8 empty] | 1.00% |  |  | Feb-27 | Feb - 27 | Work under progress.
| EL-062D5 |  |  | Augmentation of transformation capacity at Banaskantha (Raghanesda) PS (GIS) by 2x500 MVA, 400/220 kV ICTs (3rd and 4th) | 1000 |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | [8 empty] | 30.00% |  |  | Mar-27 | Mar - 27 | Work under progress.
| EL-FDD95 | Kurnool Phase-I | Kurnool Phase-I | Establishment of 4x1500 MVA, 765/400 kV and 4x500 MVA, 400/220 kV Kurnool-IV Pooling Station | 8000 |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Pvt Land (191 Acre): Pending (191) Acre. RDO held meeting with land owners on 19.06.2025 and third tripartite meeting held on 02.07.2025 and land rate has been finalised. 33 out of 96 landowners have given consent for 74.69 acres of land and remaining are being pursued.
| EL-7F40C | Kurnool Phase-I | Kurnool Phase-I | Kurnool-IV – Bidar 765 kV D/C line |  |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | 533 | 698 | 41 |  |  | 0.06 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | Forest, Telangana (11.66 ha, ): Stage-I Awaited
| EL-CF840 | Kurnool Phase-I | Kurnool Phase-I | Kurnool-IV – Kurnool-III PS 765 kV D/C line |  |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | 252 | 333 | 51 | 6 |  | 0.15 | 0.02 | 0 |  |  |  | Mar-27 | Mar - 27 | Work under progress.
| EL-FD4AF | Kurnool Phase-I | Kurnool Phase-I | 300 MVAr STATCOM at Kurnool-IV PS along with 2x125 MVAr MSR |  |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Engg under progress
| EL-80660 | Kurnool Phase-I | Kurnool Phase-I | Augmentation by 1x1500 MVA, 765/400 kV ICT (3rd) at C’Peta | 1500 |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | [8 empty] | 1.00% |  |  | Mar-27 | Mar - 27 | Work under progress.
| EL-0686D | Kurnool Phase-I | Kurnool Phase-I | LILO of Vijayawada-Nellore 400 kV D/C line at C’Peta |  |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | 64 | 99 |  |  |  | 0 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | Engg under progress
| EL-93A88 | Rajasthan REZ Phase-V | Rajasthan REZ Phase-V | Aaugmentation by 4x500 MVA, 400/220 kV ICTs at Sirohi S/s | 2000 |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Engg. under progress.
| EL-B6BDF | Rajasthan REZ Phase-V | Rajasthan REZ Phase-V | Sirohi – Mandsaur PS 765 kV D/C line |  |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | 622 | 861 | 93 |  |  | 0.11 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | (i) Forest,Rajasthan (53.2984 ha, ): Stage-I Awaited (ii) Forest,Madhya Pradesh (10.9947 ha, ): Stage-I Awaited
| EL-C7A50 | Rajasthan REZ Phase-V | Rajasthan REZ Phase-V | Mandsaur PS – Khandwa (New) 765 kV D/C line |  |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | 535 | 712 | 162 | 20 |  | 0.23 | 0.03 | 0 |  |  |  | Mar-27 | Mar - 27 | Forest,Madhya Pradesh (87.68 ha, ): Stage-I Awaited
| EL-6B2D5 | Karnataka | Karnataka | Establishment of 765/400 kV, 4x1500 MVA, 400/220 kV 4x500 MVA Pooling Station near Davanagere / Chitradurga, Karnataka | 8000 |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Land (145 Acre), all Pvt: Pending (145) Acre
| EL-E5AB2 | Karnataka | Karnataka | LILO of Narendra New – Madhugiri 765 kV D/C line at Davanagere / Chitradurga 765/400 kV PS |  |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | 137 | 204 |  |  |  | 0 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | Engg. under progress.
| EL-2D88D | Karnataka | Karnataka | Upgradation of Madhugiri {Tumkur (Vasantnarsapura)} substation to its rated voltage of 765 kV level alongwith 3x1500 MVA, 765/400 kV ICTs | 4500 |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | [8 empty] | 7.00% |  |  | Mar-27 | Mar - 27 | work under progress
| EL-41C4D | Karnataka | Karnataka | Upgradation of Narendra New – Madhugiri 765 kV D/C line (presently charged at 400 kV level) at its rated 765 kV voltage level |  |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Engg. under progress.
| EL-B7ABA | Karnataka | Karnataka | Establishment of 4x500 MVA, 400/220 kV Pooling Station near Bellary area (Bellary PS), Karnataka | 2000 |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | [11 empty] | Sep-27 | Sep - 27 | Pvt. (68 Acre): Pending (68) Acre. Request letter has been submitted to DC, Vijayanagar on 27.02.25 for voluntary acquisition of land under Karnataka state specific amendments/rules in RFTLARR Act, 2013.
| EL-B6E95 | Karnataka | Karnataka | Bellary PS – Davanagere / Chitradurga 400 kV D/C line |  |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | 200 | 183 | 7 |  |  | 0.04 | 0 | 0 |  |  |  | Sep-27 | Sep - 27
| EL-BCA12 | Fatehgarh | Fatehgarh | Augmentation with 765/400 kV, 1x1500 MVA Transformer (7th ) at Fatehgarh-II PS | 1500 |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | [11 empty] | Dec-26 | Mar - 27 | Engg Under Progress
| EL-16065 | Fatehgarh | Fatehgarh | Augmentation with 400/220 kV, 3x500 MVA (6th ,7th & 8th) ICTs at Fatehgarh-IV PS(Section-II) | 1500 |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | [11 empty] | Nov-26 | Mar - 27 | Engg Under Progress
| EL-36E7B | Fatehgarh | Fatehgarh | Augmentation with 400/220 kV, 2x500 MVA (3rd & 4th) ICTs at Barmer-I PS | 1000 |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | [11 empty] | Nov-26 | Mar - 27 | Engg Under Progress
| EL-9E2F0 | Kurnool | Kurnool | Augmentation of transformation capacity by 3x1500 MVA, 765/400 kV ICTs at Kurnool-III PS | 4500 |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | [8 empty] | 2.00% |  |  | Mar-27 | Mar - 27 | Work Under Progress
| EL-DB781 | Kurnool | Kurnool | Kurnool-III PS – Chilakaluripeta 765 kV D/c line |  |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | 584 | 778 | 28 |  |  | 0.04 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | Work Under Progress
| EL-539BA | Kurnool | Kurnool | Augmentation of 1x1500 MVA 765/400 kV ICT (7th) at Kurnool-II PS | 1500 |  |  | TBCB | [5 empty] | PGCIL | Mar-25 | [8 empty] | 5.00% |  |  | Mar-27 | Mar - 27 | Work Under Progress
| EL-2B9E5 | Madhya Pradesh | Madhya Pradesh | Mahan (existing bus) – Rewa PS (PG) 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line |  |  |  | TBCB | [5 empty] | PGCIL | Jun-25 | 277 | 399 |  |  |  | 0 | 0 | 0 |  |  |  | Dec-27 | Dec - 27 | Forest,Madhya Pradesh (140.47 ha, ): Stage-I Awaited. Proposal submitted on 16.09.2025. Proposal recommended in PSC-I meeting on 23.09.2025 and forwarded to DFO for filing of part-II on 24.09.2025. Wildlife (2.039 Ha), Madhya Pradesh: Proposal submitted online on 16.09.2025. Queries raised for revision in wildlife area on 25.10.25. Reply under process.
| EL-E672B | Madhya Pradesh | Madhya Pradesh | 2 Nos. 400 kV bays at Rewa PS (PG) for termination of Mahan (existing bus) – Rewa PS (PG) 400 kV D/c line (Quad ACSR/AAAC/AL59 moose equivalent) line |  |  |  | TBCB | [5 empty] | PGCIL | Jun-25 | [11 empty] | Dec-27 | Dec - 27 | Engg Under Progress
| EL-28A30 |  |  | Augmentation of Transformation Capacity by 4x500 MVA, 400/220 kV ICTs (5th-8th) at Davanagere PS | 2000 |  |  | TBCB | [5 empty] | PGCIL | Sep-25 | [11 empty] | Sep-27 | Sep - 27
| EL-CC1FB |  |  | Augmentation of Davanagere/Chitradurga PS by 765/400kV, 1x1500 MVA ICTs | 1500 |  |  | TBCB | [5 empty] | PGCIL | Sep-25 | [11 empty] | Sep-27 | Sep - 27
| EL-6877D |  |  | 02 Nos. of 220kV line bays at Davanagere/Chitradurga PS for termination of dedicated transmission lines of RE generation Projects. |  |  |  | TBCB | [5 empty] | PGCIL | Sep-25 | [11 empty] | Sep-27 | Sep - 27
| EL-629BD | Madhya Pradesh | Madhya Pradesh | Augmentation of Transformation capacity by 1x1500MVA, 765/400 kV ICT (4th) (Terminated at 400 kV & 765kV Bus Section-II). |  |  |  | TBCB | [5 empty] | PGCIL | Oct-25 | [11 empty] | Mar-27 | Mar - 27
| EL-F51AF | Madhya Pradesh | Madhya Pradesh | Augmentation of Transformation capacity by 1x500MVA, 400/220kV ICT (6th) (Terminated on 400 kV Bus Section-I & 220kV Bus Section- II). |  |  |  | TBCB | [5 empty] | PGCIL | Oct-25 | [11 empty] | Mar-27 | Mar - 27
| EL-A64C6 | Madhya Pradesh | Madhya Pradesh | Augmentation of Transformation capacity by 1x500MVA, 400/220kV ICT (7th) (Terminated on 400 kV Bus Section-II & 220kV Bus Section- III) at Mandsaur PS |  |  |  | TBCB | [5 empty] | PGCIL | Oct-25 | [11 empty] | Mar-27 | Mar - 27
| EL-59C19 |  |  | Establishment of 765 kV Prayagraj S/s near Prayagraj (Uttar Pradesh) along with 2x330 MVAr 765 kV Bus reactors |  |  |  | TBCB | [5 empty] | PGCIL | Oct-25 | [11 empty] | Oct-27 | Oct - 27 | Pvt. (123 Acre): Pending (123) Acre.
| EL-AD2C9 |  |  | LILO of 765 kV Fatehpur-Varanasi S/C line at Prayagraj |  |  |  | TBCB | [5 empty] | PGCIL | Oct-25 | 30 | [6 empty] | 0 |  |  |  | Oct-27 | Oct - 27
| EL-CB642 |  |  | LILO of 765 kV Fatehpur-Sasaram S/C line at Prayagraj |  |  |  | TBCB | [5 empty] | PGCIL | Oct-25 | 28 | [6 empty] | 0 |  |  |  | Oct-27 | Oct - 27
| EL-FE4F8 |  |  | 765 kV Vindhyachal Pool - Prayagraj D/C line along with 330 MVAr line reactor (switchable) at Prayagraj end on each circuit of 765 Kv Vindhyachal Pool - Prayagraj D/C line |  |  |  | TBCB | [5 empty] | PGCIL | Oct-25 | 440 | [6 empty] | 0 |  |  |  | Oct-27 | Oct - 27 | CMETS meeting(s): 31, 35
| EL-9D045 |  |  | Bypassing of both circuits of 765 kV Sasan – Vindhyachal Pool 2xS/C line at Vindhyachal Pool and connecting it with 765 kV Vindhyachal Pool - Prayagraj D/C line, thus forming 765 kV Sasan - Prayagraj D/C line |  |  |  | TBCB | [5 empty] | PGCIL | Oct-25 | 1 | [6 empty] | 0 |  |  |  | Oct-27 | Oct - 27
| EL-DD979 |  |  | Parli New – Bidar 765 kV D/C line with 240 MVAr SLR at Bidar end on both circuits |  |  |  | TBCB | [5 empty] | PGCIL | Oct-25 | 240 | [6 empty] | 0 |  |  |  | Oct-27 | Oct - 27
| EL-5B8E0 |  |  | LILO of one ckt. of Narendra (existing) - Narendra (New) 400kV D/c line at Xeldem |  |  |  | TBCB | [5 empty] | Sterlite | Mar-18 | 210 | 279 | 77 | 35 | 0 | 0.28 | 0.13 | 0 |  |  |  | Nov-21 | Mar - 27 | 1.RoW (7 locs.) : Dharwad (7) 2. Forest (174.634 Ha, 104 locs, 75.928 cKm) in Karnataka (Wildlife area included): Stage I Pending. Applied on 22-07-2023 3. Wildlife (32.06 Ha, 22 locs, 13.92 cKm) in Karnataka: Pending with the Chief Wildlife Warden on account of SBWL recommendation. 4. Forest (76.994 Ha, 49 locs, 33.478 cKm) in Goa (Wildlife area included): Stage I Pending. 5. Wildlife (27.092 Ha, 16 locs, 11.78 cKm) in Goa: Received on 23-08-24 from NBWL.
| EL-DD342 |  |  | Xeldem - Mapusa 400kV D/c line |  |  |  | TBCB | [5 empty] | Sterlite | Mar-18 |  | 142 | 142 | 142 | 105.64 | 1 | 1 |  |  |  |  | May-21 | Nov - 24 | Deemed COD declared w.e.f 00:00 hrs of 19-11-2024. Powerflow commenced on 31-05-2025.
| EL-251B2 |  |  | Xeldem (existing) – Xeldem (new) 220kV D/C line |  |  |  | TBCB | [5 empty] | Sterlite | Mar-18 |  | 66 | 66 | 66 | 45.4 | 1 | 1 |  |  |  |  | May-21 | Nov - 24 | Deemed COD declared w.e.f 00:00 hrs of 19-11-2024. Powerflow commenced on 31-05-2025.
| EL-8DAA1 |  |  | Dharamjaygarh Pool section B - Raigarh (Tamnar) Pool 765kV D/c line |  |  |  | TBCB | [5 empty] | Sterlite | Mar-18 |  | 179 |  |  | 137 | 0 | 0 |  |  |  |  | Jul-21 | Jun - 22 | TL Completed
| EL-41840 |  |  | 2x500MVA, 400/220kV Xeldem |  |  |  | TBCB | [5 empty] | Sterlite | Mar-18 | [8 empty] | 100.00% | 100.00% | 100.00% | May-21 | Nov - 24 | Charged on no load basis on 05-11-2024. Deemed COD declared w.e.f 19-11- 2024.Powerflow commenced on 31-05-2025.
| EL-7985F |  |  | Mangalore (Udupi PCL) – Kasargode 400kV D/c line |  |  |  | TBCB | [5 empty] | Sterlite | Sep-19 | 232 | 281 | 212 | 173 | 7.8 | 0.75 | 0.62 | 0.03 |  |  |  | Nov-22 | Jun - 26 | 1.RoW (31locs.) in Karnataka: Dakshin Kannada (31locs.) 2. Row in Kerala: 87 ckm of stringing halted due to non finalisation of land compensation order by Govt. of Kerala. 3. Forest (31.07 Ha, 17 locs, 13.5 ckm) in Karnataka: Stage II awaited. Stage-I received on 27-10-2022. Mangalore Division (22.11 Ha) & Kundapur Division (8.96 Ha): WP received in Oct'24 & TCP received in Jan'25 and Nov'24 resp. 4. Forest (17.07 Ha, 8 locs, 7.8 ckm) in Kerala: Stage II awaited. WP & TCP received on 15-10-2024. Stage-I received on 27-10-2022.
| EL-08026 |  |  | 2x500MVA, 400/220 kV Kasargode | 1000 |  |  | TBCB | [5 empty] | Sterlite | Sep-19 | [8 empty] | 99.93% | 100.00% | 99.86% | Nov-22 | Jun - 26 | Commissioning is dependent on completion of Udupi – Kasargode 400kV D/c line.
| EL-B0D29 |  |  | LILO of one circuit of Kishenpur – Dulhasti 400 kV D/c at Kishtwar |  |  |  | TBCB | [5 empty] | Sterlite | Dec-22 | 3 | 5 | 5 | 5 | 2.8 | 1 | 1 | 0.93 |  |  |  | Apr-25 | Dec - 25 | Deemed COD w.e.f 26.11.2025 as per TSA .
| EL-8E08C |  |  | 7x66.67 MVA, 400/132 kV Kishtwar | 400 |  |  | TBCB | [5 empty] | Sterlite | Dec-22 | [8 empty] | 100.00% | 100.00% | 100.00% | Apr-25 | Dec - 25 | Deemed COD declared for 400/132 kV pooling station at Kishtwar w.e.f 26.11.2025 as per TSA . Total Land (32 Acres): 1. Pvt. (29.2 Acres): All acquired 2. Govt. (2.8 Acre Non-Forest): Indent given by JKPDD.
| EL-AC732 | Rajasthan Phase-III | Rajasthan Phase-III Part G | Fatehgarh3– Beawar 765kV D/c (2nd) |  |  |  | TBCB | [5 empty] | Sterlite | Aug-23 | 635 | 817 | 815 | 802 | 458 | 1 | 0.98 | 0.72 |  |  |  | Feb-25 | Jan - 26 | 1. RoW (7 locs.) in Rajasthan: Barmer (4 locs.: 1 Foundation & 3 Erection) & Balotra (3 locs.: 3 Erection). 2. Forest (11.35 Ha, 4 locs, 3.39 cKm) in Rajasthan: Stage II received on 29-08- 2025. Stage I received on 11-09-2024, WP received on 26-05-25 & TCP recieved.
| EL-8E874 | Rajasthan Phase-III | Rajasthan Phase-III Part F | Fatehgarh3– Beawar 765kV D/c |  |  |  | TBCB | [5 empty] | Sterlite | Sep-23 | 635 | 806 | 801 | 726 | 265 | 0.99 | 0.9 | 0.42 |  |  |  | Mar-25 | Mar - 26 | 1.RoW (24 locs.) in Rajasthan: Barmer (8 locs.: 3 Foundation & 5 Erection) & Balotra (16 locs.: 16 Erection). 2. Forest (10.89 Ha, 4 locs, 3.26 cKm) in Rajasthan: Stage II awaited. WP recieved on 16-06-25. Stage I received on 05-07-2024.
| EL-C7DA6 | Rajasthan Phase-III | Rajasthan Phase-III Part F | LILO of both circuits of Ajmer – Chittorgarh 765 kV D/c at Beawar |  |  |  | TBCB | [5 empty] | Sterlite | Sep-23 | 136 | 178 | 175 | 168 | 48 | 0.98 | 0.94 | 0.35 |  |  |  | Mar-25 | Mar - 26 | 1. Forest (22.66 Ha, 7 locs, 6.76 cKm) in Rajasthan: Stage II awaited. WP received on 13-05-25 & TCP received on 20-05-25. Stage I received on 05-11-2024. 2. PLC Approval pending with M/s Shree Cement.since mar'24.
| EL-9F9FE | Rajasthan Phase-III | Rajasthan Phase-III Part F | LILO of of Kota – Merta 400 kV D/c at Beawar |  |  |  | TBCB | [5 empty] | Sterlite | Sep-23 | 66 | 90 | 89 | 81 | 28 | 0.99 | 0.9 | 0.42 |  |  |  | Mar-25 | Mar - 26 | 1. PLC Approval pending with M/s Shree Cement since Mar'24.. 2. Delay in replacement of existing earth wire with OPGW in Kota -Merta TL by PGCIL. .
| EL-22203 | Rajasthan Phase-III | Rajasthan Phase-III Part F | 2X1500MVA , 765/400kV Beawar S/s | 3000 |  |  | TBCB | [5 empty] | Sterlite | Sep-23 | [8 empty] | 98.00% | 100.00% | 94.00% | Mar-25 | Jan - 26 | Total Land (58.28 Ha): Govt. Land (12.32 Ha) & Pvt. Land (45.96 Ha) : All acquired
| EL-D0594 | Rajasthan Phase-III | Rajasthan Phase-III Part F | (+/-)2x300 MVAr Statcom, 4x125 MVAr MSC, 2x125 MVAr MSR at Fatehgarh-III PS |  |  |  | TBCB | [5 empty] | Sterlite | Sep-23 | [8 empty] | 98.00% | 100.00% | 75.00% | Sep-25 | Mar - 26
| EL-0E237 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV (Part-1) PART B | Establishment of 765/400 kV, 4x1500 MVA (along with one spare unit of 500 MVA) Neemrana-II S/s | 6000 |  |  | TBCB | [5 empty] | Sterlite | Dec-23 | [8 empty] | 0.46% | 78.50% | 0.00% | Dec-25 | Aug - 26 | 1. Total Land (57.96 Ha All private): Pending 39.98 Ha
| EL-2453D | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV (Part-1) PART B | Neemrana-II -Kotputli 400 kV D/c line (Quad) |  |  |  | TBCB | [5 empty] | Sterlite | Dec-23 | 87 | 126 | 107 | 92 | 40 | 0.85 | 0.73 | 0.46 |  |  |  | Dec-25 | Aug - 26 | 1.RoW (10 locs.) in Rajasthan: Kotputli-Behror (10 locs.). 2. Forest (8.39 Ha, 6 locs, 7.09 cKm ) in Rajasthan. Stage II awaited. Stage I received on 14-08-2025.
| EL-EF0A0 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV (Part-1) PART B | LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s |  |  |  | TBCB | [5 empty] | Sterlite | Dec-23 | 395 | 517 | 429 | 306 | 34.2 | 0.83 | 0.59 | 0.09 |  |  |  | Dec-25 | Aug - 26 | 1. RoW (7 locs.) in Rajasthan: Khairthal-Tijara (7 locs) . 2. RoW (2 locs.) in Haryana: Nuh (2 locs). 3. Forest (22.86 Ha, 14 locs, 11.47 cKm) in Haryana: Stage I is awaited. Recommended in PSC-II dated 18-08-25 . Applied on 30-03-2024. 4. Forest (21.77 Ha, 17 locs, 19.66 cKm) in Rajasthan:Stage I received on 14-08- 2025.
| EL-A4341 | Khavda Phase-IV | Khavda Phase-IV Part C | Establishment of 4x1500 MVA, 765/400 kV & 2x500 MVA, 400/220 kV Boisar-II (GIS) S/s | 7000 |  |  | TBCB | [5 empty] | Sterlite | Aug-24 | [8 empty] | 30.00% | 44.10% | 0.00% | Oct-26 | Oct - 26 | Total land (142 Acres): Pending 52 Acres. Pvt. (90 Acres): All acquired Forest (52 Acres): Pending 52 Acre, Applied 06-06-2025.
| EL-3C3ED | Khavda Phase-IV | Khavda Phase-IV Part C | South Olpad (GIS) – Boisar-II (GIS) 765 kV D/c line |  |  |  | TBCB | [5 empty] | Sterlite | Aug-24 | 475 | 626 | 240 | 49 | 0 | 0.38 | 0.08 | 0 |  |  |  | Oct-26 | Oct - 26 | 1. RoW (126 locs.) in Gujarat: Olpad tehsil (51), Mangrol (6), Mandvi (7), Kamrej (31), Bardoli (22), Mahuva (2), Chikhli Taluka (7) 2. RoW (02 locs.) in Maharashtra: Palghar (2 locs) 3. Delay in Allocation of Space/Land for establishment of 2 Nos. of 765 kV line bays at south Olpad S/s due to non-finalisation of South Olpad S/s location by PGCIL. 4. PLC approval pending from PGCIL in Gujarat portion. 6. Forest (134.15 Ha, 51 locs., 40 ckm) in Gujarat 7. Forest (180.37 Ha, 61 locs., 50 ckm) in Maharashtra - Accepted in PSC-1 on 07- 04-2025, Tree enumeration completed. File is with DFO for part 2 processing. 8. Forest (8.49 Ha) in DNH: Stage-I approval pending
| EL-08928 | Khavda Phase-IV | Khavda Phase-IV Part C | Boisar-II (Sec-II) – Velgaon (MH) 400 kV D/c line |  |  |  | TBCB | [5 empty] | Sterlite | Aug-24 | 50 | 74 | 4 | 0 | 0 | 0.05 | 0 | 0 |  |  |  | Oct-26 | Oct - 26 | 1. RoW (4 locs.) in Maharashtra: Palghar (4) 2. Forest (62.5 Ha, 35 locs., 27.17 ckm) in Maharashtra. Stage I awaited, applied on 07-03-25. PSC-1 accepted on 12-08-2025. 3. 16 locs and 10 Kms of route length are on hold due to non-finalization of S/S land by MSETCL.
| EL-0CD22 | Khavda Phase-IV | Khavda Phase-IV Part C | LILO of Babhaleswar – Padghe (M) 400 kV D/c line at Boisar-II (Sec-I) |  |  |  | TBCB | [5 empty] | Sterlite | Aug-24 | 116 | 174 | 29 | 3 | 0 | 0.17 | 0.02 | 0 |  |  |  | Oct-26 | Oct - 26 | 1. RoW (51 locs.) in Maharashtra: Palghar District (6), Thane District(45) 2. PLC approval between AP 78/0 – 79/0 pending with PGCIL. 3. Forest (66.02 Ha, 46 locs, 28.7 ckm) in Maharashtra: Stage-I awaited. CCF visit done on 27-11-25.
| EL-98CE4 | Khavda Phase-IV | Khavda Phase-IV Part C | ± 300 MVAR STATCOM with 3x125 MVAR MSC, 1x125 MVAR MSR at 400 kV level of Navsari (New) (PG) S/s |  |  |  | TBCB | [5 empty] | Sterlite | Aug-24 | [8 empty] | 34.59% | 36.90% | 0.00% | Oct-26 | Oct - 26
| EL-FDB97 | Khavda Phase-IV | Khavda Phase-IV Part C | ±200 MVAR STATCOM with 2x125 MVAR MSC, 1x125 MVAR MSR at 400 kV bus section-I of Boisar-II and ±200 MVAR STATCOM with 2x125 MVAR MSC, 1x125 MVAR MSR at 400 kV bus section-II of Boisar-II. |  |  |  | TBCB | [5 empty] | Sterlite | Aug-24 | [8 empty] | 7.90% | 35.70% | 0.00% | Oct-26 | Oct - 26
| EL-F07FC | Khavda Phase-IV | Khavda Phase-IV Part C | LILO of Navsari (New) – Padghe (PG) 765 kV D/c line at Boisar-II |  |  |  | TBCB | [5 empty] | Sterlite | Aug-24 | 51 | 74 | 41 | 9 | 0 | 0.55 | 0.12 | 0 |  |  |  | Oct-26 | Oct - 26 | Forest: (38.94 Ha, 18 Locs, 12.68 cKm) in Maharashtra. Stage 1 awaited. applied on 19-01-2025. EDS rasied, A/p resubmitted on 02-04-2025. PSC 1 accepted on 07- 04-2025.
| EL-147DB |  |  | Establishment of 4x1500 MVA, 765/400 & 6x500 MVA, 400/220 kV Ananthapuram- II Pooling Station near Kurnool, Andhra Pradesh | 9000 |  |  | TBCB | [5 empty] | Sterlite | Mar-25 | [8 empty] | 0.00% | 22.00% | 0.00% | Mar-27 | Mar - 27 | Present Scope: 238 Ha Acquired Land: 193 Ha
| EL-0DACF |  |  | Ananthapuram- II - Davangere 765 kV D/c line |  |  |  | TBCB | [5 empty] | Sterlite | Mar-25 | 236 | 236 | 54 | 1 | 0 | 0.23 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | 1. Delay in handover of critical D&E inputs of Davanagere S/s by PGCIL for route finalisation and construction of 2 nos. 765 kV line bays at the Davanagere S/s . 2. RoW (6 locs.) in Andhra Pradesh: Ananthpuram (6 locs.)
| EL-E06AD |  |  | Ananthapuram- II - Cuddapah 765 kV D/c line |  |  |  | TBCB | [5 empty] | Sterlite | Mar-25 | 565 | 565 | 258 | 4 | 0 | 0.46 | 0.01 | 0 |  |  |  | Mar-27 | Mar - 27 | RoW (50 locs.) in Andhra Pradesh: Ananthpuram (44 locs.) & Y S R Kadapa (6 locs.)
| EL-1E3DC |  |  | ±300 MVAr STATCOM at Ananthapuram-II PS along with 2x125 MVAr MSR |  |  |  | TBCB | [5 empty] | Sterlite | Mar-25 | [8 empty] | 0.00% | 10.27% |  | Mar-27 | Mar - 27
| EL-DCBDA |  |  | LILO of both circuits of existing Bongaigaon (POWERGRID) – Balipara (POWERGRID) 400 kV D/C (Quad) line at Bornagar (ISTS) |  |  |  | TBCB | [5 empty] | Sterlite | Jul-25 | 54 | 85 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Jul-28 | Jul - 28
| EL-F98B4 |  |  | Establishment of new 400 kV Bornagar (ISTS) switching station in Assam (765 kV and 220 kV levels to be established in future) |  |  |  | TBCB | [5 empty] | Sterlite | Jul-25 | [8 empty] | 0.00% | 0.00% | 0.00% | Jul-28 | Jul - 28
| EL-93D74 |  |  | NK – Gaya 400kV D/c line |  |  |  | TBCB | [5 empty] | Adani | Jul-16 | 196 | 285 | 285 | 285 | 196.4 | 1 | 1 | 1 |  |  |  | Sep-19 | Dec - 25
| EL-E1D57 |  |  | NK – Chandwa 400kV D/c line |  |  |  | TBCB | [5 empty] | Adani | Jul-16 |  | 115 |  |  |  | 0 | 0 |  |  |  |  | Sep-19 | Oct - 22 | Line charged
| EL-989EE |  |  | LILO of both circuits of Ranchi – Maithon-RB 400kV D/c line at Dhanbad |  |  |  | TBCB | [5 empty] | Adani | Jul-16 |  | 10 |  |  |  | 0 | 0 |  |  |  |  | Sep-19 | Aug - 21 | Line charged
| EL-3E4A4 |  |  | 400/220 kV, 2x500 MVA Dhanbad |  |  |  | TBCB | [5 empty] | Adani | Jul-16 | [11 empty] | Sep-19 | Aug - 21 | Substation Charged
| EL-27D66 |  |  | Narendra New (GIS) – Pune (GIS) 765 D/c Line |  |  |  | TBCB | [5 empty] | Adani | Jan-23 | 636 | 795 | 663 | 523 | 133.2 | 0.83 | 0.66 | 0.21 |  |  |  | Jul-24 | Mar - 26 | RoW (88 loc) : a) Pune District (46) in Maharashtra. b) Vijaypura District (40) in Karnataka. 40 locations affected near Kudgi end. Forest (76.87 Ha, 29 loc)- Proposal recommended in PSC-II conducted on 12-Aug- 25. MoM & NO clearance received on 12-Sep-25. Proposal forwarded from SG to IRO on 11-Nov-25. Proposal awaiting recommendation in REC meeting.
| EL-FFDA5 |  |  | Upgradation of Narendra New (GIS) Substation to rated voltage level of 765 kV alongwith 4x1500 MVA transformer | 6000 |  |  | TBCB | [5 empty] | Adani | Jan-23 | [8 empty] | 97.50% | 100.00% | 96.00% | Jul-24 | Mar - 26 | Outdoor and indoor GIB along with GAB WIP HV Testing has been completed for Pune SS And Narendra SS HV testing under initiation
| EL-C4DEB | Khavda RE Park Phase-III | Khavda RE Park Phase-III Part A | Establishment of 765 kV Halvad switching station with 765 kV, 2x330 MVAr bus reactors |  |  |  | TBCB | [5 empty] | Adani | Dec-23 | [8 empty] | 97.00% | 97.00% | 80.00% | Dec-25 | Mar - 26 | Land required: 205 Acre (Present scope acquisition completed) Pvt. land (197): Aquired (183) Govt. land (8): Acquired (8)
| EL-85D07 | Khavda RE Park Phase-III | Khavda RE Park Phase-III Part A | KPS2(GIS) - Halvad 765 kV D/c line |  |  |  | TBCB | [5 empty] | Adani | Dec-23 | 492 | 690 | 536 | 400 | 125 | 0.78 | 0.58 | 0.25 |  |  |  | Dec-25 | Mar - 26 | RoW: 101 Locs. Tehsils: Morbi- 75 Nos (35 Morbi, 8 Maliya, 32 Halvad) Kutch 26 Locs Tehsils: (Bhuj- 2 Nos, Bhachau-24) Forest (266.6997 Ha, 99 locs) in Gujarat. Wildlife (36.6493 Ha, 18 locs.) in Gujarat.
| EL-011C3 | Khavda RE Park Phase-III | Khavda RE Park Phase-III Part A | LILO of Lakadia – Ahmedabad 765 kV D/c line at Halvad |  |  |  | TBCB | [5 empty] | Adani | Dec-23 | 68 | 100 | 90 | 59 | 2.96 | 0.9 | 0.59 | 0.04 |  |  |  | Dec-25 | Mar - 26
| EL-094A9 | Khavda Phase-IV | Khavda Phase-IV Part A | Augmentation of KPS3 (GIS) by 3x1500 MVA, 765/400 kV ICTs | 4500 |  |  | TBCB | [5 empty] | Adani | Aug-24 | [8 empty] | 42.00% | 20.00% | 5.00% | Aug-26 | Aug - 26 | Land required for Lakadia bay extension: 13 Acres, same under acquisition
| EL-009FA | Khavda Phase-IV | Khavda Phase-IV Part A | 765 kV KPS3 (GIS) – Lakadia (AIS) D/C line |  |  |  | TBCB | [5 empty] | Adani | Aug-24 | 404 | 513 | 262 | 121 | 4.8 | 0.51 | 0.24 | 0.01 |  |  |  | Aug-26 | Aug - 26 | 1) ROW: 40 Locs : Khavda (1), Bhuj - (15), Bhachau - (24). Application for Section 16(1) is submitted 2) Forest- KPS3-Lakadia -(317.61 Ha, 128 locs) - Proposal recommended in PSC-II vide MoM dated 23-Sep-25. Proposal forwarded from Nodal officer to state government on 15-Oct-25. Proposal forwarding to IRO is awaited.
| EL-3A9B0 | Khavda Phase-IV | Khavda Phase-IV Part A | 765 kV KPS1 (GIS)– Bhuj PS D/C line (2nd) |  |  |  | TBCB | [5 empty] | Adani | Aug-24 | 217 | 286 | 185 | 119 | 18.08 | 0.65 | 0.42 | 0.08 |  |  |  | Aug-26 | Aug - 26 | 1) ROW: 4 Locs, Bhuj - (4). Application for Section 16(1) is submitted. 2) Forest (220.81 Ha, 84 locs) - Proposal recommended in PSC-II vide MoM dated 23-Sep-25. Proposal forwarded from Nodal officer to state government on 15-Oct- 25. Proposal forwarding to IRO is awaited.
| EL-D0C5D | Khavda Phase-IV | Khavda Phase-IV Part A | ±300MVAR STATCOM with 1x125 MVAR MSC, 2x125 MVAR MSR at KPS3 400 kV. |  |  |  | TBCB | [5 empty] | Adani | Aug-24 | [8 empty] | 5.00% |  |  | Aug-26 | Aug - 26 | Land required: ROU permission required from GPCL/Govt of Gujarat. Letter submitted to GPCL , Further letter written to collector for land handover.
| EL-21714 | Gujarat | Gujarat | Establishment of 4x1500 MVA, 765/400 kV Navinal (Mundra) S/s (GIS) | 6000 |  |  | TBCB | [5 empty] | Adani | Oct-24 | [8 empty] | 45.00% | 25.00% | 0.00% | Jul-26 | Jul - 26 | Land (70 Acre): All acquired Supply, Civil & ETC ordering completed. EPC package ordering completed. ICTs, Reactors: Sept;25 to Mar’26
| EL-92E76 | Gujarat | Gujarat | LILO of Bhuj-II – Lakadia 765 kV D/C line at Navinal (Mundra) (GIS) S/s |  |  |  | TBCB | [5 empty] | Adani | Oct-24 | 257 | 368 | 137 | 65 | 0 | 0.37 | 0.18 | 0 |  |  |  | Jul-26 | Jul - 26 | 1] Forest-(73.9278 Ha, 42 locs) in Gujarat,Proposal from DFO, Kutch East & Kutch SF forwarded to CCF. Kutch West to CCF on 20-Sep-25. Proposal forwarded from CCF to Nodal Officer on 10-Oct-25. PSC-II completed on 6-Nov-25. 2] ROW- Mundra Tehsil. (129 Locs, 44 Km)
| EL-4B19B | Gujarat Phase-I | Gujarat Phase-I | Establishment of 2x1500 MVA 765/400 kV Jamnagar (GIS) PS | 3000 |  |  | TBCB | [5 empty] | Adani | Oct-24 | [11 empty] | Oct-26 | Oct - 26 | Land (115 Acre): Land acquisition under progress.
| EL-BD3BF | Gujarat Phase-I | Gujarat Phase-I | Halvad – Jamnagar 765 kV D/c line |  |  |  | TBCB | [5 empty] | Adani | Oct-24 | 340 | 391 | 58 | 7 |  | 0.15 | 0.02 | 0 |  |  |  | Oct-26 | Oct - 26 | 1] Check survey under progress 89 km off 147 Km completed 2] Forest: 16.552 Ha, 2 Locations 3.54 km affected- Modification in proposal due to change in Jamnagar SS land. Revised hard copies submitted in all divisions in August 2025 EDS compliance completed.
| EL-CAF70 | Gujarat Phase-I | Gujarat Phase-I | LILO of Jam Khambhaliya PS – Lakadia 400 kV D/c (triple snowbird) line at Jamnagar |  |  |  | TBCB | [5 empty] | Adani | Oct-24 | 20 | 28 | 0 |  |  | 0 | 0 | 0 |  |  |  | Oct-26 | Oct - 26 | 1] Check survey under progress. 2] Forest: 0.12 Ha, 0 Locations 0.012 km affected. Proposal submitted on Parivesh portal on 06-08-25.
| EL-93439 | Gujarat Phase-I | Gujarat Phase-I | Jamnagar – Jam Khambhaliya 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line |  |  |  | TBCB | [5 empty] | Adani | Oct-24 | 100 | 112 | 0 |  |  | 0 | 0 | 0 |  |  |  | Oct-26 | Oct - 26 | 1) Forest: 2.43 Ha, 2 Locations 0.528 km affected. Proposal submitted on Parivesh portal on 06-08-25. 2) Check survey completed 37 Km off 41 Km.
| EL-784A4 | Gujarat Phase-I | Gujarat Phase-I | LILO of CGPL – Jetpur 400kV D/c (triple snowbird) line at Jamnagar |  |  |  | TBCB | [5 empty] | Adani | Oct-24 | 260 | 339 | 13 |  |  | 0.04 | 0 | 0 |  |  |  | Oct-26 | Oct - 26 | 1] Check survey under progress 123 Km off 123 Km 2] Forest: 1.08 Ha, 0 Locations 0.234 km affected. Proposal submitted on Parivesh portal on 06-08-25.
| EL-57331 | Gujarat Phase-I | Gujarat Phase-I | LILO of both ckts of Kalavad – Bhogat 400kV D/c line (Twin AL-59) at Jam Khambhaliya PS |  |  |  | TBCB | [5 empty] | Adani | Oct-24 | 40 | 35 | 0 |  |  | 0 | 0 | 0 |  |  |  | Oct-26 | Oct - 26 | Check survey under progress.
| EL-4C948 | Gujarat Phase-I | Gujarat Phase-I | ±400 MVAr STATCOM with 3x125 MVAr MSC & 2x125 MVAr MSR at Jamnagar 400kV Bus section |  |  |  | TBCB | [5 empty] | Adani | Oct-24 | [11 empty] | Oct-26 | Oct - 26 | Engineering under progress
| EL-D3829 | Khavda Phase-IV | Khavda Phase-IV Part D | Establishment of 2x1500 MVA, 765/400 kV & 3x500 MVA, 400/220 kV Pune- III (GIS) S/s | 4500 |  |  | TBCB | [5 empty] | Adani | Nov-24 | [11 empty] | Nov-26 | Nov - 26 | Pune - III Substation : Land (105 Acre, all Pvt.): Land under posession and Land development work is in progress. 2 Nos Bays at Boisar II: OGA finalization is on hold due to non availablity of sufficeient space to accomodate scope alocated to Pune - III Tranmsiison limited and mismatch in Future scope of Khavda IV C Transmission Limited and present scope of Pune - III Tranmsission Limited.
| EL-A9256 | Khavda Phase-IV | Khavda Phase-IV Part D | Boisar-II – Pune-III 765 kV D/c line (228 km) |  |  |  | TBCB | [5 empty] | Adani | Nov-24 | 456 | 629 | 5 |  |  | 0.01 | 0 | 0 |  |  |  | Nov-26 | Nov - 26 | ROW: Palghar (2), Pune (4). Forest- Area: (~50 Km) : 765 KV Boisar II to Pune III Transmission Line passes through Jawahar, Thane, Alibaugh, and Pune Forest Divisions.
| EL-726F8 | Khavda Phase-IV | Khavda Phase-IV Part D | LILO of Narendra (New) – Pune (GIS) 765 kV D/c line at Pune-III (85.6 km) |  |  |  | TBCB | [5 empty] | Adani | Nov-24 | 171 | 213 | 20 |  |  | 0.09 | 0 | 0 |  |  |  | Nov-26 | Nov - 26 | RoW : Pune (2, Baramati and Purandar Taluka) Forest ( ~28 Ha combined with 400 KV LILO Line) : Under Sec. (Mantralaya - Mumbai) GOM has recomended proposal to RO MoEF&CC ( GOI)
| EL-B495D | Khavda Phase-IV | Khavda Phase-IV Part D | LILO of Hinjewadi-Koyna 400 kV S/c line at Pune-III (GIS) S/s (8.516 km) |  |  |  | TBCB | [5 empty] | Adani | Nov-24 | 17 | 24 |  |  |  | 0 | 0 | 0 |  |  |  | Nov-26 | Nov - 26 | RoW : Pune (2, Baramati and Purandar Taluka) Forest ( ~28 Ha combined with 765 KV LILO Line ) : Under Sec. (Mantralaya - Mumbai) GOM has recomended proposal to RO MoEF&CC ( GOI)
| EL-C10DF | Rajasthan Phase III | Rajasthan Phase III Part I | Establishment of 6000 MW (4x1500 MW), ± 800 kV (HVDC) [LCC] near Bhadla-III S/s and at Fatehpur(UP) (Bipole-1: 3000 MW) | 3000 |  |  | TBCB | [5 empty] | Adani | Jan-25 | [11 empty] | Jul-29 | Jul - 29 | Land (156 Acre, all Pvt.): All Acquire Engg. Under progress
| EL-6E493 | Rajasthan Phase III | Rajasthan Phase III Part I | Establishment of 5x1500 MVA, 765/400 kV ICTs at Fatehpur HVDC | 7500 |  |  | TBCB | [5 empty] | Adani | Jan-25 | [11 empty] | Jul-29 | Jul - 29 | Engg. Under Progress
| EL-2A912 | Rajasthan Phase III | Rajasthan Phase III Part I | ±800 kV HVDC line (Hexa lapwing) between Bhadla (HVDC) and Fatehpur (HVDC) (with DMR) |  |  |  | TBCB | [5 empty] | Adani | Jan-25 | 955 | 2,173 | [5 empty] | 0 |  |  |  | Jul-29 | Jul - 29 | Forest: Rajasthan State (88 Ha), Madhya Pradesh : (35 Ha) :LoA has been issued Forest: Uttar Pradesh : (4 Ha) Land Finalization under progress. Wildlife: Rajasthan State : (7 Ha) LOA has been issued. Wildlife: Madhya Pradesh : (7 Ha)
| EL-71B35 | Rajasthan Phase III | Rajasthan Phase III Part I | 400 kV 2xD/c Bhadla III-Bhadla (HVDC) line (Quad Moose) |  |  |  | TBCB | [5 empty] | Adani | Jan-25 | 2 | 18 |  |  |  | 0 | 0 | 0 |  |  |  | Jul-29 | Jul - 29 | Engg under progress
| EL-BBD19 | Rajasthan Phase III | Rajasthan Phase III Part I | LILO of both ckts of 765 kV Varanasi– Kanpur(GIS) D/c line at Fatehpur |  |  |  | TBCB | [5 empty] | Adani | Jan-25 | 47 | 86 |  |  |  | 0 | 0 | 0 |  |  |  | Jul-29 | Jul - 29 | Engg under progress
| EL-AF8BD | Gujarat Phase-I | Gujarat Phase-I Part B1 scheme | Augmentation of Transformation capacity at 765/400 kV Navinal(Mundra) S/s (GIS) by 2x1500 MVA ICTs | 3000 |  |  | TBCB | [5 empty] | Adani | Mar-25 | [11 empty] | Mar-28 | Mar - 28 | Enquiry floated to vendor
| EL-86676 | Gujarat Phase-I | Gujarat Phase-I Part B1 scheme | Navinal(Mundra) (GIS) – Bhuj 765 kV D/c line |  |  |  | TBCB | [5 empty] | Adani | Mar-25 | 140 | 202 |  |  |  | 0 | 0 | 0 |  |  |  | Mar-28 | Mar - 28 | Enquiry floated to vendor
| EL-F948A | Gujarat Phase-I | Gujarat Phase-I Part B1 scheme | ±300MVAr STATCOM along with 2x125MVAr MSC & 1x125MVAr MSR at Navinal(Mundra) (GIS) 400 kV Bus section-I |  |  |  | TBCB | [5 empty] | Adani | Mar-25 | [11 empty] | Mar-28 | Mar - 28 | Enquiry floated to vendor
| EL-7DAF5 | Gujarat Phase-I | Gujarat Phase-I Part B1 scheme | ±300MVAr STATCOM along with 2x125MVAr MSC & 1x125MVAr MSR at Navinal(Mundra) (GIS) 400 kV Bus section-II |  |  |  | TBCB | [5 empty] | Adani | Mar-25 | [11 empty] | Mar-28 | Mar - 28 | Enquiry floated to vendor
| EL-3B268 | Madhya Pradesh | Madhya Pradesh | Establishment 2x1500 MVA, 765/400 kV Substation near South of Kalamb with 2x330 MVAr, 765 kV bus reactor and 2x125 MVAr, 420 kV bus reactor. | 3000 |  |  | TBCB | [5 empty] | Adani | May-25 | [11 empty] | Jan-28 | Jan - 28 | Land (350 Acre, all Pvt.): Pending (350 Acre)
| EL-F0437 | Madhya Pradesh | Madhya Pradesh | LILO of Pune-III – Boisar-II 765 kV D/C line at South Kalamb S/s with associated bays at South Kalamb S/s. |  |  |  | TBCB | [5 empty] | Adani | May-25 | 2 | 6 |  |  |  | 0 | 0 | 0 |  |  |  | Jan-28 | Jan - 28 | EPC ordering under progress.
| EL-AA7D2 | Sikar | Sikar | Koteshwar - Rishikesh 400kV D/C line |  |  |  | TBCB | [5 empty] | Tata Power | Aug-16 | 77 | 102 | 102 | 102 | 77 | 1 | 1 | 1 | 100.00% | 100.00% | 100.00% | Dec-19 | Dec - 25 | Approval for charging of is in progress.
| EL-78DF3 | Sikar | Sikar | LILO of one ckt of 400 kV D/C Sikar (PG)-Neemrana (PG) line at Babai. |  |  |  | TBCB | [5 empty] | Tata Power | Aug-16 |  | 6 |  |  |  | 0 | 0 |  |  |  |  | Dec-16 | Oct - 17 | Line charged in Oct'17
| EL-70DDF | Sikar | Sikar | Babai (RRVPNL) – Bhiwani (PG) 400 kV D/C line |  |  |  | TBCB | [5 empty] | Tata Power | Aug-16 |  | 304 |  |  |  | 0 | 0 |  |  |  |  | Jun-19 | Oct - 23 | Line charged in Nov'23
| EL-4535D | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV (Part-1) PART C | Bikaner-III - Neemrana-II 765 kV D/C line (2nd) |  |  |  | TBCB | [5 empty] | Tata Power | Dec-23 | 692 | 884 | 861 | 418 | 66 | 0.97 | 0.47 | 0.1 | 50.00% | 57.00% | 0.00% | Dec-25 | Jun - 26 | • RoW Foundation (7 Loc) : Bikaner (1), Kotputli (1), Sikar (1), Jhunjhunu (4) in Rajasthan State • Erection (35 Loc) : Bikaner (7), Churu (0), Kotputli (5), Jhunjhunu (14) Sikar (1) in Rajasthan State & Mahendrgarh (8) in Haryana State • RAC Land work stopped for Erection & Stringing: 1 Location (Distt Kotputli) • Forest (10.66 Ha, 5 Locs, 4 ckm) in Haryana: Stage I awaited • Forest (2.22 Ha) in Rajasthan : Stage I Received on 08.08.2025. Payment deposited.
| EL-F440A |  |  | Establishment of new 765/400 kV, 2x1500 MVA GIS S/s at Gopalpur, Odisha | 3000 |  |  | TBCB | [5 empty] | Tata Power | Nov-24 | [8 empty] | 0.00% |  |  | Dec-27 | Dec - 27 | 70 acres of land at Chattrapur for the Gopalpur substation is in progress
| EL-DF73D |  |  | Angul - Gopalpur 765 kV D/c line |  |  |  | TBCB | [5 empty] | Tata Power | Nov-24 | 399 | 452 | 33 | 0 | 0 | 0.07 | 0 | 0 | 7.00% |  |  | Dec-27 | Dec - 27
| EL-2AAC2 |  |  | Gopalpur - Gopalpur (OPTCL) 400 kV D/c (Quad) line |  |  |  | TBCB | [5 empty] | Tata Power | Nov-24 | 51 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00% |  |  | Dec-27 | Dec - 27
| EL-09B5F |  |  | Extension at 765 kV level at Angul (PG) S/s including bus extension in GIS |  |  |  | TBCB | [5 empty] | Tata Power | Nov-24 | [8 empty] | 0.00% |  |  | Dec-27 | Dec - 27 | Delay in issuance of tree cutting permission for commencement of 765 kV bay extension works in the premises of PGCIL. FM Notice has been issued.
| EL-B818B |  |  | Extension at 400 kV level at Gopalpur (OPTCL) GIS S/s |  |  |  | TBCB | [5 empty] | Tata Power | Nov-24 | [8 empty] | 0.00% |  |  | Dec-27 | Dec - 27
| EL-371DF |  |  | Angul (POWERGRID) – Paradeep 765 kV D/c line |  |  |  | TBCB | [5 empty] | Tata Power | Nov-24 | 179 | 477 | 92 | 1 | 0 | 0.19 | 0 | 0 | 20.00% |  |  | Nov-26 | Nov - 26 | Delay in receipt of NOC for revised route from the Aviation Research Center (ARC) affecting civil foundation work at 14 Nos. locations.
| EL-7B228 |  |  | Paradeep – Paradeep (OPTCL) 400 kV D/c (Quad) line |  |  |  | TBCB | [5 empty] | Tata Power | Nov-24 | 13 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00% |  |  | Nov-26 | Nov - 26 | Tower foundation work is planned to commence from December, 2025 onwards.
| EL-60329 | Gadag Phase-II | Gadag Phase-II Part A, Phase | Gadag Pooling station – Koppal PS 400 kV D/C line |  |  |  | TBCB | [5 empty] | Renew | Nov-22 | 100 | 127 | 110 | 105 | 72.72 | 0.87 | 0.83 | 0.73 |  |  |  | May-24 | Jan - 26 | Foundation RoW (13 loc.): District Koppal, Taluka Kuknoor, village Tadkal (13 Loc) Erection RoW (01 loc.): District Koppal, Taluka Kuknoor , village Tadkal (01 Loc) in Karnataka.
| EL-D9028 | Gadag Phase-II | Gadag Phase-II Part A, Phase | 400/220 kV, 3x500MVA ICT Augmentation at Gadag | 1500 |  |  | TBCB | [5 empty] | Renew | Nov-22 | [8 empty] | 100.00% | 100.00% | 100.00% | May-24 | Oct - 25 | Work completed.
| EL-44487 |  |  | LILO of one circuit of Jabalpur – Orai 765 kV D/c line at Ishanagar 765 kV S/s |  |  |  | TBCB | [5 empty] | Indigrid | Feb-24 | 35 | 45 | 19 | 1 |  | 0.42 | 0.02 | 0 |  |  |  | Feb-26 | Jun - 26 | Work under progress
| EL-EBD1F |  |  | 2x1500 MVA, 765/400 kV and 2x500 MVA, 400/220 kV S/s at Ishanagar (New) | 4000 |  |  | TBCB | [5 empty] | Indigrid | Feb-24 | [8 empty] | 2.00% |  |  | Feb-26 | Jun - 26 | Land (157.67 Acre): Pending (30 Acre) Govt. (18.46 Acre): Pending (18.46 Acre) in Chhtarpur District, Govt of MP has issued the working permission for Govt. land vide letter dated 16th Oct’25 for 18.46 Acres. Pvt. (139.21 Acre): Pending (7.21Acre). Registration of 132Acres of Pvt. land completed acqusition of balance land is in Progress. Civil works started on ICT, Reactor, SPR & Gantry Towers
| EL-2E0EF |  |  | Dhule PS – Dhule (BDTCL) 400 kV D/c line |  |  |  | TBCB | [5 empty] | Indigrid | Feb-24 | 131 | 178 | 58 | 25 | 0 | 0.33 | 0.14 | 0 |  |  |  | Feb-26 | Feb - 26 | RoW (10) : Dhule (10). Forest (25.0593 Ha, 16 Loc, 10.80 ckm) in the State of Maharashtra. Stage-I is pending. Part I and Part II filing done, file is forwarded to State Secretary Forest for signing.
| EL-D29C3 |  |  | 4x500 MVA, 400/220 kV Pooling Station near Dhule (New) | 2000 |  |  | TBCB | [5 empty] | Indigrid | Feb-24 | [8 empty] | 39.00% |  |  | Feb-26 | Feb - 26 | Works in progress
| EL-D52CC | Kallam | Kallam | LILO of both circuits of Parli(M) – Karjat(M)/Lonikand-II (M) 400 kV D/c line (twin moose) at Kallam PS |  |  |  | TBCB | [5 empty] | Indigrid | Apr-24 | 54 | 41 | 11 | 2 |  | 0.27 | 0.05 | 0 |  |  |  | Oct-25 | Dec - 25 | Substation element commissioned on 28th Sep'25. RoW resolution with support from administration ongoing.
| EL-56F25 |  |  | LILO of 400 kV Kishenpur-Dulhasti line at Kishtwar S/s |  |  |  | TBCB | [5 empty] | Indigrid | Mar-25 | 2 | 14 |  |  |  | 0 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | Check Survey is completed.
| EL-9BDD4 |  |  | 400 kV Kishenpur-Samba D/C line . |  |  |  | TBCB | [5 empty] | Indigrid | Mar-25 | 70 | 122 | 10 |  |  | 0.08 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | Foundation Work Started. All statutory proposal and forest diversion proposal submitted
| EL-F5C1B |  |  | Bypassing of one ckt of 400 kV Kishtwar – Kishenpur 400kV D/C line at Kishenpur and connecting it with one of the circuit of Kishenpur- Samba 400 kV D/C line, thus forming 400 kV Kishtwar - Samba direct line (one ckt) |  |  |  | TBCB | [5 empty] | Indigrid | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Check Survey completed.
| EL-0A7EF |  |  | 400 kV Samba- Jalandhar D/C line |  |  |  | TBCB | [5 empty] | Indigrid | Mar-25 | 299 | 397 | 61 |  |  | 0.15 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | Foundation Work Started. All statutory proposal and forest diversion proposal submitted
| EL-806B8 |  |  | Bypassing 400 kV Jalandhar – Nakodar line at Jalandhar and connecting it with one of the circuit of Samba-Jalandhar 400 kV D/C line, thus forming 400 kV Samba – Nakodar direct line |  |  |  | TBCB | [5 empty] | Indigrid | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Check Survey completed.
| EL-02F72 | Madhya Pradesh Phase II | Madhya Pradesh Phase II | Pachora PS – Ujjain (MPPTCL) 400 kV D/c line |  |  |  | TBCB | [5 empty] | GR Infra | Feb-24 | 118 | 145 | 134 | 113 | 19.01 | 0.92 | 0.78 | 0.16 |  | 99.00% |  | Feb-26 | Mar - 26 | RoW (12 locs.): Agar Malwa (Fdn-9 Nos & Erection-1 Nos), Ujjain (Stringing-2 Locs) Forest & WLC: Nil Status of receipt of Conductors- 1440/1440 kms -completed Tower material: 3697/3772 MT, Balance tower to be supplied till 15th Dec’25
| EL-0C8C8 | Madhya Pradesh Phase II | Madhya Pradesh Phase II | 400/220 kV, 3x500 MVA ICT augmentation (4th, 5th and 6th) at Pachora PS. | 1500 |  |  | TBCB | [5 empty] | GR Infra | Feb-24 | [8 empty] | 87.00% | 96.00% | 55.00% | Feb-26 | Mar - 26 | Land (11 Acre): 100% Govt.: 100% acquire in Ujjain SS. Pvt: 100% at lease for 35 years, SS Agar Malwa, Dist.- Agar Malwa -Completed
| EL-3BCA9 | Karnataka | Karnataka | Establishment of 400/220 kV 4x500 MVA Pooling Station near Tumkur, Karnatak | 2000 |  |  | TBCB | [5 empty] | GR Infra | Sep-24 | [8 empty] | 40.00% | 0.00% | 0.00% | Sep-26 | Sep - 26 | Land: 70 Acre acquired. Status of receipt of Transformers/Reactors: Expected by 30.04.2026
| EL-80353 | Karnataka | Karnataka | Tumkur-II – Tumkur (Pavagada) line 400 kV (Quad ACSR moose) D/c line. |  |  |  | TBCB | [5 empty] | GR Infra | Sep-24 | 53 | 73 | 15 | 0 | 0 | 0.21 | 0 | 0 |  |  |  | Sep-26 | Sep - 26 | Status of receipt of conductors/Tower material: Conductor (680 Kms/ 680 Kms ). Tower material: 40/1672 MT;balance expected by 31.01.2026.
| EL-6CEFA | Karnataka | Karnataka | Establishment of 400/220 kV, 5x500 MVA Pooling Station near Bijapur (Vijayapura), Karnataka | 2500 |  |  | TBCB | [5 empty] | GR Infra | Jan-25 | [8 empty] | 0.00% | 0.00% | 0.00% | Jan-27 | Jan - 27 | Land (65 Acre): Pvt. (65 Acre): 100% acquisition done. Status of receipt of Transformers/ Reactors: Expected by 31.10.2026
| EL-74B4E | Karnataka | Karnataka | Bijapur PS – Raichur New 400kV (Quad ACSR moose) D/c line |  |  |  | TBCB | [5 empty] | GR Infra | Jan-25 | 276 | 360 | 21 | 0 | 0 | 0.06 | 0 | 0 |  |  |  | Jan-27 | Jan - 27 | Status of receipt of conductors/Tower material: Expected by 30.05.2026
| EL-28D61 | Madhya Pradesh Phase III | Madhya Pradesh Phase III | Creation of New 220 kV Bus Section with 220 kV Bus Sectionaliser and 400/220 kV, 3x500 MVA ICT augmentation at Pachora PS. | 1500 |  |  | TBCB | [5 empty] | GR Infra | Sep-25 | [8 empty] | 0.00% | 0.00% | 0.00% | Sep-27 | Sep - 27 | Land (11.357 Acre - Private): 3.357 Acquired
| EL-F68B8 | Madhya Pradesh Phase III | Madhya Pradesh Phase III | Pachora PS – Rajgarh(PG) 400 kV D/c line |  |  |  | TBCB | [5 empty] | GR Infra | Sep-25 | 185 |  | 0 | 0 | 0 |  |  | 0 |  |  |  | Sep-27 | Sep - 27 | Eco Sensitive Zone: 39.1 Ha (Estimated)
| EL-7F602 | Madhya Pradesh Phase III | Madhya Pradesh Phase III | Creation of New 220 kV Bus Section-II at Neemuch PS with Augmentation of transformation capacity by 3x500 MVA, 400/220 kV ICTs at Neemuch S/s. | 1500 |  |  | TBCB | [5 empty] | GR Infra | Sep-25 | [8 empty] | 0.00% | 0.00% | 0.00% | Sep-27 | Sep - 27
| EL-2288D | Madhya Pradesh Phase III | Madhya Pradesh Phase III | Neemuch PS – Pachora PS 400 kV D/c line. |  |  |  | TBCB | [5 empty] | GR Infra | Sep-25 | 221 |  | 0 | 0 | 0 |  |  | 0 |  |  |  | Sep-27 | Sep - 27 | Forest: 79.80 Ha (Estimated)
| EL-0E0B6 | Madhya Pradesh Phase III | Madhya Pradesh Phase III | Establishment of 2x500 MVA, 400/220 kV S/s at Handiya. | 1000 |  |  | TBCB | [5 empty] | GR Infra | Sep-25 | [8 empty] | 0.00% | 0.00% | 0.00% | Sep-27 | Sep - 27 | Land (40 Acre): Land acquisition under process.
| EL-09ABE | Madhya Pradesh Phase III | Madhya Pradesh Phase III | Pachora PS – Handiya 400 kV D/c line. |  |  |  | TBCB | [5 empty] | GR Infra | Sep-25 | 214 |  | 0 | 0 | 0 |  |  | 0 |  |  |  | Sep-27 | Sep - 27 | Forest: 24.01 Ha (Estimated)
| EL-FF89F | Madhya Pradesh Phase III | Madhya Pradesh Phase III | LILO of Khandwa (PG) – Itarsi (PG) 400 kV D/c line at Handiya S/s. |  |  |  | TBCB | [5 empty] | GR Infra | Sep-25 | 30 |  | 0 | 0 | 0 |  |  | 0 |  |  |  | Sep-27 | Sep - 27
| EL-C0F3C | Madhya Pradesh | Madhya Pradesh | 400 kV D/c Khandukhal (Srinagar) – Rampura (Kashipur) line |  |  |  | TBCB | [5 empty] | Megha Engg. | Oct-22 | 384 | 498 | 442 | 283 | 24.88 | 0.89 | 0.57 | 0.06 |  |  |  | Sep-24 | Dec - 25 | RoW in Uttarakhand (56 locs.): Pouri Gehwal (52 locs): Udam singh nagar (4 Locs) Forest (191.31Ha, 73 locs., 50 ckm) in Uttarakhand State : Stage I approval granted on 17.02.2025. Estimation received on 11.03.2025 and payment is under process. Status of receipt of conductors/Tower material: All Tower material supplies been completed. Conductor Order given on Sep’2024. For Substation Bay Extension Work: Land Lease / Rent agreement to be finalized by PTCUL for Space to construct Bay Extension at Rampura & Khandhukal Substations.
| EL-59D0D | Rajasthan phase III | Rajasthan phase III Part A3 | Fatehgarh 3- Bhadla-3 400kV D/C line (Quad) line |  |  |  | TBCB | [5 empty] | Apraava Energy | Aug-23 | 446 | 584 | 485 | 389 | 112.14 | 0.83 | 0.67 | 0.25 | 0.00% |  |  | Feb-25 | Jun - 26 | RoW (80 loc.): Barmer (3), Jaisalmer (38), Phalodi (39) in Rajasthan State Forest (22.2778, 9.686 ckm) in Rajasthan: Stage I Pending Applied on 31.07.2024 Curr. Status : Proposal pending at REC.
| EL-783FC | Rajasthan phase III | Rajasthan phase III Part A1 | 5x500MVA, 400/220kV pooling station at Fatehgarh-4 | 2500 |  |  | TBCB | [5 empty] | Apraava Energy | Aug-23 | [8 empty] | 95.00% | 99.50% | 100.00% | Feb-25 | Dec - 25 | All land acquired (134.4 Acre, All Private)
| EL-5BC1C | Rajasthan phase III | Rajasthan phase III Part A1 | Fatehgarh-4 PS- Fatehgarh-3 PS 400kV D/c |  |  |  | TBCB | [5 empty] | Apraava Energy | Aug-23 | 42 | 61 | 61 | 61 | 42.68 | 1 | 1 | 1.02 | 0.00% |  |  | Feb-25 | Dec - 25 | Forest (1.6054 Ha, 5 locs, 0.7 ckm ) in Rajasthan Stage-I In-principle approval is granted on 20/06/2025. Stage-II Final Approval granted in 10/09/2025 Ckt I charged on 29.11.2025, Ckt II charged on 29.11.2025
| EL-EA589 |  |  | 2x1500 MVA, 765/400 kV and 2x500 MVA, 400/220 kV S/s at Karera (near Datiya) | 4000 |  |  | TBCB | [5 empty] | Apraava Energy | Feb-24 | [11 empty] | Feb-26 | Apr - 26 | Land (165.5): Pending (90 Acre) Govt. (54.215): All Pending Pvt. (111.28): Pending (35.985 Acre) For Govt. Land, DC Datia has allocated Govt. Land to Energy Dept. M.P as per M.P Govt Policy for further leasing to TSP, WP given by Govt. of MP , Energy Dept. on 16.10.2025
| EL-0832E |  |  | LILO of Satna-Gwalior 765 kV S/c line at Karera |  |  |  | TBCB | [5 empty] | Apraava Energy | Feb-24 | 85 | 117 | 89 | 15 | 0 | 0.76 | 0.13 | 0 | 0.00% |  |  | Feb-26 | Apr - 26
| EL-063ED | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part A | Construction of Section-2 with 4x1500 MVA, 765/400 kV and 5x500 MVA, 400/220 kV ICTs at Fatehgarh-IV PS | 8500 |  |  | TBCB | [5 empty] | Apraava Energy | Aug-24 | [8 empty] | 38.00% | 40.00% |  | Aug-26 | Aug - 26 | Land required: Included with Fatehgarh IV PS land
| EL-C6426 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part A | Fatehgarh-IV PS (Section-2) - Bhinmal (PG) 400 kV D/C line (Twin HTLS) |  |  |  | TBCB | [5 empty] | Apraava Energy | Aug-24 | 369 | 512 | 234 | 137 | 0 | 0.46 | 0.27 | 0 |  |  |  | Aug-26 | Aug - 26 | RoW: Bytu ( 15 LOC ), Bagoda ( 11 LOC) , Sayla ( 20 LOC) , Sindhari ( 13 Loc) Forest (0.7636, .332ckm) in Rajasthan) Stage I Pending Applied on 12.04.2025 Current Status : Pending at DFO/CF/Nodal Officer/Jalore
| EL-04FA7 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part A | LILO of both ckts of 765 kV Fatehgarh-III - Beawar D/C line at Fatehgarh-IV PS (Section-2) |  |  |  | TBCB | [5 empty] | Apraava Energy | Aug-24 | 17 | 46 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | Aug-26 | Aug - 26 | LILO proposal approved by Beawar Transmission Limited on 3rd Oct. 2025
| EL-6CB92 |  |  | Establishment of 400/220 kV, 4x500 MVA ICTs at Solapur PS alongwith 2x125 MVAR, 420 kV Bus Reactors. | 2000 |  |  | TBCB | [5 empty] | Torrent | Mar-24 | [8 empty] | 20.00% | 0.00% |  | Mar-26 | Mar - 26 | Substation Land ( 80 Acres) : Private land acquired (60.7 Acres).
| EL-0480B |  |  | Solapur PS – Solapur (PG) 400 kV D/c line |  |  |  | TBCB | [5 empty] | Torrent | Mar-24 | 80 | 111 | 71 | 39 |  | 0.64 | 0.35 | 0 |  |  |  | Mar-26 | Jun - 26 | RoW (13 locs) : Dharashiv (13). Applications submitted to DC (Dharashiv Dist.) for all13 locations for resolution under Section 16(1). Orders awaited.
| EL-274FA |  |  | Gogamukh (ISTS) (Assam) – Gerukamukh (Arunachal Pradesh) 132 kV D/c line |  |  |  | TBCB | [5 empty] | Techno Electric | Jun-24 | 58 | [6 empty] | 0 |  |  |  | Nov-26 | Nov - 26 | Route Alignment completed. Design and engineering under process.
| EL-506B2 |  |  | LILO of both circuits of Lower Subansiri - Biswanath Chariali 400 kV D/c line at Gogamukh S/s |  |  |  | TBCB | [5 empty] | Techno Electric | Jun-24 | 31 | [6 empty] | 0 |  |  |  | Nov-26 | Nov - 26 | Route Alignment completed. Design and engineering under process.
| EL-CD073 |  |  | 400/220/132 kV Gogamukh S/s (2x500 MVA, 400/220 kV ICT; 2x200 MVA, 220/132 kV ICT) | 1400 |  |  | TBCB | [5 empty] | Techno Electric | Jun-24 | [11 empty] | Nov-26 | Nov - 26 | Land (58.04 Acre) :Land Parcel finalized and further pursuing with DC, ADC & Circle office of Dhemaji District for acquisition of the Gogamukh Sub Station land. Gogamukh SS Land Acquisition will be completed by Dec-2025.
| EL-53094 |  |  | 400 kV Switching Station (to be upgraded to 400/220 kV in future) at Bokajan (Assam) |  |  |  | TBCB | [5 empty] | Techno Electric | Jul-24 | [11 empty] | Dec-26 | Dec - 26 | The project has been suspended.
| EL-15B25 |  |  | LILO of both circuits of 400 kV D/c Misa (PG) to New Mariani (PG) line at Bokajan S/s |  |  |  | TBCB | [5 empty] | Techno Electric | Jul-24 | 24 | [6 empty] | 0 |  |  |  | Dec-26 | Dec - 26 | The project has been suspended.
| EL-8F5F7 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part B | Establishment of 765/400 kV, 2x1500 MVA S/s at Merta-II Substation | 5500 |  |  | TBCB | [5 empty] | DRAIPL | Dec-24 |  |  | 19 | 0 | 0 |  |  |  | 2.20% | 0.00% | 0.00% | Dec-26 | Dec - 26 | Land (165 Acre)- Acquisition In progress Order Placed for Transformers/Reactors.
| EL-45D71 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part B | Merta II- Barmer I PS 765 kV D/c line |  |  |  | TBCB | [5 empty] | DRAIPL | Dec-24 | 686 | 864 | 359 | 19 | 0 | 0.42 | 0.02 | 0 | 0.00% | 0.00% | 0.00% | Dec-26 | Dec - 26 | RoW (84 locs) in Rajasthan: Barmer (13), Jodhpur (71) Forest Clearance - Detailed survey in progress.
| EL-D7C90 | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part B | Merta II – Beawar 400 kV D/c line (Quad). |  |  |  | TBCB | [5 empty] | DRAIPL | Dec-24 | 143 | 186 | 45 | 0 | 0 | 0.24 | 0 | 0 | 0.00% | 0.00% | 0.00% | Dec-26 | Dec - 26 | RoW (46 Locs) in Rajasthan: Beawar (10) , Nagaur (36) Forest (0.1646 Ha, 2 locs) in Rajasthan: Forest Proposal submitted on 29.05.2025.
| EL-F4EEC | Rajasthan REZ Phase-IV | Rajasthan REZ Phase-IV Part B | Merta II – Dausa 765 kV D/c line |  |  |  | TBCB | [5 empty] | DRAIPL | Dec-24 | 494 | 619 | 336 | 1 | 0 | 0.54 | 0 | 0 | 0.00% | 0.00% | 0.00% | Dec-26 | Dec - 26 | RoW (42 Locs) in Rajasthan: Ajmer (11) , Jaipur (12) , Dausa(2) , Didwana (17) Forest Clearance - Forest (1.3636 Ha, 5 locs) Forest proposal submitted on 29.05.2025.
| EL-1BFA1 | Gujarat Phase-I | Gujarat Phase-I | Establishment 3x1500 MVA, 765/400 kV Substation near Raghanesda (GIS) with 2x330 MVAr, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor | 7000 |  |  | TBCB | [5 empty] | DRAIPL | Jul-25 | [11 empty] | Oct-27 | Oct - 27 | Land is identification in progress Order of Transformer & Reactors are placed. Order of GIS is placed
| EL-572CA | Gujarat Phase-I | Gujarat Phase-I | Raghanesda (GIS) – Banaskantha (PG) 765 kV D/c line |  |  |  | TBCB | [5 empty] | DRAIPL | Jul-25 | 155 | [6 empty] | 0 |  |  |  | Oct-27 | Oct - 27 | Detailed Survey Work completed.
| EL-8A35C | Gujarat Phase-I | Gujarat Phase-I | 2 Nos. 765 kV line bays at Banaskantha (PG) S/s |  |  |  | TBCB | [5 empty] | DRAIPL | Jul-25 | [11 empty] | Oct-27 | Oct - 27
| EL-9902A | Gujarat | Gujarat Part B | Augmentation by 2x500 MVA, 400/220 kV ICTs (3rd & 4th) at Lakadia PS | 1000 |  |  | TBCB | [5 empty] | Reliance | Feb-25 | [8 empty] | 36.41% | 0.00% | 0.00% | Aug-26 | Aug - 26 | Land: AESL to provide encumbrance-free land, pending due to an existing 400kV double-circuit Lakadia–Jam Khambaliya transmission line passing over the Bays 4, 5, and 6 at 220kV Bus Section-I. CEA (PSPM) convened a meeting on 08-Sep-25 with RIL, AESL, O2 Power, and CTU, directing CTU to provide technical solution. Transformer Supply: Ordered on 20-Feb-25. Expected by Mar’26.
| EL-E3418 | Gujarat | Gujarat Part B | Augmentation by 2x500 MVA, 400/220 kV ICTs (5th & 6th) at Lakadia PS on new 220 kV Bus Section-II | 1000 |  |  | TBCB | [5 empty] | Reliance | Feb-25 | [8 empty] | 36.85% | 0.00% | 0.00% | Aug-26 | Aug - 26 | Land: AESL to provide encumbrance-free land, pending due to an existing 400kV double-circuit Lakadia–Jam Khambaliya transmission line passing over the Bays 4, 5, and 6 at 220kV Bus Section-I. CEA (PSPM) convened a meeting on 08-Sep-25 with RIL, AESL, O2 Power, and CTU, directing CTU to provide technical solution. Transformer Supply: Ordered on 20-Feb-25. Expected by Mar’26.
| EL-B485B | Gujarat | Gujarat Part B | Augmentation by 500 MVA, 400/220 kV ICTs (7th) at Lakadia PS on new 220 kV Bus Section-II | 500 |  |  | TBCB | [5 empty] | Reliance | Feb-25 | [8 empty] | 35.86% | 0.00% | 0.00% | Dec-26 | Dec - 26 | Land: WRSS XXI (A) Transco Limited, to provide the required land for the Lakadia B Power Transmission Limited project. Transformer Supply: Ordered on 20-Feb-25. Expected by Oct’26.
| EL-26CF4 | Gujarat | Gujarat Part B | Augmentation by 500 MVA, 400/220 kV ICTs (8th) at Lakadia PS on new 220 kV Bus Section-II | 500 |  |  | TBCB | [5 empty] | Reliance | Feb-25 | [8 empty] | 39.10% | 0.00% | 0.00% | Jun-27 | Jun - 27 | Land: WRSS XXI (A) Transco Limited, to provide the required land for the Lakadia B Power Transmission Limited project. Transformer Supply: Ordered on 20-Feb-25. Expected by Nov’26.
| EL-68D76 | Gujarat | Gujarat Part B | Augmentation of transformation capacity at Lakadia PS by 1x1500 MVA, 765/400 kV ICT (3rd) | 1500 |  |  | TBCB | [5 empty] | Reliance | Feb-25 | [8 empty] | 32.90% | 0.00% | 0.00% | Aug-26 | Aug - 26 | Land: WRSS XXI (A) Transco Limited, to provide the required land for the Lakadia B Power Transmission Limited project. Transformer Supply: Transformer (03 nos) ordered on 21-Feb-25 & expected by Mar’26; Reactor (03 nos) ordered on 21-Feb-25 & expected by Jun’26.
| EL-99714 |  |  | LILO of both circuits of Angul – Sundargarh (Jharsuguda) 765 kV 2xS/c lines at NLC-Talabira generation switchyard |  |  |  | TBCB | [5 empty] | HGIEL | Jul-25 | 100 | [6 empty] | 0 |  |  |  | Mar-28 | Mar - 28
| EL-8721B | Ananthapuram Phase-II | Ananthapuram Phase-II | Augmentation of Ananthapuram-II PS by 400/220 kV, 1x500 MVA ICT | 500 |  |  | TBCB | [5 empty] | SCL | Oct-25 | [11 empty] | Oct-27 | Oct - 27
| EL-7A440 | Ananthapuram Phase-II | Ananthapuram Phase-II | Augmentation of Ananthapuram-II PS by 765/400 kV, 2x1500 MVA and 400/220 kV, 6x500 MVA ICTs | 6000 |  |  | TBCB | [5 empty] | SCL | Oct-25 | [11 empty] | Apr-28 | Apr - 28
| EL-A7BA4 | Ananthapuram Phase-II | Ananthapuram Phase-II | Establishment of 3x1500 MVA, 765/400 kV CN’Halli Station with 2x330 MVAr (765 kV) bus reactors | 4500 |  |  | TBCB | [5 empty] | SCL | Oct-25 | [11 empty] | Apr-28 | Apr - 28
| EL-0CB0A | Ananthapuram Phase-II | Ananthapuram Phase-II | Ananthapuram-II PS – CN’Halli 765 kV D/c line with 330 MVAr SLR at Ananthapuram-II end on both circuits |  |  |  | TBCB | [5 empty] | SCL | Oct-25 | 363 | [6 empty] | 0 |  |  |  | Apr-28 | Apr - 28
| EL-628FF | Ananthapuram Phase-II | Ananthapuram Phase-II | LILO of one circuit of Talaguppa - Neelmangala 400 kV D/c line at CN’Halli |  |  |  | TBCB | [5 empty] | SCL | Oct-25 | 19 | [6 empty] | 0 |  |  |  | Apr-28 | Apr - 28
| EL-54384 | Ananthapuram Phase-II | Ananthapuram Phase-II | LILO at CN’Halli of already LILOed section of one circuit of Talaguppa - Neelmangala 400 kV line at Hassan |  |  |  | TBCB | [5 empty] | SCL | Oct-25 | 36 | [6 empty] | 0 |  |  |  | Apr-28 | Apr - 28
| EL-302B4 | Khavda Phase II | Khavda Phase II Part D | LILO of Pirana (PG) – Pirana (T) 400kV line at Ahmedabad S/s |  |  |  | RTM | [5 empty] | Torrent |  | 240 | 174 |  |  | 204 |  |  | 0.85 | 0.00% | 0.00% | 0.00% | Mar-25 | Feb - 26 | Right of Way (RoW) : In the balance stretch at Village Adroda, Taluka Bavla. Balance stringing work of about 9 km M/C is being carried out under police protection.
| EL-678BB |  |  | Augmentation of transformation capacity at Amargarh (GIS) S/s by 1x315MVA, 400/220 kV ICTs (3rd) | 315 |  |  | RTM | [5 empty] | Indigrid | [9 empty] | 99.00% | 100.00% | 98.00% | Jan-25 | Feb - 26 | Shutdown from NRLDC pending due to grid constraint beacuse of adverse weather condition in the Region, post approval of the shutdown from NRLDC the balance work i.e. interconnection with the existing bus will complete, only the interconnection work with the existing bus is pending from our end.
| EL-15017 | Gujarat | Gujarat Part A | 1x500 MVA, 400/220 kV ICT (Bank 1) |  |  |  | RTM | [5 empty] | Adani | [9 empty] | 100.00% | 100.00% | 0.00% | Aug-25 | Jan - 26 | Elements Charged on 09-Jan-26
| EL-AE322 | Gujarat | Gujarat Part A | 1x500 MVA, 400/220 kV ICT (Bank 2) | 500 |  |  | RTM | [5 empty] | Adani | [9 empty] | 100.00% | 100.00% | 0.00% | Aug-25 | Feb - 26 | Elements Charged on 03-Feb-26
| EL-6C6E3 |  |  | 2x500 MVA, 400/230 kV ICT (3rd & 4th) | 1000 |  |  | RTM | [5 empty] | Adani | [9 empty] | 40.00% | 80.00% |  | Sep-25 | Oct - 26 | Constraint in Transformer delivery
| EL-9DACA | KPS phase-V | KPS phase-V part B3 scheme | 765/400 kV ICT – 1 (1x1500 MVA) and associated bays | 1500 |  |  | RTM | [5 empty] | Adani | [9 empty] | 45.00% | 60.00% |  | Nov-26 | Nov - 26 | Engineering under Progress ICT & EPC ordering Completed Civil work under progress
| EL-CFE81 | Rajasthan Phase-IV | Rajasthan Phase-IV Part I Bikaner Complex Part E | 1x1500MVA 765/400kV (4th) ICT at 765/400kV Bikaner SS |  |  |  | RTM | [5 empty] | PGCIL | Apr-23 | [8 empty] | 100.00% | 100.00% | 100.00% | May-24 | Aug - 25 | ICT Charged on 30.08.2025
| EL-E9D6B | Rajasthan Phase-IV | Rajasthan Phase-IV Part I Bikaner Complex Part E | 1x500MVA 400/220kV (3rd) ICT at Kotputli PG | 500 |  |  | RTM | [5 empty] | PGCIL | Apr-23 | [8 empty] | 99.00% | 100.00% | 85.00% | Dec-25 | Mar - 26 | ICT Recieved, Erection work under progress
| EL-F665E | Rajasthan Phase-III | Rajasthan Phase-III Part J | 765/400kV, 1x1500MVA Transformer (3rd) at Bikaner (PG) |  |  |  | RTM | [5 empty] | PGCIL | Dec-22 | [8 empty] | 100.00% | 100.00% | 100.00% | Dec-23 | Apr - 23 | Charged on 27.04.23
| EL-16647 | Rajasthan Phase-III | Rajasthan Phase-III Part J | 400/220kV, 1x500MVA Transformer (11th) at Fatehgarh-2 PS | 500 |  |  | RTM | [5 empty] | PGCIL | Dec-22 | [8 empty] | 5.00% | 0.00% | 0.00% | Jan-26 | Jul - 26 | Work under progress
| EL-B3C3A | Rajasthan Phase-III | Rajasthan Phase-III Part J | 765/400kV, 1x1500MVA Transformer (5th) at Bhadla-2 PS | 1500 |  |  | RTM | [5 empty] | PGCIL | Dec-22 | [8 empty] | 40.00% | 15.00% | 0.00% | Mar-26 | Apr - 26 | Work under progress
| EL-F7AAC | Rajasthan Phase-III | Rajasthan Phase-III Part J | 1x1500 MVA ICT (3rd), 765/400kV ICT at Jhatikara Substation (Bamnoli/Dwarka section) (Bays associated with X-mer) | 1500 |  |  | RTM | [5 empty] | PGCIL | Dec-22 | [8 empty] | 60.00% | 70.00% | 15.00% | Aug-25 | Mar - 26 | Work under progress
| EL-4513E |  |  | AUGMT 1500MVA 765KV ICT-4+BAYS @BHIWANI | 1500 |  |  | RTM | [5 empty] | PGCIL | Feb-24 | [8 empty] | 98.00% | 98.00% | 75.00% | May-25 | Mar - 26 | Work under progress
| EL-E0DC9 | Rajasthan phase-III | Rajasthan phase-III Part D | 400KV JHATIKARA-DWARKA D/C LINE (QUAD) |  |  |  | RTM | [5 empty] | PGCIL | Oct-24 | 36 | 90 | [5 empty] | 0 |  |  |  | Feb-26 | Dec - 26 | Forest, Delhi (22.0887 ha, 40 Loc): Proposal submitted on 03.11.25. Proposal recommended in PSC II on 07.01.26. SG forwarded proposal to IRO, Lucknow on 12.01.26. Proposal is proposed to be discussed in next REC meeting. Route alignment proposal submitted to Technical Committee,DDA for approval on 26.07.24,approval received on 28.10.2025.
| EL-931DE | Rajasthan phase-III | Rajasthan phase-III Part D | 02 Nos. of 400 KV Line bay at Jhatikara |  |  |  | RTM | [5 empty] | PGCIL | Oct-24 | [8 empty] | 4.00% | 0.00% | 0.00% | Feb-26 | Dec - 26 | Work Under progress
| EL-6BCB9 | Rajasthan phase-III | Rajasthan phase-III Part D | 02 Nos. of 400 KV Line bay at Dwarka |  |  |  | RTM | [5 empty] | PGCIL | Oct-24 | [8 empty] | 0.00% | 0.00% | 0.00% | Feb-26 | Dec - 26 | Engg Under progress
| EL-B4820 | Rajasthan Phase III | Rajasthan Phase III Part E2 | 400/220KV, 2X500 MVA ICT -1 & 2 at Fatehgarh-III 765/400 KV, 3X1500 MVA ICT-1,2 &3 at Fatehgarh-III | 5500 |  |  | RTM | [5 empty] | PGCIL | Nov-23 | [8 empty] | 93.00% | 88.00% | 72.00% | Jun-25 | Mar - 26 | Work under progress
| EL-18D81 |  |  | Augmentation of Transformation Capacity at 400/220KV Allahabad (PG) substation by 400/220 KV, 1x500 MVA (4th) ICT | 500 |  |  | RTM | [5 empty] | PGCIL | Nov-23 | [8 empty] | 95.00% | 98.00% | 80.00% | Feb-25 | Feb - 26 | Work under progress
| EL-3CAF6 | Rajasthan | Rajasthan | 500MVA, 400/220 KV ICT Bay for existing 50MVAr Bus Reactor | 500 |  |  | RTM | [5 empty] | PGCIL | May-24 | [8 empty] | 40.00% | 20.00% |  | Sep-25 | Apr - 26 | Work Under Progress
| EL-BCA8B |  |  | 315 MVA, 400/220 KV ICT (3x105 MVA Single Units) | 315 |  |  | RTM | [5 empty] | PGCIL | Jul-24 | [8 empty] | 4.00% |  |  | Dec-25 | Jun - 27 | As per CTU OM Amendment Dated 03.09.2025 Schedule completion of the project revised to Jun'27 from Dec'25.
| EL-CFEED | Rajasthan | Rajasthan | 1x500 MVA, 400/220 KV ICT | 500 |  |  | RTM | [5 empty] | PGCIL | Aug-24 | [8 empty] | 90.00% | 10.00% |  | Dec-25 | Jun - 26 | Work Under Progress
| EL-A980D |  |  | 400/220kV, 1x500MVA ICT (4th) at Malerkotla (PG) S/s in Punjab | 500 |  |  | RTM | [5 empty] | PGCIL | Sep-24 | [8 empty] | 85.00% | 30.00% |  | Mar-26 | Sep - 26 | Work Under Progress
| EL-C7A6B | Bikaner | Bikaner | Augmentation of ransformation Capacity at 765/400/220kV Bikaner PS in Rajasthan by 400/220kV, 1x500MVA ICT (4th) | 500 |  |  | RTM | [5 empty] | PGCIL | Nov-24 | [8 empty] | 12.00% |  |  | Jan-26 | Jul - 26 | Work Under Progress
| EL-4E363 | Rajasthan | Rajasthan | Augmentation of Transformation Capacity at 400/220 KV Bhiwadi ( PG) S/s in Rajasthan by 400/220 KV ,1x500 MVA ICT(4th) | 500 |  |  | RTM | [5 empty] | PGCIL | Dec-24 | [8 empty] | 50.00% |  |  | Jan-26 | Jul - 26 | Work Under Progress
| EL-0EE32 | Bhadla | Bhadla | Augmentation of transformation capacity at Bhadla-II PS (Section-1) by 1x500 MVA, 400/220KV ICT (6th) along with associated bays. | 500 |  |  | RTM | [5 empty] | PGCIL | Jan-25 | [8 empty] | 60.00% | 25.00% |  | Mar-26 | Jul - 26 | Work Under Progress
| EL-35F13 |  |  | Augmentation of 400/220KV, 1x500MVA (4th) iCT at Hissar (PG) S/S along with associated transformer bays | 500 |  |  | RTM | [5 empty] | PGCIL | Jan-25 | [8 empty] | 60.00% | 10.00% |  | Mar-26 | Jul - 26 | Work Under Progress
| EL-5E410 | fatehgarh | fatehgarh | Augmentation of Transformation capacity at 400/220KV Fatehgarh III PS (Section-1) by 400/220KV, 1x500MVA ICT (5th) | 500 |  |  | RTM | [5 empty] | PGCIL | May-24 | [8 empty] | 75.00% | 80.00% | 20.00% | Apr-25 | Mar - 26 | Work under progress, ICT under transit
| EL-133F7 | Bikaner | Bikaner | 400/220KV, 1x500MVA ICT (9th) at Bikaner-II | 500 |  |  | RTM | [5 empty] | PGCIL | Jan-25 | [8 empty] | 5.00% |  |  | Jan-26 | Oct - 26 | Work Under Progress
| EL-80EC9 | Bhadla | Bhadla | 400 kV Bareilly (765/400 kV) – Bareilly (PG) D/c line (Quad) (2nd ) |  |  |  | RTM | [5 empty] | PGCIL | May-25 | 8 | [6 empty] | 0 |  |  |  | Jun-26 | Aug - 26 | Forest , Uttar Pradesh (0.0672 Ha): Stage-I Awaited
| EL-9A8ED | Bhadla | Bhadla | Augmentation with 1x1500 MVA, 765/400 kV ICT (3rd) at Bareilly (765/400 kV) S/s | 1500 |  |  | RTM | [5 empty] | PGCIL | May-25 | [11 empty] | Jun-26 | Aug - 26 | Enggg Work Under Progress
| EL-7916D | Bikaner | Bikaner | 1x500 MVA, 400/220kV ICT (6th) along with associated bays | 500 |  |  | RTM | [5 empty] | PGCIL | Aug-25 | [8 empty] | 2.00% |  |  | Jul-26 | Dec - 26 | Work Under Progress
| EL-7C1A5 | Bikaner | Bikaner | 500 MVA, 400/220 kV ICT1 no. (10th) | 500 |  |  | RTM | [5 empty] | PGCIL | Aug-25 | [8 empty] | 2.00% |  |  | Jul-26 | Dec - 26 | Work Under Progress
| EL-D1C81 | Rajasthan | Rajasthan | • 500 MVA, 400/220 kV ICT- 1 no. (3rd) | 500 |  |  | RTM | [5 empty] | PGCIL | May-25 | [11 empty] | Oct-26 | Dec - 26 | Under Tendering
| EL-B5AAD |  |  | • 500 MVA, 400/220 kV ICT- 1 no. (5th) | 500 |  |  | RTM | [5 empty] | PGCIL | Apr-25 | [11 empty] | Jul-26 | Dec - 26 | Cable Package Awarded, Bay work package Under retendering
| EL-C8B22 | Bhadla | Bhadla | 500 MVA, 400/220 kV ICT1 no. (4th) | 500 |  |  | RTM | [5 empty] | PGCIL | May-25 | [11 empty] | Jul-26 | Dec - 26 | Enggg Work Under Progress
| EL-9FD3D |  |  | 400 kV PS-1 (Pang) - Pang D/C (quad moose) line |  |  |  | RTM | [5 empty] | PGCIL | May-25 | 14 | [6 empty] | 0 |  |  |  | Mar-31 | Mar - 31
| EL-4B52B |  |  | 400 kV PS-2 (Pang) - Pang D/C (quad moose) line |  |  |  | RTM | [5 empty] | PGCIL | May-25 | 54 | [6 empty] | 0 |  |  |  | Mar-31 | Mar - 31
| EL-3C7A5 |  |  | 400 kV PS-3 (Pang) - Pang D/C (quad moose) line |  |  |  | RTM | [5 empty] | PGCIL | May-25 | 82 | [6 empty] | 0 |  |  |  | Mar-31 | Mar - 31
| EL-F843D |  |  | 220 kV Pang – Leh (Phyang) S/C line |  |  |  | RTM | [5 empty] | PGCIL | May-25 | 158 | [6 empty] | 0 |  |  |  | Mar-31 | Mar - 31
| EL-9DF28 |  |  | ±350 kV HVDC line between Pang & Kaithal PS |  |  |  | RTM | [5 empty] | PGCIL | May-25 | 960 | [6 empty] | 0 |  |  |  | Mar-31 | Mar - 31
| EL-288E7 |  |  | ± 350kV 5000MW VSC HVDC terminal each at Pang(Leh) and Kaithal (Haryana) | 5000 |  |  | RTM | [5 empty] | PGCIL | May-25 | [11 empty] | Mar-31 | Mar - 31
| EL-F1DBA |  |  | 02 Nos. of 400/200/33KV, 315 MVA Transformers along with associated bays at Pang | 630 |  |  | RTM | [5 empty] | PGCIL | May-25 | [11 empty] | Mar-31 | Mar - 31
| EL-5D536 |  |  | 03 Nos. of 765/400/33KV, 1500 MVA Transformers along with associated bays at kaithal | 4500 |  |  | RTM | [5 empty] | PGCIL | May-25 | [11 empty] | Mar-31 | Mar - 31
| EL-82F09 |  |  | 500 MVA, 400/220 kV ICT– 1 No at Maharanibagh | 500 |  |  | RTM | [5 empty] | PGCIL | Dec-25 | [11 empty] | May-27 | May - 27 | Under Tendering
| EL-D2711 | Bikaner | Bikaner | Augmentation of 400/220 kV, 2x500 MVA (7th & 8th) ICTs at Bikaner-IV PS along with associated transformer bays | 500 |  |  | RTM | [5 empty] | PGCIL | Oct-25 | [11 empty] | Feb-27 | Feb - 27 | Under Tendering
| EL-30BEC | Bikaner | Bikaner | 220 kV Sectionalizer bay (1 set), 220 kV BC (1 no.) bay and 220 kV TBC (1 no.) bay at BikanerIV PS |  |  |  | RTM | [5 empty] | PGCIL | Oct-25 | [11 empty] | Feb-27 | Feb - 27 | Under Tendering
| EL-F2AE5 | Kurnool | Kurnool Part A & Part | 765kV D/C Kurnool III (PS) - Kurnool (New) line |  |  |  | RTM | [5 empty] | PGCIL | Mar-23 |  | 299 |  |  | 226 | [6 empty] | Nov-24 | Mar - 25 | Charged on 31.03.2025
| EL-89CE4 | Kurnool | Kurnool Part A & Part | 765kV D/C Kurnool III (PS) - Maheshwaram (PG) line |  |  |  | RTM | [5 empty] | PGCIL | Mar-23 | 504 | 676 |  |  | 461 |  |  | 0.91 |  |  |  | Nov-24 | Mar - 26 | Forest: Telangana (26.993 Hac., 8 loc ,8.04 Ckm). Stage-II received on 02.09.2025
| EL-D24A9 | Kurnool | Kurnool Part A & Part | Establishment of 765/400/220 kV Kurnool-III (New) 3x1500MVA 765/400kV ICT 9x500MVA 400/220kV ICT 2 no. 765kV Line bays for Kurnool III- Kurnool (New) line 2 no. 765kV Line bays alongwith 240MVAr Line Reactor on each ckt for Kurnool-III- Maheshwaram Line 15no. 220kV Line bays, 1x330MVAr 765kV Bus Reactor | 1000 |  |  | RTM | [5 empty] | PGCIL | Mar-23 | [8 empty] | 98.00% | 98.00% | 98.00% | Nov-24 | Mar - 26 | 6x500 MVA 400/220KV ICT-1 to 4, 6 & 7 Charged in Mar'25. 3x1500 MVA 765/400 KV ICT-1 to 3 Charged in Mar'25. Major work commissioned in Mar'25/ Apr'25. 1x500 MVA 400/220KV ICT-5 Chargedon 30.10.2025. Balance work under progress.
| EL-2B8B4 | Kurnool | Kurnool Part A & Part | Ext. at Maheshwaram (PG) SS 2no. 765kV Line bays alongwith 240MVAr Line Reactor on each ckt for Kurnool- III- Maheshwaram Line |  |  |  | RTM | [5 empty] | PGCIL | Mar-23 | [8 empty] | 100.00% | 100.00% | 100.00% | Nov-24 | Mar - 26 | Charged in Sep'25. Commissioning matching with line.
| EL-7FF1F | Kurnool | Kurnool Part A & Part | Ext. at Kurnool (New) SS 2no. 765kV Line bays for Kurnool III- Kurnool (New) line |  |  |  | RTM | [5 empty] | PGCIL | Mar-23 | [8 empty] | 100.00% | 100.00% | 100.00% | Nov-24 | Mar - 25 | Charged on 19.10.2024. commissioned with line in Mar'25.
| EL-19D14 | Telangana | Telangana | Augmentation of Transformation Capacity by 1X1500 MVA (3rd) , 765/400 KV ICT at Maheswaram (PG) | 1500 |  |  | RTM | [5 empty] | PGCIL | Nov-23 | [8 empty] | 100.00% | 100.00% | 98.00% | Apr-25 | Feb - 26 | Work under progress.
| EL-EAEDF | Kurnool | Kurnool | 765/400KV 1500MVA ICT (3rd) -1 No. (4x500 MVA units including one spare unit) | 1500 |  |  | RTM | [5 empty] | PGCIL | Jun-24 | [8 empty] | 95.00% | 95.00% | 65.00% | Sep-25 | Mar - 26 | Work under progress.
| EL-8E17C | Karnataka | Karnataka | Augmentation of Transformation Capacity by 2x500MVA (9th & 10th ), 400/220kV ICTs at Tumkur (Pavagada) 400/220 kV Pooling Station in Karnataka | 1000 |  |  | RTM | [5 empty] | PGCIL | Mar-25 | [8 empty] | 20.00% | 12.00% |  | May-26 | May - 26 | Work under progress. Work affected due to RoW. KSPDCL has to facilitate registration of land.
| EL-F01C4 | Karnataka | Karnataka | Implementation of 01 No. 220KV line Bay at Tumkur (Pavagada) 400/220KV PS for providing connectivity to RE Generation Project (M/s TEQ Green Power XVIII Pvt. Ltd.) |  |  |  | RTM | [5 empty] | PGCIL | Mar-25 | [8 empty] | 5.00% | 2.00% |  | May-26 | May - 26 | Work under progress. Work affected due to RoW. KSPDCL has to facilitate registration of land.
| EL-25983 | Tamil nadu | Tamil nadu | 500MVA, 400/230KV ICT (6th) at Tuticorin-II GIS | 500 |  |  | RTM | [5 empty] | PGCIL | Jun-24 | [8 empty] | 30.00% | 20.00% |  | Dec-25 | Jun - 26 | Work under progress.
| EL-DB8E9 | Andhra | Andhra | PART A: 400/220KV ICT (1X500MVA) | 500 |  |  | RTM | [5 empty] | PGCIL | Jun-24 | [8 empty] | 35.00% | 5.00% |  | Sep-25 | Jun - 26 | Work under progress.
| EL-AC89A | Andhra | Andhra | PART B: Implementation of common facility works at NP Kunta for providing connectivity to RE generation Projects. 220KV Bus Works for 06 nos. of Bays-1 set |  |  |  | RTM | [5 empty] | PGCIL | Jun-24 | [8 empty] | 35.00% | 5.00% |  | Mar-25 | Jun - 26 | Work under progress.
| EL-7A738 |  |  | 1x500MVA (7th), 400/220kV ICTs at Tumkur (Pavagada) | 500 |  |  | RTM | [5 empty] | PGCIL | Apr-24 | [8 empty] | 40.00% | 50.00% | 5.00% | Aug-25 | May - 26 | Work under progress. Work affected due to RoW. KSPDCL has to facilitate registration of land.
| EL-8AF3A |  |  | 1x500MVA (8th), 400/220kV ICTs at Tumkur (Pavagada) | 500 |  |  | RTM | [5 empty] | PGCIL | Apr-24 | [8 empty] | 25.00% | 20.00% |  | Nov-25 | Jun - 26 | Time frame has been revised from 18 Months to 21 Months vide CTU OM Dated 18.09.2024 Work affected due to RoW. KSPDCL has to facilitate registration of land.
| EL-4E6C2 | Karnataka | Karnataka | Augmentation of Transformation Capacity at 400/220KV Yelahanka (GIS) S/s in Karnataka by 400/220KV, 1x500MVA ICT (3rd) | 500 |  |  | RTM | [5 empty] | PGCIL | Feb-25 | [11 empty] | Jul-26 | Mar - 27 | Under award.
| EL-B6FB7 | Tamil Nadu | Tamil Nadu | Establishment of 2x500 MVA, 400/230 kV Onshore Pooling Station near Avaraikulam, Tirunelveli District in Tamil Nadu with provision of expansion upto 5 GW | 1000 |  |  | RTM | [5 empty] | PGCIL | Feb-25 | [11 empty] | Mar-30 | Mar - 30
| EL-4A9A5 | Tamil Nadu | Tamil Nadu | Avaraikulam Onshore PS – Tuticorin PS 400 kV D/c quad line |  |  |  | RTM | [5 empty] | PGCIL | Feb-25 | 200 | [6 empty] | 0 |  |  |  | Mar-30 | Mar - 30
| EL-CED4F | Tamil Nadu | Tamil Nadu | 300 MVAr STATCOM along with 2x125 MVAr MSR |  |  |  | RTM | [5 empty] | PGCIL | Feb-25 | [11 empty] | Mar-30 | Mar - 30
| EL-3D8D5 | Tamil Nadu | Tamil Nadu | Establishment of 2x315 MVA, 230/66kV Off-Shore Substation-1 with 10 nos. of 66kV line bays for RE integration | 630 |  |  | RTM | [5 empty] | PGCIL | Feb-25 | [11 empty] | Mar-30 | Mar - 30
| EL-311CE | Tamil Nadu | Tamil Nadu | Offshore substation 1 (OSS-1) – Avaraikulam Onshore PS 2 nos. 230kV (atleast 300 MVA capacity) Submarine cables (~35 - 40 km) with 2x50MVAr switchable line reactors at OSS-1 end |  |  |  | RTM | [5 empty] | PGCIL | Feb-25 | [11 empty] | Mar-30 | Mar - 30
| EL-E64F6 |  |  | Augmentation of 1x500MVA, 400/230 KV ICT (7th) at Tuticorin-II GIS | 500 |  |  | RTM | [5 empty] | PGCIL | Feb-25 | [9 empty] | 0.00% |  | Mar-27 | Mar - 27
| EL-F219C |  |  | 01 No. of 230 KV Line Bay for termination of Dedicated Transmission Line of M/s NCL Industries Ltd. |  |  |  | RTM | [5 empty] | PGCIL | Feb-25 | [9 empty] | 0.00% |  | Mar-27 | Mar - 27
| EL-A008A | Karnataka | Karnataka | 500MVA, 400/220kV ICT – 1no. | 500 |  |  | RTM | [5 empty] | PGCIL | May-25 | [9 empty] | 0.00% |  | Jul-26 | Mar - 27 | Tendering under progress
| EL-55309 |  |  | 1x500 MVA, 400/220kV ICT (4th) | 500 |  |  | RTM | [5 empty] | PGCIL | Sep-25 | [9 empty] | 0.00% |  | Feb-27 | Feb - 27 | Tendering under progress
| EL-C6E1D |  |  | Augmentation / replacement of existing 400/230kV, 315 MVA ICT-2 with 400/230kV, 500 MVA ICT at Udumalpet 400/230kV S/s | 185 |  |  | RTM | [5 empty] | PGCIL | Aug-25 | [9 empty] | 0.00% |  | Feb-27 | Feb - 27 | Tendering under progress
| EL-7A29B | Gujarat | Gujarat Part B | 400 kV D/C (Twin HTLS) Navasari (New) (South Gujarat)- Magarwada line |  |  |  | RTM | [5 empty] | PGCIL | Jul-22 |  |  |  |  | 192 | [6 empty] | Jun-23 | Dec - 25 | Navsari-Magarwada TL Ckt-I & Ckt-II charged on 04.03.25 & 05.03.25 respectively. Navsari-Kala TL Ckt-I & Ckt-II antitheft charged at rated Voltage (174 Ckm) on 26.03.25 & 27.03.25 respectively.
| EL-32BB4 | Gujarat | Gujarat Part B | 400 kV D/C (Twin HTLS) Navasari (New) (South Gujarat)-- Kala line (M/C portion upto Magarwada alongwith Navsari-Magarwada Line) (Tower locations also include towers of Navsari-Magarwada Line) |  |  |  | RTM | [5 empty] | PGCIL | Jul-22 | 284 | 308 |  |  | 266.816 |  |  | 0.94 |  |  |  | Jun-23 | Mar - 26 | Forest (24.62 Ha) in Maharashtra: Stage-I received on 30.08.2024. Stage-II received on 07.01.2025
| EL-32F80 | Gujarat | Gujarat Part B | Navsari(New) (South Gujarat) (GIS) – Padghe (GIS) 765 kV D/c line |  |  |  | RTM | [5 empty] | PGCIL | Jul-22 | 452 | 616 |  |  | 224.9 |  |  | 0.5 |  |  |  | Jun-23 | May - 26 | Forest (305.476 Ha) in Maharashtra: Forest proposal re-submitted on 23.11.2023. Stage -I received on 30.08.2024. Stage-II received on 07.01.2025.
| EL-01F3A | Gujarat | Gujarat Part B | Establishment of 765/400/220 kV Navsari (new) (South Gujarat) S/s (GIS) (2x1500MVA 765/400kV ICT & 3x500MVA 400/220kV ICT) | 500 |  |  | RTM | [5 empty] | PGCIL | Jul-22 | [8 empty] | 99.00% | 100.00% | 99.00% | Jun-23 | Mar - 26 | 2x500MVA 400/220kV ICTs, 1x125MVAr 400kV Bus Reactor charged in Mar'25. 2x1500 MVA 765/400kV ICTs charged in Apr'25. Balance work under progress.
| EL-D03AA | Gujarat | Gujarat Part B | Ext at 765/400kV Padghe (GIS) PG SS (1x1500MVA 765/400kV ICT) | 1500 |  |  | RTM | [5 empty] | PGCIL | Jul-22 | [8 empty] | 100.00% | 100.00% | 100.00% | Jun-23 | May - 26 | ICT charged on 30.06.24. Line bay shall be charged along with line.
| EL-239A6 | Khavda RE park Phase III | Khavda RE park Phase III | 765/400 KV Navsari (New) S/S Extension Augmentation of Transformation capacity at Navsari (New) 765/400 KV S/S by 1x1500 MVA (ICT-IV) | 1500 |  |  | RTM | [5 empty] | PGCIL | Jun-23 | [8 empty] | 80.00% | 60.00% | 20.00% | Oct-25 | Jun - 26 | Work under progress.
| EL-7821B |  |  | Creation of 220KV level at 765/400 KV Jabalpur PS 400/220 KV, 500 MVA ICT-02 Nos. | 1000 |  |  | RTM | [5 empty] | PGCIL | Jun-23 | [8 empty] | 78.00% | 62.00% | 35.00% | Dec-25 | Mar - 26 | Work under progress.
| EL-B387B |  |  | 220KV Line Bay 04 Nos. for LILO of Narsinghpur-Jabalpur (MP) 220KV D/c Line at Jabalpur PS |  |  |  | RTM | [5 empty] | PGCIL | Jun-23 | [8 empty] | 78.00% | 72.00% | 35.00% | Dec-25 | Mar - 26 | Work under progress.
| EL-EDEA2 | Khavda phase IV | Khavda phase IV Part E4 | Augmentation of Transformation Capacity at padghe (PG) (GIS) by 1x1500MVA, 765/400 KV ICT (4th) along with Extension of 765KV Padghe (GIS) Substation | 1500 |  |  | RTM | [5 empty] | PGCIL | Nov-23 | [8 empty] | 95.00% | 95.00% | 15.00% | Jul-25 | Mar - 26 | Work under progress.
| EL-FB4E2 | Khavda Phase IV | Khavda Phase IV Part E3 | 1X1500MVA 765/400KV ICT-4 AT KPS3 (GIS) | 1500 |  |  | RTM | [5 empty] | PGCIL | Jan-24 | [8 empty] | 80.00% | 90.00% | 75.00% | Jul-25 | Mar - 26 | Work under progress.
| EL-C70C1 | Gujarat | Gujarat | Augmentation of Transformation Capacity at Navsari (New) (South Gujarat) 765/400KV GIS Substation by 765/400KV, 1x1500 MVA ICT (3rd) along with its asociated bays. | 1500 |  |  | RTM | [5 empty] | PGCIL | Nov-22 | [8 empty] | 100.00% | 98.00% | 88.00% | Jan-25 | Mar - 26 | Work under progress.
| EL-D3A7D |  |  | Installation of 1x500MVA (4th) 400/220kV ICT at Satna (PG) SS along with associated bays and 2 no. 220kV Line Bays for LILO of 220kV Satna-Maihar line at Satna (PG) | 500 |  |  | RTM | [5 empty] | PGCIL | Apr-23 | [8 empty] | 92.00% | 85.00% | 82.00% | Dec-25 | Mar - 26 | Work under progress.
| EL-8AE00 |  |  | 1X500 MVA ICT(3RD) AT MAGARWADA | 500 |  |  | RTM | [5 empty] | PGCIL | Jan-24 | [11 empty] | Jul-25 | Mar - 27 | under Award
| EL-36983 | Madhya Pradesh | Madhya Pradesh | Part A: Augmentation of Transformation Capacity at 400/220KV Rajgarh S/S 400/220 KV ICT (1x500 MVA)- 01 No. | 500 |  |  | RTM | [5 empty] | PGCIL | Jun-24 | [8 empty] | 60.00% | 40.00% |  | Nov-25 | Jun - 26 | Work under progress.
| EL-A2137 | Madhya Pradesh | Madhya Pradesh | Part B: Implementation of 220KV GIS Line Bay at Rajgarh 400/220KV (PG) S/S for RE Interconnection |  |  |  | RTM | [5 empty] | PGCIL | Jun-24 | [8 empty] | 60.00% | 40.00% |  | Dec-26 | Dec - 26 | Work under progress.
| EL-4EA6F |  |  | 400/220KV, 1x500 MVA (5th) ICT at 400/220 KV Boisar Substation | 500 |  |  | RTM | [5 empty] | PGCIL | Jun-24 | [8 empty] | 50.00% | 20.00% | 0.00% | Sep-25 | Apr - 26 | Work under progress.
| EL-02B2F | Gujarat | Gujarat | Augmentation of Transformation Capacity at 765/400/220kV Vadodara (GIS) S/s in Gujarat by 400/220kV, 1x500MVA ICT (3rd) | 500 |  |  | RTM | [5 empty] | PGCIL | Oct-24 | [11 empty] | Mar-26 | Mar - 27 | Under Tendering
| EL-444C3 | Madhya Pradesh | Madhya Pradesh | Augmentation of Transformation Capacity at 400/220KV Rajgarh (PG) S/s in MP by 400/220KV 500MVA ICT (4th) | 500 |  |  | RTM | [5 empty] | PGCIL | Feb-25 | [11 empty] | Dec-26 | Dec - 26 | Under Tendering
| EL-3C32F | Gujarat Phase-1 | Gujarat Phase-1 | Establishment of 2x500 MVA, 400/220 kV Mahuva Onshore Pooling Station (GIS) (Mahuva PS) alongwith 1x125 MVAR, 420 kV bus reactor (with space provision for upgradation to 765 kV level to cater to future Offshore Wind Projects adjacent to B3, B4, B5 pockets in future) | 1000 |  |  | RTM | [5 empty] | PGCIL | Feb-25 | [11 empty] | Mar-29 | Mar - 29
| EL-3FB7A | Gujarat Phase-1 | Gujarat Phase-1 | Creation of 400kV switchyard along with Installation of 2x1500 MVA, 765/400 kV ICTs at Vataman (AIS) with 2x125 MVAr (420 kV) Bus Reactors | 3000 |  |  | RTM | [5 empty] | PGCIL | Feb-25 | [11 empty] | Feb-26 | Sep - 26
| EL-DBEED | Gujarat Phase-1 | Gujarat Phase-1 | 2 nos. 400kV bays at Vataman for termination of Mahuva Onshore PS (GIS) – Vataman 400 kV D/c line |  |  |  | RTM | [5 empty] | PGCIL | Feb-25 | [11 empty] | Mar-29 | Mar - 29
| EL-27838 | Gujarat Phase-1 | Gujarat Phase-1 | Mahuva Onshore PS (GIS) – Vataman 400 kV D/c line (Quad ACSR/AAAC/AL59 moose equivalent) with 63MVAr & 50 MVAr, 420 kV switchable line reactors on each ckt at Mahuva & Vataman ends respectively. |  |  |  | RTM | [5 empty] | PGCIL | Feb-25 | [11 empty] | Mar-29 | Mar - 29
| EL-1AB74 | Gujarat Phase-1 | Gujarat Phase-1 | ± 300 MVAr STATCOM at 220 kV level of Mahuva PS (GIS) with 1 No. of 220 kV bay |  |  |  | RTM | [5 empty] | PGCIL | Feb-25 | [11 empty] | Mar-29 | Mar - 29
| EL-B095D | Gujarat Phase-1 | Gujarat Phase-1 | Establishment of 2x315 MVA, 220/66 kV Gujarat Offshore B3 Sub-Station Station-1 (B3-OSS-1) with 66 kV line bays – 10 Nos. for RE Interconnection | 630 |  |  | RTM | [5 empty] | PGCIL | Feb-25 | [11 empty] | Mar-29 | Mar - 29
| EL-2ACDA | Gujarat Phase-1 | Gujarat Phase-1 | B3-OSS-1 – Mahuva Onshore PS (GIS) 220 kV two nos. (3 core) cables (45 kmunder sea cable of about 35 km & under ground cable of about 10 km) alongwith associated line bays at both ends (with capacity of 300 MVA/ckt at nominal voltage) with 1x50 MVAr switchable line reactors at B3-OSS-1 end on each cable |  |  |  | RTM | [5 empty] | PGCIL | Feb-25 | [11 empty] | Mar-29 | Mar - 29
| EL-20B33 |  |  | 3x500 MVA, 400/220 KV ICT (7th, 8th & 9th) | 1500 |  |  | RTM | [5 empty] | PGCIL | Sep-25 | [11 empty] | Dec-26 | Mar - 27 | Engg under progress
| EL-7F689 |  |  | 1x1500 MVA, 765/400 KV ICT (4th) | 1500 |  |  | RTM | [5 empty] | PGCIL | Sep-25 | [11 empty] | Dec-26 | Mar - 27 | Engg under progress
| EL-6E17B |  |  | Installation of 1x330MVAR 765KV Bus Reactor (2nd) along with associated bay |  |  |  | RTM | [5 empty] | PGCIL | Sep-25 | [11 empty] | Dec-26 | Mar - 27 | Engg under progress
| EL-B0B1C |  |  | 01 No. of 220KV line Bay for Aditya Birla Renewables Subsidiary limited (ABRSL) (2MW) 01 No. of 220KV line Bay for ACME Cleantech Solutions Pvt ltd. (ACSPL) (350 MW) 01 No. of 220KV line Bay for ACME Cleantech Solutions Pvt ltd. (ACSPL) (50 MW) 01 No. of 220KV line Bay for Avaada Energy Pvt ltd. (EPL) (100 MW) 01 No. of 220KV line Bay for Adani Green Energy Thirty- Two ltd. (AGE32L) (260.5 MW) 01 No. of 220KV line Bay for Adani Renewable Energy Eight ltd. (ARE8L) (115 MW) |  |  |  | RTM | [5 empty] | PGCIL | Sep-25 | [11 empty] | Dec-26 | Mar - 27 | Engg under progress
| EL-47C40 |  |  | 2x500 MVA, 400/220 KV ICT (5th & 6th) 1x1500 MVA, 765/400KV ICR (3rd) | 2500 |  |  | RTM | [5 empty] | PGCIL | Aug-25 | [11 empty] | Nov-26 | Mar - 27 | Engg under progress
| EL-FE16F |  |  | 220KV GIS Line Bay at Bhuj-II PS for ABREL (RJ) Projects Limited |  |  |  | RTM | [5 empty] | PGCIL | Aug-25 | [11 empty] | Nov-26 | Mar - 27 | Engg under progress
| EL-BBF51 |  |  | Augmentation of transformation capacity at 400/220kV Bhuj PS in Gujarat by 1x500 MVA, 400/220kV ICT (10th) along with associated transformer bays | 500 |  |  | RTM | [5 empty] | PGCIL | May-25 | [11 empty] | Oct-26 | Mar - 27 | Engg under progress
| EL-EF423 |  |  | 220kV Bays (Hybrid/MTS) – 2 Nos. at Bhuj PS for Interconnection of 600MW REGS of Indianoil NTPC Green Energy Pvt. Ltd. (INGEPL) |  |  |  | RTM | [5 empty] | PGCIL | May-25 | [11 empty] | Oct-26 | Mar - 27 | Engg under progress
| EL-54677 |  |  | Augmentation at 400/220KV lakhisarai (POWERGRID) S/s by 2x500 MVA ICT alongwith 400KV ICT Bay: 02 Nos & Creation of 220KV level in GIS at lakhisarai (POWERGRID) 400/132KV S/s incl. 220KV GIS line bay= 02 No., 220KV GIS Bus Coupler bay= 01 No., 220KV GIS ICT Bay= 02 No. | 1000 |  |  | RTM | [5 empty] | PGCIL | Sep-23 | [8 empty] | 95.00% | 96.00% | 80.00% | May-25 | Mar - 26 | Work under progress.
| EL-AEF0F |  |  | Shifting of ranchi (POWERGRID)-Raghunathpur (DVC) 400KV D/c (Quad) line to bays 431 & 434 at ranchi (POWERGRID) |  |  |  | RTM | [5 empty] | PGCIL | Feb-24 | 3 | 5 | [5 empty] | 0 |  |  |  | Oct-25 | May - 26 | Survey completed. Route finalised. Foundation under progress.
| EL-D5C44 |  |  | Bay Extension at New Ranchi SS with installation of 2x80 MVAr Line Reactors |  |  |  | RTM | [5 empty] | PGCIL | Feb-24 | [8 empty] | 75.00% | 50.00% | 30.00% | Oct-25 | May - 26 | Work under progress. Terminal equipments of Line (Both Ckts) shifted and charged on 22.10.2025.
| EL-F18E6 |  |  | Bay Extension at Ranchi SS with shifting of existing Bus Reactor |  |  |  | RTM | [5 empty] | PGCIL | Feb-24 | [8 empty] | 55.00% | 55.00% | 20.00% | Oct-25 | May - 26 | Work under progress. ERS erected. WIP
| EL-107CA |  |  | 500MVA 400/220KV ICT-3 AT RAJARHAT | 500 |  |  | RTM | [5 empty] | PGCIL | Jan-24 | [8 empty] | 8.00% |  |  | Jul-25 | Dec - 26 | Work under progress
| EL-40A4C |  |  | Installation of new 1x500MVA, 400/220KV (3rd) ICT at pandiabili (POWERGRID) S/S along with associated bays at 220KV level | 500 |  |  | RTM | [5 empty] | PGCIL | Jan-25 | [11 empty] | Sep-26 | Jul - 27 | Under Tendering
| EL-93CB1 |  |  | Reconductoring of Melriat (GIS) (POWERGRID) – Zuangtui (Mizoram) 132kV ACSR Panther S/c line with Single HTLS conductor of 900A (at nominal voltage level) |  |  |  | RTM | [5 empty] | PGCIL | May-23 | 10 |  |  |  | 10.13 |  |  | 1.01 |  |  |  | Apr-25 | Apr - 25 | Supply completed. S/D availed from 22.02.2025 to start reconductoring work. Line Charged on 01.04.2025
| EL-B2D3A |  |  | One (1) new 132kV line bay at Melriat (GIS) (POWERGRID) S/s (of rating commensurate with rating of HTLS viz. 900A) for shifting of Melriat (GIS) (POWERGRID) - Zuangtui (Mizoram) 132kV HTLS line from exting bay and termination of the HTLS line in the new bay (0.5km including approx. 5 nos. towers) 132kV GIS line bay -1. New 132kV S/c HTLS line section -0.5km (including approx. 5 nos. towers) |  |  |  | RTM | [5 empty] | PGCIL | May-23 | 1 | 2 | [5 empty] | 0 | 100.00% | 100.00% | 100.00% | Apr-25 | Mar - 26 | # Survey completed. Major supply completed. Work is in progress. Physical work is being hampered due to continuous rain. # GIS Bay has been commissioned on 31st Jan'26.
| EL-2083C |  |  | Replacement of existing CT of 600/1A at Zuangtui (Mizoram) end in Melriat (GIS) (POWERGRID) -Zuangtui (Mizoram) 132kV S/c line with rating commensurate with ampacity (900A) of HTLS conductor of 800A (at nominal voltage level) |  |  |  | RTM | [5 empty] | PGCIL | May-23 | [8 empty] | 0.00% | 100.00% | 0.00% | Apr-25 | Apr - 25 | Survey completed. CT supplied. However, CT replacement work has been done by P&E Department, Mizoram as informed by email on 27.03.2025.
| EL-3E1CB |  |  | Replacement of existing CT of 600/1A at Luangmual (Mizoram) end in 132kV Aizawl (PG) - Luangmual (Mizoram) 132kV line with rating commensurate with ampacity (800A) of HTLS conductor. |  |  |  | RTM | [5 empty] | PGCIL | May-23 | [8 empty] | 0.00% | 0.00% | 0.00% | Apr-25 | Apr - 25 | Scope deleted as per CTU OM dated: 23.10.2024
| EL-B4BB1 |  |  | Installation of OPGW in Aizawl (POWERGRID) - Luangmual (Mizoram) 132kV S/c line |  |  |  | RTM | [5 empty] | PGCIL | May-23 | [8 empty] | 0.00% | 0.00% | 0.00% | Apr-25 | Apr - 25 | Scope deleted as per CTU OM dated: 23.10.2024
| EL-5C5AB |  |  | Installation of new 1x50 MVA, 132/33KV (3rd) ICT at Namsai (POWERGRID) along with associated bays | 50 |  |  | RTM | [5 empty] | PGCIL | Apr-25 | [11 empty] | Apr-26 | Jan - 27 | Engg under progress.
| EL-D16E2 |  |  | 1x500 MVA, 400/220kV ICT 3rd | 500 |  |  | RTM | [5 empty] | PGCIL | Jan-26 | [11 empty] | Aug-27 | Aug - 27 | Under tendering
| EL-970B4 |  |  | 2 Nos. of 220kV line bays for termination of 220kV transmission lines along with 220kV bus sectionaliser |  |  |  | RTM | [5 empty] | PGCIL | Jan-26 | [11 empty] | Aug-27 | Aug - 27 | Under tendering
| EL-41C4D |  |  | Extension of 220kV GIS hall to accommodate 6 Nos. of 220kV bays (2 Nos. of 220kV ICT bays and 4 Nos. of 220kV line bays) and associated 220kV bus sectionaliser |  |  |  | RTM | [5 empty] | PGCIL | Jan-26 | [11 empty] | Aug-27 | Aug - 27 | Under tendering
| EL-B27D3 |  |  | 500 MVA, 400/230 kV ICT – 1 No | 500 |  |  | RTM | [5 empty] | PGCIL | Jan-26 | [11 empty] | Jun-27 | Jun - 27 | Under tendering
| EL-EAF22 | Gujarat | Gujarat | Augmentation of Transformation capacity at Pirana (PG) S/s in Gujarat by 400/220 kV, 1x500 MVA (3rd) ICT along with associated bays at both ends | 500 |  |  | RTM | [5 empty] | PGCIL | Dec-25 | [11 empty] | Dec-27 | Dec - 27 | Under tendering
| EL-A5B08 | Madhya Pradesh | Madhya Pradesh | PART A: Vindhyachal IV – Vindhyachal PS 400kV 1st D/c (quad) line (of POWERGRID) and Vindhyachal PS – Sasan 400kV D/c (twin) line (of POWERGRID) to be bypassed at Vindhyachal PS and interconnected with each other at outskirts of Vindhyachal PS (Under scope of ISTS) so as to form Vindhyachal IV (2x500MW) – Sasan 400kV D/c line. |  |  |  | RTM | [5 empty] | PGCIL | Dec-25 | [11 empty] | Feb-27 | Feb - 27 | Under tendering
| EL-33A2A |  |  | Creation of 220KV switchyard along with installation of 2x500MVA, 400/220KV ICTs at vataman (AIS) | 1000 |  |  | RTM | [5 empty] | PGCIL | Feb-25 | [8 empty] | 8.00% |  |  | Mar-26 | Dec - 26 | work under progress
| EL-2FB1F | Kurnool-V & Ananthapuram-III | Kurnool-V Phase-I & Ananthapuram-III Phase-I | Establishment of 4x1500 MVA, 765/400 kV and 5x500 MVA, 400/220kV Kurnool V Pooling Station near Kodumur in Kurnool district along with 2x330 MVAr (765 kV) bus reactors at Kurnool-V PS with provision of two (2) sections of 4500 MVA each at 400kV level | 8500 |  |  | NCT
| EL-C1384 | Kurnool-V & Ananthapuram-III | Kurnool-V Phase-I & Ananthapuram-III Phase-I | + 300 MVAr STATCOM at Kurnool-V PS |  |  |  | NCT
| EL-56BE6 | Kurnool-V & Ananthapuram-III | Kurnool-V Phase-I & Ananthapuram-III Phase-I | Kurnool-V-Shadnagar 765 kV D/c line (about 240 km) with 240 MVAr SLR (convertible) at both ends on both circuits |  |  |  | NCT | [7 empty] | 480
| EL-1AD60 | Kurnool-V & Ananthapuram-III | Kurnool-V Phase-I & Ananthapuram-III Phase-I | Kurnool-V-Raichur New 765 kV D/c line (about 150 km) with 240 MVAr SLR (convertible) at Raichur New end on both circuits |  |  |  | NCT | [7 empty] | 300
| EL-891A3 | Kurnool-V & Ananthapuram-III | Kurnool-V Phase-I & Ananthapuram-III Phase-I | Establishment of 3x1500 MVA, 765/400 kV Sagar substation with 2x330 MVAr (765 kV) bus reactors with space provision for establishment of 220 kV switchyard | 4500 |  |  | NCT
| EL-B3A7E | Kurnool-V & Ananthapuram-III | Kurnool-V Phase-I & Ananthapuram-III Phase-I | Kurnool-V-Sagar 765 kV D/c line (about 240 km) with 240 MVAr SLR (convertible) at both ends on both circuits |  |  |  | NCT | [7 empty] | 480
| EL-917D9 | Kurnool-V & Ananthapuram-III | Kurnool-V Phase-I & Ananthapuram-III Phase-I | Sagar-Nagarjunasagar 400 kV quad D/c line (about 25 km) |  |  |  | NCT | [7 empty] | 50
| EL-37FFF | Kurnool-V & Ananthapuram-III | Kurnool-V Phase-I & Ananthapuram-III Phase-I | Conversion of 765 kV Bus Reactor bays to 765 kV SLR Line bays-2 Nos. (at Raichur New) |  |  |  | RTM | [5 empty] | PGCIL
| EL-99040 | Kurnool-V & Ananthapuram-III | Kurnool-V Phase-I & Ananthapuram-III Phase-I | Shifting of existing 50 MV Ar bus reactor at Nagarjunasagar to a new bay for termination of one circuit of Sagar Nagarjunasagar 400 kV quad D/c line |  |  |  | NCT
| EL-08FAB | Augmentation of Tumkur-II | Augmentation of Tumkur-II | Augmentation of Tumkur-II PS by 400/220 kV, 3x500 MVA ICTs (5 th to 7 th) | 1500 |  |  | NCT
| EL-0F17C | Augmentation of Tumkur-II | Augmentation of Tumkur-II | Tumkur-II-Madhugiri 400kV (Quad) D/c line (~ 100 km) |  |  |  | NCT | [7 empty] | 200
| EL-22FF0 | Augmentation of Tumkur-II | Augmentation of Tumkur-II | ± 300 MVAR STATCOM at Tumkur II PS with switching arrangement of under implementation 2x125 MVAr bus reactors |  |  |  | NCT
| EL-82941 | Augmentation of Tumkur-II | Augmentation of Tumkur-II | 2 Nos. of 220kV line bay at Tumkur-II PS for termination of dedicated transmission lines of RE developers |  |  |  | NCT
| EL-B21D7 | Augmentation of Tumkur-II | Augmentation of Tumkur-II | Augmentation of Tumkur-II PS by 400/220 kV, 3x500 MVA ICTs (8 th to 10 th) | 1500 |  |  | NCT
| EL-A38F1 | WR-ER Inter Regional Network | WR-ER Inter-Regional Network Expansion - Part A | Establishment of 3x1500MVA, 765/400kV S/s at Raigarh (Kotra)-II S/s in Chhattisgarh with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor | 4500 |  |  | NCT
| EL-62294 | WR-ER Inter Regional Network | WR-ER Inter-Regional Network Expansion - Part A | Extension at Raigarh (Kotra)-II 765/400kV S/s |  |  |  | NCT
| EL-FE9B1 | WR-ER Inter Regional Network | WR-ER Inter-Regional Network Expansion - Part A | LILO of Dharamjaygarh (Sec-B)-Jharsuguda (Sec-A) 765kV D/c line at Raigarh (Kotra)-II S/s |  |  |  | NCT | [7 empty] | 80
| EL-C6E67 | WR-ER Inter Regional Network | WR-ER Inter-Regional Network Expansion - Part A | Installation of new 765/400kV, 1x1500MVA (3x500MVA single phase units) ICT (3) at Jeerat (New) S/s of M/s POWERGRID Medinipur Jeerat Transmission Limited (PMJTL) along with associated bays at both ends | 1500 |  |  | NCT
| EL-14740 | WR-ER Inter Regional Network | WR-ER Inter-Regional Network Expansion - Part A | LILO of Ranchi (New) Medinipur 765kV D/c line at Jamshedpur (New) |  |  |  | NCT | [7 empty] | 200
| EL-2DF79 | WR-ER Inter Regional Network | WR-ER Inter-Regional Network Expansion - Part A | LILO of Ranchi (New) New PPSP 400kV D/c line at Jamshedpur (New) Jamshedpur (New) to LILO section towards Ranchi (New) needs to be implemented with Twin Moose Jamshedpur (New) to LILO section towards New PPSP needs to be implemented with Twin HTLS (ampacity of single HTLS as 1574A at nominal voltage) |  |  |  | NCT | [7 empty] | 252
| EL-5E7E7 | WR-ER Inter Regional Network | WR-ER Inter-Regional Network Expansion - Part A | Extension at Raigarh (Kotra)-II S/s 765/400kV S/s |  |  |  | NCT
| EL-5E6D3 | WR-ER Inter Regional Network | WR-ER Inter-Regional Network Expansion - Part A | Bypassing of Raigarh (Tamnar) Dharamjaygarh (Sec B) 765kV D/c line & Raigarh(Kotra) Raigarh (Tamnar) 765kV D/c line at Raigarh (Tamnar) S/s so as to form at Raigarh (Kotra) Dharamjaygarh (Sec B) 765kV D/c line |  |  |  | NCT | [7 empty] | 20
| EL-E55F5 | WR-ER Inter Regional Network | WR-ER Inter-Regional Network Expansion - Part A | Raigarh (Tamnar) Raigarh(Kotra)-II S/s 765kV D/c line |  |  |  | NCT | [7 empty] | 100
| EL-624A8 | WR-ER Inter Regional Network | WR-ER Inter-Regional Network Expansion - Part A | Extension at Raigarh (Tamnar) 765/400kV S/s |  |  |  | NCT
| EL-107B7 | WR-ER Inter Regional Network | WR-ER Inter-Regional Network Expansion - Part A | Extension at Jamshedpur (New) 765/400kV S/s |  |  |  | NCT
| EL-C176B | WR-ER Inter Regional Network | WR-ER Inter-Regional Network Expansion - Part A | Raigarh(Tamnar) @ Jamshedpur (New) 765kV D/c line |  |  |  | NCT | [7 empty] | 630
| EL-00011 |  |  | 4x500 MVA, 400/220kV ICTs at Pali PS | [24 empty] | CMETS meeting(s): 38, 39
| EL-00650 |  |  | Augmentation of 1x1500 MVA ICT (3rd), 765/400kV ICT at Jhatikara Substation (Bamnoli/Dwarka section) *minimum 2100 MVA per ckt at nominal voltage | [24 empty] | CMETS meeting(s): 31
| EL-00F7B |  |  | Common Pooling Station for M/s Adani Renewable Energy Holding Twelve Limited RE Power Projects (App. No. 2200001907 :520 MW & App. No. 2200001908 :303.33 MW) – Barmer-IV PS 400 kV S/c line on D/c tower (suitable to carry minimum 900 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 38
| EL-023ED |  |  | Solarcraft Power India 8 Private Limited Solar Power Project – Bikaner-V PS 220 kV S/c line on D/c tower(Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-030D1 |  |  | In the scheme, the evacuation of 6000 MW is proposed from VSC HVDC link from Barmer-II (new) substation to South Kalamb (Murbad). It is mention here that Barmer-II is a new substation which will be connected only to 400 kV Fatehgarh-IV PS and Barmer-I PS via LILO of 400kV Fatehgarh-IV PS - Barmer-I PS D/C. This connectivity means that Barmer-II would be a radial/hanging station with low system strength | [24 empty] | CMETS meeting(s): 36
| EL-039DF |  |  | Common Pooling station of M/s Solarcraft Power India 4 Pvt. Ltd. for Solar Power Projects (Appl. Nos | [24 empty] | CMETS meeting(s): 27
| EL-041C4 |  |  | Robertsganj PS – Prayagraj S/s 765 kV D/c line along with 240 MVAr line reactor for each circuit at Robertsganj end. Additional Inter regional (WR-NR)Transmission system for Connectivity under GNA (Tentative) | [24 empty] | CMETS meeting(s): 31
| EL-04AC2 |  |  | 400 kV Kishenpur-Samba D/c line (Quad) (2nd) | [24 empty] | CMETS meeting(s): 38
| EL-04FBF |  |  | Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS | [24 empty] | CMETS meeting(s): 27, 31, 36, 39
| EL-05218 |  |  | Sanchore PS – Sirohi (HVDC) PS 400 kV D/c line(Quad) | [24 empty] | CMETS meeting(s): 33, 38, 39
| EL-0581F |  |  | 5 GW (Solar) Fatehgarh-IV: 1 GW Barmer-I: 2.5 GW 3 Rajasthan REZ Ph-IV (Part- 5 : 6GW) (Barmer Complex) 6 GW (Solar) Barmer-II : 6GW Scheme planned for 2029 time frame (HVDC) 4 Rajasthan REZ Ph-IV (Part- 6 : 6GW) (Bhadla/Bikaner Complex) 6 GW (Solar) Bhadla-IV: 2 GW Bikaner-V: 4 GW* | [24 empty] | CMETS meeting(s): 27
| EL-05C8E |  |  | Augmentation of 2x1500 MVA (3rd & 4th ),765/400 kV ICTs at Neemrana-II S/s Minutes for 27th Consultation meeting for Evolving Transmission Schemes in NR 63 | [24 empty] | CMETS meeting(s): 27
| EL-05D64 |  |  | 4 Transmission System for Rajasthan REZ Phase-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex) | [24 empty] | CMETS meeting(s): 18
| EL-06311 |  |  | STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS | [24 empty] | CMETS meeting(s): 27, 31, 36, 39
| EL-06A29 |  |  | Infrastructure required for sharing dedicated transmission system – under the scope of M/s Unique Hytech Renewable Energy Pvt. Ltd | [24 empty] | CMETS meeting(s): 36
| EL-071AA |  |  | 3x500 MVA, 400/220kV ICTs at Sanchore PS | [24 empty] | CMETS meeting(s): 39
| EL-079D8 |  |  | 1 no of 220 kV bay at Sanchore PS shall be under the scope of ISTS | [24 empty] | CMETS meeting(s): 38
| EL-08044 |  |  | Bypassing of 400 kV Kankroli - Bhinmal-Zerda line at Bhinmal to form 400 kV Kankroli – Zerda (direct) line # | [24 empty] | CMETS meeting(s): 14, 15, 16, 17, 22, 23
| EL-09251 |  |  | Augmentation of 2x1500 MVA (1st & 2nd), 765/400 kV Fatehgarh- IV (Section-2) Pooling Station along with 2x240 MVAr (765 kV) Bus Reactor & 2x125 MVAr (400 kV) Bus Reactor | [24 empty] | CMETS meeting(s): 15
| EL-09900 |  |  | Augmentation of 1x500 MVA (9th), 400/220 kV ICT at Bhadla-III PS | [24 empty] | CMETS meeting(s): 27
| EL-099D8 |  |  | 400kV Sanchore PS – Barmer-IV PS D/c line (Quad) | [24 empty] | CMETS meeting(s): 38, 39
| EL-09D53 |  |  | Furies Solren Private Limited Solar Power Project– Bikaner-IV PS 220 kV S/c line D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-0A96D |  |  | 400/220kV, 5x500 MVA ICTs at Bikaner-VI PS | [24 empty] | CMETS meeting(s): 38
| EL-0A99D |  |  | Bhadla-III – Bhadla (HVDC) 400 kV 2xD/c quad moose line along with the line bays at both substations | [24 empty] | CMETS meeting(s): 27, 31, 38
| EL-0AC0E |  |  | 9 Transmission System for Rajasthan REZ Phase-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex) | [24 empty] | CMETS meeting(s): 18
| EL-0B24F |  |  | Augmentation of 500 MVA ICT (4th) ICT at Samba(PG) S/s along with associated transformer bays | [24 empty] | CMETS meeting(s): 31
| EL-0B6FA |  |  | Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor | [24 empty] | CMETS meeting(s): 25, 27, 31, 33
| EL-0C837 |  |  | Termination of another circuit of 400 kV Kishenpur-Samba D/c line (Quad) at Kishenpur at 400kV bay vacated at Kishenpur (After bypassing of one ckt of 400 kV Kishtwar-Kishenpur at Kishenpur) | [24 empty] | CMETS meeting(s): 38
| EL-0C9F0 |  |  | Establishment of 400 kV Beawar (HVDC) S/s at a suitable location near Beawar | [24 empty] | CMETS meeting(s): 34, 35, 38, 39
| EL-0CB10 |  |  | BN Peak Power-3 Private Limited RE Power Project– Ramgarh-III PS 220 kV S/c line on D/c tower (Suitable to carry minimum 350 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 38
| EL-0D2E2 |  |  | Sabarmati Green Energy Private Limited RE Power Project – Jalore PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 38
| EL-0D343 |  |  | 5 MW) – Barmer-III PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) Minutes for 37th Consultation Meeting for Evolving Transmission Schemes in Northern Region scheduled to be held on 27-03-2025 | [24 empty] | CMETS meeting(s): 37
| EL-0DA0D |  |  | LILO of 400kV Kota –Merta line at Beawar substation | [24 empty] | CMETS meeting(s): 14, 16, 22, 39
| EL-0DDF0 |  |  | STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR | [24 empty] | CMETS meeting(s): 16, 39
| EL-0E610 |  |  | Augmentation of 2x500 MVA, 400/220kV ICT (4th & 5th) at Bhadla-II Pooling station (220kV Section-I) | [24 empty] | CMETS meeting(s): 36
| EL-0ECFA |  |  | Establishment of 765/400kV, 4x1500 MVA, 400/220kV, 4x500 MVA ICTs pooling station at suitable location near Bhadla (Bhadla-IV PS) along with 2x125 MVAr & 2x240 MVAr bus reactor along with 2x125 MVAr & 2x240 MVAr bus reactor | [24 empty] | CMETS meeting(s): 34
| EL-0F136 |  |  | 420 kV, 1x125 MVAR Bus Reactor at Kiru generation switchyard | [24 empty] | CMETS meeting(s): 31
| EL-0F451 |  |  | Apraava Energy Private Limited RE Power Project – Barmer-III PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 37
| EL-0F661 |  |  | Augmentation of 1x500 MVA (3rd), 400/220kV ICT at Fatehgarh-3 pooling station (Section-II) | [24 empty] | CMETS meeting(s): 14
| EL-0F996 |  |  | Establishment of 765/400kV, 2x1500 MVA pooling station at suitable location near Bhadla (Bhadla-VI PS) along with 2x125 MVAr & 2x240 MVAr bus reactor | [24 empty] | CMETS meeting(s): 39
| EL-0FE43 |  |  | HVDC line between Sirohi (HVDC) & HVDC terminal station in WR/SR/ER (with Dedicated Metallic Return) | [24 empty] | CMETS meeting(s): 33, 34, 38, 39
| EL-10110 |  |  | 6000 MW, ±800 kV Merta (HVDC) [LCC] terminal station (4x1500 MW) | [24 empty] | CMETS meeting(s): 27
| EL-101A7 |  |  | Bikaner-II PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 23
| EL-10327 |  |  | Hexa Climate Solutions Private Limited Solar Power Project– Merta-II PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-10C94 |  |  | LILO of 765 kV Meerut- Bhiwani S/c line at Narela | [24 empty] | CMETS meeting(s): 14, 15, 16, 17, 36
| EL-10D9C |  |  | Augmentation of 1x500MVA (6th) 400/220 kV ICT at Bikaner –II PS | [24 empty] | CMETS meeting(s): 23
| EL-10FC4 |  |  | RJS Renewable Private Limited Solar Power Project– Ramgarh-II PS 220 kV S/c line on D/c tower(Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-11BA3 |  |  | HVDC line between Bikaner-VI (HVDC) & HVDC terminal station in WR/SR/ER (with Dedicated Metallic Return) | [24 empty] | CMETS meeting(s): 38
| EL-11BD7 |  |  | Establishment of 6000 MW, Ramgarh(HVDC) terminal station (4x1500 MW) at a suitable location near Ramgarh-II substation | [24 empty] | CMETS meeting(s): 33, 34, 35, 36, 37, 38
| EL-12429 |  |  | M/s Prespa Solar Private Limited Renewable Power Park – Merta-III PS 220 kV S/c line on D/c tower(suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 34
| EL-12818 |  |  | Infrastructure required for sharing dedicated transmission system - under the scope of M/s Hexa Climate Solutions Private Limited | [24 empty] | CMETS meeting(s): 33
| EL-12A1E |  |  | M/s RJS Renewable Pvt. Ltd. RE Power Project – Ramgarh-II PS 220 kV S/c line on D/c tower(Suitable to carry minimum 350 MW at nominal voltage) along with associated bay at generation end - Under the scope of M/s RJS Renewable Private Limited | [24 empty] | CMETS meeting(s): 38
| EL-12C20 |  |  | Through sharing of dedicated transmission system of M/s Avaada RJ Bikaner Private Limited. (App. No. 2200000561-136 MW) – Bikaner-V PS 220 kV S/c line on D/c tower(suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-13290 |  |  | Godavari Green Energy Private Limited RE Power Project – Sanchore PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 38
| EL-134B2 |  |  | LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation | [24 empty] | CMETS meeting(s): 14, 16, 22, 39
| EL-139DB |  |  | Common Pooling Station for Anboto Solar Private Limited Solar Power Projects(App. No. 2200000281-250 MW & 2200000492-50 MW)– Barmer-I PS 220 kV S/c line on D/c tower(Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-13B18 |  |  | Inputs on Load Generation Balance: In base cases shared, demand of Rajasthan considered in scenario-4: Jul month(31GW) seems to be on higher side. Similarly, in scenario-7: Feb month (35.4GW) seems to be on very higher side. Powerfactor of load also to be revised according to practical values to get correct picture of any low voltage scenario. State Scen7 Scen7 p.f. Scen4 Scen4 p.f. CHANDIGARH P | [24 empty] | CMETS meeting(s): 36
| EL-13D4F |  |  | Infrastructure required for sharing dedicated transmission system - under the scope of M/s SA Renewable Infra Private Limited | [24 empty] | CMETS meeting(s): 33
| EL-13E37 |  |  | 1x330 MVAr switchable line reactor for each circuit at each end of Sikar-II – Aligarh 765kV D/c line | [24 empty] | CMETS meeting(s): 16, 36
| EL-141A2 |  |  | Augmentation of 765/400 kV, 3x1500 MVA ICTs (1st to 3rd) at Merta-II S/s | [24 empty] | CMETS meeting(s): 27
| EL-141F6 |  |  | Associated EHVAC system strengthening in WR/SR/ER | [24 empty] | CMETS meeting(s): 33, 34, 35, 36, 37
| EL-145D8 |  |  | Through sharing of dedicated transmission of M/s Junachay Wind Energy Pvt. Ltd. RE Power Project – Ramgarh-II PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 36
| EL-14747 |  |  | Establishment of 400/220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor | [24 empty] | CMETS meeting(s): 31, 33, 35
| EL-15294 |  |  | Soltown Infra Private Limited RE Power Park – Bikaner-II PS 220 kV S/c line on D/c tower (Suitable to carry minimum 350 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 34
| EL-15D03 |  |  | M/s Sunsure Solarpark RJ One Private Limited Solar Power Project – Bikaner-V PS 220 kV S/c line on D/c tower (suitable to carry minimum 350 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 34
| EL-1627C |  |  | Common pooling station for NTPC Renewable Energy Limited Solar Power Projects (App No.2200000179(500 MW) & | [24 empty] | CMETS meeting(s): 25
| EL-1677A |  |  | Fatehgarh-IV (Sec-II) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end | [24 empty] | CMETS meeting(s): 27
| EL-16884 |  |  | Common Pooling station for Avaada Rjsustainable Private Limited RE Power Project(2200001316 - 660 MW) & M/s Avaada Energy Private Limited ( 2200001316 - 660 MW) & M/s Avaada Energy Private Limited ( | [24 empty] | CMETS meeting(s): 36
| EL-16C00 |  |  | 2028(interim). Final date shall be confirmed upon award of the system In view of that revised transmission system for connectivity application of M/s Avaada Waterbattery ((App No. 220000553-1120 MW) is as under: Details of Revised Transmission system for Connectivity under GNA: A. Associated Transmission System (ATS): NIL B. Transmission System under applicant scope | [24 empty] | CMETS meeting(s): 35
| EL-16C93 |  |  | Establishment of 765/400 kV, 3x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor | [24 empty] | CMETS meeting(s): 25
| EL-17567 |  |  | M/s Solarcraft Power India 4 Pvt. Ltd. shall share the dedicated transmission system granted for connectivity of M/s Solarcraft Power India 4 Pvt. Ltd under applicatio | [24 empty] | CMETS meeting(s): 38
| EL-177EE |  |  | 1 no. of 400 kV Bay at Ramgarh-II PS shall be under the scope of ISTS | [24 empty] | CMETS meeting(s): 38
| EL-180AA |  |  | Augmentation of 1x500MVA (3rd) 400/220 kV ICT at Bikaner –II PS B. Common Transmission system (Part of Transmission system associated with SEZ in Rajasthan under 8.1 GW Phase-II scheme) for both LTA application | [24 empty] | CMETS meeting(s): 17
| EL-18207 |  |  | AM Green Energy Private Limited Solar Power Project – Bikaner-IV PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 27
| EL-18361 |  |  | Establishment of 765/400 kV 2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor | [24 empty] | CMETS meeting(s): 25, 27, 31, 33, 36, 39
| EL-18587 |  |  | Comparison of VSC and LCC based HVDC Feature LCC-HVDC VSC-HVDC Converter Technology Thyristor-based IGBT-based (or similar switching devices) Reactive Power Requirements Requires substantial reactive power compensation (e.g., Filter Banks, SVC, STATCOM, SynCons). Capable of independent reactive power control. Generally, no external compensation needed | [24 empty] | CMETS meeting(s): 36
| EL-18947 |  |  | 1 no. of 220 kV bay at Bikaner-V PS under ISTS | [24 empty] | CMETS meeting(s): 38
| EL-18BDE |  |  | Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-3 substation | [24 empty] | CMETS meeting(s): 16
| EL-19650 |  |  | Establishment of 3x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor | [24 empty] | CMETS meeting(s): 25, 31
| EL-1989E |  |  | Transmission system for Connectivity under GNA: (Tentative) | [24 empty] | CMETS meeting(s): 35
| EL-1990B |  |  | STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS | [24 empty] | CMETS meeting(s): 27, 31
| EL-1A1E8 |  |  | Furies Solren Private Limited Solar Power Project– Bikaner-IV PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) A. Transmission system for Connectivity under GNA | [24 empty] | CMETS meeting(s): 27
| EL-1AC03 |  |  | Augmentation of 1x1500 MVA (3rd), 765/400kV ICT at Bikaner (PG) | [24 empty] | CMETS meeting(s): 14, 15, 17
| EL-1BA2E |  |  | Augmentation of 2x1500 MVA (1st & 2nd), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) | [24 empty] | CMETS meeting(s): 22
| EL-1BF5F |  |  | Augmentation of 1x1500 MVA ICT (3rd), 765/400kV ICT at Jhatikara Substation (Bamnoli/Dwarka section) | [24 empty] | CMETS meeting(s): 23, 31, 34
| EL-1CC5F |  |  | Rohat Solar Park Pvt. Ltd. RE Power Park – Barmer-III PS 220 kV S/c line (suitable to carry minimum 350 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 36
| EL-1D2C6 |  |  | ±800 kV HVDC line between Barmer-IV (HVDC) & Suitable location in WR/ER/SR (with Dedicated Metallic Return) | [24 empty] | CMETS meeting(s): 38, 39
| EL-1D9BF |  |  | Fatehgarh-2 – Bhadla-3 400kV D/c line (Quad) along with 50 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh 2- Bhadla- 3 400kV D/c line | [24 empty] | CMETS meeting(s): 16
| EL-1DCA8 |  |  | Tepsol Sun Sparkle Private Limited Renewable Power Park Project– Bhadla-III PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 23
| EL-1DD32 |  |  | Hinduja Renewables Energy Private Ltd Solar Power Project – Barmer-I PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-1F425 |  |  | Common Pooling station for Avaada RJBikaner Private Limited RE power project (App. No. 2200000561- 136 MW & App. No. 2200001326- 354 MW) – Bikaner-V PS 220 kV D/c line (suitable to carry minimum 300 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 36
| EL-201B3 |  |  | Augmentation of 2x1500 MVA (2nd & 3rd), 765/400kV ICT at Fatehgarh-3 pooling station (Section-II) | [24 empty] | CMETS meeting(s): 22
| EL-20781 |  |  | M/s Renew Solar Power Private Limited Solar Power Project – Pali PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 38
| EL-207DF |  |  | 400/220kV, 5x500 MVA ICTs at Bikaner-V PS | [24 empty] | CMETS meeting(s): 31, 33, 34, 35
| EL-226AA |  |  | Establishment of 400/220kV 5x500MVA Pooling Station at suitable location near Barmer (Barmer-III PS) along with 2x125 MVAr bus reactor | [24 empty] | CMETS meeting(s): 33, 34, 35
| EL-22F86 |  |  | Addition of BESS: In the 500 GW RE Transmission Report by CEA, ~22.5 GW BESS was planned at different pooling stations in NR (Rajasthan). However, so far, the BESS capacity addition has not taken place as per the plan. Planning of the envisaged BESS capacity as a generation resource could help in optimizing the transmission being planned for RE evacuation in Rajasthan and will also provide necessary flexibility support during the non- solar hours. CTU Reply : Noted | [24 empty] | CMETS meeting(s): 36
| EL-23514 |  |  | Establishment of 2x1500 MVA, 765/400 kV & 1x500MVA 400/220kV Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor at a suitable location near Bikaner | [24 empty] | CMETS meeting(s): 25
| EL-23675 |  |  | ±800 kV HVDC line between Bikaner-V (HVDC) & Begunia (HVDC) (with Dedicated Metallic Return) | [24 empty] | CMETS meeting(s): 31, 33, 34, 35, 36, 38, 39
| EL-23874 |  |  | Additional Inter regional (WR-NR) Transmission system for Connectivity under GNA (Tentative) | [24 empty] | CMETS meeting(s): 31, 35
| EL-23E4F |  |  | 1 no. of 220 kV bay at Bhadla-V PS end - Under the scope of ISTS | [24 empty] | CMETS meeting(s): 39
| EL-244EB |  |  | Augmentation of 6x500 MVA (4th to 9th), 400/220 kV ICTs at Barmer-I PS | [24 empty] | CMETS meeting(s): 27
| EL-24C0A |  |  | Bhadla-VI PS – Bhadla-IV PS 400kV D/c line (Quad) | [24 empty] | CMETS meeting(s): 39
| EL-24C88 |  |  | 1 no of 400 kV bay at Bhadla-V PS is under ISTS | [24 empty] | CMETS meeting(s): 38
| EL-24D0D |  |  | Avaada Suryaenergy Private Limited Solar Power Project – Bikaner-V PS 400 kV S/c line on D/c tower (suitable to carry minimum 900 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 35
| EL-250F9 |  |  | Applications for Connectivity to ISTS under CERC (Connectivity and General Network Access to the inter-Stat Transmission System) Regulations, 2022 received in Sep’23: Following 8 Nos. of applications for Connectivity to ISTS are received in the month of Sep’23 Minutes for 25th Consultation meeting for Evolving Transmission Schemes in NR 22 TABLE 2 | [24 empty] | CMETS meeting(s): 25
| EL-26050 |  |  | Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) | [24 empty] | CMETS meeting(s): 25, 27, 31, 33, 36, 39
| EL-26318 |  |  | 765kV Bhadla-IV PS – Bikaner-V PS D/c line | [24 empty] | CMETS meeting(s): 33, 34, 35, 36, 38, 39
| EL-26639 |  |  | 2 765 kV Churu- Siwani D/c line | [24 empty] | CMETS meeting(s): 25
| EL-26D98 |  |  | Establishment of 2x500 MVA (3rd & 4th) 400/220kV ICTs at Fatehgarh-III Pooling station B. Common Transmission system (Part of Transmission system associated with SEZ in Rajasthan under 8.1 GW Phase-II scheme) | [24 empty] | CMETS meeting(s): 16
| EL-2785C |  |  | Common Pooling station for NTPC Renewable Energy Limited Solar Power Projects ( | [24 empty] | CMETS meeting(s): 33
| EL-27C14 |  |  | M/s EG Mega Urja Private Limited Renewable Power Park – Barmer-I PS 220 kV S/c line on D/c towers (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-28506 |  |  | 1 no. of 220 kV bay at Ramgarh-II PS shall be under the scope of ISTS | [24 empty] | CMETS meeting(s): 38
| EL-28727 |  |  | 1 no. of 400 kV bay at Bhadla-V PS end – Under the scope of ISTS Scope | [24 empty] | CMETS meeting(s): 39
| EL-28995 |  |  | Common pooling station of Onevolt Energy, Grian Energy & Amplus Ages Private Limited Solar Power Project of 100 MW each for Application Nos. 1200003626, 1200003625 & | [24 empty] | CMETS meeting(s): 23
| EL-29625 |  |  | 6 1 Transmission System for Rajasthan REZ Phase-IV (Part-3: 3.6 GW) (Bikaner Complex) Exhibit-I Base Case June Solar Max Scenario EXHIBIT-1 | [24 empty] | CMETS meeting(s): 25
| EL-29B38 |  |  | Removal of LILO of Bawana – Mandola 400kV D/c (Quad) line at Maharani Bagh /Gopalpur S/s. Extension of above LILO section from Maharani Bagh/ GopalpuruptoNarela S/s so as to form Maharanibagh – Narela 400kV D/c(Quad) and Maharanibagh-Gopalpur-Narela 400 kV D/c (Quad) lines | [24 empty] | CMETS meeting(s): 14, 15, 16, 17, 36
| EL-2A125 |  |  | Establishment of 6000 MW, Barmer-III(HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-III PS | [24 empty] | CMETS meeting(s): 33, 34, 35, 36, 37
| EL-2B272 |  |  | Establishment of 6000 MW, ±800 kV terminal station (4x1500 MW) at suitable location in WR/ER/SR | [24 empty] | CMETS meeting(s): 31, 33, 34, 35, 36, 37, 38, 39
| EL-2B49F |  |  | Common Pooling station for Avaada Suryaenergy Private Limited Solar power project (App. No. 2200001254- 560 MW) & Avaada Energy Pvt. Ltd. RE Power Project (App. No. 2200001353- 350 MW) – Bikaner-V PS 400 kV S/c line on D/c tower (suitable to carry minimum 910 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 36
| EL-2BDBE |  |  | 6kV through already existing 2 numbers of Generation Transformers of Capacity | [24 empty] | CMETS meeting(s): 31
| EL-2BFBD |  |  | Bypassing of one ckt of 400kV Kiru- Pakaldul 400kV D/c line (Triple HTLS) at Pakaldul and connecting it with one of the circuit of Pakaladul- Kishtwar 400kV D/c line (Triple HTLS), thus forming 400kV Kishtwar - Kiru (Triple HTLS) direct line (one ckt) | [24 empty] | CMETS meeting(s): 31
| EL-2C853 |  |  | Considering the contribution of RE getting connected 13560 29058  Installed capacity considered at 220 kV level: 2000 MW  Installed capacity considered at 400 kV level: 4000 MW  SCR at 220 kV level – (10788/2000): 5.394  SCR at 400 kV level – (23409/12000): 1.95 (HVDC capacity of 6000 MW also included) | [24 empty] | CMETS meeting(s): 36
| EL-2E45B |  |  | Augmentation of 3x1500 MVA (1st, 2nd & 3rd), 765/400kV ICTs at Ramgarh PS | [24 empty] | CMETS meeting(s): 33
| EL-2ED08 |  |  | Clean Max Gamma Private Limited Renewable Power Park– Bikaner-IV PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) Minutes for 27th Consultation meeting for Evolving Transmission Schemes in NR 87 | [24 empty] | CMETS meeting(s): 27
| EL-2EE71 |  |  | Pravat Renewables India Project Pvt. Ltd. Renewable Power Park – Ramgarh PS 220 kV S/c line on D/c tower(suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-2F7DB |  |  | 400/220kV 2x500MVA ICTs at Bhadla-V PS (for connectivity agreed for grant at 220kV level) | [24 empty] | CMETS meeting(s): 37
| EL-2FDA6 |  |  | 2 509.5 1 Transmission System for Rajasthan REZ Phase-IV (Part-3: 3.6 GW) (Bikaner Complex) Outage of one ckt of 400 kV RAPS-Sujalpur D/c line Feb Solar Max Scenario x | [24 empty] | CMETS meeting(s): 25
| EL-2FEF3 |  |  | Adani Renewable Energy Holding Four Limited Solar Power Project – Barmer-II PS 400 kV S/c line (Suitable to carry minimum 900 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-30734 |  |  | Establishment of 6000 MW, Ramgarh-III(HVDC) terminal station (4x1500 MW) at a suitable location near Ramgarh-III substation | [24 empty] | CMETS meeting(s): 38, 39
| EL-30D5A |  |  | Establishment of 6000 MW, ± 800 kV Barmer-IV(HVDC) terminal station (4x1500 MW) at suitable location near Barmer | [24 empty] | CMETS meeting(s): 38, 39
| EL-31139 |  |  | Augmentation of 2x1500 MVA (3rd & 4th), 765/400kV ICT at Bhadla-III | [24 empty] | CMETS meeting(s): 31, 33
| EL-31BA6 |  |  | 1 no. of 220 kV Bay at Ramgarh-III PS shall be under the scope of ISTS | [24 empty] | CMETS meeting(s): 38
| EL-31CD6 |  |  | Avaada Energy Private Limited Hybrid Power Project – Barmer-I PS 220 kV S/c line on D/c tower(Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 27
| EL-32392 |  |  | Siwani – Patran (Indi Grid) 400 kV D/c line (Quad Moose) along with 80 MVAr switchable line reactor for each circuit at Siwani S/s end | [24 empty] | CMETS meeting(s): 25
| EL-326E0 |  |  | Establishment of 6000 MW, ± 800 kV Bikaner-V (HVDC) terminal station (4x1500 MW) at suitable location near Bikaner | [24 empty] | CMETS meeting(s): 31, 33, 34, 35, 36, 38, 39
| EL-3276C |  |  | Common Pooling Station for Kantida Renewables India Project Private Limited RE Power Park(App. No. 2200000761- 300 MW) & Vismaya Four Renewables Private Limited Solar Power Project (App. No. 2200000910- 250 MW) – Bhadla-IV PS 400 kV S/c line on D/c tower(suitable to carry minimum 900 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-328D7 |  |  | Augmentation of 1x500MVA (8th) 400/220 kV ICT at Bikaner –II PS | [24 empty] | CMETS meeting(s): 34
| EL-32D0B |  |  | 400/220kV, 2x500 MVA ICTs (7th & 8th) ICTs at Bikaner-IV PS | [24 empty] | CMETS meeting(s): 31
| EL-32FE8 |  |  | LILO of Indore – Bhopal 765 kV S/c line at Kurawar | [24 empty] | CMETS meeting(s): 25, 27, 31, 33, 36, 39
| EL-342CB |  |  | Augmentation of 2x1500 MVA (3rd and 4th), 765/400kV ICT at Fatehgarh-3 pooling station (Section-II) B. Common Transmission system (Part of Transmission system associated with SEZ in Rajasthan under Phase-III (20 GW) scheme) | [24 empty] | CMETS meeting(s): 14
| EL-3466E |  |  | shall share dedicated transmission system for connectivity granted to M/s Iraax International Private Ltd under App. No. 2200000484 | [24 empty] | CMETS meeting(s): 39
| EL-351F9 |  |  | Establishment of 2x1500 MVA, 765/400 kV Ramgarh-III Pooling Station at a suitable location near Ramgarh along with 2x125 MVAr & 2x240 MVAr bus reactor | [24 empty] | CMETS meeting(s): 38, 39
| EL-3535F |  |  | STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani S/s | [24 empty] | CMETS meeting(s): 27, 31
| EL-35672 |  |  | 8x500 MVA, 400/220kV ICTs at Bikaner-V PS | [24 empty] | CMETS meeting(s): 38, 39
| EL-35A84 |  |  | Jalore PS – Merta-II PS 400 kV D/c line(Quad) | [24 empty] | CMETS meeting(s): 33, 34, 38
| EL-35C79 |  |  | 400/220kV, 2x500 MVA ICTs (1st & 2nd ) at Ramgarh PS | [24 empty] | CMETS meeting(s): 31
| EL-35E33 |  |  | Augmentation of 2x1500 MVA (5th & 6th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) | [24 empty] | CMETS meeting(s): 39
| EL-365F9 |  |  | LILO of one ckt of 765 kV Bikaner-III -Neemrana-II D/c line (2nd) at Bikaner-IV PS along with 330 MVAR switchable line reactor at Bikaner-IV PS end of each ckt of 765 kV Bikaner-IV -Neemrana-II line (formed after LILO) | [24 empty] | CMETS meeting(s): 25
| EL-36700 |  |  | Common Pooling Station for JSW Neo Energy Limited Solar Power Projects (App. No. 220000706(700 MW), App. No. 2200000689(700 MW) & 2200000797(700 MW)) – Ramgarh-II PS 400 kV D/c line (Suitable to carry minimum 1050 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-36B72 |  |  | 24, which is as under: Details of Transmission system for Connectivity under GNA: A. Associated Transmission System (ATS): NIL B. Transmission System under applicant scope | [24 empty] | CMETS meeting(s): 35
| EL-37199 |  |  | Begunia – Gopalpur (ISTS) 765kV D/c line along with associated bays at both ends along with 240MVAr switchable line reactor for each circuit at Begunia end of Begunia –Gopalpur (ISTS) 765kV D/c line | [24 empty] | CMETS meeting(s): 31, 33, 34, 35, 36, 38, 39
| EL-37646 |  |  | Common Pooling station for Adani Renewable Energy Holding Four Limited (App. No. 1200003689(500 MW), 2200000661(250 MW) & 2200000661(250 MW) & | [24 empty] | CMETS meeting(s): 33
| EL-376B4 |  |  | 0 1 Outage of one ckt of 765 kV Rishabhdeo-Mandsaur D/c line June Solar Max Scenario | [24 empty] | CMETS meeting(s): 18
| EL-37BE5 |  |  | 2023 confirmed space availability for Augmentation of 400/220 kV transformer (5th, 500MVA) along with transformer bays at 400/220kV Maharani Bagh (PG) S/s. In the meeting, NRLDC stated that at present 400/220kV ICTs at Maharani Bagh are not violating N-1 criteria, howeve | [24 empty] | CMETS meeting(s): 35
| EL-381CB |  |  | Maharani Bagh/ Gopalpur upto Narela S/s so as to form Maharanibagh – Narela 400kV D/c(Quad) and Maharanibagh-Gopalpur-Narela 400 kV D/c (Quad) lines | [24 empty] | CMETS meeting(s): 16
| EL-3877B |  |  | Jhatikara – Dwarka 400kV D/c line (Twin HTLS*) | [24 empty] | CMETS meeting(s): 31, 34
| EL-38782 |  |  | LILO of both ckts of 765kV Ramgarh-II PS – Bhadla-IV PS D/c line at Ramgarh-III PS along with 240 MVAr switchable line reactor for each circuit at Ramgarh-III PS end | [24 empty] | CMETS meeting(s): 38, 39
| EL-38FD7 |  |  | Augmentation of 1x500 MVA (4th), 400/220 kV ICT at Barmer-I PS | [24 empty] | CMETS meeting(s): 27
| EL-3A4DE |  |  | 400kV Sectionalizer bay (1 set) at Bikaner-IV PS Minutes for 27th Consultation meeting for Evolving Transmission Schemes in NR 74 | [24 empty] | CMETS meeting(s): 27
| EL-3ABED |  |  | Common Pooling station for Adani Renewable Energy Holding Four Limited Solar Power Project (App. No. 1200003689(500 MW). 2200000662(284 MW)) & Adani Solar Energy AP Three Limited Solar Power Project(App. No. 0212100038(150 MW))– Ramgarh PS 400 kV S/c line on D/c tower (Suitable to carry minimum 1184 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-3AD7A |  |  | Bypassing of both ckts of 765kV Sasan – Vindhyachal Pool 2xS/c line at Vindhyachal Pool and connecting it with 765kV Vindhyachal Pool - Prayagraj D/c line, thus forming 765kV Sasan - Prayagraj D/c line | [24 empty] | CMETS meeting(s): 31
| EL-3AE0E |  |  | Kiru HEP – Pakaldul generation switchyard 400 kV D/c line (Triple HTLS Conductor –Equivalent to about 2400MW-considering 10% overload) along with 400kV bays at Kiru generation switchyard | [24 empty] | CMETS meeting(s): 31
| EL-3AEEC |  |  | Renew Solar Power Private Limited Solar Power Project – Barmer-III PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 34
| EL-3B6C3 |  |  | Serentica Renewables India Private Limited Solar Power Project– Sirohi PS 220 kV S/c line on D/c tower(suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-3BFE1 |  |  | Ramgarh-II PS – Bhadla-IV PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Ramgarh-II PS end | [24 empty] | CMETS meeting(s): 33, 34, 35, 36, 37, 38
| EL-3CB80 |  |  | Augmentation of 2x1500 MVA (1st & 2nd), 765/400kV ICT at Ramgarh PS | [24 empty] | CMETS meeting(s): 31
| EL-3CE98 |  |  | Augmentation of 5x500 MVA, 400/220kV ICTs at Sirohi PS | [24 empty] | CMETS meeting(s): 31, 33
| EL-3CFCF |  |  | 765kV Bhadla-V PS – Bikaner-VI PS D/c line | [24 empty] | CMETS meeting(s): 38, 39
| EL-3DB34 |  |  | Junachay Wind Energy Pvt. Ltd. RE Power Project – Ramgarh-II PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 36
| EL-3DDDE |  |  | Establishment of 2x1500 MVA, 765/400 kV Ramgarh-II Pooling Station at a suitable location near Ramgarh along with 2x125 MVAr & 2x240 MVAr bus reactor | [24 empty] | CMETS meeting(s): 33, 34, 35, 36, 37, 38
| EL-3DE89 |  |  | Common Pooling Station for Acme Cleantech Solutions Pvt Ltd. (App. No. 2200000387(600 MW) & 2200000396(250 MW)) Solar Power Projects – Fatehgarh-II PS 400 kV S/c line on D/c tower (Suitable to carry minimum 900 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-3EA43 |  |  | ACME Greentech Urja Private Limited RE Power Project– Ramgarh-III PS 400 kV D/c line (Suitable to carry minimum 2182 MW per circuit at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-3F385 |  |  | Common Pooling Station for M/s Adani Renewable Energy Holding Twelve Limited RE Power Projects (App. No. 2200001907 :520 MW & App. No. 2200001908 :303.33 MW) – Barmer-IV PS 400 kV S/c line (suitable to carry minimum 900 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 38
| EL-3F657 |  |  | LILO of Ramgarh PS – Ramgarh-II PS 400kV D/c line (Quad) at Ramgarh-III PS | [24 empty] | CMETS meeting(s): 38, 39
| EL-3F9F2 |  |  | 400/220kV, 6x500 MVA ICTs at Barmer-II PS | [24 empty] | CMETS meeting(s): 31, 33, 35
| EL-3FA83 |  |  | Infrastructure required for sharing dedicated transmission system - under the scope of M/s Juniper Green Energy Private Limited | [24 empty] | CMETS meeting(s): 33
| EL-3FB44 |  |  | M/s Vena Energy Konkan Wind Power Private Limited Standalone ESS Project – Pali PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-3FCFD |  |  | Establishment of 765/400kV, 2x1500 MVA & 400/220kV 1x500MVA (1st) pooling station at suitable location near Bhadla (Bhadla-IV PS) along with 2x125 MVAr & 2x240 MVAr bus reactor | [24 empty] | CMETS meeting(s): 27
| EL-403FD |  |  | Augmentation of 1x500 MVA (2rd), 400/220kV ICT at Fatehgarh-IV pooling station (Section-1) B. Common Transmission system (Part of Transmission system associated with SEZ in Rajasthan under Phase-III (20 GW) scheme) | [24 empty] | CMETS meeting(s): 16
| EL-417DD |  |  | Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | [24 empty] | CMETS meeting(s): 25, 27, 31, 33, 36
| EL-41D01 |  |  | M/s Enren-III Energy Private Limited Solar Power Project – Merta-III PS 220 kV S/c line on D/c tower(suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 34
| EL-43445 |  |  | Pali PS – Beawar (HVDC) S/s 400 kV D/c line(Quad) | [24 empty] | CMETS meeting(s): 34, 38, 39
| EL-4428E |  |  | Renew Solar Power Private Limited Solar Power Project – Barmer-III PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 35
| EL-468EF |  |  | M/s Hexa Climate Solutions Private Limited RE Power Project – Merta-III PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-46A03 |  |  | Augmentation with 765/400kV, 1x1500 MVA Transformer (5th) at Bhadla-II PS | [24 empty] | CMETS meeting(s): 34
| EL-47B1F |  |  | 7 1 Outage of one ckt of 765 kV Jalore-Rishabhdeo D/c line June Solar Max Scenario | [24 empty] | CMETS meeting(s): 18
| EL-47D10 |  |  | Vayuna Renewables India Project Private Limited Solar Power Park – Sirohi PS 220 kV S/c line on D/c tower(Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-4816A |  |  | , it may be seen that ICTs Peak Utilization of 86% in June’24. POWERGRID vide mail dated | [24 empty] | CMETS meeting(s): 35
| EL-48EFF |  |  | Sirohi(HVDC) PS – Sirohi PS 400 kV D/c line(Quad) | [24 empty] | CMETS meeting(s): 33, 38, 39
| EL-48FFB |  |  | 1 no. of 400 kV bay at Ramgarh-III PS end - Under the scope of ISTS | [24 empty] | CMETS meeting(s): 39
| EL-4A753 |  |  | Infrastructure required for sharing dedicated transmission system - under the scope of M/s Aditya Birla Renewables Limited | [24 empty] | CMETS meeting(s): 35, 37
| EL-4AEF9 |  |  | 765kV Bhadla-V PS – Bikaner-V PS D/c line | [24 empty] | CMETS meeting(s): 37
| EL-4B103 |  |  | Associated EHVAC system strengthening in WR/SR/ER for onwards dispersal of power | [24 empty] | CMETS meeting(s): 38, 39
| EL-4BA7E |  |  | Removal of LILO of Bawana – Mandola 400kV D/c (Quad) line at Maharani Bagh /Gopalpur S/s. Extension of above LILO section from | [24 empty] | CMETS meeting(s): 16
| EL-4BF62 |  |  | Juniper Green Energy Private Limited Solar Power Project– Merta-II PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-4C59F |  |  | 400kV Sectionalizer bay (1 set) at at Siwani S/s | [24 empty] | CMETS meeting(s): 27, 31
| EL-4C6E2 |  |  | shall be the same system as indicated in LTA intimation. In some cases due to surrender of LTA by other applicants, the transmission system granted LTA shall be revised and upgraded. However, start date of GNA shall not be changed. Details of LTA grantees, their likely effective date & their revised transmission system (in some cases) for connectivity under GNA are as below: S. No. Applicant Na | [24 empty] | CMETS meeting(s): 22
| EL-4C729 |  |  | 1 no. of 220 kV bay at Sanchore PS end - Under the scope of ISTS | [24 empty] | CMETS meeting(s): 39
| EL-4C759 |  |  | 1 no of 220 kV bay at Jalore PS shall be under the scope of ISTS | [24 empty] | CMETS meeting(s): 38
| EL-4C95B |  |  | Additional Scheme to relieve overloading of 400 kV Bhinmal-Zerda line (Twin Moose) | [24 empty] | CMETS meeting(s): 23
| EL-4D705 |  |  | A. Associated Transmission System (ATS): NIL | [24 empty] | CMETS meeting(s): 38
| EL-4E236 |  |  | Augmentation of 2x1500 MVA (4th and 5th), 765/400kV ICT at Fatehgarh-3 pooling station (Section-II) | [24 empty] | CMETS meeting(s): 16
| EL-4EA41 |  |  | Augmentation with 765/400kV, 2x1500MVA Transformer (3rd & 4th ) at Fatehgarh-IV PS (Sec-II) | [24 empty] | CMETS meeting(s): 27
| EL-4EA69 |  |  | STATCOM: • Fatehgarh – II S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAR MSC, 2x125 MVAr MSR • Bhadla – II S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAR MSC, 2x125 MVAr MSR *with minimum capacity of 2100 MVA on each circuit at nominal voltage **Gopalpur Substation is under implementation by DTL by LILO of Bawana – Maharanibagh 400kV D/c(Quad) at Gopalpur substation | [24 empty] | CMETS meeting(s): 36
| EL-4EBF7 |  |  | Bypassing both ckts of 400kV Kishenpur – Samba D/c line (Twin) & 400 kV Samba – Jalandhar D/c line (Twin) at Samba and connecting them together to form Kishenpur– Jalandhar D/c direct line (Twin) | [24 empty] | CMETS meeting(s): 38
| EL-50021 |  |  | 8 Transmission System for Rajasthan REZ Phase-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex) | [24 empty] | CMETS meeting(s): 18
| EL-50132 |  |  | Establishment of 765/400 kV, 2x1500 MVA & 2x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s | [24 empty] | CMETS meeting(s): 31, 33, 36, 39
| EL-51E8F |  |  | Siwani – Jind (PG) 400 kV D/c line (Quad Moose) Minutes for 25th Consultation meeting for Evolving Transmission Schemes in NR 11 | [24 empty] | CMETS meeting(s): 25
| EL-51FF0 |  |  | 6 1 Transmission System for Rajasthan REZ Phase-IV (Part-3: 3.6 GW) (Bikaner Complex) Base Case Feb Solar Max Scenario | [24 empty] | CMETS meeting(s): 25
| EL-5264E |  |  | 1 no. of 220 kV bay at Bikaner-VI PS shall be under the scope of ISTS | [24 empty] | CMETS meeting(s): 38
| EL-533DB |  |  | 400kV Samba- Jalandhar D/c line (Quad) (only one circuit is to be terminated at Jalandhar while second circuit would be connected to bypassed circuit of Jalandhar –Nakodar 400kV D/c line) | [24 empty] | CMETS meeting(s): 38
| EL-53661 |  |  | 8 1 Outage of one ckt of 765 kV Fatehgarh-IV-Jalore D/c line Feb Solar Max Scenario | [24 empty] | CMETS meeting(s): 18
| EL-547E5 |  |  | Augmentation of 5x1500 MVA (1st to 5th), 765/400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor | [24 empty] | CMETS meeting(s): 25, 27, 31, 33, 38
| EL-54975 |  |  | Fatehgarh 3- Bhadla-3 400kV D/c line(Quad) along with 50 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh 3- Bhadla-3 400kV D/c line | [24 empty] | CMETS meeting(s): 14, 16, 22
| EL-553D7 |  |  | Barmer-I PS – Merta-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end of Barmer-I PS – Merta-II 765 kV D/c line | [24 empty] | CMETS meeting(s): 27, 31, 36, 39
| EL-56771 |  |  | Saurya Urja Company of Rajasthan Limited Renewable Power Park– Bikaner-V PS 220 kV S/c (high capacity) line on D/c tower(Suitable to carry minimum 400 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-5730E |  |  | 4x1500 MVA (1st to 4th), 765/400 kV ICTs at Fatehgarh-IV (Section-2) Pooling Station | [24 empty] | CMETS meeting(s): 31
| EL-57324 |  |  | Establishment of 6x1500 MVA, 765/400 kV Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner | [24 empty] | CMETS meeting(s): 25, 27
| EL-5754F |  |  | Khetri- Bhiwadi 400 kV D/c line (Twin HTLS)* | [24 empty] | CMETS meeting(s): 14, 15, 17
| EL-579A0 |  |  | 6° N-2 of 765 kV Jalore – Rishabdeo D/C line | [24 empty] | CMETS meeting(s): 18
| EL-57AA1 |  |  | Bhadla-II PS – Sikar-II 765kV D/c line(2nd) | [24 empty] | CMETS meeting(s): 16, 31, 34
| EL-58072 |  |  | 5 MW (at Hissar S/s), through separate applications. In the same RoP, CERC had also directed CTUIL to process the same expeditiously keeping in view the SCOD on | [24 empty] | CMETS meeting(s): 38
| EL-5996E |  |  | Kurawar – Astha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | [24 empty] | CMETS meeting(s): 39
| EL-59A52 |  |  | Common Pooling station for Iraax International (OPC) Private Ltd Solar Power Projects(App. No. 2200000484-100 MW & App. No. 2200000540- 150 MW) – Bikaner-V PS 220 kV S/c line on D/c tower(Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-5A0ED |  |  | Establishment of 765/400kV, 4x1500 MVA pooling station at suitable location near Bhadla (Bhadla-IV PS) along with 2x125 MVAr & 2x240 MVAr bus reactor along with 2x125 MVAr & 2x240 MVAr bus reactor | [24 empty] | CMETS meeting(s): 31, 33, 35, 36
| EL-5A444 |  |  | Izhma Solar Private Limited Solar Power Project – Sirohi PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-5B6A8 |  |  | Sunsure Solarpark RJ One Private Limited Solar Power Project – Jalore PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-5B721 |  |  | Establishment of 400 kV pooling station at a suitable location near Pali (Pali PS) along with 2x125 MVAr bus reactor | [24 empty] | CMETS meeting(s): 39
| EL-5C02D |  |  | Common Pooling station of M/s Renew Solar Power Private Limited Solar Power Projects (Appl. No. 2200000186 (300 MW) & Appl. No. 2200000187 (300 MW))– Fatehgarh-IV PS (Section-2) 400 kV S/c line on D/c towers (Suitable to carry minimum 900 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 25
| EL-5C930 |  |  | Private Limited Solar Power Project – Bhadla-IV PS 220 kV S/c line on D/c tower (Suitable to carry minimum 335 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-5C94B |  |  | Hazel Hybren Private Limited Solar Power Project– Bikaner-IV PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) A. Transmission system for Connectivity under GNA | [24 empty] | CMETS meeting(s): 27
| EL-5D6BC |  |  | Common Pooling station for Adani Renewable Energy Holding Four (App. No. 2200000598(500 MW) & | [24 empty] | CMETS meeting(s): 33
| EL-5DAFB |  |  | Augmentation with 1x1500 MVA, 765/400 kV ICT at Bareilly (765/400kV) S/s (3rd) | [24 empty] | CMETS meeting(s): 27, 33
| EL-5EA00 |  |  | Merta-III PS – Beawar(HVDC) PS 400 kV D/c line (Quad) | [24 empty] | CMETS meeting(s): 34, 35, 39
| EL-5F6B8 |  |  | Establishment of 400kV Pooling Station at suitable location near Barmer (Barmer-III PS) along with 2x125 MVAr bus reactor | [24 empty] | CMETS meeting(s): 36, 37
| EL-60041 |  |  | Fatehgarh-IV- Fatehgarh-III 400 kV D/c (Twin HLTS*) line | [24 empty] | CMETS meeting(s): 16
| EL-60909 |  |  | 1 no. of 220 kV bay at Pali PS shall be under the scope of ISTS | [24 empty] | CMETS meeting(s): 38
| EL-6095C |  |  | M/s Waaree Forever Energies Private Limited RE Power Project – Pali PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-61F37 |  |  | 400/220kV, 5x500 MVA ICTs at Bhadla-VI PS | [24 empty] | CMETS meeting(s): 39
| EL-62002 |  |  | Common Pooling station for Renew Solar Power Private Limited Solar Power Projects (App. No. 2200000516(300 MW), 2200000522(300MW) – Bhadla-IV PS 400 kV S/c line on D/c tower (suitable to carry minimum 900 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-6206E |  |  | Development Commissioner (Power) Power Development Department, Grid Substation Complex, Janipur, Jammu | [24 empty] | CMETS meeting(s): 36
| EL-62CF6 |  |  | Through sharing of dedicated transmission system of M/s Renew Surya Ravi Pvt. Ltd.– Bikaner (PG) 400 kV S/c line (Suitable to carry minimum 900 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 27
| EL-63399 |  |  | Iraax International (Opc) Private Limited Renewable Power Park– Bikaner-IV PS 220 kV S/c line on D/c tower(Suitable to carry minimum 300 MW at nominal voltage) A | [24 empty] | CMETS meeting(s): 27
| EL-63408 |  |  | 1 no. of 220 kV bay at Barmer-IV PS end - Under the scope of ISTS | [24 empty] | CMETS meeting(s): 39
| EL-63CA3 |  |  | 8 1 Outage of one ckt of 765 kV Rishabhdeo-Mandsaur D/c line Feb Solar Max Scenario | [24 empty] | CMETS meeting(s): 18
| EL-63D48 |  |  | Vannur Solar Power Private Limited RE Power Project – Barmer-IV PS 220 kV S/c line (Suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-6423F |  |  | Common Pooling Station for Renew Solar Power Private Limited Solar Power Projects (App. No. 2200000551-400 MW & 2200000779 -300 MW) – Sirohi PS 400 kV S/c line (Suitable to carry minimum 900 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-64276 |  |  | Common Pooling Station for M/s Adani Renewable Energy Holding Twelve Limited (App. No. 2200002006-520 MW & App. No. 2200002009-400 MW) & Adani Renewable Energy Holding Nine Limited (App. No. 2200002010-180 MW) RE Power Projects – Ramgarh-III PS 400 kV S/c line on D/c (suitable to carry minimum 1100 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-64346 |  |  | M/s Amplus Centaur Solar Private Limited Solar Power Project– Sirohi (HVDC) PS (Sirohi-II) 220 kV S/c line on D/c tower (suitable to carry minimum 350 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 34
| EL-64979 |  |  | Eden Renewable Cadet Private Limited – Barmer-I PS 220 kV S/c line on D/c towers (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 25
| EL-649B8 |  |  | Additional Transmission system for Inter-regional power transfer: Minutes for 27th Consultation meeting for Evolving Transmission Schemes in NR 90 | [24 empty] | CMETS meeting(s): 27
| EL-64DF7 |  |  | Waaree Forever Energies Private Limited RE Power Project– Bhadla-VI PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-6573E |  |  | Common Pooling station for Kantida Renewables India Project Private Limited RE Power Park (App. No. 2200000761- 300 MW) & Vismaya Four Renewables Private Limited Solar Power Projects (App. No. 2200000910- 250 MW & App. No. 2200001284-50MW) – Bhadla-IV PS 400 kV S/c line on D/c tower (suitable to carry minimum 900 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 35
| EL-65D44 |  |  | Associated transmission system in WR/ER for onwards dispersal of power | [24 empty] | CMETS meeting(s): 31, 33, 34, 35, 36, 37, 38, 39
| EL-65D5C |  |  | Renew Solar Power Private Limited Solar Power Project – Barmer-II PS 220 kV S/c line on D/c tower(Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-67039 |  |  | Removal of LILO of one circuit of Bhadla-Bikaner (RVPN) 400kV D/c(Quad) line at Bikaner (PG). Extension of above LILO section from Bikaner (PG) upto Bikaner-II PS to form Bikaner-II PS – Bikaner (PG) 400kV D/c(Quad) line | [24 empty] | CMETS meeting(s): 14, 15, 17
| EL-682A8 |  |  | 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) * with minimum capacity of 2100 MVA/ckt at nominal voltage | [24 empty] | CMETS meeting(s): 27
| EL-69266 |  |  | Augmentation by 1x1500 MVA ICT at 765/400kV Kanpur (GIS) substation | [24 empty] | CMETS meeting(s): 16, 25, 27, 31, 33, 38
| EL-6A564 |  |  | Common Pooling Station for ReNew Solar Power Private Limited RE Power Projects(App. No. 2200001781-200 MW, App. No. 2200001864-300 MW, App. No. 2200001865-300 MW ,App. No. 2200001997-300 MW & App. No. 2200002063-300 MW) – Bhadla-V PS 400 kV D/c line (suitable to carry minimum 900 MW per circuit at nominal voltage) along with associated bays at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-6A5A4 |  |  | Infrastructure required for sharing dedicated transmission system – under the scope of M/s Dangri Wind Energy Pvt. Ltd | [24 empty] | CMETS meeting(s): 36
| EL-6A951 |  |  | Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Minutes for 27th Consultation meeting for Evolving Transmission Schemes in NR 67 | [24 empty] | CMETS meeting(s): 27
| EL-6ACC9 |  |  | Ramgarh PS – Ramgarh-II PS 400 kV D/c line (Quad) | [24 empty] | CMETS meeting(s): 33, 34, 35, 36, 37, 38
| EL-6B099 |  |  | Common Pooling station for Juniper Green Energy Private Limited (App. No. 2200000499(150 MW) & 2200000550(150 MW)) Solar Power Projects –– Ramgarh PS 220 kV S/c line on D/c tower(Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-6B356 |  |  | Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s | [24 empty] | CMETS meeting(s): 27
| EL-6B418 |  |  | Waaree Forever Energies Private Limited RE Power Project – Sanchore PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 38
| EL-6B5A6 |  |  | M/s Green Infra Renewable Energy Farms Private Limited RE Power Project – Sanchore PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-6B862 |  |  | Ampin Energy Utility Private Limited RE Power Project – Sanchore PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-6B87E |  |  | M/s Avaada Waterbattery Private Limited Pumped Storage Project– Robertsganj Pooling Station 400 kV D/c line (Quad moose or equivalent conductor suitable to carry 1716 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 31, 35
| EL-6B998 |  |  | Through sharing of dedicated transmission system of M/s Adani Renewable Energy Holding Four Limited (App. No. 1200003685 (500 MW)) Solar Power Project – Bhadla-II PS 400 kV S/c line on D/c tower (suitable to carry minimum 900 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 34
| EL-6CA5E |  |  | Common Pooling station for Pumped Storage Projects of M/s Greenko UP01 IREP Private Limited (App. No. 220000527-672 MW, 220000529- 672 MW, 220000524-672 MW, 220000525-672 MW, 220000526-672 MW & 220000528-672 MW) – Robertsganj Pooling Station 400 kV 2xD/c line(suitable to carry minimum 1400 MW per circuit at nominal voltage)* *Minimum One unit to operate in Synchronous Condenser mode as per the requirement of the grid | [24 empty] | CMETS meeting(s): 31
| EL-6D14B |  |  | JIRE Green Energy Project Two Limited RE Power Project– Barmer-IV PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 38
| EL-6D9D5 |  |  | 1x500 MVA (1st), 400/220 kV pooling station at Bhadla-3 PS B. Common Transmission system (Part of Transmission system associated with SEZ in Rajasthan under Phase-III (20 GW) scheme) | [24 empty] | CMETS meeting(s): 16
| EL-6DEF0 |  |  | Common Pooling Station for M/s Adani Renewable Energy Holding Twelve Limited (App. No. 2200002006-520 MW & App. No. 2200002009-400 MW) & Adani Renewable Energy Holding Nine Limited (App. No. 2200002010-180 MW) RE Power Projects – Ramgarh-III PS 400 kV S/c line (suitable to carry minimum 1100 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-6E116 |  |  | STATCOM: Fatehgarh – II S/s: STATCOM: ± 600 MVAr, 4x125 MVAR MSC, 2x125 MVAr MSR Bhadla – II S/s: STATCOM: ± 600 MVAr, 4x125 MVAR MSC, 2x125 MVAr MSR *with minimum capacity of 2100 MVA on each circuit at nominal voltage | [24 empty] | CMETS meeting(s): 16
| EL-6EB09 |  |  | HVDC line between Ramgarh (HVDC) & HVDC terminal station in WR/SR/ER (with Dedicated Metallic Return) | [24 empty] | CMETS meeting(s): 33, 34, 35, 36, 37, 38, 39
| EL-6EB5E |  |  | LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh- IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) | [24 empty] | CMETS meeting(s): 25, 27, 31
| EL-6F66E |  |  | 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | [24 empty] | CMETS meeting(s): 27, 31, 33, 36, 39
| EL-6F9F6 |  |  | Through sharing of dedicated transmission of M/s Hinduja Renewables Energy Pvt. Ltd. RE Power Project – Barmer-I PS 220 kV S/c line (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 36
| EL-6FD3E |  |  | 765kV Bhadla-VI PS – Ramgarh-III D/c line | [24 empty] | CMETS meeting(s): 39
| EL-6FD9F |  |  | 2x500 MVA (1st & 2nd), 400/220 kV & 2x1500 MVA (1st & 2nd) 765/400kV pooling station at Bhadla-III along with 2x330 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor | [24 empty] | CMETS meeting(s): 23
| EL-703D7 |  |  | Through sharing of dedicated transmission system of M/s Green Infra Clean Solar Farms Limited (App. No. 2200000408-130 MW)– Barmer-II PS 220 kV S/c line on D/c tower (suitable to carry minimum 310 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-70C46 |  |  | 400 kV Bikaner-V – Bikaner-VI D/c line(Quad) | [24 empty] | CMETS meeting(s): 38
| EL-71ABE |  |  | Augmentation of 1x500MVA (9th) 400/220 kV ICT at Bikaner –II PS | [24 empty] | CMETS meeting(s): 34
| EL-71BF9 |  |  | 4 GW (Solar) Bikaner-IV : 2.4GW Scheme planned for 2026-27 time frame (EHVAC)- Present proposal 2 Rajasthan REZ Ph-IV (Part- 4 :3.5GW) (Jaisalmer/Barmer Complex) | [24 empty] | CMETS meeting(s): 27
| EL-724C2 |  |  | HR Saraswati Energy Private Limited Solar Power Project – Sanchore PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-72545 |  |  | Adani Renewable Energy Holding Four Limited Solar Power Project – Bhadla-IV PS 400 kV S/c line on D/c tower(Suitable to carry minimum 900 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-72571 |  |  | Establishment of 400/220 kV, 5x500 MVA S/s at suitable location near Merta (Merta-III Substation) along with 2x125 MVAr bus reactor | [24 empty] | CMETS meeting(s): 34, 35, 39
| EL-7263A |  |  | Common Pooling Station for Acme Cleantech Solutions Pvt Ltd. (App. No. 2200000387(600 MW), 2200000396(250 MW) & 22000001065(150MW)) Solar Power Projects– Fatehgarh-II PS 400 kV S/c line on D/c tower (suitable to carry minimum 1000 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 34
| EL-733B4 |  |  | Juniper Green Energy Private Limited Hybrid Power Project – Barmer-II PS 220 kV S/c line on D/c tower(Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-73496 |  |  | Establishment of 5x1500 MVA 765/400 kV Robertsganj Pooling Station near Robertsganj area in Sonbhadra distt. Uttar Pradesh | [24 empty] | CMETS meeting(s): 31, 35
| EL-73A05 |  |  | Establishment of 6000 MW, Sirohi(HVDC) terminal station (4x1500 MW) at a suitable location near Sirohi(HVDC) PS | [24 empty] | CMETS meeting(s): 33, 34, 38, 39
| EL-73F58 |  |  | STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV line bays at Bikaner-IV PS | [24 empty] | CMETS meeting(s): 25
| EL-7448F |  |  | 400/220kV, 5x500 MVA ICTs at Barmer-IV PS | [24 empty] | CMETS meeting(s): 38, 39
| EL-74588 |  |  | Common Pooling Station for Renew Solar (Shakti Six) Private Limited (App. No. 120003848(550 MW), 0312100004(450 MW) & 2200000275(400 MW)) – Bhadla-III PS 400 kV D/c line (Suitable to carry minimum 900 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 27
| EL-745F8 |  |  | Begunia – Paradeep (ISTS) 765kV D/c line along with associated bays at both ends | [24 empty] | CMETS meeting(s): 31, 33, 34, 35, 36, 38, 39
| EL-74937 |  |  | Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | [24 empty] | CMETS meeting(s): 25, 27, 31, 33, 36, 39
| EL-75464 |  |  | Establishment of 400/220 kV, 5x500 MVA S/s at suitable location near Pali (Pali PS) along with 2x125 MVAr bus reactor | [24 empty] | CMETS meeting(s): 34
| EL-75882 |  |  | ±800 kV HVDC line between Bhadla-V (HVDC) & Suitable location in WR/ER (with Dedicated Metallic Return) | [24 empty] | CMETS meeting(s): 37, 38, 39
| EL-759C3 |  |  | 1 no. of 400 KV bay at Sanchore PS end - Under the scope of ISTS | [24 empty] | CMETS meeting(s): 39
| EL-75F9E |  |  | Establishment of 765/400kV, 5x1500 MVA S/s substation station at Begunia along with 2x125 MVAr & 2x240 MVAr bus reactor | [24 empty] | CMETS meeting(s): 31, 33, 34, 35, 36, 38, 39
| EL-7782E |  |  | Common Pooling Station for JSW Neo Energy Limited Solar Power Projects (App. No. 220000706(700 MW), App. No. 2200000689(700 MW) & | [24 empty] | CMETS meeting(s): 33
| EL-77A48 |  |  | Common Pooling Station for Waaree Forever Energies Private Limited RE Power Projects(App. No. 2200002066-200 MW, App. No. 2200002071-300 MW & , App. No. 2200002072-200 MW) – Bhadla-V PS 400 kV S/c line on D/c tower (suitable to carry minimum 900 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-77D24 |  |  | 5x500 MVA, 400/220kV ICTs at Jalore PS | [24 empty] | CMETS meeting(s): 33, 34, 38
| EL-7A0CC |  |  | Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) S Additional Transmission system for inter-regional power transfer | [24 empty] | CMETS meeting(s): 34
| EL-7A64F |  |  | Reliance Nu Energies Private Limited RE Power Project – Sanchore PS 220 kV S/c line on D/c tower (suitable to carry minimum 350 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-7B4A8 |  |  | Bikaner-II PS – Khetri 400 kV 2xD/c line (Twin HTLS* on M/c Tower) | [24 empty] | CMETS meeting(s): 14, 15, 17
| EL-7B912 |  |  | Common pooling station of M/s Juniper Green Beta Private Limited Solar power projects of 300 MW (0212100027(150 MW), 0312100013 (40 MW), SW…1670400777119(70 MW) & 312100021(40 MW)) –Bhadla-III PS 220 kV S/c (high capacity) line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 23
| EL-7BBDE |  |  | 400/220kV, 4x500 MVA ICTs at Bhadla-IV PS | [24 empty] | CMETS meeting(s): 31, 33, 34
| EL-7BD8D |  |  | 1 no. of 220 kV bay at Bhadla-VI PS end – Under the scope of ISTS Scope | [24 empty] | CMETS meeting(s): 39
| EL-7BE5E |  |  | 23, applicability of N-1 criteria to the immediate connectivity system of Pump storage Projects with Grid was deliberated and it was decided that N-1 criterion would be applicable on to the immediate connectivity system for Pump storage Projects. 765/400kV Varanasi (PG) substation is existing substation and is about 70 kms from project locations as per the coordinates provided in the application. POWERGRID vide mail | [24 empty] | CMETS meeting(s): 25
| EL-7BEC7 |  |  | 3° N-1 of 765 kV Jalore – Rishabdeo D/C line | [24 empty] | CMETS meeting(s): 18
| EL-7C392 |  |  | Common pooling station for NTPC Renewable Energy Limited Solar Power Projects (App No. 2200000244(150 MW), 2200000373(400 MW) & 2200000373(400 MW) & | [24 empty] | CMETS meeting(s): 27
| EL-7C445 |  |  | 3 Transmission System for Rajasthan REZ Phase-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex) | [24 empty] | CMETS meeting(s): 18
| EL-7C9B8 |  |  | LILO of 765 kV Fatehpur-Varanasi S/c line at Prayagraj S/s | [24 empty] | CMETS meeting(s): 31, 35
| EL-7DADA |  |  | 2x330 MVAr bus reactors at 765kV level at Sikar -II | [24 empty] | CMETS meeting(s): 16
| EL-7E7E2 |  |  | Sirohi(HVDC) PS – Bhinmal(PG) 400 kV D/c line(Quad) | [24 empty] | CMETS meeting(s): 33, 38, 39
| EL-7ECBC |  |  | ±800 kV HVDC line (Hexa lapwing) between Merta-II (HVDC) & Baripada (HVDC) (with Dedicated Metallic Return) | [24 empty] | CMETS meeting(s): 27
| EL-7F1CE |  |  | Common Pooling station for Avaada Energy Private Limited RE Power Projects (App. No. 22000001352 – 750 MW & App. No. 22000001422– 800 MW) – Barmer-III PS 400 kV D/c line (suitable to carry minimum 900 MW per circuit at nominal voltage) along with associated bays at generation end | [24 empty] | CMETS meeting(s): 37
| EL-7F39F |  |  | Illuminate Hybren Private Limited Solar Power Project– Sirohi PS 220 kV S/c line on D/c tower(Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-80081 |  |  | Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) | [24 empty] | CMETS meeting(s): 27, 31, 33, 36, 39
| EL-80AC0 |  |  | 1 no. of 400 kV bay at Bhadla-V PS end shall be under the scope of ISTS | [24 empty] | CMETS meeting(s): 38
| EL-80AE9 |  |  | Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Sikar (Sikar-II Substation) with 1x125 MVAr at 400kV level & 2x330 MVAr bus reactors at 765kV level at Sikar -II | [24 empty] | CMETS meeting(s): 16, 31, 36
| EL-81053 |  |  | Enfinity Global Surya Kiran Private Limited Renewable Power Park– Barmer-I PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-81BDC |  |  | 4 517.2 1 Transmission System for Rajasthan REZ Phase-IV (Part-3: 3.6 GW) (Bikaner Complex) Outage of one ckt of 765 kV Bikaner-IV-Churu D/c line June Solar Max Scenario x | [24 empty] | CMETS meeting(s): 25
| EL-81C54 |  |  | 1x500 MVA (2nd), 400/220 kV & 2x1500 MVA (1st & 2nd) 765/400kV pooling station at Bhadla-III along with 2x330 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor | [24 empty] | CMETS meeting(s): 23
| EL-82D7A |  |  | 400 kV D/c line | [24 empty] | CMETS meeting(s): 35
| EL-82E5F |  |  | Additional Transmission system for Inter-regional power transfer | [24 empty] | CMETS meeting(s): 25, 27
| EL-82F00 |  |  | LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror – Fatehpur line | [24 empty] | CMETS meeting(s): 27, 33
| EL-836ED |  |  | 2x1500 MVA (2nd & 3rd), 765/400 kV ICTs at Barmer-I Pooling Station | [24 empty] | CMETS meeting(s): 25
| EL-83715 |  |  | Diyos Three Renewables Private Limited Renewable Power Park – Pali PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 34
| EL-83858 |  |  | 400kV Sectionalizer bay (1 set) at at Siwani S/s B. Additional Transmission system for Inter-regional power transfer | [24 empty] | CMETS meeting(s): 27
| EL-84062 |  |  | Jaisalmer (RVPN) S/s - Fatehgarh-III PS (Twin HTLS) D/c line | [24 empty] | CMETS meeting(s): 16
| EL-844B3 |  |  | Migos Hybren Private Limited Solar Power Project –– Ramgarh PS 220 kV D/c line (Suitable to carry minimum 300 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-84756 |  |  | Shudh Solar Power Private Limited Solar Power Project– Bikaner-IV PS 220 kV S/c line on D/c tower(Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 27
| EL-84DBB |  |  | 1 no. of 400 kV bay at Barmer-IV PS end shall be under the scope of ISTS | [24 empty] | CMETS meeting(s): 38
| EL-85255 |  |  | LILO of both ckts of 400kV Bikaner-II PS- Khetri D/c line at Bikaner-V PS | [24 empty] | CMETS meeting(s): 31, 33, 34, 35, 36, 38, 39
| EL-85879 |  |  | Jindal India RE Limited RE Power Project – Bikaner-VI PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 38
| EL-85CFA |  |  | Infrastructure required for sharing dedicated transmission system – Under the scope of M/s Adyant Enersol Private Limited | [24 empty] | CMETS meeting(s): 38
| EL-85FD1 |  |  | 2 no. of 400 kV bays at Bhadla-V PS end Under the scope of ISTS | [24 empty] | CMETS meeting(s): 39
| EL-860DB |  |  | Jalore PS – Sirohi(HVDC) PS (Sirohi-II) 400 kV 2xD/c line(Quad) | [24 empty] | CMETS meeting(s): 34
| EL-86667 |  |  | 1 no. of 220 kV bay at Pali PS end - Under the scope of ISTS | [24 empty] | CMETS meeting(s): 39
| EL-88DFA |  |  | Establishment of 6000 MW, ± 800 kV Bhadla-VI (HVDC) terminal station (4x1500 MW) at suitable location near Bhadla | [24 empty] | CMETS meeting(s): 39
| EL-894BD |  |  | Through sharing of dedicated transmission system of M/s Renew Solar Power Private Limited(App. No | [24 empty] | CMETS meeting(s): 33
| EL-8995D |  |  | Common Pooling station of M/s Solarcraft Power India 4 Private Limited for Solar Power Projects with Appl. Nos.2200000152 (150 MW) & 2200000192 (110 MW) – Bhadla-III PS 220 kV S/c line on D/c towers(Suitable to carry minimum 310 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 25
| EL-89B68 |  |  | Waaree Forever Energies Private Limited RE Power Project– Ramgarh-II PS 400 kV S/c line on D/c tower (Suitable to carry minimum 900 MW at nominal voltage) along with associated bay at generation end | [24 empty] | CMETS meeting(s): 38
| EL-89EA0 |  |  | M/s TEQ Green Power XV Private Limited Renewable Power Park – Pali PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 34
| EL-8A87E |  |  | NTPC Renewable Energy Limited Solar Power Project– Bikaner-V PS 400 kV S/c line on D/c tower (Suitable to carry minimum 1000 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-8ACC2 |  |  | Common Pooling Station for Renew Solar Power Private Limited Solar Power Projects (App. No. 2200000850(300 MW), | [24 empty] | CMETS meeting(s): 33
| EL-8B247 |  |  | 400kV Sectionalizer bay (1 set) at Bikaner-IV PS Minutes for 27th Consultation meeting for Evolving Transmission Schemes in NR 83 | [24 empty] | CMETS meeting(s): 27
| EL-8B314 |  |  | Common Pooling Station of M/s Unique Hytech Renewable Energy Private Limited REPower Projects (App. No. 2200001407 -150 MW & App. No. 2200001622 – 1000 MW) – Barmer-III PS 400 kV S/c line on D/c tower (suitable to carry minimum 1150 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 37
| EL-8B84F |  |  | Bhadla-II PS – Sikar-II 765kV 2xD/c line | [24 empty] | CMETS meeting(s): 36
| EL-8CDC3 |  |  | A. Associated Transmission System (ATS): NIL B. Transmission System under applicant scope | [24 empty] | CMETS meeting(s): 34
| EL-8D20D |  |  | Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | [24 empty] | CMETS meeting(s): 25
| EL-8D787 |  |  | 765 kV Bhadla-V – Bikaner-VI D/c line | [24 empty] | CMETS meeting(s): 38
| EL-8E167 |  |  | Juniper Green Energy Private Limited Solar Power Project– Barmer-I PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 27
| EL-8F19A |  |  | Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors | [24 empty] | CMETS meeting(s): 25, 27, 31, 33, 34, 36, 39
| EL-8F215 |  |  | Siwani – Jind (PG) 400 kV D/c line (Quad) | [24 empty] | CMETS meeting(s): 27, 31
| EL-8FDAD |  |  | Establishment of 6000 MW, ± 800 kV Merta (HVDC) [LCC] terminal station (4x1500 MW) in Merta-II substation | [24 empty] | CMETS meeting(s): 27
| EL-905E4 |  |  | Begunia – Khuntuni (OPTCL) 765kV D/c line | [24 empty] | CMETS meeting(s): 31, 34, 35, 38, 39
| EL-90627 |  |  | Switchyard Capacity must be able to handle about 2400MW power generated by the generation projects located in downstream of the Kiru HEP. GIS switchyard equipment and XLPE cables provided may be designed for carrying 4000 Amps current | [24 empty] | CMETS meeting(s): 31
| EL-90BC8 |  |  | Common pooling station for NTPC Renewable Energy Limited Solar Power Projects (App No. 2200000244(150 MW) , 2200000308(700 MW), 2200000308(700 MW), 2200000308(700 MW), 2200000308(700 MW), | [24 empty] | CMETS meeting(s): 27
| EL-90D75 |  |  | Jalore PS – Sirohi(HVDC) PS 400 kV 2xD/c line(Quad) | [24 empty] | CMETS meeting(s): 33, 38
| EL-90F2A |  |  | Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation | [24 empty] | CMETS meeting(s): 25, 27, 31, 33, 38
| EL-911E3 |  |  | Establishment of 6000 MW, ± 800 kV Bhadla-V (HVDC) terminal station (4x1500 MW) at suitable location near Bhadla | [24 empty] | CMETS meeting(s): 37, 38, 39
| EL-91598 |  |  | Avaada RJBikaner Private Limited Solar Power Project – Bikaner-V PS 220 kV S/c line on D/c tower(Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-91FDC |  |  | 2 Transmission System for Rajasthan REZ Phase-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex) | [24 empty] | CMETS meeting(s): 18
| EL-92100 |  |  | LILO of Pune-III – Boisar-II 765kV D/c line at South Kalamb with associated bays at South Kalamb S/s | [24 empty] | CMETS meeting(s): 31, 33, 35
| EL-923E9 |  |  | Augmentation of 2x1500 MVA(3rd & 4th), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station | [24 empty] | CMETS meeting(s): 25
| EL-9267B |  |  | Bhadla-IV PS – Bhadla-III PS 400kV D/c line (Quad) | [24 empty] | CMETS meeting(s): 31, 33, 34, 35, 36
| EL-9275B |  |  | Augmentation with 765/400kV, 2x1500MVA Transformer (5th & 6th) at Fatehgarh-II PS | [24 empty] | CMETS meeting(s): 16
| EL-92873 |  |  | Bundelkhand Saur Urja Limited Renewable Power Park– Orai(PG) 400 kV S/c (high capacity) line on D/c tower (Suitable to carry minimum 1200 MW per circuit at nominal voltage) B. Transmission system for Connectivity under GNA: Existing system beyond 400 kV Orai (PG) S/s (GIS) | [24 empty] | CMETS meeting(s): 27
| EL-93482 |  |  | 0 1 Outage of one ckt of 765 kV Fatehgarh-IV-Jalore D/c line June Solar Max Scenario | [24 empty] | CMETS meeting(s): 18
| EL-938A3 |  |  | 1x330 MVAr Switchable line reactor for each circuit at Narela end of Khetri – Narela 765kV D/c line | [24 empty] | CMETS meeting(s): 14, 15, 16, 17, 36
| EL-94DEC |  |  | Augmentation of 2x1500 MVA, 765/400 kV ICT (4th & 5th) at Bhadla-II Pooling station | [24 empty] | CMETS meeting(s): 31
| EL-94ECD |  |  | 1 no. of 220 kV bay at Barmer-IV PS end shall be under the scope of ISTS | [24 empty] | CMETS meeting(s): 38
| EL-95044 |  |  | Tata Power Renewable Energy Limited RE Power Project – Ramgarh-II PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end | [24 empty] | CMETS meeting(s): 37
| EL-951CC |  |  | 2024 41 ¦ P a g e * with minimum capacity of 2100 MVA/ckt at nominal voltage Additional Transmission system for Inter-regional power transfer | [24 empty] | CMETS meeting(s): 31
| EL-95995 |  |  | 400/220kV, 2x500 MVA ICTs (2nd & 3rd ) at Ramgarh PS | [24 empty] | CMETS meeting(s): 33
| EL-95C39 |  |  | Adani Renewable Energy Holding Twelve Limited RE Power Project – Sanchore PS 400 kV S/c line on D/c tower (suitable to carry minimum 900 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-95D93 |  |  | Augmentation of 2x1500 MVA (3rd & 4th),765/400 kV ICTs at Neemrana-II S/s | [24 empty] | CMETS meeting(s): 23, 33, 34
| EL-96B8C |  |  | Reconductoring of 400 kV Jodhpur (Surpura)(RVPN) – Kankroli S/c (twin moose) line with twin HTLS conductor*-188 km # with necessary arrangement for bypassing Kankroli- Zerda line at Bhinmal with suitable switching equipment inside the Bhinmal substation. * with minimum capacity of 1940 MVA/ckt at nominal voltage; Upgradation of existing 400kV bay equipments each at Jodhpur (Surpura)(RVPN) and Kankroli S/s(3150 A) | [24 empty] | CMETS meeting(s): 14, 15, 16, 17, 22
| EL-97075 |  |  | Existing system beyond 400 kV Shree Cement generation switchyard Start Date of Connectivity | [24 empty] | CMETS meeting(s): 31
| EL-970EB |  |  | M/s Terra Clean Limited RE Power Project – Pali PS 220 kV S/c line (suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-97F77 |  |  | Augmentation of 2x1500 MVA (3rd & 4th), 765/400kV ICTs at Bhadla-III PS | [24 empty] | CMETS meeting(s): 27
| EL-9864E |  |  | 5GW (Solar) Fatehgarh-IV: 4 GW Barmer-I: 1.5 GW 2 Rajasthan REZ Ph-IV (Part-4:3.5GW) (Jaisalmer/Barmer Complex) EHVAC system-Present proposal | [24 empty] | CMETS meeting(s): 27
| EL-988D2 |  |  | STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani S/s Minutes for 27th Consultation meeting for Evolving Transmission Schemes in NR 76 | [24 empty] | CMETS meeting(s): 27
| EL-98D24 |  |  | Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) tart Date of Connectivity under GNA: 31-12-2025 | [24 empty] | CMETS meeting(s): 34
| EL-98DE8 |  |  | Common Pooling Station for M/s Adani Renewable Energy Holding Twelve Limited RE Power Projects (App. No. 2200001907 :520 MW & App. No. 2200001908 :303.33 MW) – Barmer-IV PS 400 kV S/c line on D/c tower (suitable to carry minimum 1004 MW at nominal voltage) along with associated bay at generation end - - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-98E67 |  |  | Barmer-II PS- Barmer-I PS 400kV D/c line (Quad)(20km) | [24 empty] | CMETS meeting(s): 33, 35
| EL-9915B |  |  | Vismaya Four Renewables Private Limited RE Power Project – Bhadla-V PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 38
| EL-9AAB9 |  |  | LILO of both ckts of 400kV Barmer-I PS – Barmer-II PS D/c line (Quad) at Barmer-III PS | [24 empty] | CMETS meeting(s): 33, 34, 35, 36, 37
| EL-9ADBC |  |  | Common Pooling Station for Adani Renewable Energy Park Rajasthan Limited RE Power Parks (App. No. 2200000600-1000 MW & | [24 empty] | CMETS meeting(s): 33
| EL-9AF8D |  |  | Common Pooling station for Kantida Renewables India Project Private Limited RE Power Park(App. No. 2200000761- 300 MW) & Vismaya Four Renewables Ptivate Limited Solar Power Project (App. No. 2200000910- 250 MW) – Bhadla-IV PS 400 kV S/c line on D/c tower (suitable to carry minimum 900 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-9BFCD |  |  | 1 no. of 220 kV bay at Bhadla-V PS end shall be under the scope of ISTS | [24 empty] | CMETS meeting(s): 38
| EL-9C16A |  |  | Common Pooling Station of Renew Solar Power Private Limited RE Power Projects (App. No. 2200001026-200 MW, App. No 2200001188-250 MW & App. No. 2200001503-300 MW) – Barmer-III PS 400 kV S/c line on D/c tower (suitable to carry minimum 900 MW at nominal voltage) along with associated bay at generation end | [24 empty] | CMETS meeting(s): 37
| EL-9C614 |  |  | 1 no of 400 kV bay at Barmer-IV PS shall be under the scope of ISTS | [24 empty] | CMETS meeting(s): 38
| EL-9D040 |  |  | STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR Additional Scheme to relieve overloading of 400 kV Bhinmal-Zerda line (Twin Moose) | [24 empty] | CMETS meeting(s): 14, 16, 22
| EL-9D405 |  |  | 2 no. of 400 kV bays at Ramgarh-III PS end - Under the scope of ISTS | [24 empty] | CMETS meeting(s): 39
| EL-9D5D3 |  |  | Acme Solar Holdings Limited Solar Power Project– Merta-II PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-9D9D5 |  |  | 1 no. of 220 kV bay at Barmer-I PS - Under the scope of ISTS | [24 empty] | CMETS meeting(s): 39
| EL-9EA33 |  |  | Infrastructure required for sharing dedicated transmission system – under the scope of M/s Hexa Climate Solutions Pvt. Ltd | [24 empty] | CMETS meeting(s): 36
| EL-9EFA0 |  |  | Renew Solar Power Private Limited Solar Power Project– Sirohi PS 220 kV S/c (high capacity) line on D/c tower (suitable to carry minimum 400 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-9FCD4 |  |  | 1x80MVAr switchable Line reactor on each circuit at Khetri end of Bikaner-II – Khetri 400 kV 2xD/c Line | [24 empty] | CMETS meeting(s): 14, 15, 17
| EL-9FD2A |  |  | Common Pooling Station for Sembcorp Green Infra Private Limited Solar Power Projects (App. No. 2200000812:300 MW & 2200000813:300 MW)– Merta-II PS 220 kV D/c line (Suitable to carry minimum 300 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-A0BD5 |  |  | 420 kV bus Reactor | [24 empty] | CMETS meeting(s): 39
| EL-A0D4D |  |  | Apraava Energy Private Limited Solar Power Project – Barmer-II PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-A10F2 |  |  | Deshraj Solar Energy Private Limited – Bikaner-IV PS 220 kV S/c line on D/c towers (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 25
| EL-A1757 |  |  | Common pooling station for Sprng Renewable Resources Private Limited(App. No. 2200000531(200 MW) & Sprng Urja Private Limited(App. No. 2200000539(200 MW) Solar Power Projects– Barmer-II PS 220 kV S/c (high capacity) line on D/c tower (Suitable to carry minimum 400 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-A1D4E |  |  | Establishment of 6000 MW, HVDC terminal station (4x1500 MW) at suitable location in WR/SR/ER | [24 empty] | CMETS meeting(s): 33, 34, 35, 36, 37, 38, 39
| EL-A1F2C |  |  | Bikaner-IV PS – Churu 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Bikaner-IV PS end | [24 empty] | CMETS meeting(s): 25
| EL-A1FDB |  |  | 1 no. of 220 kV bay at Ramgarh-III PS end - Under the scope of ISTS | [24 empty] | CMETS meeting(s): 39
| EL-A2220 |  |  | Sirohi(HVDC) PS (Sirohi-II) – Bhinmal(PG) 400 kV D/c line(Quad) | [24 empty] | CMETS meeting(s): 34
| EL-A331D |  |  | Begunia – Khuntuni (OPTCL) 765kV D/c line Additional system for connectvity at 220kV level only of Bikaner-V PS | [24 empty] | CMETS meeting(s): 33
| EL-A475F |  |  | Siwani – Jind (PG) 400 kV D/c line (Quad Moose) | [24 empty] | CMETS meeting(s): 25
| EL-A495D |  |  | LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha | [24 empty] | CMETS meeting(s): 25, 27, 31, 33, 36, 39
| EL-A4C5F |  |  | ±800 kV HVDC line between Bhadla-IV (HVDC) & Suitable location in WR/ER (with Dedicated Metallic Return) | [24 empty] | CMETS meeting(s): 31, 33, 34, 35, 36
| EL-A4E7D |  |  | Associated transmission system in WR/ER/SR for onwards dispersal of power | [24 empty] | CMETS meeting(s): 39
| EL-A50EC |  |  | 1 no. of 220 kV bay at Merta-III PS end - Under the scope of ISTS | [24 empty] | CMETS meeting(s): 39
| EL-A5BEB |  |  | Establishment of 400 kV Sirohi(HVDC) PS at a suitable location near Sirohi | [24 empty] | CMETS meeting(s): 33, 34, 38, 39
| EL-A5E2F |  |  | Through sharing of dedicated transmission of M/s TEQ Green Power IX Ltd. RE Power Project – Barmer-III PS 220 kV S/c line (suitable to carry minimum | [24 empty] | CMETS meeting(s): 36
| EL-A63E4 |  |  | Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end | [24 empty] | CMETS meeting(s): 15, 25
| EL-A658A |  |  | 1 no of 400 kV bay at Bhadla-V PS shall be under the scope of ISTS | [24 empty] | CMETS meeting(s): 38
| EL-A6870 |  |  | Demeter Sun Power Private Limited Solar Power Project – Bhadla-IV PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-A6A24 |  |  | Establishment of 5x500 MVA, 400/220kV S/s at a suitable location near Sirohi(HVDC) PS (Sirohi-II) | [24 empty] | CMETS meeting(s): 34
| EL-A6B39 |  |  | Hazel Hybren Private Limited Solar Power Project– Bikaner-IV PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) A | [24 empty] | CMETS meeting(s): 27
| EL-A6B97 |  |  | 400/220kV, 3x500 MVA ICTs at Ramgarh-II PS | [24 empty] | CMETS meeting(s): 33, 34, 35, 36, 37
| EL-A6DAA |  |  | Acme Gamma Urja Private Limited RE Power Project – Barmer-III PS 220 kV S/c line on D/c tower (suitable to carry minimum 350 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 36
| EL-A7A85 |  |  | 1x500 MVA (1st) 400/220 kV ICT at Bhadla-III PS B. Common Transmission system (Part of Transmission system associated with SEZ in Rajasthan under Phase-III (20 GW) scheme) | [24 empty] | CMETS meeting(s): 16
| EL-A7D91 |  |  | Radiant Star Solar Park Private Limited – Barmer-I PS 220 kV S/c line on D/c towers (Suitable to carry minimum 300 MW at nominal voltage) Minutes for 25th Consultation meeting for Evolving Transmission Schemes in NR 19 1B) Conventional Applications received in month of Aug’23 for Connectivity to ISTS | [24 empty] | CMETS meeting(s): 25
| EL-A83CD |  |  | Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line | [24 empty] | CMETS meeting(s): 25, 27, 31, 33, 36, 39
| EL-A856A |  |  | LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS | [24 empty] | CMETS meeting(s): 27, 31
| EL-A8719 |  |  | 2024 to CTU also requested to review the requirement of additional ICTs at some of the substations (including Maharani Bagh S/s) of Northern region due to non-compliance of N-1 contingency. In the letter POWERGRID stated that, it has been observed that ICTs in few of the substations in Northern region are having high utilization and violating N-1 contingency criteria. POWERGRID highlighted that from the loading data at Maharani Bagh S/s (April-June | [24 empty] | CMETS meeting(s): 35
| EL-A9814 |  |  | Bhadla-IV PS – Bhadla-V PS 400kV D/c line (Quad) | [24 empty] | CMETS meeting(s): 37, 38, 39
| EL-A9AB8 |  |  | LILO of 765 kV Fatehpur-Sasaram S/c line at Prayagraj S/s | [24 empty] | CMETS meeting(s): 31, 35
| EL-AA42A |  |  | Common Pooling station for Vismaya Five Renewables Private Limited Solar Power Projects (App. No. 2200000954- 250 MW & App. No. 2200001285-50MW) – Barmer-II PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 35
| EL-AA42F |  |  | Juniper Green Energy Private Limited Hybrid Power Project – Ramgarh-II PS 220 kV S/c line on D/c tower (Suitable to carry minimum 360 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-AA65C |  |  | 1 Transmission System for Rajasthan REZ Phase-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex) | [24 empty] | CMETS meeting(s): 18
| EL-AA9CE |  |  | Common Pooling Station for Renew Solar (Shakti Six) Private Limited (App. No. 120003848(550 MW), 0312100004(450 MW), 2200000309(400 MW)) Solar power projects – Bhadla-III PS 400 kV D/c line (Suitable to carry minimum 900 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 27
| EL-AAE2C |  |  | Establishment of 765/400 kV 2x1500 MVA Prayagraj substation near Prayagraj(Uttar Pradesh) | [24 empty] | CMETS meeting(s): 31, 35
| EL-AB6F6 |  |  | Augmentation of 5x500 MVA (5th to 9th), 400/220 kV ICTs at Barmer-I PS | [24 empty] | CMETS meeting(s): 27, 31, 36, 39
| EL-ACF06 |  |  | Termination of another circuit of 400 kV Samba -Jalandhar D/c line (Quad) at Jalandhar at bay vacated at Jalandhar (After bypassing of one ckt of 400 kV Jalandhar - Nakodar at Jalandhar) | [24 empty] | CMETS meeting(s): 38
| EL-AD046 |  |  | Fatehgarh-II PS – Fatehgarh-III PS 400 kV (Twin HTLS) D/c line | [24 empty] | CMETS meeting(s): 16
| EL-AD084 |  |  | LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS | [24 empty] | CMETS meeting(s): 31, 33, 35
| EL-ADC60 |  |  | Augmentation with 765/400kV, 2x1500 MVA Transformer (6th & 7th) at Fatehgarh-II PS | [24 empty] | CMETS meeting(s): 31, 34
| EL-AE2D7 |  |  | Establishment of 6000 MW, ± 800 kV South Kalamb S/s (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) | [24 empty] | CMETS meeting(s): 31, 33, 35
| EL-AE30F |  |  | 1x240 MVAr Switchable line reactor for each circuit at Bhadla-II end of Bhadla-II – Sikar-II 765kV D/c line | [24 empty] | CMETS meeting(s): 16, 36
| EL-AE35C |  |  | Through sharing of dedicated transmission system of M/s Azure Power India Pvt. Ltd (650 MW) – Bhadla-II PS 400 kV S/c line (Suitable to carry minimum 1000 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-AE530 |  |  | Augmentation of 1x500MVA (2nd) 400/220 kV ICT at Bikaner –II PS B. Common Transmission system (Part of Transmission system associated with SEZ in Rajasthan under 8.1 GW Phase-II scheme) | [24 empty] | CMETS meeting(s): 14
| EL-AEB5A |  |  | Establishment of 400kV at suitable location near Pali (Pali PS) along with 2x125 MVAr bus reactor | [24 empty] | CMETS meeting(s): 38
| EL-B075D |  |  | Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) | [24 empty] | CMETS meeting(s): 23, 27, 33, 34
| EL-B0DFF |  |  | Common Pooling Station for Purvah Green Power Private Limited Solar Power Projects (App. No. 2200001261 – 300 MW & | [24 empty] | CMETS meeting(s): 35
| EL-B1EED |  |  | 400kV Barmer-II PS – Barmer-IV PS D/c line (Quad) | [24 empty] | CMETS meeting(s): 38, 39
| EL-B2C6A |  |  | 7 1 Feb Solar Max Scenario Outage of one ckt of 400 kV RAPS-Sujalpur D/c line | [24 empty] | CMETS meeting(s): 18
| EL-B2D1F |  |  | Avaada Energy Private Limited RE Power Project – Bhadla-V PS 400 kV S/c line on D/c tower (suitable to carry minimum 1000 MW at nominal voltage) along with associated bay at generation end | [24 empty] | CMETS meeting(s): 37
| EL-B359D |  |  | 8 517.9 1 Transmission System for Rajasthan REZ Phase-IV (Part-3: 3.6 GW) (Bikaner Complex) Outage of one ckt of 765 kV Churu-Siwani D/c line June Solar Max Scenario x | [24 empty] | CMETS meeting(s): 25
| EL-B3765 |  |  | Establishment of 1x500 MVA (1st), 400/220 kV & 2x1500 MVA (1st & 2nd) 765/400kV pooling station at Bhadla-III along with 2x330 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor | [24 empty] | CMETS meeting(s): 23
| EL-B3E52 |  |  | Auxo Sunlight Private Limited Solar Power Project – Barmer-I PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 27
| EL-B3FD0 |  |  | Bhadla-II PS – Sikar-II 765kV D/c line | [24 empty] | CMETS meeting(s): 16
| EL-B4A45 |  |  | 400/220kV, 2x500 MVA ICTs at Bhadla-V PS | [24 empty] | CMETS meeting(s): 38
| EL-B5782 |  |  | Establishment of 2x1500 MVA, 765/400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor | [24 empty] | CMETS meeting(s): 16
| EL-B5AA8 |  |  | 400/220kV 5x500MVA ICTs at Barmer-III PS (for connectivity agreed for grant at 220kV level) | [24 empty] | CMETS meeting(s): 36
| EL-B5B2D |  |  | 2 no of line bays at Narela each for Maharanibagh – Narela 400 kV D/c (Quad) and Maharanibagh –Gopalpur**-Narela 400 kV D/c (Quad) lines formed after removal of LILO of Bawana – Mandola 400kV D/c(Quad) line at Maharani Bagh/Gopalpur S/s and Extension of above LILO section from Maharani Bagh/Gopalpur upto Narela S/s. *with minimum capacity of 2100 MVA on each circuit at nominal voltage Additional Scheme to relieve overloading of 400 kV Bhinmal-Zerda line (Twin Moose) | [24 empty] | CMETS meeting(s): 16
| EL-B5F9A |  |  | Common Pooling Station for Adani Renewable Energy Park Rajasthan Limited RE Power Parks (App. No. 2200000600-1000 MW & 2200000601- 1000 MW) – Ramgarh-II PS 400 kV D/c line (Suitable to carry minimum 1000 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-B6A41 |  |  | Sprng Vaayu Urja Private Limited Solar Power Project – Jalore PS 220 kV D/c line (Suitable to carry minimum 300 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-B6C33 |  |  | Establishment of 1x500 MVA 400/220 kV Fatehgarh- IV (Section-2) Pooling Station B. Common Transmission system (Part of Transmission system associated with SEZ in Rajasthan under Phase-III (20 GW) scheme) | [24 empty] | CMETS meeting(s): 15
| EL-B73B1 |  |  | Augmentation of 2x1500 MVA (1st & 2nd), 765/400kV ICT at Fatehgarh-3 pooling station (Section-II) | [24 empty] | CMETS meeting(s): 22
| EL-B8BAA |  |  | Infrastructure required for sharing dedicated transmission system - under the scope of M/s Adani Renewable Energy Holding Eighteen Limited | [24 empty] | CMETS meeting(s): 34
| EL-B8CEB |  |  | Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) | [24 empty] | CMETS meeting(s): 16, 25, 27, 31, 33, 38
| EL-B9274 |  |  | Green Infra Clean Solar Farms Limited Solar Power Project – Barmer-II PS 220 kV S/c line (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-B96FE |  |  | Establishment of 6000 MW, Bikaner-VI(HVDC) terminal station (4x1500 MW) at a suitable location near Bikaner-VI PS | [24 empty] | CMETS meeting(s): 38
| EL-B97CE |  |  | Common Pooling Station for Renew Solar Power Private Solar Power Projects (App. No. 2200000850(300 MW), 2200000886(100 MW), 2200000887(200 MW), 2200000888(200 MW) 2200000889(100 MW), 2200000890(100 MW)) – Jalore PS 400 kV S/c line on D/c tower (Suitable to carry minimum 1000 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-B9C26 |  |  | Torrent Green Energy Private Limited RE Power Project – Bhadla-V PS 400 kV S/c line on D/c tower (suitable to carry minimum 1000 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 38
| EL-BA03C |  |  | NTPC Renewable Energy Limited Solar Power Project– Fatehgarh-IV PS(Sec-II) 400 kV S/c line on D/c tower (Suitable to carry minimum 900 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 27
| EL-BBDA4 |  |  | Common Pooling station for NTPC Renewable Energy Limited Solar Power Projects ( 2200000567(300MW) & 2200000567(300MW) & 2200000567(300MW) & | [24 empty] | CMETS meeting(s): 33
| EL-BBDD5 |  |  | Common pooling station for NTPC Renewable Energy Limited Solar Power Projects (App No. 2200000244(150 MW) , 2200000308(700 MW), 2200000373(400 MW) & 2200000358(250 MW) – Bikaner-IV PS 400 kV D/c line (Suitable to carry minimum 900 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 27
| EL-BC07B |  |  | Common Pooling station for Foxtrot Solar Renewables Energy Private Limited Solar Power Projects (App. No. 22000001057 – 100 MW & 2200001088 – 80 MW & App. No. 2200001252-74 MW) – Barmer-III PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 35
| EL-BC130 |  |  | Juniper Green Energy Private Limited Solar Power Project – Bikaner-V PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 35
| EL-BC27D |  |  | Prerak Solar Urja Private Limited Renewable Power Park– Bhadla-IV PS 220 kV S/c (high capacity) line on D/c tower (Suitable to carry minimum 400 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 27
| EL-BD5C2 |  |  | Tata Power Renewable Energy Limited RE Power Project – Bikaner-VI PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end | [24 empty] | CMETS meeting(s): 38
| EL-BDC29 |  |  | Augmentation of 2x1500 MVA (3rd & 4th), 765/400kV ICT at Bhadla-III PS | [24 empty] | CMETS meeting(s): 25, 27, 31, 38
| EL-BDCD9 |  |  | Establishment of 6000 MW, ±800 kV Begunia (HVDC) terminal station (4x1500 MW) at Begunia (Distt. Khordha), Orissa (ER) | [24 empty] | CMETS meeting(s): 31, 33, 34, 35, 36, 38, 39
| EL-BE348 |  |  | Bypassing 400kV Jalandhar – Nakodar line (Quad) at Jalandhar and connecting it with one of the circuit of Samba-Jalandhar 400kV D/c line (Quad Moose), thus forming Samba –Nakodar line | [24 empty] | CMETS meeting(s): 38
| EL-BE37F |  |  | Fatehgarh-III - Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla- III 400kV D/c line | [24 empty] | CMETS meeting(s): 23, 25, 27, 31, 33, 38, 39
| EL-BE4F7 |  |  | Iraax International (Opc) Private Limited Renewable Power Park– Bikaner-IV PS 220 kV S/c line on D/c tower(Suitable to carry minimum 300 MW at nominal voltage) A. Transmission system for Connectivity under GNA | [24 empty] | CMETS meeting(s): 27
| EL-BE8DC |  |  | Fatehgarh-IV (Sec-II) PS – Barmer-I PS 400 kV D/c line (Quad) | [24 empty] | CMETS meeting(s): 27
| EL-BE974 |  |  | Bikaner PS 400 kV S/c line on D/c tower (Suitable to carry minimum 900 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-BE978 |  |  | Common Pooling station for Avaada Energy Private Limited Solar Power Projects (App. No. 2200000580(200 MW) & | [24 empty] | CMETS meeting(s): 33
| EL-BF006 |  |  | Common Pooling station for Avaada RJ Bikaner Private Limited (App No. 220000013(50 MW), App. No. 2200000254(600 MW)) & Avaada Energy Private Limited (App No. 2200000289(300 MW)) Solar Power Projects – Bikaner-IV PS 400 kV S/c line on D/c tower (Suitable to carry minimum 950 MW at nominal voltage) A. Transmission system for Connectivity under GNA | [24 empty] | CMETS meeting(s): 27
| EL-BF27C |  |  | Enren-IV Energy Private Limited RE Power Project – Barmer-III PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 36
| EL-BFED7 |  |  | Vismaya Five Renewables Private Limited – Barmer-II PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 35
| EL-C06E3 |  |  | Rajasthan BESS Private Limited – Bhadla-III 220 kV cable (Suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-C071C |  |  | Power reversal on ±500 KV, 2500 Balia- Bhiwadi HVDC line upto 2000 MW from Bhiwadi to Balia - Power reversal in Balia-Bhiwadi HVDC line *with minimum capacity of 2100 MVA on each circuit at nominal voltage **Gopalpur Substation is under implementation by DTL by LILO of Bawana – Maharanibagh 400kV D/c(Quad) at Gopalpur substation. Additional Scheme to relieve overloading of 400 kV Bhinmal-Zerda line (Twin Moose) | [24 empty] | CMETS meeting(s): 14
| EL-C1084 |  |  | Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor | [24 empty] | CMETS meeting(s): 25
| EL-C1136 |  |  | LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line (2nd) at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactors at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV PS - Beawar D/c line (formed after LILO) | [24 empty] | CMETS meeting(s): 15
| EL-C1BDA |  |  | Fatehgarh-IV PS(Sec-II) – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end | [24 empty] | CMETS meeting(s): 27, 31
| EL-C1D16 |  |  | M/s Malur Renewables Private Limited Renewable Power Park– Bhadla-III PS 400 kV S/c line on D/c tower (Suitable to carry minimum 900 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 27
| EL-C2310 |  |  | Bhadla-III – Bhadla (HVDC) 400 kV 2xD/c line(Quad) along with the line bays at both substations | [24 empty] | CMETS meeting(s): 31, 33
| EL-C23B0 |  |  | Augmentation of 1x500 MVA (2nd), 400/220kV ICT at Fatehgarh-3 pooling station (Section-II) | [24 empty] | CMETS meeting(s): 22
| EL-C2590 |  |  | LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS | [24 empty] | CMETS meeting(s): 23, 27, 33, 34
| EL-C2F66 |  |  | 400kV Barmer-III PS – Barmer-IV PS D/c line (Quad) | [24 empty] | CMETS meeting(s): 38, 39
| EL-C3549 |  |  | Common Pooling Station for ReNew Solar Power Private Limited RE Power Projects(App. No. 2200001781-200 MW, App. No. 2200001864-300 MW & , App. No. 2200001865-300 MW) – Bhadla-V PS 400 kV S/c line on D/c(suitable to carry minimum 900 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 38
| EL-C3BC4 |  |  | Common Pooling station for M/s Foxtrot Solar Renewables Energy Private Limited (App. No. 2200001057 (100 MW) & 2200001088 (80MW) Solar Power Project – Barmer-III PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 34
| EL-C5410 |  |  | Mahanadi Renewable Energy Private Limited RE Power Project– Ramgarh-III PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 38
| EL-C5523 |  |  | 1 no of 220 kV bay at Bhadla-V PS shall be under the scope of ISTS | [24 empty] | CMETS meeting(s): 38
| EL-C5579 |  |  | Common pooling station for NTPC Renewable Energy Limited Solar Power Projects (App No. 2200000244(150 MW) , 2200000420(400 MW) – Bikaner-IV PS 400 kV D/c line (Suitable to carry minimum 950 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-C567C |  |  | Prerak Greentech Solar Private Limited Solar Power Project – Bhadla-III PS 220 kV S/c (high capacity) line on D/c tower (Suitable to carry minimum 400 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 23
| EL-C638D |  |  | Common Pooling station for Iraax International Private Ltd Solar Power Projects (App. No. 2200000484 - 100 MW & App. No. 2200000540 - 150 MW) – Bikaner-V PS 220 kV S/c line on D/c tower (Suitable to carry minimum 370 MW at nominal voltage) along with associated bays at generation and ISTS ends – Under the scope of M/s Iraax International Pvt. Ltd | [24 empty] | CMETS meeting(s): 39
| EL-C6A87 |  |  | Common Pooling Station for Green Infra Renewable Energy Farms Private Limited Solar Power Projects (App. No. 2200001141 – 300 MW & App. No. 2200001194 – 300 MW) – Barmer-III PS 220 kV D/c line (Suitable to carry minimum 300 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 35
| EL-C8513 |  |  | 4x500 MVA, 400/220kV ICTs at Bhadla-V PS | [24 empty] | CMETS meeting(s): 39
| EL-C89B9 |  |  | Beawar(HVDC) PS – Beawar 400 kV D/c line(Quad) | [24 empty] | CMETS meeting(s): 34, 35, 38, 39
| EL-C89EE |  |  | Establishment of 765/400 kV, 3X1500 MVA GIS substation at Narela with 765 kV (2x330 MVAr) bus reactor and 400kV (1x125 MVAR) bus reactor | [24 empty] | CMETS meeting(s): 14, 15, 16, 17, 36
| EL-C8D83 |  |  | 400/220kV, 5x500 MVA ICTs at Ramgarh-II PS | [24 empty] | CMETS meeting(s): 38
| EL-C8E53 |  |  | Sirohi(HVDC) PS (Sirohi-II) – Sirohi PS 400 kV D/c line(Quad) | [24 empty] | CMETS meeting(s): 34
| EL-C91AF |  |  | Augmentation of 2x500MVA (2nd & 3rd) 400/220 kV ICTs at Bikaner –II PS B. Common Transmission system (Part of Transmission system associated with SEZ in Rajasthan under 8.1 GW Phase-II scheme) for both LTA application | [24 empty] | CMETS meeting(s): 15
| EL-C91CC |  |  | Common Pooling station for Avaada RJ Bikaner Private Limited (App No. 220000013(50 MW), App. No. 2200000254(600 MW)) & Avaada Energy Private Limited (App No. 2200000289(300 MW)) Solar Power Projects – Bikaner-IV PS 400 kV S/c line on D/c tower (Suitable to carry minimum 950 MW at nominal voltage) A | [24 empty] | CMETS meeting(s): 27
| EL-CA2EA |  |  | LILO of 400 kV Kishenpur- Dulhasti line (Twin Zebra) at Kishtwar S/s (one ckt already LILOed as part of Pakaldul transmission system) | [24 empty] | CMETS meeting(s): 38
| EL-CA7A7 |  |  | 2028(interim). Final date shall be confirmed upon award of the system B.5 Inter-regional (NR-WR) Transmission System strengthening to relieve the loading of 765kV Vindhyachal-Varanasi D/c line It was stated that in 220th NR-OCC meeting held on | [24 empty] | CMETS meeting(s): 35
| EL-CAA1E |  |  | Bikaner-IV PS – Siwani 765 kV 2xD/c line along with 240 MVAr switchable line reactor for each circuit at each end | [24 empty] | CMETS meeting(s): 27, 31
| EL-CAB21 |  |  | Renew Sun Power Private Limited Solar Power Project– Barmer-I PS 220 kV S/c line on D/c tower(Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 27
| EL-CB5A3 |  |  | 2025(on hearing of Petition No. 395/MP/2025 by BBMB) had directed BBMB to apply to CTUIL seeking connectivity for its solar projects of 10 MW (at Bhiwani S/s) and | [24 empty] | CMETS meeting(s): 38
| EL-CB8FF |  |  | Sprng Green Energy 4 Private Limited RE Power Project – Bhadla-V PS 220 kV S/c line on D/c tower (suitable to carry minimum 400 MW at nominal voltage) along with associated bay at generation end | [24 empty] | CMETS meeting(s): 37
| EL-CBFD4 |  |  | Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) | [24 empty] | CMETS meeting(s): 23, 27, 33, 34
| EL-CC36B |  |  | Dynamic Simulation Studies – With more than 100 GW solar generation and two HVDC terminals in Rajasthan in close vicinity, it is important that stability aspects are also studied in detail at the planning stage. The generation is also getting evacuated through large EHV lines and hence, transient stability analysis also becomes important. Therefore, it is suggested that the results of the dynamic simulation studies may be shared | [24 empty] | CMETS meeting(s): 36
| EL-CC73C |  |  | Gamma Renewables India Project Private Limited Renewable Power Park– Barmer-I PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 27
| EL-CC9A2 |  |  | Common Pooling Station for Waaree Forever Energies Pvt Ltd RE Power Projects (App. No. 2200001901-300 MW & App. No. 2200001955-600 MW) – Sanchore PS 400 kV S/c line on D/c tower(suitable to carry minimum 900 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-CD00C |  |  | ±800 kV HVDC line between Bhadla (HVDC) & Fatehpur (HVDC) (with Dedicated Metallic Return) | [24 empty] | CMETS meeting(s): 31, 33, 38
| EL-CDD2B |  |  | Augmentation of 1x500 MVA (7th) 400/220kV ICT at Bhadla-III PS | [24 empty] | CMETS meeting(s): 25
| EL-CDE18 |  |  | Common Pooling station for Avaada Energy Private Limited Solar Power Projects (App. No. 2200000580(200 MW) & 2200000636(450MW) – Barmer-II PS 220 kV D/c line (suitable to carry minimum 325 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-CE062 |  |  | Sikar-II – Aligarh 765kV D/c line | [24 empty] | CMETS meeting(s): 16, 36
| EL-CE304 |  |  | Augmentation of 2x1500 MVA, 765/400 kV ICT (3rd & 4th) at Bhadla-II Pooling station B. Common Transmission system (Part of Transmission system associated with SEZ in Rajasthan under 8.1 GW Phase-II scheme) | [24 empty] | CMETS meeting(s): 36
| EL-CE816 |  |  | 765 kV Bhadla-III – Bikaner-III D/c line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end | [24 empty] | CMETS meeting(s): 25, 27, 31, 33, 38
| EL-CE849 |  |  | Establishment of 6000 MW, ± 800 kV Bhadla-IV (HVDC) terminal station (4x1500 MW) at suitable location near Bhadla | [24 empty] | CMETS meeting(s): 31, 33, 34, 35, 36
| EL-CEC8C |  |  | 2 no of line bays at Narela each for Maharanibagh – Narela 400 kV D/c (Quad) and Maharanibagh –Gopalpur**-Narela 400 kV D/c (Quad) lines formed after removal of LILO of Bawana – Mandola 400kV D/c(Quad) line at Maharani Bagh/Gopalpur S/s and Extension of above LILO section from Maharani Bagh/Gopalpur upto Narela S/s | [24 empty] | CMETS meeting(s): 14, 15, 16, 17, 36
| EL-CF209 |  |  | Augmentation of 1x500 MVA (4th) 400/220kV ICT at Fatehgarh-III Pooling station B. Common Transmission system (Part of Transmission system associated with SEZ in Rajasthan under 8.1 GW Phase-II scheme) | [24 empty] | CMETS meeting(s): 16
| EL-CF906 |  |  | Common Pooling station for Pumped Storage Projects of M/s Greenko UP01 IREP Private Limited (App. No. 220000527-672 MW, 220000529- 672 MW, 220000524-672 MW, 220000525-672 MW, 220000526-672 MW & 220000528-672 MW) – Robertsganj Pooling Station 400 kV 2xD/c line(suitable to carry minimum 1400 MW per circuit at nominal voltage)* | [24 empty] | CMETS meeting(s): 31
| EL-CF954 |  |  | Enren Solar Private Limited RE Power Project– Ramgarh-III PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-CF972 |  |  | Establishment of 4x1500 MVA 765/400 kV Robertsganj Pooling Station near Robertsganj area in Sonbhadra distt. (Uttar Pradesh) along with 2x240 MVAr 765 kV & 2x125 MVAr 400 kV Bus reactors | [24 empty] | CMETS meeting(s): 35
| EL-CFCC2 |  |  | HVDC line between Barmer-III (HVDC) & HVDC terminal station in WR/SR/ER (with Dedicated Metallic Return) | [24 empty] | CMETS meeting(s): 33, 34, 35, 36, 37
| EL-CFE69 |  |  | Anboto Solar Private Limited Solar Power Project– Barmer-I PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 27
| EL-D04F6 |  |  | Common Pooling station for Juniper Green Energy Private Limited (App. No. 2200000499(150 MW) & | [24 empty] | CMETS meeting(s): 31
| EL-D0DE2 |  |  | 400/220kV 7x500MVA ICTs at Barmer-III PS (for connectivity agreed for grant at 220kV level) | [24 empty] | CMETS meeting(s): 37
| EL-D0E44 |  |  | 400kV Sectionalizer bay (1 set) at Barmer-I S/s | [24 empty] | CMETS meeting(s): 27, 31, 36, 39
| EL-D1558 |  |  | Power reversal on ±500 KV, 2500 Balia- Bhiwadi HVDC line upto 2000 MW from Bhiwadi to Balia - Power reversal in Balia-Bhiwadi HVDC line *with minimum capacity of 2100 MVA on each circuit at nominal voltage **Gopalpur Substation is under implementation by DTL by LILO of Bawana – Maharanibagh 400kV D/c(Quad) at Gopalpur substation | [24 empty] | CMETS meeting(s): 15, 17
| EL-D1B6F |  |  | M/s Juniper Green Energy Private Limited Solar Power Project – Bikaner-V PS 220 kV S/c line on D/c tower (suitable to carry minimum 400 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 34
| EL-D235D |  |  | 0 Transmission System for Rajasthan REZ Phase-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex) | [24 empty] | CMETS meeting(s): 18
| EL-D2426 |  |  | Vena Energy Vindhya Wind Power Private Limited Solar Power Project – Bikaner-V PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-D2CF8 |  |  | SHN Green Power Private Limited Wind Power Project – Ramgarh-II PS 220 kV S/c line on D/c tower(suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 35
| EL-D3904 |  |  | Common Pooling station for Adani Renewable Energy Holding Four (App. No. 2200000598(500 MW) & 2200000599(500 MW)) Solar Power Projects –– Ramgarh PS 400 kV S/c line on D/c tower (suitable to carry minimum 1000 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-D397F |  |  | 765 kV Bhadla-V PS – Ramgarh-III PS D/c line along with 240 MVAr switchable line reactor for each circuit at Ramgarh-III PS end | [24 empty] | CMETS meeting(s): 38, 39
| EL-D3AAA |  |  | Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) Additional Transmission system for inter-regional power transfer | [24 empty] | CMETS meeting(s): 34
| EL-D487C |  |  | LILO of one ckt of 765 kV Sikar-II (PG) -Khetri (PG) D/c line at Churu S/s | [24 empty] | CMETS meeting(s): 25
| EL-D4A9F |  |  | Infrastructure required for sharing dedicated transmission system – under the scope of M/s JIRE Green Energy Project Three Limited | [24 empty] | CMETS meeting(s): 38
| EL-D4AAF |  |  | 1 no. of 220 kV bay at Bhadla-III PS end - Under the scope of ISTS | [24 empty] | CMETS meeting(s): 39
| EL-D4FCF |  |  | Addition of BESS: In the 500 GW RE Transmission Report by CEA, ~22.5 GW BESS was planned at different pooling stations in NR (Rajasthan). However, so far, the BESS capacity addition has not taken place as per the plan. Planning of the envisaged BESS capacity as a generation resource could help in optimizing the transmission being planned for RE evacuation in Rajasthan and will also provide necessary flexibility support during the non-solar hours | [24 empty] | CMETS meeting(s): 36
| EL-D55CD |  |  | 7 Transmission System for Rajasthan REZ Phase-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex) | [24 empty] | CMETS meeting(s): 18
| EL-D6782 |  |  | Establishment of 765/400kV, 2x1500 MVA pooling station at suitable location near Bhadla (Bhadla-V PS) along with 2x125 MVAr & 2x240 MVAr bus reactor | [24 empty] | CMETS meeting(s): 37, 38, 39
| EL-D77E9 |  |  | HR Saraswati Energy Private Limited RE Power Project – Bhadla-V PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-D78BE |  |  | NTPC Renewable Energy Limited Solar Power Project– Barmer-III PS 220 kV S/c line on D/c tower(suitable to carry minimum 300 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-D7DF8 |  |  | M/s Avaada Waterbattery Private Limited Pumped Storage Project– Robertsganj Pooling Station 400 kV D/c line (Quad moose or equivalent conductor suitable to carry minimum 1716 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 35
| EL-D8B0A |  |  | Bundelkhand Saur Urja Limited Renewable Power Park– Orai(PG) 400 kV S/c (high capacity) line on D/c tower (Suitable to carry minimum 1200 MW per circuit at nominal voltage) B | [24 empty] | CMETS meeting(s): 27
| EL-D92F2 |  |  | Augmentation of 2x1500 MVA (5th & 6th)765/400 kV ICTs at Bikaner-III Pooling Station | [24 empty] | CMETS meeting(s): 27, 33
| EL-D94DF |  |  | Fatehgarh-II PS – Bhadla-II PS 765kV D/c line (2nd) | [24 empty] | CMETS meeting(s): 16, 31
| EL-D98C6 |  |  | 3 1 Outage of one ckt of 765 kV Beawar-Mandsaur D/c line June Solar Max Scenario | [24 empty] | CMETS meeting(s): 18
| EL-D9A07 |  |  | Establishment of 765/400kV, 4x1500 MVA pooling station at suitable location near Bikaner (Bikaner-V PS) along with 2x125 MVAr & 2x240 MVAr bus reactor | [24 empty] | CMETS meeting(s): 31, 33, 34, 35, 36, 38, 39
| EL-D9D1E |  |  | Common Pooling station for NTPC Renewable Energy Limited Solar Power Projects ( 2200000973-100 MW) – Barmer-II PS 400 kV S/c line on D/c tower (Suitable to carry minimum 900 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 35
| EL-D9DCD |  |  | Infrastructure required for sharing dedicated transmission system - under the scope of M/s Green Infra Clean Wind Ltd | [24 empty] | CMETS meeting(s): 31
| EL-DA776 |  |  | Common Pooling Station for NTPC Renewable Solar Power Projects (App. No. 2200000726 – 1000 MW & 2200001126 – 600 MW) – Bikaner-V PS 400 kV D/c line (suitable to carry minimum 900 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 35
| EL-DA901 |  |  | LILO of one circuit of 765 kV Chittorgarh-Banaskantha D/c line at Rishabdeo S/s | [24 empty] | CMETS meeting(s): 31, 36, 39
| EL-DB586 |  |  | LILO of both ckts of 765kV Ramgarh PS – Bhadla-III PS D/c line at Ramgarh-II PS along with 240 MVAr switchable line reactor for each circuit at Ramgarh-II PS end | [24 empty] | CMETS meeting(s): 33, 34, 35, 36, 37, 38
| EL-DB837 |  |  | HVDC line between Beawar (HVDC) & HVDC terminal station in WR/SR/ER (with Dedicated Metallic Return) | [24 empty] | CMETS meeting(s): 34, 35, 38, 39
| EL-DBBE6 |  |  | Avaada Energy Private Limited Solar Power Project – Bhadla-IV PS 400 kV S/c line on D/c tower (Suitable to carry minimum 900 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 34
| EL-DBCF2 |  |  | LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Minutes for 27th Consultation meeting for Evolving Transmission Schemes in NR 53 | [24 empty] | CMETS meeting(s): 27
| EL-DC354 |  |  | Establishment of 6000 MW, Beawar (HVDC) terminal station (4x1500 MW) at a suitable location near Beawar (HVDC) substation | [24 empty] | CMETS meeting(s): 34, 35, 38, 39
| EL-DCE1A |  |  | 5 GW and Barmer-I PS: 1.5 GW), comprehensive transmission system including above Phase-I scheme is required as per Annexure-1. Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex) Fatehgarh-IV (Section-2): 4 GW and Barmer-I PS: 1.5 GW A. Fatehgarh-IV: 4 GW (Considering 2 GW injection at 400 kV and 2 GW injection at 220 kV level) 7 File No.CEA-PS-11-22(17)/1/2018-PSPA-I Division I/27407/2023 938 | [24 empty] | CMETS meeting(s): 18
| EL-DD8DD |  |  | Bhadla-III – Sikar-II 765 kV D/c line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV D/c line @ The above system is identified considering both injection & drawl of power during non-solar hours and considering only drawl of power during solar hours | [24 empty] | CMETS meeting(s): 23, 25, 27, 31, 33, 38, 39
| EL-DEBDE |  |  | Bhadla-VI PS – Bhadla-V PS 400kV D/c line (Quad) | [24 empty] | CMETS meeting(s): 39
| EL-DEDF4 |  |  | Prayagraj – Sohawal 400 kV D/c line (Quad) | [24 empty] | CMETS meeting(s): 31, 35
| EL-DF178 |  |  | Through sharing of dedicated transmission of M/s Green Infra Clean Solar Farms Limited Solar Power Project – Barmer-II PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 35
| EL-DFA86 |  |  | Common Pooling Station for Renew Solar Power Private Limited RE Power Projects (App. No. 2200001550-300 MW, App. No. 2200001684-200 MW, App. No. 2200001689-300 MW & 2200002000-300 MW) – Barmer-IV PS 400 kV S/c line (Suitable to carry minimum 1100 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-E140C |  |  | Azure Power Fifty One Private Limited RE Power Project – Bhadla-V PS 400 kV S/c line on D/c tower (suitable to carry minimum 900 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 38
| EL-E173B |  |  | Augmentation of 2x1500 MVA (3rd & 4th)765/400 kV ICTs at Bikaner-III Pooling Station | [24 empty] | CMETS meeting(s): 23, 34
| EL-E1797 |  |  | A. Associated Transmission System (ATS): NIL B. Transmission System u | [24 empty] | CMETS meeting(s): 33
| EL-E191F |  |  | ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) | [24 empty] | CMETS meeting(s): 31, 33, 35
| EL-E1B3D |  |  | Bhadla-III – Bhadla (HVDC) 400 kV D/c (1st & 2nd) quad moose line along with the line bays at both substations | [24 empty] | CMETS meeting(s): 25, 27
| EL-E24A2 |  |  | 1 no. of 400 kV bay at Ramgarh-III PS end – Under the Scope of ISTS Common | [24 empty] | CMETS meeting(s): 39
| EL-E2AA3 |  |  | Sprng Urja Private Limited Renewable Power Park – Barmer-II PS 400 kV S/c line on D/c tower(Suitable to carry minimum 1000 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-E2C4A |  |  | CESC Ltd. Solar Power Project– Sirohi PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-E2ECB |  |  | Churu – Fatehabad (PG) 400 kV D/c line (Quad Moose) along with 63 MVAr switchable line reactor for each circuit at Churu S/s end | [24 empty] | CMETS meeting(s): 25
| EL-E354F |  |  | 8x500 MVA, 400/220kV ICTs at Bikaner-V PS ((for connectivity agreed for grant at 220kV level) | [24 empty] | CMETS meeting(s): 36
| EL-E4517 |  |  | Common Pooling Station for ReNew Solar Power Private Limited RE Power Projects(App. No. 2200001781-200 MW, App. No. 2200001864-300 MW & , App. No. 2200001865-300 MW) – Bhadla-V PS 400 kV S/c line on D/c tower (suitable to carry minimum 900 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 38
| EL-E4767 |  |  | Green Infra Renewable Projects Limited Solar Power Project – Barmer-I PS 220 kV D/c line (Suitable to carry minimum 300 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-E4838 |  |  | Aright Foods and Energy Pvt. Ltd. RE Power Park – Bhadla-IV PS 400 kV D/c line (suitable to carry minimum 1000 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 36
| EL-E4911 |  |  | Establishment of 2x1500 MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor | [24 empty] | CMETS meeting(s): 14, 15, 16, 22, 39
| EL-E4EB8 |  |  | Jhatikara – Dwarka 400kV D/c line (Quad) | [24 empty] | CMETS meeting(s): 23
| EL-E5409 |  |  | Banyan Energy Private Limited Solar Power Project– Merta-II PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-E5DD2 |  |  | Augmentation of 1x500 MVA (3rd), 400/220kV ICT at Fatehgarh-3 pooling station (Section-II) B. Common Transmission system (Part of Transmission system associated with SEZ in Rajasthan under Phase-III (20 GW) scheme) | [24 empty] | CMETS meeting(s): 16
| EL-E5FDE |  |  | Begunia – Khuntuni (OPTCL) 765kV D/c line For connectivity at 220kv level | [24 empty] | CMETS meeting(s): 36
| EL-E67AA |  |  | Amaresha Renawables India Project Private Limited Renewable Power Park – Barmer-II PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-E81E2 |  |  | M/s Sunbreeze Renewables Seven Private Limited Renewable Power Park – Ramgarh-II PS 220 kV S/c line on D/c tower (suitable to carry minimum 400 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 34
| EL-E8645 |  |  | LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line | [24 empty] | CMETS meeting(s): 14, 15, 16, 39
| EL-E8969 |  |  | Establishment of 765/400kV, 3x1500 MVA S/s & 400/220kV 3x500MVA pooling station at suitable location near Bhadla (Bhadla-IV PS) along with 2x125 MVAr & 2x240 MVAr bus reactor | [24 empty] | CMETS meeting(s): 27
| EL-E8A3E |  |  | Siwani – Fatehabad (PG) 400 kV D/c line (Quad) Minutes for 27th Consultation meeting for Evolving Transmission Schemes in NR 71 | [24 empty] | CMETS meeting(s): 27
| EL-E93BC |  |  | TEQ Green Power XV Private Limited Renewable Power Park – Jalore PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 34
| EL-EA57A |  |  | Reconductoring of 400 kV Kishenpur-Kishtwar line* (Twin HTLS) (minimum 2100 MVA capacity) (formed after LILO of KishenpurDulhasti line at Kishtwar S/s) along with bay upgradation works (2000A to 3150A) at Kishenpur end for above line Common Transmission system fo | [24 empty] | CMETS meeting(s): 38
| EL-EA661 |  |  | Reconductoring of 400 kV Jodhpur (Surpura)(RVPN) – Kankroli S/c (twin moose) line with twin HTLS conductor*-188 km # with necessary arrangement for bypassing Kankroli- Zerda line at Bhinmal with suitable switching equipment inside the Bhinmal substation. * with minimum capacity of 2100 MVA/ckt at nominal voltage; Upgradation of existing 400kV bay equipments each at Jodhpur (Surpura)(RVPN) and Kankroli S/s(3150 A) | [24 empty] | CMETS meeting(s): 23
| EL-EA9C1 |  |  | LILO of Indore – Bhopal 765 kV S/c line at Kurawar Minutes for 27th Consultation meeting for Evolving Transmission Schemes in NR 65 | [24 empty] | CMETS meeting(s): 27
| EL-EAAE1 |  |  | 400/220kV, 5x500 MVA ICTs at Ramgarh-III PS | [24 empty] | CMETS meeting(s): 38, 39
| EL-EAECB |  |  | Establishment of 2x1500 MVA 765/400 kV Pooling Station at suitable location near Bikaner (Bikaner-VI PS) along with 2x330 MVAr & 2x125 MVAr bus reactors | [24 empty] | CMETS meeting(s): 38
| EL-EB9F7 |  |  | Hinduja Renewables Energy Private Limited RE power Project – Barmer-I PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-EBDC5 |  |  | Bypassing of 400kV Kishtwar – Kishenpur line (Quad) (Under implementation as part of Pakaldul transmission scheme) at Kishenpur and connecting it with one of the circuit of Kishenpur-Samba 400kV D/c line(Quad), thus forming 400kV KishtwarSamba (Quad) direct line (one ckt) | [24 empty] | CMETS meeting(s): 38
| EL-EC5C1 |  |  | Augmentation of 2x500 MVA (8th & 9th), 400/220 kV ICT at Bhadla-III PS | [24 empty] | CMETS meeting(s): 31, 38
| EL-ED235 |  |  | Fatehgarh-III – Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III – Beawar 765 kV D/c line (2nd) | [24 empty] | CMETS meeting(s): 39
| EL-ED253 |  |  | Bhadla-3 – Bhadla (HVDC) 400 kV D/c (1st) quad moose line along with the line bays at both substations | [24 empty] | CMETS meeting(s): 16
| EL-ED63C |  |  | 2027(interim). Final date shall be confirmed upon award of the system Further, Transmission system for connectivity of M/s Avaada Waterbattery Private Limited under GNA, was also agreed in 31st CMETS- NR meeting held on | [24 empty] | CMETS meeting(s): 35
| EL-ED8D0 |  |  | Common Pooling Station for Purvah Green Power Private Limited Solar Power Projects(App. No. 2200001261 – 300 MW & 2200001262 – 300 MW) – Bikaner-V PS 220 kV D/c line (suitable to carry minimum 300 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 35
| EL-ED937 |  |  | Augmentation of 2x500 MVA (3rd & 4th), 400/220 kV ICTs at Barmer-I PS | [24 empty] | CMETS meeting(s): 27
| EL-ED97C |  |  | Vismaya Five Renewables Private Limited Solar Power Project – Barmer-III PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-EE5CB |  |  | Augmentation of 1x500 MVA (7th), 400/220kV ICTs at Fatehgarh-IV (Section-2) Pooling Station | [24 empty] | CMETS meeting(s): 31
| EL-EEBBC |  |  | M/s Jindal Green Private Limited RE Power Project – Pali PS 220 kV S/c line on D/c tower (suitable to carry minimum 350 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 39
| EL-EECEF |  |  | 5 1 Outage of one ckt of 765 kV Jalore-Rishabhdeo D/c line Feb Solar Max Scenario | [24 empty] | CMETS meeting(s): 18
| EL-EF09B |  |  | LILO of Indore – Bhopal 765 kV S/c line at Kurawar Minutes for 25th Consultation meeting for Evolving Transmission Schemes in NR 13 | [24 empty] | CMETS meeting(s): 25
| EL-EF289 |  |  | Common Pooling Station for Renew Solar Power Private Limited RE Power Projects (App. No. 2200001550-300 MW, App. No. 2200001684-200 MW & App. No. 2200001689-300 MW)– Barmer-IV PS 400 kV S/c line (Suitable to carry minimum 900 MW at nominal voltage) along with associated bay at generation end - Under Applicant Scope | [24 empty] | CMETS meeting(s): 38
| EL-EF788 |  |  | LILO of both circuits of 765 kV Varanasi- Gaya 2XS/c line at Robertsganj Pooling Station along with 240MVAr switchable line reactor at each ckt of Robertsganj PS end of 765 kV Robertsganj PS - Gaya 2xS/c line | [24 empty] | CMETS meeting(s): 31, 35
| EL-EF8E0 |  |  | 1 no. of 400 kV bay at Barmer-IV PS end Under the scope of ISTS | [24 empty] | CMETS meeting(s): 39
| EL-EFF44 |  |  | 1x330 MVAr Switchable line reactor for each circuit at Sikar-II end of Bhadla-II –Sikar-II 765kV D/c line | [24 empty] | CMETS meeting(s): 16, 36
| EL-F0027 |  |  | Common Pooling Station of Soltown Infra Private Limited (0212100008-125 MW & 1200003889-200 MW) RE Power Parks – Bikaner-II PS 220 kV S/c line on D/c tower(Suitable to carry minimum 325 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 34
| EL-F0D41 |  |  | M/s Juniper Green Energy Pvt. Ltd RE Power Project(App. No. 2200001210-130 MW) – Bikaner-V PS 220 kV S/c line on D/c tower(Suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end – Under the scope of M/s Juniper Green Energy Limited | [24 empty] | CMETS meeting(s): 38
| EL-F1B66 |  |  | 1x500 MVA (2nd), 400/220 kV ICT at Barmer-I Pooling Station | [24 empty] | CMETS meeting(s): 25
| EL-F1D12 |  |  | Merta-III PS – Merta-II PS 400 kV D/c line(Quad) | [24 empty] | CMETS meeting(s): 34, 35, 39
| EL-F20FC |  |  | LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV 2xS/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line | [24 empty] | CMETS meeting(s): 31, 36, 39
| EL-F278C |  |  | LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Minutes for 27th Consultation meeting for Evolving Transmission Schemes in NR 69 | [24 empty] | CMETS meeting(s): 27
| EL-F29A2 |  |  | Hexa Climate Solutions Private Limited RE Power Project– Bhadla-V PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) along with associated bay at generation end | [24 empty] | CMETS meeting(s): 38
| EL-F31CC |  |  | M/s Aditya Birla Renewables Limited Solar Power Project – Merta-III PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 35
| EL-F339F |  |  | Bypassing of both ckts of 765kV Sasan – Vindhyachal Pool 2xS/c line at Vindhyachal Pool and connecting it with 765kV Vindhyachal Pool - Prayagraj D/c line, thus forming 765kV Sasan - Prayagraj D/c line Start Date of Connectivity | [24 empty] | CMETS meeting(s): 31, 35
| EL-F4B8D |  |  | 5 Transmission System for Rajasthan REZ Phase-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex) | [24 empty] | CMETS meeting(s): 18
| EL-F5025 |  |  | Establishment of 400kV pooling station at suitable location near Barmer(Barmer-IV PS) along with 2x125 MVAr bus reactor | [24 empty] | CMETS meeting(s): 38, 39
| EL-F525F |  |  | Augmentation of 2x500 MVA (7th & 8th) 400/220kV ICTs at Bhadla-III PS | [24 empty] | CMETS meeting(s): 25
| EL-F5E74 |  |  | Avaada Energy Private Limited Solar Power Project – Bhadla-III PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-F66C7 |  |  | LILO of both ckts of 400kV Bikaner-II PS- Khetri D/c line (2nd) at Bikaner-VI PS | [24 empty] | CMETS meeting(s): 38
| EL-F697A |  |  | Serentica Renewables India 11 Private Limited – Barmer-II PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-F7376 |  |  | Tata Power Renewable Energy Limited Solar Power Project – Ramgarh PS 400 kV S/c line on D/c tower (suitable to carry minimum 900 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-F7B5C |  |  | 2x500 MVA, 400/220kV ICTs at Sanchore PS | [24 empty] | CMETS meeting(s): 33, 38
| EL-F7FAC |  |  | Bhadla-IV PS – Merta-II 765KV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Bhadla-IV PS – Merta-II 765KV D/c line | [24 empty] | CMETS meeting(s): 27
| EL-F8B67 |  |  | Renew Solar Power Private Limited Solar Power Project – Ramgarh-II PS 220 kV S/c line on D/c tower(Suitable to carry minimum 400 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-F92C8 |  |  | ±800 kV HVDC line between Bhadla-VI (HVDC) & Suitable location in WR/ER/SR (with Dedicated Metallic Return) | [24 empty] | CMETS meeting(s): 39
| EL-F97E5 |  |  | Robertsganj PS – Prayagraj 765 kV D/c line along with 330 MVAr line reactor at each circuit of Robertsganj end of Robertsganj PS – Prayagraj 765 kV D/c line | [24 empty] | CMETS meeting(s): 35
| EL-F9AF9 |  |  | Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation | [24 empty] | CMETS meeting(s): 31, 33, 35
| EL-FB298 |  |  | Sikar-II – Neemrana 400kV D/c line (Twin HTLS)* | [24 empty] | CMETS meeting(s): 16, 36
| EL-FB49D |  |  | Furies Solren Private Limited Solar Power Project– Bikaner-IV PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) A | [24 empty] | CMETS meeting(s): 27
| EL-FBEE4 |  |  | 1 1 Outage of one ckt of 400 kV RAPS-Sujalpur D/c line June Solar Max Scenario | [24 empty] | CMETS meeting(s): 18
| EL-FBF5E |  |  | Augmentation of 2x1500 MVA, 765/400 kV ICT (3rd & 4th) at Bhadla-II Pooling station | [24 empty] | CMETS meeting(s): 16
| EL-FDB51 |  |  | 9 1 Feb Solar Max Scenario Outage of one ckt of 765 kV Beawar-Mandsaur D/c line | [24 empty] | CMETS meeting(s): 18
| EL-FE151 |  |  | 1x240 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-II – Bhadla-II 765kV D/c line | [24 empty] | CMETS meeting(s): 16
| EL-FE432 |  |  | SJVN Green Energy Limited Solar Power Project – Bikaner-IV PS 220 kV D/c line (Suitable to carry minimum 300 MW per circuit at nominal voltage) | [24 empty] | CMETS meeting(s): 31
| EL-FE938 |  |  | Purvah Green Power Private Limited Solar Power Project– Merta-II PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage) | [24 empty] | CMETS meeting(s): 33
| EL-FFEB8 |  |  | 400kV Sectionalizer bay (1 set) at Bikaner-IV PS | [24 empty] | CMETS meeting(s): 27, 31
Formulas:
Tentative SCOD = DATE(YEAR(TODAY()), MONTH(TODAY()+[Execution Timeline]), DAY(TODAY()))