## Data Sources
SN | Connectivity Application Status | Frequency
1 | CTU ¦ Central Transmission Utility of India Limited CMETS (Agenda and Minutes: Region wise) link:https://ctuil.in/ists-consultation-meeting | Daily
2 | CTU ¦ Central Transmission Utility of India Limited JCC (Region wise as per document release Agenda/Minutes) link https://ctuil.in/ists-joint-coordination-meeting | Daily
3 | Status of effectiveness of connectivity granted to RE generators (Effective date of connectivity wise) link | Daily
4 | CTU ¦ Central Transmission Utility of India Limited Re-allocation meetings (Agenda and Minutes: Region wise) link | Weekly
5 | CTU ¦ Central Transmission Utility of India Limited Bidding Calendar link | Weekly
6 | Transmission Reports - Central Electricity Authority TBCB report from CEA transmission (monthly comparison) link | Daily
7 | CTUIL (OPEN ACCESS) (Compliance of Land and Financial Closure) link | Daily
8 | Monitoring of Connectivity (all 3 Annexures and monthly document release comparison) link | Daily
SN | Substation and Transmission Tracking | Frequency
9 | (Status of allocation of bays at ISTS substations for connectivity grantees, Connectivity margins at existing ISTS (non RE) substations for future RE integration and Connectivity Margin in ISTS RE Substations available by Mar-2030) link | Weekly
10a | Potential RE Zones Report link | Weekly
10b | NCT (Agenda and Minutes Summary and Comparison of Scheme wise elements) link Link: https://cea.nic.in/comm-trans/national-committee-on-transmission/?lang=en | Daily
10c | Tender websites PFCCL and RECPDCL mentioned in NCT under TBCB and RTM (RFP and other tender documents in folders; Bidding Status: Bid Submission Date or Deadline, Commissioning Timeline and Expected SCOD) RECPDCL: https://www.recpdcl.in/rectpcltender PFCCL:https://www.pfcclindia.com/tender-new.php PFCCL Notice: https://www.pfcclindia.com/notice.php?AM1 | Daily
10d | CEA monthly transmission reports: (track status for tender elements timelines from 1) CEA Monthly report for actual physical progress of elements and 2) Actual COD from completion report) CEA https://cea.nic.in/transmission-reports/?lang=en | Daily
10e | Map of the above Section 2 data to be created for review and edit by users
11 | Bulk Consumers and Green Hydrogen link | Weekly
12 | CEA: transmission schemes, substations (transformation capacity) and transmission lines published each month on CEA monthly reports section under transmission. | Weekly
13 | Global Wind Atlas (India Map Visualization) | Weekly
14 | Open Infrastructure Map (India Map Visualization) | Weekly

## Data to be captured
| Sr.no. | Region | State | Substation | Coordinates | Name of Developers | Group | GNA/ST II Application ID | LTA Application ID | Application ID under Enhancement 5.2 or revision | CMETS GNA Approved | CMETS LTA Approved | CMETS GNA Meeting Date | CMETS LTA Meeting Date | Type | Application Quantum (MW)(ST II) | Granted Quantum GNA/LTA(MW) | Installed/Break-up Capacity (MW) |  |  | Battery |  |  | PSP |  |  | Commissioned |  | Application/Submission Date | Mode(Criteria for applying) | Applied Start of Connectivity sought by developer date( start date of connectivity as per the application) | GNA Operationalization Date | GNA Operationalization (Yes/No) | Date from which additional capacity is to be added | Nature of Applicant | Status of application(Withdrawn / granted. Revoked.) | Voltage level | Bay No | CTS Element Unique Code | ATS Element Unique Code | DTL Element Code Unique | Date of Last Element Unique Code | In-principle Grant | Final Grant | In case of Land BG Conversion Date | Remarks
| 1 | NR | Rajasthan | Sirohi PS |  | ACME Solar Holdings Limited (erstwhile ACME Solar Holdings |  | 2200000788 | [7 empty] | 300 |  | Solar | Wind | Hybrid | MWh | Injection (MW) | Drawl (MW) | MWh | Injection (MW) | Drawl (MW) | TGNA | GNA | 07.05.2024 | Land BG Route | 31.03.2027 |  |  |  | Generator (Solar) | Withdrawn
| 2 | NR | Rajasthan | Sirohi PS |  | SAEL Industries Limited |  | 2200000793 | [7 empty] | 300 | [12 empty] | 10.05.2024 | Land BG Route | 30.05.2026 |  |  |  | Generator (Solar) | Withdrawn
| 3 | NR | Rajasthan | Sirohi PS |  | SAEL Industries Limited |  | 2200000794 | [7 empty] | 300 | [12 empty] | 10.05.2024 | Land BG Route | 30.05.2026 |  |  |  | Generator (Solar) | Withdrawn
| 4 | NR | Rajasthan | Sirohi PS |  | Amplus Centaur Solar Private Limited |  | 2200000827 | [7 empty] | 350 | [12 empty] | 20.05.2024 | Land BG Route | 30.04.2027 |  |  |  | Generator (Solar) | Granted
| 5 | NR | Rajasthan | Nagaur (MERTA-II) PS |  | ACME Solar Holdings Limited (erstwhile ACME Solar Holdings Private Limited) |  | 2200000841 | [7 empty] | 100 | [12 empty] | 31.05.2024 | Land BG Route | 31.03.2027 |  |  |  | Generator (Solar) | Withdrawn
| 6 | NR | Rajasthan | Rishabhdeo PS |  | Serentica Renewables India Private Limited |  | 2200000891 | [7 empty] | 400 | [12 empty] | 31.05.2024 | Land BG Route | 30.06.2026 |  |  |  | Generator (Solar) | Withdrawn
Data Scoure (Sl. No.(s) 1,2,3,4,7,8,9,11) | 7 | NR | Rajasthan | Nagaur Complex (Merta-II) PS |  | Enren-III Energy Private Limited |  | 2200000860 | [7 empty] | 300 | [12 empty] | 31.05.2024 | Land BG Route | 31.01.2027 |  |  |  | Generator (Solar) | Granted
| 8 | NR | Rajasthan |  |  | Sindhari Solar Power Private Limited |  | 2200000894 | [7 empty] | 300 | [12 empty] | 31.05.2024 | Land BG Route | 30.06.2027 |  |  |  | Renewable Power Park developer (Solar)
| 1 | NR | Rajasthan | Nagaur Complex (Merta-II PS) |  | Prespa Solar Private Limited |  | 2200000832 | [7 empty] | 250 | [12 empty] | 04.06.2024 | Land BG Route | 31.12.2026 |  |  |  | Renewable Power Park developer (Solar)
| 1 | NR | Rajasthan | bikaner-V ps |  | Sunsure Solarpark RJ One Private Limited |  | 2200001021 | [7 empty] | 350 | [12 empty] | 05.07.2024 | Land BG Route | 31.03.2029 |  |  |  | Generator (Solar) | Granted
| 2 | NR | Rajasthan | Ramgarh-II PS |  | Sunbreeze Renewables Seven Private Limited |  | 2200000983 | [7 empty] | 400 | [12 empty] | 05.07.2024 | Land Route | 31.03.2026 |  |  |  | Renewable Power Park developer (Solar) | Withdrawn
| 3 | NR | Rajasthan | Bikaner-IV PS |  | Juniper Green Energy Private Limited |  | 2200001056 | [7 empty] | 400 | [12 empty] | 16.07.2024 | Land BG Route | 30.06.2029 |  |  |  | Generator (Solar) | Granted
| 4 | NR | Rajasthan | Barmer II PS |  | Foxtrot Solar Renewables Energy Private Limited |  | 2200001057 | [7 empty] | 100 | [12 empty] | 17.07.2024 | Land Route | 31.12.2030 |  |  |  | Generator (Solar)
| 5 | NR | Rajasthan | Fatehgarh-II PS |  | ACME Cleantech Solutions Private Limited |  | 2200001065 | [7 empty] | 150 | [12 empty] | 17.07.2024 | Land BG Route | 31.10.2026 |  |  |  | Generator (Solar) | Withdrawn
| 6 | NR | Rajasthan | Barmer PS |  | Renew Solar Power Private Limited |  | 2200001026 | [7 empty] | 200 | [12 empty] | 19.07.2024 | REMCL LOA | 30.09.2026 |  |  |  | Generator (Solar) | Granted
| 7 | NR | Rajasthan | Bhadla - II PS |  | Adani Renewable Energy Holding Eighteen Limited |  | 2200001044 | [7 empty] | 150 | (Reduced to 50 MW) | [11 empty] | 24.07.2024 | Land Route | 15.06.2025 |  |  |  | Generator (Solar) | Granted
| 8 | NR | Rajasthan | Pali PS |  | TEQ Green Power XV Private Limited |  | 2200001089 | [7 empty] | 300 | [12 empty] | 26.07.2024 | Land BG Route | 15.06.2027 |  |  |  | Renewable Power Park developer (Solar) | Granted
| 9 | NR | Rajasthan | Jalore PS |  | TEQ Green Power XV Private Limited |  | 2200001087 | [7 empty] | 300 | [12 empty] | 26.07.2024 | Land BG Route | 15.06.2027 |  |  |  | Renewable Power Park developer (Solar) | Granted
| 10 | NR | Rajasthan | Barmer II PS |  | Foxtrot Solar Renewables Energy Private Limited |  | 2200001088 | [7 empty] | 80 | [12 empty] | 26.07.2024 | Land Route | 31.12.2031 |  |  |  | Generator (Solar) | Granted
| 11 | NR | Rajasthan | bhadla-IV ps |  | Avaada Energy Private Limited |  | 2200001085 | [7 empty] | 700 | [12 empty] | 26.07.2024 | NHPC LOA | 30.04.2026 |  |  |  | Generator (Solar) | Granted
| 12 | NR | Rajasthan | Pali PS |  | Diyos Three Renewables Private Limited |  | 2200001100 | [7 empty] | 300 | [12 empty] | 31.07.2024 | Land BG Route | 01.04.2031 |  |  |  | Renewable Power Park developer (Solar) | Granted
| 1 |  | NR |  |  | Asian Fine Cements Private Limited |  | 2200001060 | [7 empty] | 4 | [12 empty] | 17.07.2024 |  | 01.09.2024 |  |  |  | Drawee entity connected to Intra State Transmission System | Granted
| 2 |  | NR |  |  | Ambuja Cements Limited |  | 2200001058 | [7 empty] | 10 | [12 empty] | 17.07.2024 |  | 01.09.2024 |  |  |  | Drawee entity connected to Intra State Transmission System | Granted
| 3 |  | NR |  |  | Ambuja Cements Limited |  | 2200001059 | [7 empty] | 3 | [12 empty] | 17.07.2024 |  | 01.09.2024 |  |  |  | Drawee entity connected to Intra State Transmission System | Granted
| 4 |  | NR |  |  | ACC Limited |  | 2200001081 | [7 empty] | 4.5 | [12 empty] | 26.07.2024 |  | 01.09.2024 |  |  |  | Drawee entity connected to Intra State Transmission System | Granted
| 5 |  | NR |  |  | Ambuja Cements Limited |  | 2200001101 | [7 empty] | 5.85 | [12 empty] | 31.07.2024 |  | 01.09.2024 |  |  |  | Drawee entity connected to Intra State Transmission System | Granted
| 1 |  | 16.11.2026 |  |  | 672 |  |  | Greenko UP01 IREP Private Limited | [19 empty] | 610 |  | 16.11.2026 |  |  |  | 672
| 2 |  | 31.03.2028 |  |  | 1120 |  |  | Avaada Waterbattery Private Limited | [19 empty] | 900 |  | 31.03.2028 |  |  |  | 1120
|  | NR | Rajasthan | Barmer-I |  | ENREN-I ENERGY PRIVATE LIMITED |  | 2200000286 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ANBOTO SOLAR PRIVATE LIMITED |  | 2200000281 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-I |  | AUXO SUNLIGHT PRIVATE LIMITED |  | 2200000312 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200000153 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000161 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Barmer-I |  | EDEN RENEWABLE CADET PRIVATE LIMITED |  | 2200000181 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ANBOTO SOLAR PRIVATE LIMITED |  | 2200000492 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | RENEW SUN POWER PRIVATE LIMITED |  | 2200000316 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ENFINITY GLOBAL SURYA KIRAN PRIVATE LIMITED |  | 2200000411 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ANDHRA PRADESH RESCO ROOFTOP SOLAR PRIVATE LIMITED |  | 2200000412 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | HINDUJA RENEWABLES ENERGY PRIVATE LIMITED |  | 2200000425 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-I |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000305 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | GREEN INFRA RENEWABLE PROJECTS LIMITED |  | 2200000410 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Barmer-II |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000636 | [6 empty] | Solar | 450
|  | NR | Rajasthan | Barmer-II |  | SPRNG URJA PRIVATE LIMITED |  | 2200000681 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Barmer-II |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000810 | [6 empty] | Solar | 717
|  | NR | Rajasthan | Barmer-II |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000906 | [6 empty] | Solar | 500
|  | NR | Rajasthan | Barmer-II |  | ADITYA BIRLA RENEWABLES LIMITED |  | 2200001128 | [6 empty] | Hybrid (RHGS) | 100
|  | NR | Rajasthan | Barmer-II |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000973 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Barmer-II |  | VISMAYA FIVE RENEWABLES PRIVATE LIMITED |  | 2200000954 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-II |  | VISMAYA FIVE RENEWABLES PRIVATE LIMITED |  | 2200001285 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Barmer-II |  | GREEN INFRA CLEAN SOLAR FARMS LIMITED |  | 2200000408 | [6 empty] | Solar | 130
|  | NR | Rajasthan | Barmer-II |  | SPRNG RENEWABLE RESOURCES PRIVATE LIMITED |  | 2200000531 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Barmer-II |  | SPRNG URJA PRIVATE LIMITED |  | 2200000539 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Barmer-II |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000567 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-II |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000580 | [6 empty] | Solar | 500
|  | NR | Rajasthan | Barmer-II |  | AMARESHA RENAWABLES INDIA PROJECT PRIVATE LIMITED |  | 2200000715 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-II |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000778 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | GREEN INFRA RENEWABLE ENERGY FARMS PRIVATE LIMITED |  | 2200001141 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II |  | ADANI RENEWABLE ENERGY HOLDING EIGHTEEN LIMITED |  | 2200001044 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bhadla-II |  | GREEN INFRA CLEAN WIND LIMITED |  | 2200000437 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II PS |  | NTPC Ltd. |  | St-II:1200002501 (300 MW) (TSSPDCL | 1200003110 | [5 empty] | Solar | 211.65
|  | NR | Rajasthan | Bhadla-II PS |  | NTPC Ltd. |  | St-II:1200002483 (300 MW) (TSSPDCL | 1200003109 | [5 empty] | Solar | 211.65
|  | NR | Rajasthan | Bhadla-II PS |  | NTPC Ltd. |  | St-II:1200002483 (300 MW) (TSNPDCL | 1200003120 | [5 empty] | Solar | 88.35
|  | NR | Rajasthan | Bhadla-II PS |  | NTPC Ltd. |  | St-II:1200002340 (250 MW) (TSNPDCL | 1200003122 | [5 empty] | Solar | 73.625
|  | NR | Rajasthan | Bhadla-II PS |  | NTPC Ltd. |  | St-II:1200002501 (300 MW) (TSNPDCL | 1200003121 | [5 empty] | Solar | 88.35
|  | NR | Rajasthan | Bhadla-II PS |  | ABC Solar (India) Private Limited |  | St-II:1200002359 (300 MW | 1200003357 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II PS |  | ACME Solar Holdings Private Limited |  | St-II:1200002471 (300 MW | 1200003505 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II PS |  | Azure Power India Private Limited |  | St-II: 1200002401 (500 MW | 1200003586 | [5 empty] | Solar | 267
|  | NR | Rajasthan | Bhadla-II PS |  | Azure Power India Private Limited |  | St-II:1200002403(500 MW | 1200003843 | [5 empty] | Solar | 50
|  | NR | Rajasthan | Bhadla-II PS |  | AMP Energy Green Private Limited |  | St-II:1200002676 (100 MW | 1200003882 | [5 empty] | Solar | 100
|  | NR | Rajasthan | Bhadla-II PS |  | AMP Energy Green Private Limited |  | 1200002987 (Enh.) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bhadla-II PS |  | Eden Renewable Alma Private Limited |  | 1200002554 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II PS |  | Solarpack Corporacion Technologica S.A. |  | 1200002742 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II PS |  | AMP Energy Green Pvt. Ltd. |  | 1200002559 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bhadla-II PS |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED |  | 2200000037 | [6 empty] | Solar | 450
|  | NR | Rajasthan | Bhadla-III |  | JUNIPER GREEN INDIA SIX PRIVATE LIMITED |  | 2200000062 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III |  | FRUGAL ENERGY PRIVATE LIMITED |  | 2200000118 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bhadla-III |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000144 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III |  | SOLARCRAFT POWER INDIA 4 PRIVATE LIMITED |  | 2200000192 | [6 empty] | Solar | 110
|  | NR | Rajasthan | Bhadla-III |  | GREEN INFRA CLEAN ENERGY GENERATION LIMITED |  | 2200000232 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III |  | RENEW SOLAR (SHAKTI SIX) PRIVATE LIMITED |  | 2200000275 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bhadla-III |  | MALUR RENEWABLES PRIVATE LIMITED |  | 2200000266 | [6 empty] | Solar | 650
|  | NR | Rajasthan | Bhadla-III |  | SOLARCRAFT POWER INDIA 4 PRIVATE LIMITED |  | 2200000300 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bhadla-III |  | RENEW SOLAR (SHAKTI SIX) PRIVATE LIMITED |  | 2200000309 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bhadla-III |  | PRERAK SOLAR URJA PRIVATE LIMITED |  | 2200000360 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bhadla-III |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000407 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bhadla-III PS |  | Juniper Green Beta Pvt. Ltd. |  | 412100013, 0312100013 (St-II), 1670400777119 (St-II) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bhadla-III PS |  | Tepsol Sun Sparkle Pvt. Ltd. |  | SW9990897533- M029_D001_A007- 1672319027575, 0212100030 (St-II) | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III PS |  | Juniper Green Beta Private Limited |  | 412100027 (SW5102826596- M029_D001_A003- 1670400777119 (10MW out of 70MW) + 0312100011 (40MW)) | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bhadla-III PS |  | ReNew Solar (Shakti Six) Private Limited |  | 1200003848 | [6 empty] | Solar | 550
|  | NR | Rajasthan | Bhadla-III PS |  | ReNew Solar (Shakti Six) Private Limited |  | 312100004 (Enh.) | [6 empty] | Solar | 450
|  | NR | Rajasthan | Bhadla-III PS |  | Abu Renewables India Private Limited |  | 212100026 | [6 empty] | Solar | 340
|  | NR | Rajasthan | Bhadla-III PS |  | Seven Renewable Power Pvt. Ltd. |  | 212100028 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III PS |  | Frugal Energy Pvt. Ltd. |  | 212100031 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bhadla-III PS |  | Bhadla Three SKP Green Ventures Pvt. Ltd. |  | 212100033 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000516 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000521 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Bhadla-IV |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000522 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | KANTIDA RENEWABLES INDIA PROJECT PRIVATE LIMITED |  | 2200000761 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000811 | [6 empty] | Solar | 765
|  | NR | Rajasthan | Bhadla-IV |  | DEMETER SUN POWER PRIVATE LIMITED |  | 2200000875 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001085 | [6 empty] | Solar | 700
|  | NR | Rajasthan | Bhadla-IV |  | VISMAYA FOUR RENEWABLES PRIVATE LIMITED |  | 2200000910 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bhadla-IV |  | VISMAYA FOUR RENEWABLES PRIVATE LIMITED |  | 2200001284 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner |  | AK RENEWABLE INFRA PRIVATE LIMITED |  | 2200000284 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner PS |  | Shikhar Surya (One) Private Limited |  | 1200003115 | [6 empty] | Solar | 70
|  | NR | Rajasthan | Bikaner PS |  | ReNew Surya Ravi Pvt. Ltd. |  | 1200003301 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner PS |  | Shikhar Surya (One) Private Limited |  | 1200003772 | [6 empty] | Solar | 105
|  | NR | Rajasthan | Bikaner PS |  | Shikhar Surya (One) Private Limited |  | 312100003 | [6 empty] | Solar | 125
|  | NR | Rajasthan | Bikaner-II PS |  | ACME Solar Holdings Private Limited |  | St-II:1200003683 (300 MW | 1200003829 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II PS |  | SJVN Limited |  | St- II:1200003559(1000MW | 1200003937 | [5 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-II PS |  | Onevolt Energy Private Limited |  | St-II:1200003626 (100 MW | 412100004 | [5 empty] | Solar | 62
|  | NR | Rajasthan | Bikaner-II PS |  | NHPC Ltd. |  | St-II:1200003915 (300 MW | 412100006 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II PS |  | Juniper Green Cosmic Private Limited |  | St-II:1200003740 (100 MW | 412100008 | [5 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-II PS |  | Grian Energy Private Limited |  | St-II: 1200003625 (100 MW) LTA: SW…1544323119(62 MW) | [6 empty] | Solar | 62
|  | NR | Rajasthan | Bikaner-II PS |  | Renew Dinkar Urja Pvt. Ltd. |  | St-II:1200003380 (200 MW | 1200003935 | [5 empty] | Solar | 200
|  | NR | Rajasthan | Bikaner-II PS |  | Amplus Ages Private Limited |  | SW9999482858- M029_D001_A007- 1671556542236 | [6 empty] | Solar | 62
|  | NR | Rajasthan | Bikaner-II PS |  | Prerak Greentech Private Limited |  | 412100025 | [6 empty] | Solar | 226
|  | NR | Rajasthan | Bikaner-II PS |  | Juna Renewable Energy Pvt Ltd |  | 1200003233 | [6 empty] | Solar | 290
|  | NR | Rajasthan | Bikaner-II PS |  | Juna Renewable Energy Pvt Ltd |  | 1200003389 | [6 empty] | Solar | 45
|  | NR | Rajasthan | Bikaner-II PS |  | Amplus Ages Private Limited |  | 1200003624 | [6 empty] | Solar | 38
|  | NR | Rajasthan | Bikaner-II PS |  | Grian Energy Private Limited |  | 1200003625 | [6 empty] | Solar | 38
|  | NR | Rajasthan | Bikaner-II PS |  | Onevolt Energy Private Limited |  | 1200003626 | [6 empty] | Solar | 38
|  | NR | Rajasthan | Bikaner-II PS |  | Khidrat Renewable Energy Private Limited |  | 1200003390 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II PS |  | Litsolaire Energy Private Limited |  | 1200003893 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-II PS |  | ALF Solar Amarsar Private Limited |  | 1200003785 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-II PS |  | ALF Solar Amarsar Private Limited |  | 1200003831 (Enh.) | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-II PS |  | Serentica Renewables India Pvt. Ltd. (erstwhile Sterlite Power Technologies Private Limited) |  | 1200003628 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-II PS |  | Serentica Renewables India Pvt. Ltd. (erstwhile Sterlite Power Technologies Private Limited) |  | 1200003838 | [6 empty] | Solar | 120
|  | NR | Rajasthan | Bikaner-II PS |  | Juniper Nirjara Energy Private Limited |  | 1200003623 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-II PS |  | Prerak Greentech Private Limited |  | 1200003770 | [6 empty] | Solar | 114
|  | NR | Rajasthan | Bikaner-II PS |  | Prerak Greentech Private Limited |  | 1200003839 | [6 empty] | Solar | 60
|  | NR | Rajasthan | Bikaner-II PS |  | ALF Solar Amarsar Private Limited |  | 312100008 (Enh.) | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-II PS |  | Sourya Manthan Renewable Energy Private Limited |  | 212100005 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-II PS 212100007 |  | Soltown Infra Private Limited (Park) | [8 empty] | Solar | 350
|  | NR | Rajasthan | Bikaner-II PS 212100008 |  | Soltown Infra Private Limited (Park) | [8 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-II PS 1200003889 |  | Soltown Infra Private Limited (Park) |  | (Enh.) | [6 empty] | Solar | 200
|  | NR | Rajasthan | Bikaner-III |  | JUNIPER GREEN COSMIC PRIVATE LIMITED |  | 2200000073 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-III |  | SUNBREEZE RENEWABLES NINE PRIVATE LIMITED |  | 2200000111 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-III |  | SUNBREEZE RENEWABLES NINE PRIVATE LIMITED |  | 2200000163 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000172 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000227 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000228 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III |  | MRS BUILDVISION PRIVATE LIMITED |  | 2200000098 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-III |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000179 | [6 empty] | Solar | 500
|  | NR | Rajasthan | Bikaner-III |  | DESHRAJ SOLAR ENERGY PRIVATE LIMITED |  | 2200000184 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-III |  | FIRST ENERGY PRIVATE LIMITED |  | 2200000221 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-III |  | SAIMAA SOLAR PRIVATE LIMITED |  | 2200000167 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000164 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III PS |  | Proteus Energy Private Limited (Park) |  | 212100042 | [6 empty] | Solar | 217
|  | NR | Rajasthan | Bikaner-III PS |  | TP Saurya Limited |  | 212100025 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | SJVN GREEN ENERGY LIMITED |  | 2200000423 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-IV |  | FURIES SOLREN PRIVATE LIMITED |  | 2200000419 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000244 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-IV |  | AVAADA RJBIKANER PRIVATE LIMITED |  | 2200000013 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-IV |  | SOLARCRAFT POWER INDIA 17 PRIVATE LIMITED |  | 2200000210 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | AVAADA RJBIKANER PRIVATE LIMITED |  | 2200000254 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Bikaner-IV |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000289 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | SHUDH SOLAR POWER PRIVATE LIMITED |  | 2200000306 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000308 | [6 empty] | Solar | 700
|  | NR | Rajasthan | Bikaner-IV |  | HAZEL HYBREN PRIVATE LIMITED |  | 2200000334 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | AM GREEN ENERGY PRIVATE LIMITED |  | 2200000319 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | FURIES SOLREN PRIVATE LIMITED |  | 2200000333 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | IRAAX INTERNATIONAL (OPC) PRIVATE LIMITED |  | 2200000343 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | CLEAN MAX GAMMA PRIVATE LIMITED |  | 2200000344 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000373 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000358 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000420 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-IV |  | SUNSURE SOLARPARK FOURTEEN PRIVATE LIMITED |  | 2200000285 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | SAURYA URJA COMPANY OF RAJASTHAN LIMITED |  | 2200000475 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-V |  | IRAAX INTERNATIONAL (OPC) PRIVATE LIMITED |  | 2200000484 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-V |  | IRAAX INTERNATIONAL (OPC) PRIVATE LIMITED |  | 2200000540 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-V |  | AVAADA RJBIKANER PRIVATE LIMITED |  | 2200000561 | [6 empty] | Solar | 136
|  | NR | Rajasthan | Bikaner-V |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000726 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-V |  | SA RENEWABLE INFRA PRIVATE LIMITED |  | 2200000755 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-V |  | VENA ENERGY VINDHYA WIND POWER PRIVATE LIMITED |  | 2200000796 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | SOLARCRAFT POWER INDIA 8 PRIVATE LIMITED |  | 2200000866 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200001021 | [6 empty] | Solar | 350
|  | NR | Rajasthan | Bikaner-V |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200001056 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-V |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200001261 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200001262 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | AVAADA SURYAENERGY PRIVATE LIMITED |  | 2200001254 | [6 empty] | Solar | 560
|  | NR | Rajasthan | Fatehgarh-II |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000387 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Fatehgarh-II |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000396 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Fatehgarh-II |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200001065 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Fatehgarh-II PS |  | NTPC Ltd. |  | St-II:1200002339 (150 MW)(TSNPDCL | 1200003124 | [5 empty] | Solar | 44.17
|  | NR | Rajasthan | Fatehgarh-II PS |  | NTPC Ltd. |  | St-II:1200002497(90 MW) (TSSPDCL | 1200003248 | [5 empty] | Solar | 63.5
|  | NR | Rajasthan | Fatehgarh-II PS |  | NTPC Ltd. |  | St-II:1200002497 (90 MW) (TSNPDCL | 1200003314 | [5 empty] | Solar | 26.5
|  | NR | Rajasthan | Fatehgarh-II PS |  | Adani Renewable Energy Holding Four Limited |  | St-II:1200002430 (500 MW | 1200003684 | [5 empty] | Solar | 500
|  | NR | Rajasthan | Fatehgarh-II PS |  | Eden Renewable Bercy Private Limited |  | St-II:1200002688 (300 MW | 1200003947 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III |  | JSW Renew Energy Five Limited |  | 212100039 | [6 empty] | Storage | 250
|  | NR | Rajasthan | Fatehgarh-III |  | JSW Renew Energy Five Limited |  | 212100040 | [6 empty] | Storage | 250
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | Khaba Renewable Energy Private Limited |  | 1200003502 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | ReNew Surya Jyoti Private Limited |  | 1200002746 | [6 empty] | Solar | 210
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | RENEW SURYA PRATAP PRIVATE LIMITED |  | 1200002778 | [6 empty] | Solar | 210
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | ReNew Solar (Shakti Three) Private Limited |  | 1200003447 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | ReNew Solar (Shakti Five) Private Limited |  | 1200003488 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | ReNew Solar (Shakti Five) Private Limited |  | 1200003496 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | ReNew Samir Shakti Private Limited |  | 1200003504 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | ReNew Samir Shakti Private Limited |  | 1200003514 (Enh. St-II) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | Energizent Power Private Limited |  | 1200002907 | [6 empty] | Solar | 125
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | Energizent Power Private Limited |  | 1200002939 | [6 empty] | Solar | 80
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | XL Xergi Power Private Limited |  | 412100020 (St-II: 1200002847) | [6 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000020 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | SPRNG POWER PRIVATE LIMITED |  | 2200000024 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | SPRNG ENERGY PRIVATE LIMITED |  | 2200000116 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200000123 | [6 empty] | Solar | 95
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | Serentica Renewable India Pvt. Ltd. |  | 212100034 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec-II) |  | Serentica Renewable India Pvt. Ltd. |  | 212100036 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III PS |  | Renew Surya Roshni Private Limited |  | St-II:1200002628(400 MW | 1200003269 | [5 empty] | Solar | 400
|  | NR | Rajasthan | Fatehgarh-III PS |  | ABC Renewable Energy Pvt. Ltd. |  | St-II:1200002699 (400 MW | 1200003096 | [5 empty] | Solar | 400
|  | NR | Rajasthan | Fatehgarh-III PS |  | ReNew Dinkar Jyoti Private Limited |  | St-II:1200003813 (100 MW | 1200003879 | [5 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III PS |  | IB Vogt Solar Seven Private Limited |  | St-II:1200002700 (300 MW | 1200003931 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III PS |  | XL Xergi Power Pvt. Ltd. |  | St-II:1200002847 (400 MW | 412100007 | [5 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-III PS |  | Azure Power India Private Limited |  | St-II:1200003532 (100 MW | 412100002 | [5 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-IV (Sec-I) |  | SPRNG AKSHAYA URJA PRIVATE LIMITED |  | 2200000065 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-IV (Sec-I) |  | BN HYBRID POWER-1 PRIVATE LIMITED |  | 2200000102 | [6 empty] | Hybrid (RHGS) | 180.8
|  | NR | Rajasthan | Fatehgarh-IV (Sec-I) |  | JUNIPER GREEN STELLAR PRIVATE LIMITED |  | 2200000063 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000077 | [6 empty] | Hybrid (RHGS) | 50
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | BN DISPATCHABLE-1 PRIVATE LIMITED |  | 2200000103 | [6 empty] | Hybrid (RHGS) | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | HELIA ENERGY PARK PRIVATE LIMITED |  | 2200000120 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | RADIANT STAR SOLAR PARK PRIVATE LIMITED |  | 2200000212 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | ABREL (RJ) PROJECTS LIMITED |  | 2200000140 | [6 empty] | Solar | 260
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED |  | 2200000138 | [6 empty] | Hybrid (RHGS) | 390
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000187 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | GAMMA RENEWABLES INDIA PROJECT ONE PRIVATE LIMITED |  | 2200000355 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000348 | [6 empty] | Solar | 900
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | GREEN INFRA CLEAN WIND TECHNOLOGY LIMITED |  | 2200000054 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | UTKRRISHT SOLAR ENERGY PRIVATE LIMITED |  | 2200000067 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000186 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec-II) |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000485 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Fatehgarh-IV PS |  | AMP Energy Green Pvt. Ltd. |  | St-II:1200003022 (130 MW | 1200003416 | [5 empty] | Solar | 130
|  | NR | Rajasthan | Fatehgarh-IV PS |  | ABC Renewable Energy Private Limited |  | St-II:1200003002 (380 MW | 1200003531 | [5 empty] | Solar | 380
|  | NR | Rajasthan | Fatehgarh-IV PS |  | Juniper Green Stellar Private Limited |  | 412100009 (St-II: 1200003827, 1200003910, 1200003958, 0312100010 & 0312100012) | [6 empty] | Hybrid | 150
|  | NR | Rajasthan | Fatehgarh-IV PS |  | AMP Energy Green Pvt. Ltd. |  | 412100019 (St-II: 0312100005) | [6 empty] | Hybrid | 120
|  | NR | Rajasthan | Fatehgarh-IV PS |  | ABC RJ Land 01 Private Limited |  | 1200003332 | [6 empty] | Solar | 110
|  | NR | Rajasthan | Fatehgarh-IV PS |  | ABC RJ Land 01 Private Limited |  | 1200003575 | [6 empty] | Solar | 270
|  | NR | Rajasthan | Fatehgarh-IV PS |  | Juniper Green Stellar Private Limited |  | 412100010 (St-II: 1200003827, 1200003910, 1200003958, 0312100010 & 0312100012) | [6 empty] | Hybrid | 150
|  | NR | Rajasthan | Fatehgarh-IV PS |  | AMP Energy Green Pvt. Ltd. |  | 312100007 | [6 empty] | Hybrid | 50
|  | NR | Rajasthan | Fatehgarh-IV PS |  | Cannice Renewables Energy Private Limited |  | 312100019 | [6 empty] | Hybrid | 90
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-I) |  | Luceo Solar Pvt. Ltd. |  | 212100032 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-I) |  | Luceo Solar Pvt. Ltd. |  | 0312100018 (Enhancement) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-II) |  | Helia Energy Park Private Limited |  | 212100035 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-II) |  | Radiant Star Solar Park Private Limited |  | 212100037 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-II) |  | EG Saur Urja Pvt. Ltd. (earlier Tepsol Saur Urja Private Limited) |  | 212100043 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-II) |  | Cannice Renewables Energy Private Limited |  | SW…1671600589106 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-II) |  | Cannice Renewable Energy Private Limited |  | 212100004 | [6 empty] | Solar | 80
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-II) |  | SPRNG PAVANA URJA PRIVATE LIMITED |  | 2200000018 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-II) |  | Sprng Pavana Urja Private Limited |  | 1200003719 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Fatehgarh-IV PS (Sec-II) |  | SPRNG PAVANA URJA PRIVATE LIMITED |  | 2200000034 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000850 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000886 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000887 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000888 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000889 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000890 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Jalore |  | SPRNG VAAYU URJA PRIVATE LIMITED |  | 2200001006 | [6 empty] | Solar | 600
|  | NR | Rajasthan Merta-II |  |  | BANYAN ENERGY PRIVATE LIMITED |  | 2200000823 | [6 empty] | Solar | 300
|  | NR | Rajasthan Merta-II |  |  | ACME SOLAR HOLDINGS PRIVATE LIMITED |  | 2200000840 | [6 empty] | Solar | 300
|  | NR | Rajasthan Merta-II |  |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED |  | 2200000848 | [6 empty] | Solar | 300
|  | NR | Rajasthan Merta-II |  |  | GREEN INFRA WIND ENERGY PRIVATE LIMITED |  | 2200000812 | [6 empty] | Solar | 300
|  | NR | Rajasthan Merta-II |  |  | GREEN INFRA WIND ENERGY PRIVATE LIMITED |  | 2200000813 | [6 empty] | Solar | 300
|  | NR | Rajasthan Merta-II |  |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000842 | [6 empty] | Solar | 300
|  | NR | Rajasthan Merta-II |  |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000879 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Ramgarh |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000499 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Ramgarh |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000550 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Ramgarh |  | MIGOS HYBREN PRIVATE LIMITED |  | 2200000618 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Ramgarh |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000661 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Ramgarh |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000662 | [6 empty] | Solar | 284
|  | NR | Rajasthan | Ramgarh |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000672 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Ramgarh |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000599 | [6 empty] | Solar | 500
|  | NR | Rajasthan | Ramgarh PS |  | Adani Renewable Energy Holding Four Ltd. |  | St-II: 1200002432(500 MW | 1200003689 | [5 empty] | Solar | 500
|  | NR | Rajasthan | Ramgarh PS |  | Adani Solar Energy AP Three Ltd. |  | 212100038 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Ramgarh-II |  | ADANI RENEWABLE ENERGY PARK RAJASTHAN LIMITED |  | 2200000600 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Ramgarh-II |  | ADANI RENEWABLE ENERGY PARK RAJASTHAN LIMITED |  | 2200000601 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Ramgarh-II |  | JSW NEO ENERGY LIMITED |  | 2200000689 | [6 empty] | Solar | 700
|  | NR | Rajasthan | Ramgarh-II |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000777 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Ramgarh-II |  | RJS RENEWABLES PRIVATE LIMITED |  | 2200000782 | [6 empty] | Wind | 150
|  | NR | Rajasthan | Ramgarh-II |  | SHN GREEN POWER PRIVATE LIMITED |  | 2200001198 | [6 empty] | Wind | 297
|  | NR | Rajasthan | Sanchore |  | HR SARASWATI ENERGY PRIVATE LIMITED |  | 2200000946 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000644 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | ILLUMINATE HYBREN PRIVATE LIMITED |  | 2200000646 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | VAYUNA RENEWABLES INDIA PROJECT PRIVATE LIMITED |  | 2200000758 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | CESC LTD |  | 2200000518 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000551 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Sirohi |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000779 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | IZHMA SOLAR PRIVATE LIMITED |  | 2200000743 | [6 empty] | Solar | 200
|  | NR | Rajasthan Barmer-III |  |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001026 | [6 empty] | Solar | 200
|  | NR | Rajasthan Barmer-III |  |  | FOXTROT SOLAR RENEWABLES ENERGY PRIVATE LIMITED |  | 2200001057 | [6 empty] | Solar | 100
|  | NR | Rajasthan Barmer-III |  |  | GREEN INFRA RENEWABLE ENERGY FARMS PRIVATE LIMITED |  | 2200001194 | [6 empty] | Solar | 300
|  | NR | Rajasthan Barmer-III |  |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001188 | [6 empty] | Solar | 250
|  | NR | Rajasthan Barmer-III |  |  | FOXTROT SOLAR RENEWABLES ENERGY PRIVATE LIMITED |  | 2200001252 | [6 empty] | Solar | 74
|  | NR | Rajasthan Barmer-III |  |  | FOXTROT SOLAR RENEWABLES ENERGY PRIVATE LIMITED |  | 2200001088 | [6 empty] | Solar | 80
|  | NR | Rajasthan Merta-III |  |  | ENREN-III ENERGY PRIVATE LIMITED |  | 2200000860 | [6 empty] | Solar | 300
|  | NR | Rajasthan Pali |  |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200001089 | [6 empty] | Solar | 300
|  | NR | Rajasthan Pali |  |  | DIYOS THREE RENEWABLES PRIVATE LIMITED |  | 2200001100 | [6 empty] | Solar | 300
|  | NR | UP | Orai |  | BUNDELKHAND SAUR URJA LIMITED |  | 2200000345 | [6 empty] | Solar | 1200
|  | NR | UP | Robertsganj |  | GREENKO UP01 IREP PRIVATE LIMITED |  | 2200000524 | [6 empty] | Pump Storage | 672
|  | NR | UP | Robertsganj |  | GREENKO UP01 IREP PRIVATE LIMITED |  | 2200000525 | [6 empty] | Pump Storage | 672
|  | NR | UP | Robertsganj |  | GREENKO UP01 IREP PRIVATE LIMITED |  | 2200000526 | [6 empty] | Pump Storage | 672
|  | NR | UP | Robertsganj |  | AVAADA WATERBATTERY PRIVATE LIMITED |  | 2200000553 | [6 empty] | Pump Storage | 1120
|  | NR | UP | Robertsganj |  | AVAADA WATERBATTERY PRIVATE LIMITED |  | 2200001086 | [6 empty] | Pump Storage | 520
|  | SR | Andhra Pradesh | Anantapur PS 2200000162 |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | [8 empty] | Wind | 295
|  | SR | Andhra Pradesh | Anantapur PS 2200000372 |  | RENEW VIKRAM SHAKTI PRIVATE LIMITED | [8 empty] | Hybrid (RHGS) | 160 (Solar:40 MW, Wind: 120 MW)
|  | SR | Andhra Pradesh | Anantapur PS 2200000069 |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED | [8 empty] | Wind | 400
|  | SR | Andhra Pradesh | Anantapur PS 2200000273 |  | ABC CT RE PARK (03) PRIVATE LIMITED | [8 empty] | Wind | 250
|  | SR | Andhra Pradesh | Anantapur PS 2200000318 |  | AYANA RENEWABLE POWER FOUR PRIVATE LIMITED | [8 empty] | Wind | 50
|  | SR | Andhra Pradesh | Anantapur PS 2200000032 |  | RENEW VIKRAM SHAKTI PRIVATE LIMITED | [8 empty] | Hybrid (RHGS) | Solar-750MW, Wind:960MW, BESS-288)
|  | SR | Andhra Pradesh | Anantapur PS 2200000271 |  | ABC CLEANTECH PRIVATE LIMITED | [8 empty] | Wind | 250
|  | SR | Andhra Pradesh | Anantapur PS 2200000274 |  | ABC CT RE PARK (02) PRIVATE LIMITED | [8 empty] | Wind | 250
|  | SR | Andhra Pradesh | Anantapur PS 2200000276 |  | ABC CT RE PARK (01) PRIVATE LIMITED | [8 empty] | Wind | 250
|  | SR | Andhra Pradesh | Anantapur PS 2200000713 |  | AMPLUS CENEDUS SOLAR PRIVATE LIMITED | [8 empty] | Wind | 350
|  | SR | Andhra Pradesh | Anantapur PS 2200000583 |  | RENEW VIKRAM SHAKTI PRIVATE LIMITED | [8 empty] | Wind | 140
|  | SR | Andhra Pradesh | Anantapur-II PS |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000872 | [6 empty] | Wind | 349.8
|  | SR | Andhra Pradesh | Anantapur-II PS |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000881 | [6 empty] | Wind | 339.9
|  | SR | Andhra Pradesh | Anantapur-II PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000780 | [6 empty] | Wind | 400
|  | SR | Andhra Pradesh | Anantapur-II PS |  | ORION HYBREN PRIVATE LIMITED |  | 2200001000 | [6 empty] | Hybrid (RHGS) | 300 MW (100 MW Wind, 200 MW Solar)
|  | SR | Andhra Pradesh | Anantapur-II PS |  | JSW NEO ENERGY LIMITED |  | 2200001074 | [6 empty] | Solar | 500
|  | SR | Andhra Pradesh | Anantapur-II PS |  | GREEN INFRA WIND ENERGY PRIVATE LIMITED |  | 2200000820 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh | Kurnool (new) |  | AM GREEN ENERGY PRIVATE LIMITED |  | 2200000012 | [6 empty] | Hybrid (RHGS) | 989 (Solar- 675MW, Wind:314MW)
|  | SR | Andhra Pradesh | Kurnool-III PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000335 | [6 empty] | Solar | Solar-400MW, BESS:380 MWh)
|  | SR | Andhra Pradesh | Kurnool-III PS |  | AMP ENERGY GREEN PRIVATE LIMITED |  | 2200000150 | [6 empty] | Hybrid (RHGS) | Total: 187 MW Solar: 137.5 MW Wind: 49.5 MW
|  | SR | Andhra Pradesh | Kurnool-III PS |  | AMP ENERGY C&I TWELVE PRIVATE LIMITED |  | 2200000231 | [6 empty] | Solar | 100
|  | SR | Andhra Pradesh | Kurnool-III PS |  | ADANI RENEWABLE ENERGY FORTY TWO LIMITED |  | 2200000158 | [6 empty] | Pump Storage | 600
|  | SR | Andhra Pradesh | Kurnool-III PS |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000383 | [6 empty] | Hybrid (RHGS) | Solar: 150MW Wind: 150MW BESS: 30MWh
|  | SR | Andhra Pradesh | Kurnool-III PS |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000236 | [6 empty] | Hybrid (RHGS) | Solar: 150 MW Wind:159 MW
|  | SR | Andhra Pradesh | Kurnool-III PS |  | AMPLUS EVEREST SOLAR PRIVATE LIMITED |  | 2200000543 | [6 empty] | Hybrid (RHGS) | 228(Solar:105M W; Wind: 126 MW)
|  | SR | Andhra Pradesh | Kurnool-III PS |  | AMPLUS IIFA SOLAR PRIVATE LIMITED |  | 2200000544 | [6 empty] | Hybrid (RHGS) | 228(Solar:105M W; Wind: 126 MW)
|  | SR | Andhra Pradesh | Kurnool-III PS |  | INDOSOL SOLAR PRIVATE LIMITED |  | 2200000733 | [6 empty] | Solar | 800
|  | SR | Andhra Pradesh | Kurnool-III PS |  | INDOSOL SOLAR PRIVATE LIMITED |  | 2200000734 | [6 empty] | Solar | 900
|  | SR | Andhra Pradesh | Kurnool-III PS |  | AMP ENERGY GREEN PRIVATE LIMITED |  | 2200000229 | [6 empty] | Hybrid (RHGS) | Solar: 85 MW Wind:118.8 MW
|  | SR | Andhra Pradesh | Kurnool-III PS |  | INDOSOL SOLAR PRIVATE LIMITED |  | 2200000735 | [6 empty] | Solar | 900
|  | SR | Andhra Pradesh | Kurnool-III PS |  | INDOSOL SOLAR PRIVATE LIMITED |  | 2200000736 | [6 empty] | Solar | 900
|  | SR | Andhra Pradesh | Kurnool-III PS |  | ADANI RENEWABLE ENERGY FIFTY ONE LIMITED |  | 2200000508 | [6 empty] | Pump Storage | 1250
|  | SR | Andhra Pradesh | Kurnool-IV PS 2200000844 |  | SAEL INDUSTRIES LIMITED | [8 empty] | Solar | 300
|  | SR | Andhra Pradesh | Kurnool-IV PS 2200001099 |  | PRATAPATI ENERGY (SEVEN) PRIVATE LIMITED | [8 empty] | Hybrid (RHGS) | 354 (Solar-255 MW, Wind- 99MW)
|  | SR | Andhra Pradesh | Nellore PS |  | JINDAL POWER LIMITED |  | 2200000633 | [6 empty] | Solar | 52.6
|  | SR | Andhra Pradesh | NP Kunta PS |  | FIRST ENERGY PRIVATE LIMITED |  | 2200000388 | [6 empty] | Solar | 100
|  | SR | Andhra Pradesh | NP Kunta PS |  | NHPC LIMITED |  | 2200000250 | [6 empty] | Solar | 100
|  | SR | AP | Kurnool (new) |  | Greenko AP01 IREP Pvt. Ltd |  | LTA app no.1200003664 | [6 empty] | Hybrid | 900
|  | SR | AP | Kurnool (new) |  | Greenko AP01 IREP Pvt. Ltd |  | LTA app no. 450200009 | [6 empty] | PSP | 565
|  | SR | AP | Kurnool (new) |  | Greenko AP01 IREP Pvt. Ltd. |  | 350200006 | [6 empty] | PSP | 260
|  | SR | AP | Ramagundam 1200002271 |  | NTPC Ltd. (Ramagundam FSP) | [8 empty] | Solar | 100
|  | SR | AP | Simhadri |  | NTPC Ltd. (Simhadri FSP) |  | 1200002272 | [6 empty] | Solar | 25
|  | SR | Karnataka Bidar PS |  |  | WELSPUN NARMADA PRIVATE LIMITED |  | 2200000716 | [6 empty] | Hybrid (RHGS) | 250 (150 MW Wind & 100 MW Solar)
|  | SR | Karnataka Bidar PS |  |  | SAEL INDUSTRIES LIMITED |  | 2200000759 | [6 empty] | Solar | 300
|  | SR | Karnataka Bidar PS |  |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000422 | [6 empty] | Hybrid (RHGS) | Solar: 188MW Wind: 201 MW BESS: 30MWh
|  | SR | Karnataka Bidar PS |  |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000640 | [6 empty] | Hybrid (RHGS) | Total: 312 MW Solar: 132 MW Wind:180 MW
|  | SR | Karnataka Bidar PS |  |  | PULSE HYBREN PRIVATE LIMITED |  | 2200001001 | [6 empty] | Solar | 300
|  | SR | Karnataka Bidar PS |  |  | QUEST HYBREN PRIVATE LIMITED |  | 2200001002 | [6 empty] | Solar | 300
|  | SR | Karnataka Bidar PS |  |  | AMPIN ENERGY UTILITY PRIVATE LIMITED |  | 2200000762 | [6 empty] | Hybrid (RHGS) | 185.4 (Solar- 135; Wind 50.4)
|  | SR | Karnataka Bidar PS |  |  | AMPIN ENERGY UTILITY PRIVATE LIMITED |  | 2200000763 | [6 empty] | Hybrid (RHGS) | 185.4 (Solar- 135; Wind 50.4)
|  | SR | Karnataka Bidar PS |  |  | AMPIN ENERGY UTILITY PRIVATE LIMITED |  | 2200000892 | [6 empty] | Hybrid (RHGS) | 185.4 (Solar- 135; Wind 50.4)
|  | SR | Karnataka Bijapur PS |  |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000393 | [6 empty] | Wind | 252
|  | SR | Karnataka Bijapur PS |  |  | TEQ GREEN POWER XVI PRIVATE LIMITED |  | 2200000397 | [6 empty] | Wind | 125
|  | SR | Karnataka Bijapur PS |  |  | TEQ GREEN POWER XVI PRIVATE LIMITED |  | 2200000429 | [6 empty] | Wind | 175
|  | SR | Karnataka Bijapur PS |  |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000447 | [6 empty] | Wind | 50.4
|  | SR | Karnataka Bijapur PS |  |  | UPC RENEWABLES INDIA MANAGEMENT PRIVATE LIMITED |  | 2200000584 | [6 empty] | Wind | 160
|  | SR | Karnataka Bijapur PS |  |  | TEPSOL GREEN ENERGY PRIVATE LIMITED |  | 2200000657 | [6 empty] | Hybrid (RHGS) | 200 (Wind- 160 & Solar-40)
|  | SR | Karnataka Bijapur PS |  |  | EG SOLWIN RENEWABLES PRIVATE LIMITED |  | 2200000687 | [6 empty] | Wind | 100
|  | SR | Karnataka Bijapur PS |  |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000586 | [6 empty] | Wind | 252
|  | SR |  | Karnataka Davangere PS 2200000714 |  | GENTARI RENEWABLES INDIA CASTOR ONE PVT. LTD | [8 empty] | Wind | 350
|  | SR |  | Karnataka Davangere PS 2200000932 |  | JSW NEO ENERGY LIMITED | [8 empty] | Wind | 325
|  | SR |  | Karnataka Davangere PS 2200000876 |  | JADE HYBREN PRIVATE LIMITED | [8 empty] | Hybrid (RHGS) | 300(Solar-200 MW, Wind-100 MW)
|  | SR |  | Karnataka Davangere PS 2200000625 |  | LAYER HYBREN PRIVATE LIMITED | [8 empty] | Hybrid (RHGS) | 140 (100- Solar; 40 Wind)
|  | SR |  | Karnataka Davangere PS 2200000660 |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | [8 empty] | Hybrid (RHGS) | 720(Solar:360 MW; Wind: 360)
|  | SR |  | Karnataka Davangere PS 2200000701 |  | ILLUMINATE HYBREN PRIVATE LIMITED | [8 empty] | Solar | 300
|  | SR |  | Karnataka Davangere PS 2200000700 |  | FURIES SOLREN PRIVATE LIMITED | [8 empty] | Solar | 300
|  | SR |  | Karnataka Davangere PS 2200000702 |  | LAYER HYBREN PRIVATE LIMITED | [8 empty] | Hybrid (RHGS) | 160 (110- Solar; 50 Wind)
|  | SR | Karnataka Gadag PS |  |  | Azure Power India Pvt. Ltd. |  | LTA app no. 451100008 (120 MW) & 0451100003 (50 MW) | [6 empty] | Wind | 170
|  | SR | Karnataka Gadag PS |  |  | Green Infra Wind |  | LTA app no. 451100007 | [6 empty] | Wind | 178.5
|  | SR | Karnataka Gadag PS |  |  | ReNew Naveen Urja Pvt. Ltd |  | LTA app no. 451100009 | [6 empty] | Wind | 300
|  | SR | Karnataka Gadag PS |  |  | Serentica Renewables India Pvt. Ltd |  | 451100011 | [6 empty] | Hybrid | 132
|  | SR | Karnataka Gadag PS |  |  | Serentica Renewables India Pvt. Ltd |  | 1200003761 | [6 empty] | Hybrid | 107
|  | SR | Karnataka Gadag PS |  |  | Serentica Renewables India Pvt. Ltd |  | 1200003828 | [6 empty] | Hybrid | 66
|  | SR | Karnataka Gadag PS |  |  | Serentica Renewables India Pvt. Ltd |  | 451100010 | [6 empty] | Hybrid | 165
|  | SR | Tamil Nadu | Karur PS |  | LTA app no. 1200003536 JSW Neo Energy Ltd. (earstwhile JSW Future Energy Ltd.) | [8 empty] | Wind | 150
|  | SR | Tamil Nadu | Karur PS |  | JSW Renew Energy |  | LTA app no. 1200003533 (170 MW) | [6 empty] | Wind | 170
|  | SR | Tamil Nadu | Karur PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000242 | [6 empty] | Wind | 198
|  | SR | Tamil Nadu | Karur PS |  | FIRST ENERGY PRIVATE LIMITED |  | 2200000441 | [6 empty] | Wind | 100
|  | SR | Tamil Nadu | Karur PS |  | JSP GREEN WIND 1 PRIVATE LIMITED |  | 2200000438 | [6 empty] | Wind | 300
|  | SR | Tamil Nadu | Karur PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000448 | [6 empty] | Wind | 93.6
|  | SR | Tamil Nadu | Karur PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000967 | [6 empty] | Wind | 82.5
|  | SR | Tamil Nadu | Karur PS |  | NANNAI SOLAR PARK PRIVATE LIMITED |  | 2200000628 | [6 empty] | Wind | 93
|  | SR | Tamil Nadu | Pugalur |  | SPRNG AKSHAYA URJA PRIVATE LIMITED |  | 2200000197 | [6 empty] | Wind | 52.8
|  | SR | Tamil Nadu | Pugalur |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000394 | [6 empty] | Wind | 151
|  | SR | Tamil Nadu | Pugalur |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000449 | [6 empty] | Wind | 151.2
|  | SR | Tamil Nadu | Tuticorin-II PS |  | GRT JEWELLERS (INDIA) PRIVATE LIMITED |  | 2200000594 | [6 empty] | Solar | 150
|  | WR | Gujarat | Bhuj PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000218 | [6 empty] | Wind | 155
|  | WR | Gujarat | Bhuj PS |  | SEVEN RENEWABLE POWER PRIVATE LIMITED |  | 2200000317 | [6 empty] | Wind | 50
|  | WR | Gujarat | Bhuj PS |  | NLC INDIA LIMITED |  | 2200000386 | [6 empty] | Solar | 200
|  | WR | Gujarat | Bhuj PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000566 | [6 empty] | Wind | 20
|  | WR | Gujarat | Bhuj PS |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000658 | [6 empty] | Wind | 99
|  | WR | Gujarat | Bhuj PS |  | NLC INDIA LIMITED |  | 2200000729 | [6 empty] | Solar | 100
|  | WR | Gujarat | Bhuj PS |  | OYSTER GREEN HYBRID ONE PRIVATE LIMITED |  | 2200000783 | [6 empty] | Wind | 99
|  | WR | Gujarat | Bhuj PS |  | NLC INDIA LIMITED |  | 2200000808 | [6 empty] | Wind | 50
|  | WR | Gujarat | Bhuj PS |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED |  | 2200000981 | [6 empty] | Wind | Wind - 75.6, BESS - 20)
|  | WR | Gujarat | Bhuj PS |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED |  | 2200000634 | [6 empty] | Solar | 600
|  | WR | Gujarat | Bhuj-II PS |  | SJVN GREEN ENERGY LIMITED |  | 2200000204 | [6 empty] | Solar | 360
|  | WR | Gujarat | Bhuj-II PS |  | ABREL (RJ) PROJECTS LIMITED |  | 2200000288 | [6 empty] | Hybrid (RHGS) | 314
|  | WR | Gujarat | Bhuj-II PS |  | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED |  | 2200000321 | [6 empty] | Hybrid (RHGS) | 362
|  | WR | Gujarat | Bhuj-II PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000382 | [6 empty] | Solar | 350
|  | WR | Gujarat | Bhuj-II PS |  | CGE RENEWABLES PRIVATE LIMITED |  | 2200000389 | [6 empty] | Hybrid (RHGS) | Wind: 30 MW Solar: 60 MW
|  | WR | Gujarat | Bhuj-II PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000431 | [6 empty] | Wind | 50
|  | WR | Gujarat | Bhuj-II PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000444 | [6 empty] | Solar | 100
|  | WR | Gujarat | Bhuj-II PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000497 | [6 empty] | Wind | 100
|  | WR | Gujarat | Bhuj-II PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000537 | [6 empty] | Solar | 300
|  | WR | Gujarat | Jam Khambhaliya PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000180 | [6 empty] | Wind | 500
|  | WR | Gujarat | Jam Khambhaliya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000142 | [6 empty] | Hybrid (RHGS) | 25 MW Wind + 25 MW Solar
|  | WR | Gujarat | Jam Khambhaliya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000190 | [6 empty] | Wind | 100
|  | WR | Gujarat | Jam Khambhaliya PS |  | Powerica Limited |  | 230700018 | [6 empty] | Wind | 53
|  | WR | Gujarat | Jam Khambhaliya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000209 | [6 empty] | Wind | 200
|  | WR | Gujarat | Jam Khambhaliya PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000565 | [6 empty] | Wind | 80
|  | WR | Gujarat | Jam Khambhaliya PS |  | MOUNTING RENEWABLE POWER LIMITED |  | 2200000246 | [6 empty] | Hybrid (RHGS) | 250
|  | WR | Gujarat | Jam Khambhaliya PS |  | AIRPOWER WINDFARMS PRIVATE LIMITED |  | 2200000261 | [6 empty] | Wind | 175
|  | WR | Gujarat | Jam Khambhaliya PS |  | ACME SUN POWER PRIVATE LIMITED |  | 2200000263 | [6 empty] | Wind | 400
|  | WR | Gujarat | Jam Khambhaliya PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000241 | [6 empty] | Wind | 545
|  | WR | Gujarat | Jam Khambhaliya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000445 | [6 empty] | Wind | 100
|  | WR | Gujarat | Jam Khambhaliya PS |  | POWERICA LIMITED |  | 2200000473 | [6 empty] | Wind | 50
|  | WR | Gujarat | Jam Khambhaliya PS |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED |  | 2200000503 | [6 empty] | Wind | 308.49
|  | WR | Gujarat | Jam Khambhaliya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000556 | [6 empty] | Wind | 200
|  | WR | Gujarat | Jam Khambhaliya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000253 | [6 empty] | Wind | 100
|  | WR | Gujarat | Jam Khambhaliya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000379 | [6 empty] | Wind | 200
|  | WR | Gujarat | Jam Khambhaliya PS |  | MALAREN SOLAR PRIVATE LIMITED |  | 2200000337 | [6 empty] | Solar | 150
|  | WR | Gujarat | KPS1 |  | ADANI GREEN ENERGY LIMITED |  | 2200000478 | [6 empty] | Hybrid (RHGS) | 650
|  | WR | Gujarat | KPS1 |  | ADANI GREEN ENERGY LIMITED |  | 2200000479 | [6 empty] | Hybrid (RHGS) | 100
|  | WR | Gujarat | KPS1 |  | ADANI GREEN ENERGY LIMITED |  | 2200000784 | [6 empty] | Wind | 60
|  | WR | Gujarat | KPS-1 (Sec-I) |  | Adani Green Energy Limited Connectivity: 230700008; LTA: 430700009 (1050MW); |  | 230700008 | [6 empty] | Hybrid | 1250
|  | WR | Gujarat | KPS-1 (Sec-I) |  | Adani Green Energy Ltd. |  | 1670426092248 | [6 empty] | Hybrid | 1050
|  | WR | Gujarat | KPS-1 (Sec-II) |  | Adani Green Energy Limited Connectivity: 230700006; LTA: 430700007 (1000MW); |  | 230700006 | [6 empty] | Hybrid | 1200
|  | WR | Gujarat | KPS-1 (Sec-II) |  | Adani Green Energy Limited Connectivity: 230700007; LTA: 430700008 (1000MW); |  | 230700007 | [6 empty] | Hybrid | 1166.4
|  | WR | Gujarat | KPS-1 (Sec-II) |  | Adani Green Energy Limited Connectivity: 1670426695890; LTA: 1670929494955 (250MW); |  | SW6949744157- M029_D001_A002- 1670426695890 | [6 empty] | Wind | 250
|  | WR | Gujarat | KPS-1 (Sec-II) |  | Sarjan Realities Pvt. Ltd. (SRPL) |  | 230700011 | [6 empty] | Hybrid | 1150
|  | WR | Gujarat | KPS-2 |  | Gujarat State Electricity Corporation Limited Connectivity: 1200003331 (600MW); LTA: 1200003326 (100MW) & 1200003327 (500MW); |  | 1200003331 | [6 empty] | Solar | 600
|  | WR | Gujarat | KPS-2 |  | Gujarat Industries Power Company Limited Connectivity: 1200003371; LTA: 1200003372; |  | 1200003371 | [6 empty] | Solar | 600
|  | WR | Gujarat | KPS-2 |  | NTPC Renewable Energy Limited (NREL) Connectivity: 1200003585 (265MW); LTA: 1200003712 (265+100MW); |  | 1200003585 | [6 empty] | Solar | 265
|  | WR | Gujarat | KPS-2 |  | NTPC Renewable Energy Limited (NREL) Connectivity: 1200003733 (100MW); LTA: 1200003712 (265+100MW); |  | 1200003733 | [6 empty] | Solar | 100
|  | WR | Gujarat | KPS-2 |  | NTPC Renewable Energy Limited (NREL) Connectivity: 1200003953 (890MW); LTA: 0430700002 (500); |  | 1200003953 | [6 empty] | Solar | 890
|  | WR | Gujarat | KPS-2 |  | Gujarat State Electricity Corporation Limited Connectivity: 230700005; LTA: 430000002; |  | 230700005 | [6 empty] | Solar | 1000
|  | WR | Gujarat | KPS-2 |  | NTPC Renewable Energy Limited (NREL) |  | 1200003953 | [6 empty] | Solar | 390
|  | WR | Gujarat | KPS-2 |  | NTPC Renewable Energy Limited (NTPC REL) |  | 330700007 | [6 empty] | Solar | 300
|  | WR | Gujarat | KPS3 |  | ADANI GREEN ENERGY LIMITED |  | 2200000476 | [6 empty] | Hybrid (RHGS) | 1250
|  | WR | Gujarat | KPS3 |  | ADANI GREEN ENERGY LIMITED |  | 2200000477 | [6 empty] | Hybrid (RHGS) | 75
|  | WR | Gujarat | KPS3 |  | ADANI GREEN ENERGY LIMITED |  | 2200000602 | [6 empty] | Hybrid (RHGS) | 65 MW (Solar: 50MW Wind: 35MW)
|  | WR | Gujarat | KPS3 |  | ADANI GREEN ENERGY LIMITED |  | 2200000786 | [6 empty] | Wind | 195
|  | WR | Gujarat | KPS3 |  | ADANI GREEN ENERGY LIMITED |  | 2200000953 | [6 empty] | Hybrid (RHGS) | 1530 MW (Solar:1400 MW & Wind:130 MW)
|  | WR | Gujarat | KPS-3 (Sec-I) |  | Adani Green Energy Limited Connectivity: 230700009; LTA: 430700010 (1050MW); |  | 230700009 | [6 empty] | Hybrid | 1250
|  | WR | Gujarat | KPS-3 (Sec-I) |  | Sarjan Realities Pvt. Ltd. (SRPL) |  | 230700012 | [6 empty] | Hybrid | 1332
|  | WR | Gujarat | KPS-3 (Sec-I) |  | Sarjan Realities Pvt. Ltd. (SRPL) |  | 230700014 | [6 empty] | Hybrid | 1100
|  | WR | Gujarat | KPS-3 (Sec-I) |  | NTPC Renewable Energy Limited |  | 230700010 | [6 empty] | Solar | 1200
|  | WR | Gujarat | KPS-3 (Sec-II) |  | Sarjan Realities Pvt. Ltd. (SRPL) |  | 230700013 | [6 empty] | Hybrid | 1250
|  | WR | Gujarat | KPS-3 (Sec-II) |  | NHPC Limited |  | 230700015 | [6 empty] | Solar | 600
|  | WR | Gujarat | Lakadiya PS |  | AVAADA INCLEAN PRIVATE LIMITED |  | 2200000011 | [6 empty] | Solar | 50
|  | WR | Gujarat | Lakadiya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000131 | [6 empty] | Solar | 300
|  | WR | Gujarat | Lakadiya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000200 | [6 empty] | Solar | 200
|  | WR | Gujarat | Lakadiya PS |  | ARCELORMITTAL NIPPON STEEL INDIA LIMITED |  | 2200000324 | [6 empty] | Hybrid (RHGS) | 550 (Wind 250MW+Solar 300MW)
|  | WR | Gujarat | Lakadiya PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000610 | [6 empty] | Hybrid (RHGS) | 480 (240 MW: Wind 240 MW: Solar)
|  | WR | Gujarat | Lakadiya PS |  | RDS SOLAR PARK PRIVATE LIMITED |  | 2200000639 | [6 empty] | Solar | 350
|  | WR | Gujarat | Lakadiya PS |  | PERCENTUM RENEWABLES PRIVATE LIMITED |  | 2200000673 | [6 empty] | Hybrid (RHGS) | 100MW: Solar 200MW: Wind Revised to 50MW Solar & 98MW Wind.
|  | WR | Gujarat | Lakadiya PS |  | RENEW SOLAR (SHAKTI EIGHT) PRIVATE LIMITED |  | 2200000341 | [6 empty] | Solar | 200
|  | WR | Gujarat | Lakadiya PS |  | TEQ GREEN POWER XVI PRIVATE LIMITED |  | 2200000398 | [6 empty] | Wind | 76
|  | WR | Gujarat | Lakadiya PS |  | RENEW SOLAR (SHAKTI EIGHT) PRIVATE LIMITED |  | 2200000403 | [6 empty] | Solar | 100
|  | WR | Gujarat | Lakadiya PS |  | TEQ GREEN POWER XVI PRIVATE LIMITED |  | 2200000427 | [6 empty] | Wind | 76
|  | WR | Gujarat | Lakadiya PS |  | TEQ GREEN POWER XVII PRIVATE LIMITED |  | 2200000311 | [6 empty] | Hybrid (RHGS) | 300 (200MW Solar & 100MW Wind: as per letter dated 30.11.2023 from applicant)
|  | WR | Gujarat | Lakadiya PS |  | GANEKO SOLAR PRIVATE LIMITED |  | 2200000458 | [6 empty] | Hybrid (RHGS) | 337.36
|  | WR | Gujarat | Lakadiya PS |  | GANEKO SOLAR PRIVATE LIMITED |  | 2200000515 | [6 empty] | Hybrid (RHGS) | 11.63
|  | WR | Gujarat | Lakadiya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000500 | [6 empty] | Wind | 150
|  | WR | Gujarat | Lakadiya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000511 | [6 empty] | Solar | 200
|  | WR | Gujarat | Radhanesda PS |  | SPRNG POWER EARTH PRIVATE LIMITED |  | 2200000247 | [6 empty] | Solar | 250
|  | WR | Gujarat | Radhanesda PS |  | SPRNG ENERGY PRIVATE LIMITED |  | 2200000461 | [6 empty] | Solar | 100
|  | WR | Gujarat | Radhanesda PS |  | SPRNG ENERGY PRIVATE LIMITED |  | 2200000460 | [6 empty] | Solar | 150
|  | WR | Gujarat | Radhanesda PS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000546 | [6 empty] | Solar | 50
|  | WR | Gujarat | Raghanesda PS |  | JSW NEO ENERGY LIMITED |  | 2200001014 | [6 empty] | Solar | 200
|  | WR | Gujarat | Raghanesda PS |  | JSW NEO ENERGY LIMITED |  | 2200001020 | [6 empty] | Solar | 200
|  | WR | Gujarat | Raghanesda PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000993 | [6 empty] | Solar | 300
|  | WR | Gujarat | Raghanesda PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000988 | [6 empty] | Solar | 300
|  | WR | Gujarat | Raghanesda PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000989 | [6 empty] | Solar | 100
|  | WR | Gujarat | Raghanesda PS |  | SPRNG WIND ENERGY PRIVATE LIMITED |  | 2200000612 | [6 empty] | Solar | 200
|  | WR | Gujarat | Raghanesda PS |  | SPRNG OJAS PRIVATE LIMITED |  | 2200000614 | [6 empty] | Solar | 200
|  | WR | Gujarat | Raghanesda PS |  | SPRNG VAYU KIRAN PRIVATE LIMITED |  | 2200000650 | [6 empty] | Solar | 200
|  | WR | Madhya Pradesh | Indore (PG) |  | RENEW URJA SHACHAR PRIVATE LIMITED |  | 2200000070 | [6 empty] | Wind | 300
|  | WR | Madhya Pradesh | Indore (PG) |  | RENEW SAMIR URJA PRIVATE LIMITED |  | 2200000298 | [6 empty] | Wind | 300
|  | WR | Madhya Pradesh | Mandsaur PS |  | GREENKO MP01 IREP PRIVATE LIMITED |  | 2200000089 | [6 empty] | Pump Storage | 504
|  | WR | Madhya Pradesh | Mandsaur PS |  | GREENKO MP01 IREP PRIVATE LIMITED |  | 2200000090 | [6 empty] | Pump Storage | 504
|  | WR | Madhya Pradesh | Mandsaur PS |  | GREENKO MP01 IREP PRIVATE LIMITED |  | 2200000091 | [6 empty] | Pump Storage | 504
|  | WR | Madhya Pradesh | Mandsaur PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000924 | [6 empty] | Solar | 150
|  | WR | Madhya Pradesh | Mandsaur PS |  | BHOJRAJ RENEWABLES ENERGY PRIVATE LIMITED |  | 2200000899 | [6 empty] | Wind | 300
|  | WR | Madhya Pradesh | Mandsaur PS |  | ADYANT ENERSOL PRIVATE LIMITED |  | 2200000976 | [6 empty] | Hybrid (RHGS) | 84 MW (60 MW Solar + 24 MW Wind)
|  | WR | Madhya Pradesh | Mandsaur PS |  | GANEKO ONE ENERGY PRIVATE LIMITED |  | 2200000720 | [6 empty] | Hybrid (RHGS) | Solar - 255 MW, Wind - 99 MW
|  | WR | Madhya Pradesh | Mandsaur PS |  | ADYANT POWER PRIVATE LIMITED |  | 2200000798 | [6 empty] | Hybrid (RHGS) | 200 (SOLAR 101 MW WIND 99 MW)
|  | WR | Madhya Pradesh | Mandsaur PS |  | ASNEN SOLAR PRIVATE LIMITED |  | 2200000752 | [6 empty] | Solar | 200
|  | WR | Madhya Pradesh | Mandsaur PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000428 | [6 empty] | Wind | 300
|  | WR | Madhya Pradesh | Neemuch PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000728 | [6 empty] | Solar | 500
|  | WR | Madhya Pradesh | Neemuch PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000938 | [6 empty] | Solar | 500
|  | WR | Madhya Pradesh | Pachora PS |  | BLUE LEAF ENERGY RENEWABLES PRIVATE LIMITED (BLERPL) |  | 2200000030 | [6 empty] | Solar | 235
|  | WR | Madhya Pradesh | Pachora PS |  | VEH SAUR URJA PRIVATE LIMITED (VSUPL ) |  | 2200000085 | [6 empty] | Wind | 163.2
|  | WR | Madhya Pradesh | Pachora PS |  | ABENERGIA RENEWABLES PRIVATE LIMITED |  | 2200000086 | [6 empty] | Hybrid (RHGS) | 100
|  | WR | Madhya Pradesh | Pachora PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000267 | [6 empty] | Solar | 250
|  | WR | Madhya Pradesh | Pachora PS |  | ABENERGIA RENEWABLES PRIVATE LIMITED |  | 2200000342 | [6 empty] | Hybrid (RHGS) | 81
|  | WR | Madhya Pradesh | Pachora PS |  | BHOJRAJ DEVELOPERS PRIVATE LIMITED |  | 2200000404 | [6 empty] | Hybrid (RHGS) | Wind: 160 MW Solar: 26 MW
|  | WR | Madhya Pradesh | Pachora PS |  | VEH DAMEN POWER PRIVATE LIMITED |  | 2200000356 | [6 empty] | Wind | 76.8
|  | WR | Madhya Pradesh | Pachora PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000502 | [6 empty] | Solar | 400
|  | WR | Madhya Pradesh | Pachora PS |  | AVAADA ENERGY PRIVATE LIMITED (AEPL) |  | 2200000082 | [6 empty] | Solar | 50
|  | WR | Madhya Pradesh | Pachora PS |  | JADE HYBREN PRIVATE LIMITED |  | 2200000617 | [6 empty] | Solar | 300
|  | WR | Madhya Pradesh | Pachora PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000817 | [6 empty] | Hybrid (RHGS) | 334 (250 MW Solar + 84 MW Wind)
|  | WR | Madhya Pradesh | Pachora PS |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000883 | [6 empty] | Wind | 297
|  | WR | Madhya Pradesh | Pachora PS |  | WAFT ENERGY PRIVATE LIMITED |  | 2200000923 | [6 empty] | Wind | 100
|  | WR | Madhya Pradesh | Pachora PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000956 | [6 empty] | Solar | 240
|  | WR | Madhya Pradesh | Pachora PS |  | OYSTER GREEN HYBRID THREE PRIVATE LIMITED |  | 2200000995 | [6 empty] | Hybrid (RHGS) | 140 (Solar: 100 MW Wind: 40 MW)
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG AKSHAYA URJA PRIVATE LIMITED |  | 2200000039 | [6 empty] | Wind | 100
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000028 | [6 empty] | Wind | 42
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000022 | [6 empty] | Wind | 100
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG AKSHAYA URJA PRIVATE LIMITED |  | 2200000133 | [6 empty] | Wind | 67.2
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000340 | [6 empty] | Wind | 82
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000819 | [6 empty] | Wind | 16.8
|  | WR | Maharash tra | Dhule PS (Sec- I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000081 | [6 empty] | Wind | 50
|  | WR | Maharash tra | Dhule PS (Sec- I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001036 | [6 empty] | Wind | 160
|  | WR | Maharash tra | Dhule PS (Sec- I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001035 | [6 empty] | Wind | 80
|  | WR | Maharash tra | Kallam PS |  | TEQ GREEN POWER XI PRIVATE LIMITED (TGPXIPL) |  | 2200000035 | [6 empty] | Wind | 29.7
|  | WR | Maharash tra | Kallam PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000193 | [6 empty] | Wind | 101
|  | WR | Maharash tra | Kallam PS |  | TORRENT SOLAR POWER PRIVATE LIMITED |  | 2200000198 | [6 empty] | Wind | 250
|  | WR | Maharash tra | Kallam PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000277 | [6 empty] | Wind | 200
|  | WR | Maharash tra | Kallam PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000302 | [6 empty] | Wind | 100
|  | WR | Maharash tra | Kallam PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200001090 | [6 empty] | Wind | 150
|  | WR | Maharash tra | Kallam PS |  | Serentica Renewables India 4 Pvt. Ltd. (SRI4PL) |  | 231400004 | [6 empty] | Wind | 10
|  | WR | Maharash tra | Kallam PS |  | Serentica Renewables India 4 Pvt. Ltd. (SRI4PL) |  | 331400007 | [6 empty] | Wind | 140
|  | WR | Maharash tra | Kallam PS |  | ReNew Green (MHP One) Private Limited |  | 1200003942 | [6 empty] | Wind | 33
|  | WR | Maharash tra | Kallam PS |  | TEQ Green Power XI Pvt. Ltd.(TGPXIPL) |  | 1200003901 | [6 empty] | Wind | 200
|  | WR | Maharash tra | Kallam PS |  | TEQ Green Power XI Pvt. Ltd.(TGPXIPL) |  | 1200003944 | [6 empty] | Wind | 99
|  | WR | Maharash tra | Kallam PS |  | TEQ Green Power XI Pvt. Ltd.(TGPXIPL) |  | 331400002 | [6 empty] | Wind | 21.6
|  | WR | Maharash tra | Kallam PS |  | Torrent Solar Power Private Limited (TSPPL) |  | 1670224223993 | [6 empty] | Wind | 66
|  | WR | Maharash tra | Kallam PS |  | Torrent Solar Power Private Limited (TSPPL) |  | 331400013 | [6 empty] | Wind | 92
|  | WR | Maharash tra | Kallam PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000395 | [6 empty] | Wind | 101
|  | WR | Maharash tra | Kallam PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000450 | [6 empty] | Wind | 100.8
|  | WR | Maharash tra | Kallam PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000075 | [6 empty] | Wind | 50
|  | WR | Maharash tra | Kallam PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000353 | [6 empty] | Wind | 250
|  | WR | Maharash tra | Parli |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000747 | [6 empty] | Wind | 180
|  | WR | Maharash tra | Parli (New) |  | Renew Pawan Shakti Private Limited (RPSPL) |  | 231400018 | [6 empty] | Wind | 277
|  | WR | Maharash tra | Parli (New) |  | Renew Pawan Shakti Private Limited (RPSPL) |  | 331400012 | [6 empty] | Wind | 23
|  | WR | Maharash tra | Parli PG SS |  | Renew Tej Shakti Private Limited(RTSPL) |  | 231400008 | [6 empty] | Wind | 180
|  | WR | Maharash tra | Parli PG SS |  | Renew Tej Shakti Private Limited(RTSPL) |  | 231400009 | [6 empty] | Wind | 69
|  | WR | Maharash tra | Parli PG SS |  | Renew Tej Shakti Private Limited(RTSPL) |  | 231400010 | [6 empty] | Wind | 51
|  | WR | Maharash tra | Solapur PG |  | ReNew Green Energy Solutions Pvt. Ltd. |  | 331400004 | [6 empty] | Solar | 32
|  | WR | Maharash tra | Solapur PG |  | ReNew Green Energy Solutions Pvt. Ltd. |  | 1670048864400 | [6 empty] | Solar | 50
|  | WR | Maharash tra | Solapur PG |  | ReNew Green Energy Solutions Pvt. Ltd. |  | 331400010 | [6 empty] | Solar | 70
|  | WR | Maharash tra | Solapur PG |  | ReNew Green Energy Solutions Pvt. Ltd. |  | 331400014 | [6 empty] | Solar | 100
|  | WR | Maharash tra | Solapur PG |  | RENEW GREEN ENERGY SOLUTIONS PRIVATE LIMITED |  | 2200000155 | [6 empty] | Wind | 73
|  | WR | Maharash tra | Solapur PG |  | JSW RENEW ENERGY THIRTEEN LIMITED |  | 2200001148 | [6 empty] | Solar | 300
|  | WR | Maharash tra | Solapur PG |  | WAAREE FOREVER ENERGIES PRIVATE LIMITED |  | 2200001158 | [6 empty] | Solar | 1000
|  | WR | Maharash tra | Solapur PS |  | SOLARCRAFT POWER INDIA 7 PRIVATE LIMITED |  | 2200000270 | [6 empty] | Wind | 52.8
|  | WR | Maharash tra | Solapur PS |  | JSW NEO ENERGY LIMITED |  | 2200000718 | [6 empty] | Wind | 300
|  | WR | Maharash tra | Solapur PS |  | SOLARCRAFT POWER INDIA 16 PVT. LTD. |  | 2200000440 | [6 empty] | Hybrid (RHGS) | Wind - 191.4 MW, Solar - 56 MW, BESS - 91 MW)
|  | WR | Maharash tra | Solapur PS |  | SKADAR SOLAR PRIVATE LIMITED |  | 2200000754 | [6 empty] | Solar | 200
|  | WR | Maharash tra | Solapur PS |  | SOLARCRAFT POWER INDIA 20 PRIVATE LIMITED |  | 2200000795 | [6 empty] | Hybrid (RHGS) | Wind - 66 MW, Solar - 18.75 MW, BESS - 12.56MW
|  | WR | Maharash tra | Solapur PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000083 | [6 empty] | Wind | 50
|  | WR | Maharash tra | Solapur PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000132 | [6 empty] | Hybrid (RHGS) | 25 MW Wind + 25 MW Solar
|  | WR | Maharash tra | Solapur PS |  | GANEKO TWO ENERGY PRIVATE LIMITED |  | 2200001008 | [6 empty] | Hybrid (RHGS) | 354 MW (Solar: 255 Wind: 99)
|  | WR | Maharash tra | South Kalamb 2200000177 |  | THE TATA POWER COMPANY LIMITED | [8 empty] | Pump Storage | 1150
|  | WR | MP | Mandsaur PS |  | WAAREE RENEWABLE TECHNOLOGIES LIMITED |  | 2200001192 | [6 empty] | Solar | 300
|  | WR | MP | Mandsaur PS |  | ADYANT ENERSOL PRIVATE LIMITED |  | 2200001214 | [6 empty] | Hybrid (RHGS) | 164 MW Hybrid (NTPC LOA: 70 MW Solar + 24 MW Wind and SJVN LOA: 70 MW Wind)
|  | WR | MP | Mandsaur PS |  | ACME SOLAR HOLDINGS LIMITED |  | 2200001289 | [6 empty] | Solar | 200
|  | WR | MP | Mandsaur PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001280 | [6 empty] | Solar | 300
|  | WR | MP | Mandsaur PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001279 | [6 empty] | Solar | 300
|  | WR | MP | Mandsaur PS |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED |  | 2200001037 | [6 empty] | Hybrid (RHGS) | Solar- 135 MW Wind - 160 MW BESS - 40
|  | WR | MP | Neemuch PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000991 | [6 empty] | Solar | 200
|  | WR | MP | Rajgarh SS |  | Sprng Vayu Vidyut Pvt Ltd (SVVPL) |  | 1200003510 | [6 empty] | Wind | 50.4
|  | WR | MP | Rajgarh SS |  | Sprng Vayu Vidyut Pvt Ltd (SVVPL) |  | 1200003345 | [6 empty] | Wind | 55.44
|  | WR | MP | Rajgarh SS |  | Sprng Vayu Vidyut Pvt Ltd (SVVPL) |  | 331300005 | [6 empty] | Wind | 50.4
|  | WR | MP | Rajgarh SS |  | Veh Jayin Renewables Private Limited |  | 231300002 | [6 empty] | Wind | 151.8
|  | WR | Maharashtra | Solapur PG |  | NTPC LIMITED |  | 2200001878 | [6 empty] | Solar | 13
|  | WR | Gujarat | Lakadiya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000131 | [6 empty] | Solar | 300
|  | WR | Gujarat | Lakadiya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000200 | [6 empty] | Solar | 200
|  | WR | Gujarat | Bhuj PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000218 | [6 empty] | Wind | 155
|  | WR | Madhya Pradesh | Indore (PG) |  | RENEW URJA SHACHAR PRIVATE LIMITED |  | 2200000070 | [6 empty] | Wind | 300
|  | WR | Gujarat | KPS-2 (Sec-I) |  | Gujarat State Electricity Corporation Limited Connectivity: 1200003331 (600MW); LTA: 1200003326 (100MW) & 1200003327 (500MW); |  | 1200003331 | [6 empty] | Solar | 600
|  | WR | Gujarat | KPS-2 (Sec-I) |  | Gujarat Industries Power Company Limited Connectivity: 1200003371; LTA: 1200003372; |  | 1200003371 | [6 empty] | Solar | 600
|  | WR | Gujarat | KPS-2 (Sec-II) |  | NTPC Renewable Energy Limited (NREL) Connectivity: 1200003585 (265MW); LTA: 1200003712 (265+100MW); |  | 1200003585 | [6 empty] | Solar | 265
|  | WR | Gujarat | KPS-2 (Sec-II) |  | NTPC Renewable Energy Limited (NREL) Connectivity: 1200003733 (100MW); LTA: 1200003712 (265+100MW); |  | 1200003733 | [6 empty] | Solar | 100
|  | WR | Gujarat | KPS-2 (Sec-II) |  | NTPC Renewable Energy Limited (NREL) Connectivity: 1200003953 (890MW); LTA: 0430700002 (500); |  | 1200003953 | [6 empty] | Solar | 890
|  | WR | Maharashtra | Parli PG SS |  | Renew Tej Shakti Private Limited(RTSPL) |  | 231400008 | [6 empty] | Wind | 180
|  | WR | Maharashtra | Parli PG SS |  | Renew Tej Shakti Private Limited(RTSPL) |  | 231400009 | [6 empty] | Wind | 69
|  | WR | Maharashtra | Parli PG SS |  | Renew Tej Shakti Private Limited(RTSPL) |  | 231400010 | [6 empty] | Wind | 51
|  | SR | Tamil Nadu | Karur PS |  | JSW NEO ENERGY LIMITED |  | 2200000818 | [6 empty] | Hybrid (RHGS) | 175
|  | WR | Gujarat | Bhuj PS |  | AYANA RENEWABLE POWER FOUR PRIVATE LIMITED |  | 2200000239 | [6 empty] | Hybrid (RHGS) | 129.9
|  | WR | Gujarat | KPS-1 (Sec-I) |  | Adani Green Energy Limited Connectivity: 230700008; LTA: 430700009 (1050MW); |  | 230700008 | [6 empty] | Hybrid (RHGS) | 1250
|  | WR | Gujarat | KPS-1 (Sec-II) |  | Adani Green Energy Limited Connectivity: 230700006; LTA: 430700007 (1000MW); |  | 230700006 | [6 empty] | Hybrid (RHGS) | 1200
|  | WR | Gujarat | KPS-1 (Sec-II) |  | Adani Green Energy Limited Connectivity: 230700007; LTA: 430700008 (1000MW); |  | 230700007 | [6 empty] | Hybrid (RHGS) | 1166.4
|  | WR | Gujarat | KPS-2 (Sec-I) |  | Gujarat State Electricity Corporation Limited Connectivity: 230700005; |  | 230700005 | [6 empty] | Solar | 1000
|  | WR | Gujarat | KPS-3 (Sec-I) |  | Adani Green Energy Limited Connectivity: 230700009; LTA: 430700010 (1050MW); |  | 230700009 | [6 empty] | Hybrid (RHGS) | 1250
|  | WR | Gujarat | Lakadiya PS |  | AVAADA INCLEAN PRIVATE LIMITED |  | 2200000011 | [6 empty] | Solar | 50
|  | WR | Maharashtra | Solapur PG |  | RENEW GREEN ENERGY SOLUTIONS PRIVATE LIMITED |  | 2200000155 | [6 empty] | Wind | 73
|  | WR | Maharashtra | Kallam PS |  | Serentica Renewables India 4 Pvt. Ltd. (SRI4PL) |  | 231400004 | [6 empty] | Wind | 10
|  | WR | Maharashtra | Kallam PS |  | Serentica Renewables India 4 Pvt. Ltd. (SRI4PL) |  | 331400007 | [6 empty] | Wind | 140
|  | WR | Maharashtra | Kallam PS |  | ReNew Green (MHP One) Private Limited |  | 1200003942 | [6 empty] | Wind | 33
|  | WR | Maharashtra | Kallam PS |  | TEQ Green Power XI Pvt. Ltd.(TGPXIPL) |  | 1200003901 | [6 empty] | Wind | 200
|  | WR | Maharashtra | Kallam PS |  | TEQ Green Power XI Pvt. Ltd.(TGPXIPL) |  | 1200003944 | [6 empty] | Wind | 99
|  | WR | Maharashtra | Kallam PS |  | TEQ Green Power XI Pvt. Ltd.(TGPXIPL) |  | 331400002 | [6 empty] | Wind | 21.6
|  | WR | Maharashtra | Kallam PS |  | Torrent Solar Power Private Limited (TSPPL) |  | 1670224223993 | [6 empty] | Wind | 66
|  | WR | Maharashtra | Kallam PS |  | Torrent Solar Power Private Limited (TSPPL) |  | 331400013 | [6 empty] | Wind | 92
|  | WR | Maharashtra | Kallam PS |  | TEQ GREEN POWER XI PRIVATE LIMITED (TGPXIPL) |  | 2200000035 | [6 empty] | Wind | 29.7
|  | WR | Maharashtra | Kallam PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000193 | [6 empty] | Wind | 101
|  | WR | Maharashtra | Kallam PS |  | TORRENT SOLAR POWER PRIVATE LIMITED |  | 2200000198 | [6 empty] | Wind | 250
|  | WR | Maharashtra | Kallam PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000277 | [6 empty] | Wind | 200
|  | WR | Maharashtra | Kallam PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000302 | [6 empty] | Wind | 100
|  | WR | Maharashtra | Kallam PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200001090 | [6 empty] | Wind | 150
|  | WR | Maharashtra | Kallam PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200001244 | [6 empty] | Wind | 111.8
|  | WR | Gujarat | Bhuj PS |  | SEVEN RENEWABLE POWER PRIVATE LIMITED |  | 2200000317 | [6 empty] | Wind | 50
|  | WR | Gujarat | Bhuj PS |  | NLC INDIA LIMITED |  | 2200000386 | [6 empty] | Solar | 200
|  | WR | Madhya Pradesh | Rajgarh SS |  | Veh Jayin Renewables Private Limited |  | 231300002 | [6 empty] | Wind | 151.8
|  | WR | Madhya Pradesh | Rajgarh SS |  | Veh Wind Energy Private Limited |  | 231300004 | [6 empty] | Wind | 75
|  | SR | Andhra Pradesh 30-11-25 | Anantapur PS |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED |  | 2200000162 | [6 empty] | Wind | 295
|  | SR | Andhra Pradesh 30-11-25 | Anantapur PS |  | AYANA RENEWABLE POWER FOUR PRIVATE LIMITED |  | 2200000318 | [6 empty] | Wind | 50
|  | NR | Rajasthan | Bhadla-II |  | NTPC Ltd. |  | St-II:1200002501 (300 MW) (TSSPDCL | 1200003110 | [5 empty] | Solar | 211.65
|  | NR | Rajasthan | Bhadla-II |  | NTPC Ltd. |  | St-II:1200002483 (300 MW) (TSSPDCL | 1200003109 | [5 empty] | Solar | 211.65
|  | NR | Rajasthan | Bhadla-II |  | NTPC Ltd. |  | St-II:1200002483 (300 MW) (TSNPDCL | 1200003120 | [5 empty] | Solar | 88.35
|  | NR | Rajasthan | Bhadla-II |  | ABC Solar (India) Private Limited |  | St-II:1200002359 (300 MW | 1200003357 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II |  | ACME Solar Holdings Private Limited |  | St-II:1200002471 (300 MW | 1200003505 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II |  | Azure Power India Private Limited |  | St-II: 1200002401 (500 MW | 1200003586 | [5 empty] | Solar | 267
|  | NR | Rajasthan | Bhadla-II |  | Azure Power India Private Limited |  | St-II: 1200002401 (500 MW) (233 out of 500 MW) 1200002403(500 MW) (100 | [6 empty] | Solar | 333
|  | NR | Rajasthan | Bhadla-II |  | Adani Renewable Energy Holding Four Ltd. |  | St-II:1200002428 (500 MW | 1200003685 | [5 empty] | Solar | 500
|  | NR | Rajasthan | Bhadla-II |  | Azure Power India Private Limited |  | St-II:1200002403(500 MW | 1200003843 | [5 empty] | Solar | 50
|  | NR | Rajasthan | Bhadla-II |  | AMP Energy Green Private Limited |  | St-II:1200002676 (100 MW | 1200003882 | [5 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner |  | The Tata Power Company Limited |  | St-II:1200003027 (110 MW | 1200003583 | [5 empty] | Solar | 110
|  | NR | Rajasthan | Bikaner |  | Ayana Renewable Power Three Private Limited |  | St-II:1200002986 (300 MW | 1200003933 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner |  | Shikhar Surya (One) Private Limited |  | 1200003115 | [6 empty] | Solar | 70
|  | NR | Rajasthan | Bikaner |  | ReNew Surya Ravi Pvt. Ltd. |  | 1200003301 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II |  | ACME Solar Holdings Private Limited |  | St-II:1200003683 (300 MW | 1200003829 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II |  | SJVN Limited |  | St-II:1200003559(1000MW | 1200003937 | [5 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-II |  | Onevolt Energy Private Limited |  | St-II:1200003626 (100 MW | 412100004 | [5 empty] | Solar | 62
|  | NR | Rajasthan | Bikaner-II |  | NHPC Ltd. |  | St-II:1200003915 (300 MW | 412100006 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II |  | Juniper Green Cosmic Private Limited |  | St-II:1200003740 (100 MW | 412100008 | [5 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-II |  | Grian Energy Private Limited |  | St-II: 1200003625 (100 MW) LTA: SW…1544323119(62 MW) | [6 empty] | Solar | 62
|  | NR | Rajasthan | Bikaner-II |  | Renew Dinkar Urja Pvt. Ltd. |  | St-II:1200003380 (200 MW | 1200003935 | [5 empty] | Solar | 200
|  | NR | Rajasthan | Bikaner-II |  | Amplus Ages Private Limited |  | SW9999482858- M029_D001_A007- 1671556542236 | [6 empty] | Solar | 62
|  | NR | Rajasthan | Bikaner-II |  | Prerak Greentech Private Limited |  | 412100025 | [6 empty] | Solar | 226
|  | NR | Rajasthan | Bikaner-II |  | Juna Renewable Energy Pvt Ltd |  | 1200003233 | [6 empty] | Solar | 290
|  | NR | Rajasthan | Bikaner-II |  | Juna Renewable Energy Pvt Ltd |  | 1200003389 | [6 empty] | Solar | 45
|  | NR | Rajasthan | Bikaner-II |  | Serentica Renewables India Pvt. Ltd. (erstwhile Sterlite Power Technologies Private Limited) |  | 412100014 (1200003838-St-II) | [6 empty] | Solar | 180
|  | NR | Rajasthan | Fatehgarh-II |  | NTPC Ltd. |  | St-II:1200002339 (150 MW)(TSNPDCL | 1200003124 | [5 empty] | Solar | 44.17
|  | NR | Rajasthan | Fatehgarh-II |  | NTPC Ltd. |  | St-II:1200002497(90 MW) (TSSPDCL | 1200003248 | [5 empty] | Solar | 63.5
|  | NR | Rajasthan | Fatehgarh-II |  | NTPC Ltd. |  | St-II:1200002497 (90 MW) (TSNPDCL | 1200003314 | [5 empty] | Solar | 26.5
|  | NR | Rajasthan | Fatehgarh-II |  | Adani Renewable Energy Holding Four Limited |  | St-II:1200002430 (500 MW | 1200003684 | [5 empty] | Solar | 500
|  | NR | Rajasthan | Fatehgarh-II |  | Eden Renewable Bercy Private Limited |  | St-II:1200002688 (300 MW | 1200003947 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec- I) |  | Renew Surya Roshni Private Limited |  | St-II:1200002628(400 MW | 1200003269 | [5 empty] | Solar | 400
|  | SR | Karnataka | Gadag PS |  | Azure Power India Pvt. Ltd. |  | Connectivity Appl No.- 1200003497; LTA app no. 451100008 (120 MW) & | [6 empty] | Wind | 170
|  | SR | Karnataka | Gadag PS |  | Green Infra Wind Connectivity Appl No.- 0451100007 |  | LTA app no. 451100007 | [6 empty] | Wind | 178.5
|  | SR | Karnataka | Gadag PS |  | ReNew Naveen Urja Pvt. Ltd |  | LTA app no. 451100009 | [6 empty] | Wind | 300
|  | SR | Karnataka | Gadag PS |  | Serentica Renewables India Pvt. Ltd |  | 451100011 | [6 empty] | Hybrid (RHGS) | 132
|  | SR | Karnataka | Gadag PS |  | Serentica Renewables India Pvt. Ltd |  | 1200003761 | [6 empty] | Hybrid (RHGS) | 107
|  | SR | Karnataka | Gadag PS |  | Serentica Renewables India Pvt. Ltd |  | 1200003828 | [6 empty] | Hybrid (RHGS) | 66
|  | SR | Karnataka | Gadag PS |  | Serentica Renewables India Pvt. Ltd |  | 451100010 | [6 empty] | Hybrid (RHGS) | 165
|  | SR | Karnataka | Gadag PS |  | Green Infra Wind Energy Limited |  | 251100003 | [6 empty] | Wind | 70
|  | SR | Karnataka | Gadag PS |  | Green Infra Wind Energy Limited |  | 351100002 | [6 empty] | Wind | 50
|  | SR | Karnataka | Gadag PS |  | Green Infra Wind Energy Limited |  | SW5958957243-M029_D001_A007- 1670310631002 | [6 empty] | Wind | 1.5
|  | SR | Karnataka | Hiriyur |  | Zenataris Renewable Energy Pvt. Ltd. |  | 251100011 | [6 empty] | Wind | 66
|  | SR | Karnataka | Hiriyur |  | ZENATARIS RENEWABLE ENERGY PRIVATE LIMITED |  | 2200000061 | [6 empty] | Wind | 171.6
|  | SR | Tamil Nadu | Karur PS |  | JSW Renew Energy Connectivity Appl No.-1200002868 |  | LTA app no. 1200003533 (170 MW) Connectivity Appl No.-1200002868 | [6 empty] | Wind | 170
|  | SR | Tamil Nadu | Karur PS |  | JSW Neo Energy Ltd. (earstwhile JSW Future Energy Ltd.) |  | LTA app no. 1200003536 | [6 empty] | Wind | 150
|  | SR | Tamil Nadu | Karur PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000242 | [6 empty] | Wind | 198
|  | SR | Karnataka | Koppal PS |  | Tunga Renewables Energy Pvt. Ltd. Connectivity Appl No.- 1200003577 |  | LTA app no. 1200003577 | [6 empty] | Wind | 189.84
|  | SR | Karnataka | Koppal PS |  | Project Ten Renewable Power Pvt. Ltd. ( Connectivity Appl No.-1200003530) |  | 1200003530 LTA app no. 0451100005 | [6 empty] | Wind | 150
|  | SR | Karnataka | Koppal PS |  | Kleio Solar Power Pvt. Ltd. |  | 1200003825 | [6 empty] | Hybrid (RHGS) | 209.39999999 999998
|  | SR | Karnataka | Koppal PS |  | Tunga Renewable Energy Pvt. Ltd. |  | 1200003849 | [6 empty] | Wind | 45.07
|  | SR | Karnataka | Koppal PS |  | Tunga Renewable Energy Pvt. Ltd. |  | 1200003392 | [6 empty] | Wind | 115
|  | SR | Karnataka | Koppal PS |  | Serentica Renewable India 1 Pvt. |  | 1200003822 | [6 empty] | Hybrid (RHGS) | 13.333333333 333334
|  | SR | Karnataka | Koppal PS |  | Serentica Renewable India 1 Pvt. |  | 1200003909 | [6 empty] | Hybrid (RHGS) | 120
|  | SR | Karnataka | Koppal PS |  | Serentica Renewable India 1 Pvt. |  | 451100013 | [6 empty] | Hybrid (RHGS) | 133.33333333 333334
|  | SR | Andhra Pradesh 30-11-25 | Kurnool (new) |  | Greenko AP01 IREP Pvt. Ltd (Connectivity Appl No.- 1200002672) |  | LTA app no.1200003664 | [6 empty] | Hybrid (RHGS) | 900
|  | SR | Andhra Pradesh 30-11-25 | Kurnool (new) |  | Greenko AP01 IREP Pvt. Ltd Connectivity Appl No.-1200003962 ) |  | LTA app no. 450200009 | [6 empty] | PSP | 565
|  | SR | Andhra Pradesh 30-11-25 | Kurnool (new) |  | Greenko AP01 IREP Pvt. Ltd. |  | 350200006 | [6 empty] | PSP | 260
|  | SR | Andhra Pradesh 30-11-25 | Kurnool (new) |  | AM GREEN ENERGY PRIVATE LIMITED |  | 2200000012 | [6 empty] | Hybrid (RHGS) | 989 (Solar- 675MW, Wind:314MW)
|  | SR | Andhra Pradesh 30-11-25 | Kurnool-III PS |  | AMP ENERGY GREEN PRIVATE LIMITED |  | 2200000150 | [6 empty] | Hybrid (RHGS) | Total: 187 MW Solar: 137.5
|  | SR | Andhra Pradesh 30-11-25 | Kurnool-III PS |  | AMP ENERGY C&I TWELVE PRIVATE LIMITED |  | 2200000231 | [6 empty] | Solar | 100
|  | SR | Andhra Pradesh 30-11-25 | Kurnool-III PS |  | SAEL INDUSTRIES LIMITED |  | 2200000329 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 30-11-25 | Kurnool-III PS |  | SAEL INDUSTRIES LIMITED |  | 2200000330 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 30-11-25 | Kurnool-III PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000335 | [6 empty] | Solar | Solar-400MW, 400
|  | SR | Andhra Pradesh 30-11-25 | NP Kunta PS |  | NHPC LIMITED |  | 2200000250 | [6 empty] | Solar | 100
|  | SR | Andhra Pradesh 30-11-25 | Nellore PS |  | JINDAL POWER LIMITED |  | 2200000633 | [6 empty] | Solar | 52.6
|  | SR | Karnataka | Pavagada PS |  | Project Ten Renewable Power Pvt. Ltd. |  | LTA app no. 451100004 | [6 empty] | Wind | 300
|  | SR | Karnataka | Pavagada PS |  | Solar Energy Corporation of India Ltd. |  | 1200003590 | [6 empty] | Solar | 200
|  | SR | Tamil Nadu | Pugalur |  | SPRNG AKSHAYA URJA PRIVATE LIMITED |  | 2200000197 | [6 empty] | Wind | 52.8
|  | SR | Andhra Pradesh 30-11-25 | Ramagundam |  | NTPC Ltd. (Ramagundam FSP) |  | 1200002271 | [6 empty] | Solar | 100
|  | SR | Andhra Pradesh 30-11-25 | Simhadri |  | NTPC Ltd. (Simhadri FSP) |  | 1200002272 | [6 empty] | Solar | 25
|  | SR | Tamil Nadu | Tuticorin-II PS |  | JSW RENEW ENERGY TWELVE LIMITED |  | 2200001115 | [6 empty] | Hybrid (RHGS) | 175
|  | SR | Tamil Nadu | Tuticorin-II PS |  | JSW GREEN ENERGY ONE LIMITED |  | 2200001120 | [6 empty] | Solar | 50
|  | SR | Tamil Nadu | Karur PS |  | JSP GREEN WIND 1 PRIVATE LIMITED |  | 2200000438 | [6 empty] | Wind | 300
|  | NR | Rajasthan | Bikaner |  | Shikhar Surya (One) Private Limited |  | 1200003772 | [6 empty] | Solar | 105
|  | NR | Rajasthan | Bikaner |  | Shikhar Surya (One) Private Limited |  | 312100003 | [6 empty] | Solar | 125
|  | NR | Rajasthan | Bikaner-II |  | TP Saurya Limited |  | 1200003582 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II |  | Amplus Ages Private Limited |  | 1200003624 | [6 empty] | Solar | 38
|  | NR | Rajasthan | Bikaner-II |  | Grian Energy Private Limited |  | 1200003625 | [6 empty] | Solar | 38
|  | NR | Rajasthan | Bikaner-II |  | Onevolt Energy Private Limited |  | 1200003626 | [6 empty] | Solar | 38
|  | NR | Rajasthan | Bikaner-II |  | Khidrat Renewable Energy Private Limited |  | 1200003390 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II |  | Litsolaire Energy Private Limited |  | 1200003893 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-II |  | ALF Solar Amarsar Private Limited |  | 1200003785 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-II |  | ALF Solar Amarsar Private Limited |  | 1200003831 (Enh.) | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-II |  | Serentica Renewables India Pvt. Ltd. (erstwhile Sterlite Power Technologies Private Limited) |  | 1200003628 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-II |  | Serentica Renewables India Pvt. Ltd. (erstwhile Sterlite Power Technologies Private Limited) |  | 1200003838 | [6 empty] | Solar | 120
|  | NR | Rajasthan | Bikaner-II |  | Juniper Nirjara Energy Private Limited |  | 1200003623 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-II |  | Prerak Greentech Private Limited |  | 1200003770 | [6 empty] | Solar | 114
|  | NR | Rajasthan | Bikaner-II |  | Prerak Greentech Private Limited |  | 1200003839 | [6 empty] | Solar | 60
|  | SR | Karnataka | Gadag-II PS |  | Green Infra Wind Energy Ltd. |  | 251100010 | [6 empty] | Wind | 300
|  | SR | Karnataka | Gadag-II PS |  | TP Saurya Ltd. |  | 251100006 | [6 empty] | Wind | 200
|  | SR | Karnataka | Gadag-II PS |  | Tata Power Renewable Energy Ltd. |  | 251100012 | [6 empty] | Wind | 170
|  | SR | Karnataka | Gadag-II PS |  | Tata Power Renewable Energy Ltd. |  | 351100009 | [6 empty] | Wind | 170
|  | SR | Karnataka | Gadag-II PS |  | GREENKO KA01 IREP PRIVATE LIMITED |  | 2200000088 | [6 empty] | Pump Storage | 640
|  | SR | Karnataka | Koppal-II PS |  | Tata Power Renewable Energy Ltd. |  | 251100021 | [6 empty] | Wind | 300
|  | SR | Karnataka | Koppal-II PS |  | TATA Power Renewable Energy Ltd. |  | 251100013 | [6 empty] | Wind | 85
|  | SR | Karnataka | Koppal-II PS |  | TATA Power Renewable Energy Ltd. |  | 351100008 | [6 empty] | Wind | 85
|  | SR | Karnataka | Koppal-II PS |  | TORRENT SAURYA URJA 2 PRIVATE LIMITED |  | 2200000058 | [6 empty] | Wind | 300
|  | SR | Karnataka | Koppal-II PS |  | ABREL (RJ) PROJECTS LIMITED |  | 2200000141 | [6 empty] | Wind | 184
|  | SR | Karnataka | Koppal-II PS |  | VEH GREEN ENERGY PRIVATE LIMITED |  | 2200000126 | [6 empty] | Wind | 153.6
|  | SR | Andhra Pradesh 30-12-25 | NP Kunta PS |  | FIRST ENERGY PRIVATE LIMITED |  | 2200000388 | [6 empty] | Solar | 100
|  | SR | Karnataka | Pavagada PS |  | Ircon Renewable Power Ltd. |  | 1200003815 | [6 empty] | Solar | 500
|  | SR | Karnataka | Pavagada PS |  | SOLAR ENERGY CORPORATION OF INDIA LIMITED |  | 2200000057 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ABC Renewable Energy Pvt. Ltd. |  | St-II:1200002699 (400 MW | 1200003096 | [5 empty] | Solar | 400
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ReNew Dinkar Jyoti Private Limited |  | St-II:1200003813 (100 MW | 1200003879 | [5 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | IB Vogt Solar Seven Private Limited |  | St-II:1200002700 (300 MW | 1200003931 | [5 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | XL Xergi Power Pvt. Ltd. |  | St-II:1200002847 (400 MW | 412100007 | [5 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | Khaba Renewable Energy Private Limited |  | 1200003502 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ReNew Surya Jyoti Private Limited |  | 1200002746 | [6 empty] | Solar | 210
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | RENEW SURYA PRATAP PRIVATE LIMITED |  | 1200002778 | [6 empty] | Solar | 210
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ReNew Solar (Shakti Three) Private Limited |  | 1200003447 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ReNew Solar (Shakti Five) Private Limited |  | 1200003488 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ReNew Solar (Shakti Five) Private Limited |  | 1200003496 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ReNew Samir Shakti Private Limited |  | 1200003504 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ReNew Samir Shakti Private Limited |  | 1200003514 (Enh. St-II) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ReNew Samir Shakti Private Limited |  | 1200003562 (Enh. St-II) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | Energizent Power Private Limited |  | 1200002939 | [6 empty] | Solar | 80
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | XL Xergi Power Private Limited |  | 412100020 (St-II: 1200002847) | [6 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | AMP Energy Green Pvt. Ltd. |  | St-II:1200003022 (130 MW | 1200003416 | [5 empty] | Solar | 130
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | ABC Renewable Energy Private Limited |  | St-II:1200003002 (380 MW | 1200003531 | [5 empty] | Solar | 380
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | Juniper Green Stellar Private Limited |  | 412100009 (St-II: 1200003827, 1200003910, 1200003958, 0312100010 | [6 empty] | Hybrid (RHGS) | 150
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | AMP Energy Green Pvt. Ltd. |  | 412100019 (St-II: 0312100005) | [6 empty] | Hybrid (RHGS) | 120
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | ABC RJ Land 01 Private Limited |  | 1200003332 | [6 empty] | Solar | 110
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | ABC RJ Land 01 Private Limited |  | 1200003575 | [6 empty] | Solar | 270
|  | SR | Karnataka | Gadag-II PS |  | SOLARXL BETA ENERGY PRIVATE LIMITED |  | 2200000006 | [6 empty] | Hybrid (RHGS) | 207 (Solar-138 MW, Wind-69
|  | SR | Karnataka | Gadag-II PS |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED |  | 2200000072 | [6 empty] | Wind | 480
|  | SR | Karnataka | Gadag-II PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000074 | [6 empty] | Hybrid (RHGS) | 109
|  | SR | Karnataka | Gadag-II PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000096 | [6 empty] | Wind | 50
|  | SR | Karnataka | Gadag-II PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000099 | [6 empty] | Wind | 50
|  | SR | Karnataka | Gadag-II PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000100 | [6 empty] | Wind | 50
|  | SR | Karnataka | Gadag-II PS |  | ABREL (RJ) PROJECTS LIMITED |  | 2200000139 | [6 empty] | Wind | 184
|  | SR | Karnataka | Gadag-II PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000121 | [6 empty] | Hybrid (RHGS) | 327MW [Solar- 153 MW & Wind-174MW]
|  | SR | Karnataka | Gadag-II PS |  | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED |  | 2200000238 | [6 empty] | Wind | 102
|  | SR | Karnataka | Hiriyur |  | ZENATARIS RENEWABLE ENERGY PRIVATE LIMITED |  | 2200000920 | [6 empty] | Wind | 62.7
|  | WR | Gujarat | Jam Khambhaliya PS |  | Powerica Limited |  | 230700018 | [6 empty] | Wind | 53
|  | WR | Gujarat | Jam Khambhaliya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000190 | [6 empty] | Wind | 100
|  | SR | Karnataka | Koppal-II PS |  | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED |  | 2200000237 | [6 empty] | Wind | 102
|  | SR | Karnataka | Koppal-II PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000243 | [6 empty] | Wind | 288
|  | SR | Karnataka | Koppal-II PS |  | JSP GREEN WIND 1 PRIVATE LIMITED |  | 2200000262 | [6 empty] | Wind | 400
|  | SR | Karnataka | Koppal-II PS |  | JSP GREEN WIND 1 PRIVATE LIMITED |  | 2200000402 | [6 empty] | Wind | 300
|  | SR | Karnataka | Koppal-II PS |  | GADAG POWER INDIA PRIVATE LIMITED |  | 2200000472 | [6 empty] | Wind | 300
|  | SR | Karnataka | Koppal-II PS |  | AYANA RENEWABLE POWER PRIVATE LIMITED |  | 2200000504 | [6 empty] | Wind | 100
|  | WR | Maharashtra | Parli (New) |  | Renew Pawan Shakti Private Limited (RPSPL) |  | 231400018 | [6 empty] | Wind | 277
|  | WR | Maharashtra | Parli (New) |  | Renew Pawan Shakti Private Limited (RPSPL) |  | 331400012 | [6 empty] | Wind | 23
|  | WR | Madhya Pradesh | Neemuch PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000709 | [6 empty] | Solar | 300
|  | SR | Karnataka | Koppal-II PS |  | TORRENT SOLAR POWER PRIVATE LIMITED |  | 2200000474 | [6 empty] | Wind | 125.4
|  | WR | Madhya Pradesh | Pachora PS (Sec- II) |  | Oyster Renewable Energy Private Limited (formerly Known as ABENERGIA RENEWABLES PRIVATE LIMITED) |  | 2200000086 | [6 empty] | Hybrid (RHGS) | 100
|  | WR | Madhya Pradesh | Pachora PS (Sec- II) |  | Oyster Renewable Energy Private Limited (Former name-ABENERGIA RENEWABLES PRIVATE LIMITED) |  | 2200000342 | [6 empty] | Hybrid (RHGS) | 81
|  | WR | Madhya Pradesh | Pachora PS (Sec- II) |  | BHOJRAJ DEVELOPERS PRIVATE LIMITED |  | 2200000404 | [6 empty] | Hybrid (RHGS) Wind: 160 | MW Solar: 26 MW
|  | SR | Karnataka | Gadag-II PS |  | GREENKO KA01 IREP PRIVATE LIMITED |  | 2200000092 | [6 empty] | Pump Storage | 260
|  | NR | Rajasthan | Bhadla-II |  | AMP Energy Green Private Limited |  | 1200002987 (Enh.) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bhadla-II |  | Eden Renewable Alma Private Limited |  | 1200002554 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II |  | Solarpack Corporacion Technologica S.A. |  | 1200002742 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-II |  | AMP Energy Green Pvt. Ltd. |  | 1200002559 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bhadla-III |  | Prerak Greentech Solar Private Limited (Park) |  | SW9990894382- M029_D001_A007- 1671216520154 (0212100003) | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bhadla-III |  | Juniper Green Beta Pvt. Ltd. |  | 412100012, 0212100027 (St-II) | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bhadla-III |  | Juniper Green Beta Pvt. Ltd. |  | 412100013, 0312100013 (St-II), 1670400777119 (St-II) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bhadla-III |  | Tepsol Sun Sparkle Pvt. Ltd. |  | SW9990897533- M029_D001_A007- 1672319027575, 0212100030 (St-II) | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III |  | Juniper Green Beta Private Limited |  | 412100027 (SW5102826596- M029_D001_A003-1670400777119 (10MW out of 70MW) + 0312100011 | [6 empty] | Solar | 50
|  | SR | Karnataka | Bidar PS |  | WELSPUN NARMADA PRIVATE LIMITED |  | 2200000716 | [6 empty] | Hybrid (RHGS) | 250 (150 MW Wind & 100 MW Solar)
|  | SR | Tamil Nadu | Karur PS |  | FIRST ENERGY PRIVATE LIMITED |  | 2200000441 | [6 empty] | Wind | 100
|  | SR | Tamil Nadu | Karur PS |  | NANNAI SOLAR PARK PRIVATE LIMITED |  | 2200000628 | [6 empty] | Wind | 93
|  | NR | Rajasthan | Ramgarh |  | Adani Renewable Energy Holding Four Ltd. |  | St-II: 1200002432(500 MW | 1200003689 | [5 empty] | Solar | 500
|  | WR | Maharashtra | Kallam PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000395 | [6 empty] | Wind | 101
|  | WR | Maharashtra | Kallam PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000450 | [6 empty] | Wind | 100.8
|  | SR | Tamil Nadu | Karur PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000448 | [6 empty] | Wind | 93.6
|  | SR | Tamil Nadu | Pugalur |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000394 | [6 empty] | Wind | 151
|  | SR | Tamil Nadu | Pugalur |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000449 | [6 empty] | Wind | 151.2
|  | SR | Karnataka | Koppal-II PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000390 | [6 empty] | Solar | 200-Solar; 25-BESS
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | SOLARCRAFT POWER INDIA 7 PRIVATE LIMITED |  | 2200000270 | [6 empty] | Wind | 52.8
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | SOLARCRAFT POWER INDIA 7 PRIVATE LIMITED |  | 2200000409 | [6 empty] | Wind | 47.2
|  | WR | Madhya Pradesh | Pachora PS (Sec- I) |  | VEH DAMEN POWER PRIVATE LIMITED |  | 2200000356 | [6 empty] | Wind | 76.8
|  | SR | Andhra Pradesh 31-03-26 | Anantapur PS |  | RENEW VIKRAM SHAKTI PRIVATE LIMITED |  | 2200000032 | [6 empty] | Hybrid (RHGS) | Solar-750MW, Wind:960MW, BESS-288)
|  | SR | Andhra Pradesh 31-03-26 | Anantapur PS |  | ABC CLEANTECH PRIVATE LIMITED |  | 2200000271 | [6 empty] | Wind | 250
|  | SR | Andhra Pradesh 31-03-26 | Anantapur PS |  | ABC CT RE PARK (03) PRIVATE LIMITED |  | 2200000273 | [6 empty] | Wind | 250
|  | NR | Rajasthan | Fatehgarh-III |  | JSW Renew Energy Five Limited |  | 212100040 | [6 empty] | Storage | 250
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | Juniper Green Stellar Private Limited |  | 412100010 (St-II: 1200003827, 1200003910, 1200003958, 0312100010 & 0312100012) | [6 empty] | Hybrid (RHGS) | 150
|  | WR | Madhya Pradesh | Indore (PG) |  | RENEW SAMIR URJA PRIVATE LIMITED |  | 2200000298 | [6 empty] | Wind | 300
|  | WR | Maharashtra | Solapur PG |  | JSW RENEW ENERGY THIRTEEN LIMITED |  | 2200001148 | [6 empty] | Solar | 300
|  | WR | Maharashtra | Solapur PG |  | WAAREE FOREVER ENERGIES PRIVATE LIMITED |  | 2200001158 | [6 empty] | Solar | 1000
|  | WR | Maharashtra | Solapur PS |  | JSW Renew Energy Three Limited |  | 231400016 | [6 empty] | Wind | 200
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | JSW NEO ENERGY LIMITED |  | 2200000718 | [6 empty] | Wind | 300
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | SOLARCRAFT POWER INDIA 16 PVT. LTD. |  | 2200000440 | [6 empty] | Hybrid (RHGS) Wind - 191.4 | MW, Solar - 56 MW, BESS - 91 MW)
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | SOLARCRAFT POWER INDIA 16 PRIVATE LIMITED |  | 2200001047 | [6 empty] | Hybrid (RHGS) | 247.4
|  | WR | Gujarat | Bhuj PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000566 | [6 empty] | Wind | 20
|  | SR | Karnataka | Bidar PS |  | SAEL INDUSTRIES LIMITED |  | 2200000759 | [6 empty] | Solar | 300
|  | WR | Gujarat | Lakadiya PS |  | TEQ GREEN POWER XVII PRIVATE LIMITED |  | 2200000311 | [6 empty] | Hybrid (RHGS) | 300 (200MW Solar
|  | WR | Madhya Pradesh | Pachora PS (Sec- II) |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000502 | [6 empty] | Solar | 400
|  | SR | Tamil Nadu | Tuticorin-II PS |  | GRT JEWELLERS (INDIA) PRIVATE LIMITED |  | 2200000594 | [6 empty] | Solar | 150
|  | SR | Karnataka | Pavagada PS |  | TEQ GREEN POWER XVIII PRIVATE LIMITED |  | 2200000310 | [6 empty] | Wind | 250
|  | SR | Karnataka | Pavagada PS |  | KARNATAKA SOLAR POWER DEVELOPMENT CORPORATION LIMITED |  | 2200000339 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 31-05-26 | Anantapur PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000069 | [6 empty] | Wind | 400
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | SKADAR SOLAR PRIVATE LIMITED |  | 2200000754 | [6 empty] | Solar | 200
|  | SR | Andhra Pradesh 30-06-26 | Anantapur PS |  | ABC CT RE PARK (02) PRIVATE LIMITED |  | 2200000274 | [6 empty] | Wind | 250
|  | SR | Andhra Pradesh 30-06-26 | Anantapur PS |  | ABC CT RE PARK (01) PRIVATE LIMITED |  | 2200000276 | [6 empty] | Wind | 250
|  | NR | Rajasthan | Bhadla-III |  | ReNew Solar (Shakti Six) Private Limited |  | 1200003848 | [6 empty] | Solar | 550
|  | NR | Rajasthan | Bhadla-III |  | ReNew Solar (Shakti Six) Private Limited |  | 312100004 (Enh.) | [6 empty] | Solar | 450
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | Juniper Green Steller Pvt. Ltd. |  | St-II: 312100010 (45 MW) (5 out of 45 MW), 312100012 (60 MW | 412100011 | [5 empty] | Solar | 65
|  | WR | Gujarat | Jam Khambhaliya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000209 | [6 empty] | Wind | 200
|  | WR | Gujarat | KPS-1 (Sec-I) |  | Adani Renewable Energy Holding Four Ltd. (AREH4L) |  | 1200002678 | [6 empty] | Solar | 1083
|  | WR | Gujarat | KPS-1 (Sec-I) |  | Adani Renewable Energy Holding Four Ltd. (AREH4L) |  | 1200002679 | [6 empty] | Solar | 1000
|  | WR | Gujarat | KPS-1 (Sec-I) |  | Adani Green Energy Ltd. |  | 1670426092248 | [6 empty] | Hybrid (RHGS) | 1050
|  | WR | Gujarat | KPS-1 (Sec-II) |  | Adani Green Energy Limited Connectivity: 1670426695890; LTA: 1670929494955 (250MW); |  | SW6949744157-M029_D001_A002- 1670426695890 Connectivity: 1670426695890 | [6 empty] | Wind | 250
|  | WR | Gujarat | KPS-1 (Sec-II) |  | Sarjan Realities Pvt. Ltd. (SRPL) |  | 230700011 | [6 empty] | Hybrid (RHGS) | 1150
|  | WR | Gujarat | KPS-3 (Sec-I) |  | Sarjan Realities Pvt. Ltd. (SRPL) |  | 230700012 | [6 empty] | Hybrid (RHGS) | 1332
|  | SR | Andhra Pradesh 30-06-26 | Kurnool-III PS |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000383 | [6 empty] | Hybrid (RHGS) | Solar: 150MW Wind: 150MW BESS: 30MWh
|  | WR | Gujarat | Lakadiya PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000610 | [6 empty] | Hybrid (RHGS) | 480 (240 MW: Wind 240 MW: Solar)
|  | WR | Maharashtra | Parli (New) |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000747 | [6 empty] | Wind | 180
|  | WR | Gujarat | Radhanesda PS |  | SPRNG POWER EARTH PRIVATE LIMITED |  | 2200000247 | [6 empty] | Solar | 250
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | SOLARCRAFT POWER INDIA 20 PRIVATE LIMITED |  | 2200000795 | [6 empty] | Hybrid (RHGS) | 97.31
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | SOLARCRAFT POWER INDIA 20 PRIVATE LIMITED |  | 2200001028 | [6 empty] | Hybrid (RHGS) | 84.75
|  | SR | Andhra Pradesh 01-07-26 | Kurnool-III PS |  | ADANI RENEWABLE ENERGY FORTY TWO LIMITED |  | 2200000158 | [6 empty] | Pump Storage | 600
|  | WR | Gujarat | KPS-3 (Sec-I) |  | Sarjan Realities Pvt. Ltd. (SRPL) |  | 230700014 | [6 empty] | Hybrid (RHGS) | 1100
|  | WR | Gujarat | Lakadiya PS |  | ARCELORMITTAL NIPPON STEEL INDIA LIMITED |  | 2200000324 | [6 empty] | Hybrid (RHGS) | 550 (Wind 250MW+Solar 300MW)
|  | NR | Rajasthan | Bikaner |  | AK RENEWABLE INFRA PRIVATE LIMITED |  | 2200000284 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-II |  | ALF Solar Amarsar Private Limited |  | 312100008 (Enh.) | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-II |  | Sourya Manthan Renewable Energy Private Limited |  | 212100005 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-II |  | Soltown Infra Private Limited (Park) |  | 212100007 | [6 empty] | Solar | 350
|  | NR | Rajasthan | Bikaner-II |  | Soltown Infra Private Limited (Park) |  | 212100008 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-III |  | Proteus Energy Private Limited (Park) |  | 212100042 | [6 empty] | Solar | 217
|  | NR | Rajasthan | Bikaner-III |  | TP Saurya Limited |  | 212100025 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-III |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000008 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-III |  | MRS BUILDVISION PRIVATE LIMITED |  | 2200000098 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III |  | SUNBREEZE RENEWABLES NINE PRIVATE LIMITED |  | 2200000111 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-III |  | SUNBREEZE RENEWABLES NINE PRIVATE LIMITED |  | 2200000163 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000172 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III |  | SAIMAA SOLAR PRIVATE LIMITED |  | 2200000167 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000164 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000165 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000227 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-III |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000228 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | Serentica Renewable India Pvt. Ltd. |  | 212100034 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | Serentica Renewable India Pvt. Ltd. |  | 212100036 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000020 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | SPRNG POWER PRIVATE LIMITED |  | 2200000024 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | SPRNG AKSHAYA URJA PRIVATE LIMITED |  | 2200000065 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | SPRNG ENERGY PRIVATE LIMITED |  | 2200000116 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ABREL (RJ) PROJECTS LIMITED |  | 2200000140 | [6 empty] | Solar | 260
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200000123 | [6 empty] | Solar | 95
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED |  | 2200000138 | [6 empty] | Hybrid (RHGS) | 390
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | Luceo Solar Pvt. Ltd. |  | 212100032 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | Luceo Solar Pvt. Ltd. |  | 0312100018 (Enhancement) | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | AMP Energy Green Pvt. Ltd. |  | 312100007 | [6 empty] | Hybrid (RHGS) | 50
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | BN HYBRID POWER-1 PRIVATE LIMITED |  | 2200000003 | [6 empty] | Hybrid (RHGS) | 119.2
|  | NR | Rajasthan | Fatehgarh-IV (Sec- I) |  | BN HYBRID POWER-1 PRIVATE LIMITED |  | 2200000102 | [6 empty] | Hybrid (RHGS) | 180.8
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000187 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III |  | Seven Renewable Power Pvt. Ltd. |  | 212100028 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III |  | Frugal Energy Pvt. Ltd. |  | 212100031 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bhadla-III |  | Bhadla Three SKP Green Ventures Pvt. Ltd. |  | 212100033 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Ramgarh |  | Adani Solar Energy AP Three Ltd. |  | 212100038 | [6 empty] | Solar | 150
|  | SR | Karnataka | Bijapur PS |  | TEPSOL GREEN ENERGY PRIVATE LIMITED |  | 2200000657 | [6 empty] | Hybrid (RHGS) | 200 (Wind- 160 & Solar- 40)
|  | SR | Karnataka | Davangere PS |  | LAYER HYBREN PRIVATE LIMITED |  | 2200000625 | [6 empty] | Hybrid (RHGS) | 140 (100- Solar; 40 Wind)
|  | SR | Karnataka | Tumkur-II PS |  | SAEL INDUSTRIES LIMITED |  | 2200000948 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 30-09-26 | Anantapur PS |  | SEVEN RENEWABLE POWER PRIVATE LIMITED |  | 2200000226 | [6 empty] | Wind | 150
|  | NR | Rajasthan | Bhadla-II |  | SOLARCRAFT POWER INDIA 4 PRIVATE LIMITED |  | 2200000152 | [6 empty] | Solar | 150
|  | SR | Karnataka | Davangere PS |  | LAYER HYBREN PRIVATE LIMITED |  | 2200000702 | [6 empty] | Hybrid (RHGS) | 160 (110- Solar; 50 Wind)
|  | WR | Maharashtra | Kallam PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000075 | [6 empty] | Wind | 50
|  | WR | Maharashtra | Kallam PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000353 | [6 empty] | Wind | 250
|  | WR | Gujarat | Lakadiya PS |  | RENEW SOLAR (SHAKTI EIGHT) PRIVATE LIMITED |  | 2200000341 | [6 empty] | Solar | 200
|  | WR | Gujarat | Lakadiya PS |  | TEQ GREEN POWER XVI PRIVATE LIMITED |  | 2200000398 | [6 empty] | Wind | 76
|  | WR | Gujarat | Lakadiya PS |  | RENEW SOLAR (SHAKTI EIGHT) PRIVATE LIMITED |  | 2200000403 | [6 empty] | Solar | 100
|  | WR | Gujarat | Lakadiya PS |  | TEQ GREEN POWER XVI PRIVATE LIMITED |  | 2200000427 | [6 empty] | Wind | 76
|  | SR | Karnataka | Tumkur-II PS |  | SAEL INDUSTRIES LIMITED |  | 2200001012 | [6 empty] | Solar | 300
|  | WR | Gujarat | KPS-1 (Sec-I) |  | Adani Renewable Energy Holding Four Ltd. (Erstwhile Adani Green Energy Four Ltd.) |  | 1200002678 | [6 empty] | Solar | 917
|  | WR | Maharashtra | Parli (New) |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200001054 | [6 empty] | Wind | 220
|  | WR | Gujarat | Jam Khambhaliya PS |  | MOUNTING RENEWABLE POWER LIMITED |  | 2200000246 | [6 empty] | Hybrid (RHGS) | 250
|  | WR | Gujarat | Jam Khambhaliya PS |  | AIRPOWER WINDFARMS PRIVATE LIMITED |  | 2200000261 | [6 empty] | Wind | 175
|  | WR | Gujarat | Jam Khambhaliya PS |  | ACME SUN POWER PRIVATE LIMITED |  | 2200000263 | [6 empty] | Wind | 400
|  | WR | Gujarat | Jam Khambhaliya PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000241 | [6 empty] | Wind | 545
|  | WR | Gujarat | Jam Khambhaliya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000445 | [6 empty] | Wind | 100
|  | WR | Gujarat | Jam Khambhaliya PS |  | POWERICA LIMITED |  | 2200000473 | [6 empty] | Wind | 50
|  | WR | Gujarat | Jam Khambhaliya PS |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED |  | 2200000503 | [6 empty] | Wind | 308.49
|  | WR | Gujarat | Jam Khambhaliya PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000556 | [6 empty] | Wind | 200
|  | WR | Gujarat | Jam Khambhaliya PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000565 | [6 empty] | Wind | 80
|  | WR | Gujarat | Jam Khambhaliya PS |  | MALAREN SOLAR PRIVATE LIMITED |  | 2200000337 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | EG Saur Urja Pvt. Ltd. (earlier Tepsol Saur Urja Private Limited) |  | 212100043 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | Cannice Renewables Energy Private Limited |  | 312100019 | [6 empty] | Hybrid (RHGS) | 90
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | Cannice Renewables Energy Private Limited |  | SW…1671600589106 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | Cannice Renewable Energy Private Limited |  | 212100004 | [6 empty] | Solar | 80
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | GREENKO MP01 IREP PRIVATE LIMITED |  | 2200000089 | [6 empty] | Pump Storage | 504
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | GREENKO MP01 IREP PRIVATE LIMITED |  | 2200000090 | [6 empty] | Pump Storage | 504
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | GREENKO MP01 IREP PRIVATE LIMITED |  | 2200000091 | [6 empty] | Pump Storage | 504
|  | WR | Gujarat | Navinal |  | ADANI WIND ENERGY KUTCHH THREE LIMITED |  | 2200001083 | [6 empty] | Wind | 300
|  | NR | Rajasthan | Barmer-I |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200000153 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000161 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Barmer-I |  | EDEN RENEWABLE CADET PRIVATE LIMITED |  | 2200000181 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ENREN-I ENERGY PRIVATE LIMITED |  | 2200000286 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ANBOTO SOLAR PRIVATE LIMITED |  | 2200000281 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000244 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | GREEN INFRA CLEAN WIND TECHNOLOGY LIMITED |  | 2200000054 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | UTKRRISHT SOLAR ENERGY PRIVATE LIMITED |  | 2200000067 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000077 | [6 empty] | Hybrid (RHGS) | 50
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | BN DISPATCHABLE-1 PRIVATE LIMITED |  | 2200000103 | [6 empty] | Hybrid (RHGS) | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | HELIA ENERGY PARK PRIVATE LIMITED |  | 2200000120 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | GREEN INFRA CLEAN SOLAR FARMS LIMITED |  | 2200000135 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000186 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | RADIANT STAR SOLAR PARK PRIVATE LIMITED |  | 2200000212 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000290 | [6 empty] | Hybrid (RHGS) | 250
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000485 | [6 empty] | Solar | 50
|  | SR | Karnataka | Pavagada PS |  | AYANA RENEWABLE POWER PRIVATE LIMITED |  | 2200000320 | [6 empty] | Wind | 150
|  | NR | Rajasthan | Bikaner-III |  | DESHRAJ SOLAR ENERGY PRIVATE LIMITED |  | 2200000184 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-III |  | FIRST ENERGY PRIVATE LIMITED |  | 2200000221 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-IV |  | AVAADA RJBIKANER PRIVATE LIMITED |  | 2200000013 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bikaner-IV |  | SOLARCRAFT POWER INDIA 17 PRIVATE LIMITED |  | 2200000210 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | AVAADA RJBIKANER PRIVATE LIMITED |  | 2200000254 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Bikaner-IV |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000289 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | SHUDH SOLAR POWER PRIVATE LIMITED |  | 2200000306 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000308 | [6 empty] | Solar | 700
|  | NR | Rajasthan | Bikaner-IV |  | HAZEL HYBREN PRIVATE LIMITED |  | 2200000334 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | AM GREEN ENERGY PRIVATE LIMITED |  | 2200000319 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | FURIES SOLREN PRIVATE LIMITED |  | 2200000333 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | IRAAX INTERNATIONAL (OPC) PRIVATE LIMITED |  | 2200000343 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | CLEAN MAX GAMMA PRIVATE LIMITED |  | 2200000344 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000373 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000358 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bikaner-IV |  | SJVN GREEN ENERGY LIMITED |  | 2200000423 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-IV |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000420 | [6 empty] | Solar | 1000
|  | WR | Gujarat | Bhuj PS |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED |  | 2200000634 | [6 empty] | Solar | 600
|  | WR | Gujarat | Bhuj PS |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000658 | [6 empty] | Wind | 99
|  | WR | Gujarat | Bhuj PS |  | NLC INDIA LIMITED |  | 2200000729 | [6 empty] | Solar | 100
|  | WR | Gujarat | Bhuj PS |  | OYSTER GREEN HYBRID ONE PRIVATE LIMITED |  | 2200000783 | [6 empty] | Wind | 99
|  | WR | Gujarat | Bhuj PS |  | NLC INDIA LIMITED |  | 2200000808 | [6 empty] | Wind | 50
|  | WR | Gujarat | Bhuj PS |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED |  | 2200000981 | [6 empty] | Wind | 75.6
|  | WR | Gujarat | Bhuj PS |  | CONTINUUM POWER TRADING (TN) PRIVATE LIMITED |  | 2200001070 | [6 empty] | Wind | 36
|  | WR | Gujarat | KPS-2 (Sec-I) |  | GUJARAT STATE ELECTRICITY CORPORATION LIMITED |  | 2200000048 | [6 empty] | Solar | 3325
|  | WR | Gujarat | KPS-2 (Sec-I) |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000093 | [6 empty] | Solar | 1995
|  | WR | Gujarat | KPS-2 (Sec-II) |  | NTPC Renewable Energy Limited (NREL) |  | 1200003953 | [6 empty] | Solar | 390
|  | WR | Gujarat | KPS-2 (Sec-II) |  | NTPC Renewable Energy Limited (NTPC REL) |  | 330700007 | [6 empty] | Solar | 300
|  | WR | Gujarat | KPS-3 (Sec-I) |  | NTPC Renewable Energy Limited |  | 230700010 | [6 empty] | Solar | 1200
|  | WR | Gujarat | KPS-3 (Sec-II) |  | Sarjan Realities Pvt. Ltd. (SRPL) |  | 230700013 | [6 empty] | Hybrid (RHGS) | 1250
|  | WR | Gujarat | KPS-3 (Sec-II) |  | NHPC Limited |  | 230700015 | [6 empty] | Solar | 600
|  | WR | Gujarat | Lakadiya PS |  | RDS SOLAR PARK PRIVATE LIMITED |  | 2200000639 | [6 empty] | Solar | 350
|  | WR | Gujarat | Lakadiya PS |  | PERCENTUM RENEWABLES PRIVATE LIMITED |  | 2200000673 | [6 empty] | Hybrid (RHGS) | 100MW: Solar 200MW: Wind Revised to 50MW Solar & 98MW Wind.
|  | WR | Gujarat | Bhuj-II PS (Sec-I) |  | SJVN GREEN ENERGY LIMITED |  | 2200000204 | [6 empty] | Solar | 360
|  | WR | Gujarat | Bhuj-II PS (Sec-II) |  | ABREL (RJ) PROJECTS LIMITED |  | 2200000288 | [6 empty] | Hybrid (RHGS) | 314
|  | WR | Gujarat | Bhuj-II PS (Sec-II) |  | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED |  | 2200000321 | [6 empty] | Hybrid (RHGS) | 362
|  | WR | Gujarat | Bhuj-II PS (Sec-II) |  | CGE RENEWABLES PRIVATE LIMITED |  | 2200000389 | [6 empty] | Hybrid (RHGS) Wind: 30 MW | Solar: 60 MW
|  | WR | Gujarat | Bhuj-II PS (Sec-II) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000444 | [6 empty] | Solar | 100
|  | WR | Gujarat | Bhuj-II PS (Sec-II) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000537 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-II |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000387 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Fatehgarh-II |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000396 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-I |  | ENFINITY GLOBAL SURYA KIRAN PRIVATE LIMITED |  | 2200000411 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | AUXO SUNLIGHT PRIVATE LIMITED |  | 2200000312 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | RENEW SUN POWER PRIVATE LIMITED |  | 2200000316 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | ANDHRA PRADESH RESCO ROOFTOP SOLAR PRIVATE LIMITED |  | 2200000412 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-I |  | HINDUJA RENEWABLES ENERGY PRIVATE LIMITED |  | 2200000425 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-I |  | ANBOTO SOLAR PRIVATE LIMITED |  | 2200000492 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | GAMMA RENEWABLES INDIA PROJECT ONE PRIVATE LIMITED |  | 2200000355 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000348 | [6 empty] | Solar | 900
|  | SR | Karnataka | Bidar PS |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000422 | [6 empty] | Hybrid (RHGS) | Solar: 188MW Wind: 201 MW BESS: 30MWh
|  | NR | Rajasthan | Bikaner-II |  | Soltown Infra Private Limited (Park) |  | 1200003889 (Enh.) | [6 empty] | Solar | 200
|  | NER | Assam | Bokajan (ISTS) |  | ASSAM POWER DISTRIBUTION COMPANY LIMITED |  | 2200000050 | [6 empty] | Solar | 750
|  | WR | Maharashtra | Dhule PS (Sec-I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000081 | [6 empty] | Wind | 50
|  | WR | Maharashtra | Dhule PS (Sec-I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001036 | [6 empty] | Wind | 160
|  | WR | Maharashtra | Dhule PS (Sec-I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001035 | [6 empty] | Wind | 80
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | JUNIPER GREEN STELLAR PRIVATE LIMITED |  | 2200000063 | [6 empty] | Solar | 300
|  | SR | Karnataka | Gadag PS |  | Halvad Renewables Pvt. Ltd. |  | 251100015 | [6 empty] | Wind | 130
|  | SR | Tamil Nadu | Karur PS |  | AMPLUS SUN BEAT PRIVATE LIMITED |  | 2200000698 | [6 empty] | Wind | 80
|  | SR | Tamil Nadu | Karur PS |  | AMPLUS THETA ENERGY PVT. LTD. [ERSTWHILE AMPLUS CENEDUS SOLAR PVT. LTD.] |  | 2200000699 | [6 empty] | Wind | 65
|  | SR | Karnataka | Koppal-II PS |  | VENA ENERGY AURA PRIVATE LIMITED |  | 2200000127 | [6 empty] | Wind | 50
|  | SR | Karnataka | Koppal-II PS |  | VENA ENERGY AURA PRIVATE LIMITED |  | 2200000282 | [6 empty] | Wind | 50
|  | SR | Karnataka | Koppal-II PS |  | VENA ENERGY AURA PRIVATE LIMITED |  | 2200000513 | [6 empty] | Wind | 40
|  | SR | Andhra Pradesh 31-12-26 | Kurnool-III PS |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000236 | [6 empty] | Hybrid (RHGS) | Solar: 150 MW Wind:159 MW
|  | SR | Andhra Pradesh 31-12-26 | Kurnool-III PS |  | AMPLUS EVEREST SOLAR PRIVATE LIMITED |  | 2200000543 | [6 empty] | Hybrid (RHGS) | 228(Solar:105 MW; Wind: 126 MW)
|  | SR | Andhra Pradesh 31-12-26 | Kurnool-III PS |  | AMPLUS IIFA SOLAR PRIVATE LIMITED |  | 2200000544 | [6 empty] | Hybrid (RHGS) | 228(Solar:105 MW; Wind: 126 MW)
|  | WR | Gujarat | Lakadiya PS |  | GANEKO SOLAR PRIVATE LIMITED |  | 2200000458 | [6 empty] | Hybrid (RHGS) | 337.36
|  | WR | Gujarat | Lakadiya PS |  | GANEKO SOLAR PRIVATE LIMITED |  | 2200000515 | [6 empty] | Hybrid (RHGS) | 11.63
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | ADYANT ENERSOL PRIVATE LIMITED |  | 2200000976 | [6 empty] | Hybrid (RHGS) | 84
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-II) |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200000924 | [6 empty] | Solar | 150
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-II) |  | BHOJRAJ RENEWABLES ENERGY PRIVATE LIMITED |  | 2200000899 | [6 empty] | Wind | 300
|  | NR | UP | Orai |  | BUNDELKHAND SAUR URJA LIMITED |  | 2200000345 | [6 empty] | Solar | 1200
|  | WR | Madhya Pradesh | Pachora PS (Sec- II) |  | AVAADA ENERGY PRIVATE LIMITED (AEPL) |  | 2200000082 | [6 empty] | Solar | 50
|  | WR | Madhya Pradesh | Pachora PS (Sec- II) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000267 | [6 empty] | Solar | 250
|  | WR | Maharashtra | Parli (New) |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001437 | [6 empty] | Wind | 100
|  | WR | Gujarat | Radhanesda PS |  | SPRNG ENERGY PRIVATE LIMITED |  | 2200000461 | [6 empty] | Solar | 100
|  | WR | Madhya Pradesh | Rajgarh SS |  | Sprng Vayu Vidyut Pvt Ltd (SVVPL) |  | 331300007 | [6 empty] | Wind | 100.8
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000022 | [6 empty] | Wind | 100
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG AKSHAYA URJA PRIVATE LIMITED |  | 2200000133 | [6 empty] | Wind | 67.2
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000083 | [6 empty] | Wind | 50
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000132 | [6 empty] | Hybrid (RHGS) | 50 (Wind) : revised from Hybrid (25S & 25W)after final grant
|  | WR | Maharashtra | Solapur PS (400 Sec-I) |  | GANEKO TWO ENERGY PRIVATE LIMITED |  | 2200001008 | [6 empty] | Hybrid (RHGS) | 354
|  | SR | Karnataka | Pavagada PS |  | ACME SOLAR HOLDINGS LIMITED |  | 2200001082 | [6 empty] | Solar | 350
|  | SR | Karnataka | Bijapur PS |  | APRAAVA ENERGY PRIVATE LIMITED |  | 2200000171 | [6 empty] | Wind | 300
|  | SR | Karnataka | Bijapur PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000393 | [6 empty] | Wind | 252
|  | SR | Karnataka | Bijapur PS |  | TEQ GREEN POWER XVI PRIVATE LIMITED |  | 2200000397 | [6 empty] | Wind | 125
|  | SR | Karnataka | Bijapur PS |  | TEQ GREEN POWER XVI PRIVATE LIMITED |  | 2200000429 | [6 empty] | Wind | 175
|  | SR | Karnataka | Bijapur PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000447 | [6 empty] | Wind | 50.4
|  | SR | Karnataka | Bijapur PS |  | UPC RENEWABLES INDIA MANAGEMENT PRIVATE LIMITED |  | 2200000584 | [6 empty] | Wind | 160
|  | SR | Karnataka | Bijapur PS |  | EG SOLWIN RENEWABLES PRIVATE LIMITED |  | 2200000687 | [6 empty] | Wind | 100
|  | SR | Karnataka | Gadag-II PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000045 | [6 empty] | Solar | 500
|  | SR | Karnataka | Gadag-II PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000199 | [6 empty] | Wind | 50
|  | SR | Karnataka | Gadag-II PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000385 | [6 empty] | Solar | 250
|  | SR | Karnataka | Gadag-II PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000434 | [6 empty] | Wind | 350
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | ADYANT ENERSOL PRIVATE LIMITED |  | 2200001214 | [6 empty] | Hybrid (RHGS) | 164
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-II) |  | WAAREE RENEWABLE TECHNOLOGIES LIMITED |  | 2200001192 | [6 empty] | Solar | 300
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-II) |  | ACME SOLAR HOLDINGS LIMITED |  | 2200001289 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Bikaner-IV |  | FURIES SOLREN PRIVATE LIMITED |  | 2200000419 | [6 empty] | Solar | 300
|  | SR | Karnataka | Pavagada PS |  | TEQ GREEN POWER XX PRIVATE LIMITED |  | 2200001321 | [6 empty] | Solar | 300
|  | SR | Karnataka | Davangere PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000660 | [6 empty] | Hybrid (RHGS) | 720(Solar:360 MW; Wind: 360)
|  | SR | Karnataka | Davangere PS |  | ILLUMINATE HYBREN PRIVATE LIMITED |  | 2200000701 | [6 empty] | Solar | 300
|  | SR | Karnataka | Davangere PS |  | FURIES SOLREN PRIVATE LIMITED |  | 2200000700 | [6 empty] | Solar | 300
|  | SR | Karnataka | Davangere PS |  | GENTARI RENEWABLES INDIA CASTOR ONE PVT. LTD |  | 2200000714 | [6 empty] | Wind | 350
|  | NR | Rajasthan | Bhadla-II |  | ADANI RENEWABLE ENERGY HOLDING EIGHTEEN LIMITED |  | 2200001044 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Fatehgarh-II |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200001065 | [6 empty] | Solar | 150
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | GREENKO MP01 IREP PRIVATE LIMITED |  | 2200001375 | [6 empty] | Pump Storage | 512
|  | NR | Rajasthan | Merta-II |  | BANYAN ENERGY PRIVATE LIMITED |  | 2200000823 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000644 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | ILLUMINATE HYBREN PRIVATE LIMITED |  | 2200000646 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | CESC LTD |  | 2200000518 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sirohi |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000551 | [6 empty] | Solar | 400
|  | SR | Andhra Pradesh 25-03-27 | Kurnool-IV PS |  | SAEL INDUSTRIES LIMITED |  | 2200000843 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 25-03-27 | Kurnool-IV PS |  | SAEL INDUSTRIES LIMITED |  | 2200000844 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 25-03-27 | Kurnool-IV PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000919 | [6 empty] | Solar | 400
|  | SR | Andhra Pradesh 25-03-27 | Kurnool-IV PS |  | GENTARI RENEWABLES INDIA CASTOR ONE PRIVATE LIMITED |  | 2200000931 | [6 empty] | Wind | 230
|  | SR | Andhra Pradesh 28-03-27 | Anantapur PS |  | AMPLUS CENEDUS SOLAR PRIVATE LIMITED |  | 2200000713 | [6 empty] | Wind | 350
|  | SR | Andhra Pradesh 28-03-27 | Kurnool-III PS |  | INDOSOL SOLAR PRIVATE LIMITED |  | 2200000733 | [6 empty] | Solar | 800
|  | SR | Andhra Pradesh 28-03-27 | Kurnool-III PS |  | INDOSOL SOLAR PRIVATE LIMITED |  | 2200000735 | [6 empty] | Solar | 900
|  | SR | Andhra Pradesh 31-03-27 | Anantapur-II PS |  | ACME SOLAR HOLDINGS PRIVATE LIMITED |  | 2200001003 | [6 empty] | Solar | 500
|  | SR | Andhra Pradesh 31-03-27 | Anantapur-II PS |  | JSW NEO ENERGY LIMITED |  | 2200001074 | [6 empty] | Solar | 500
|  | SR | Andhra Pradesh 31-03-27 | Anantapur-II PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200001077 | [6 empty] | Hybrid (RHGS) | 432
|  | NR | Rajasthan | Barmer-I |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000305 | [6 empty] | Solar | 300
|  | SR | Karnataka | Bidar PS |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000640 | [6 empty] | Hybrid (RHGS) | Total: 312 MW Solar: 132 MW
|  | NR | Rajasthan | Bikaner-IV |  | SUNSURE SOLARPARK FOURTEEN PRIVATE LIMITED |  | 2200000285 | [6 empty] | Solar | 300
|  | SR | Karnataka | Gadag-II PS |  | RENEW VAYU ENERGY PRIVATE LIMITED |  | 2200000292 | [6 empty] | Hybrid (RHGS) | 300 Solar-200 MW Wind-100 MW
|  | SR | Andhra Pradesh 31-03-27 | Kurnool-III PS |  | AMP ENERGY GREEN PRIVATE LIMITED |  | 2200000229 | [6 empty] | Hybrid (RHGS) | Solar: 85 MW Wind:118.8
|  | WR | Gujarat | Lakadiya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000500 | [6 empty] | Wind | 150
|  | WR | Gujarat | Lakadiya PS |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000641 | [6 empty] | Hybrid (RHGS) | 480 (240 MW: Wind 240 MW: Solar)
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | GANEKO ONE ENERGY PRIVATE LIMITED |  | 2200000720 | [6 empty] | Hybrid (RHGS) | Solar - 255 MW, Wind - 99 MW
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | ADYANT POWER PRIVATE LIMITED |  | 2200000798 | [6 empty] | Hybrid (RHGS) | 200
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-II) |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001301 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Merta-II |  | ACME SOLAR HOLDINGS PRIVATE LIMITED |  | 2200000840 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Merta-II |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED |  | 2200000848 | [6 empty] | Solar | 300
|  | WR | Madhya Pradesh | Neemuch PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000728 | [6 empty] | Solar | 500
|  | WR | Madhya Pradesh | Neemuch PS |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000938 | [6 empty] | Solar | 500
|  | WR | Madhya Pradesh | Pachora PS (Sec- II) |  | JADE HYBREN PRIVATE LIMITED |  | 2200000617 | [6 empty] | Solar | 300
|  | WR | Madhya Pradesh | Pachora PS (Sec- III) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000817 | [6 empty] | Hybrid (RHGS) | 334
|  | WR | Madhya Pradesh | Pachora PS (Sec- III) |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000883 | [6 empty] | Wind | 297
|  | WR | Madhya Pradesh | Pachora PS (Sec- III) |  | WAFT ENERGY PRIVATE LIMITED |  | 2200000923 | [6 empty] | Wind | 100
|  | WR | Madhya Pradesh | Pachora PS (Sec- III) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000956 | [6 empty] | Solar | 240
|  | WR | Madhya Pradesh | Pachora PS (Sec- III) |  | OYSTER GREEN HYBRID THREE PRIVATE LIMITED |  | 2200000995 | [6 empty] | Hybrid (RHGS) | 140
|  | SR | Karnataka | Tumkur-II PS |  | JAGALURU SOLAR POWER PRIVATE LIMITED |  | 2200001061 | [6 empty] | Solar | 300
|  | SR | Tamil Nadu | Tuticorin-II PS |  | NCL INDUSTRIES LTD |  | 2200001124 | [6 empty] | Hybrid (RHGS) | 220
|  | SR | Tamil Nadu | Tuticorin-II PS |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED |  | 2200001996 | [6 empty] | Solar | 200
|  | SR | Tamil Nadu | Tuticorin-II PS |  | VIVID SOLAIRE ENERGY PRIVATE LIMITED |  | 2200002003 | [6 empty] | Wind | 50
|  | SR | Andhra Pradesh 01-04-27 | Anantapur-II PS |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000872 | [6 empty] | Wind | 349.8
|  | SR | Andhra Pradesh 01-04-27 | Kurnool-III PS |  | INDOSOL SOLAR PRIVATE LIMITED |  | 2200000736 | [6 empty] | Solar | 900
|  | NR | Rajasthan | Sirohi |  | VAYUNA RENEWABLES INDIA PROJECT PRIVATE LIMITED |  | 2200000758 | [6 empty] | Solar | 300
|  | SR | Karnataka | Bijapur PS |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000586 | [6 empty] | Wind | 252
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | ASNEN SOLAR PRIVATE LIMITED |  | 2200000752 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Merta-II |  | Sembcorp Green Infra Pvt. Ltd. (erstwhile Green Infra Wind Energy Private Limited) |  | 2200000812 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Merta-II |  | GREEN INFRA WIND ENERGY PRIVATE LIMITED |  | 2200000813 | [6 empty] | Solar | 300
|  | NR | UP | Robertsganj |  | GREENKO UP01 IREP PRIVATE LIMITED |  | 2200000524 | [6 empty] | Pump Storage | 672
|  | NR | UP | Robertsganj |  | GREENKO UP01 IREP PRIVATE LIMITED |  | 2200000525 | [6 empty] | Pump Storage | 672
|  | NR | UP | Robertsganj |  | GREENKO UP01 IREP PRIVATE LIMITED |  | 2200000526 | [6 empty] | Pump Storage | 672
|  | SR | Karnataka | Tumkur-II PS |  | ORION HYBREN PRIVATE LIMITED |  | 2200000999 | [6 empty] | Hybrid (RHGS) | 300
|  | NR | Rajasthan | Barmer-I |  | GREEN INFRA RENEWABLE PROJECTS LIMITED |  | 2200000410 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Bhadla-II |  | GREEN INFRA CLEAN WIND LIMITED |  | 2200000437 | [6 empty] | Solar | 300
|  | SR | Karnataka | Bidar PS |  | PULSE HYBREN PRIVATE LIMITED |  | 2200001001 | [6 empty] | Solar | 300
|  | SR | Karnataka | Gadag-II PS |  | GREEN INFRA RENEWABLE PROJECTS LIMITED |  | 2200000435 | [6 empty] | Wind | 300
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-III) |  | JSP GREEN PRIVATE LIMITED |  | 2200001356 | [6 empty] | Wind | 350
|  | SR | Andhra Pradesh 30-06-27 | Anantapur-II PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000780 | [6 empty] | Wind | 400
|  | SR | Andhra Pradesh 30-06-27 | Anantapur-II PS |  | ORION HYBREN PRIVATE LIMITED |  | 2200001000 | [6 empty] | Hybrid (RHGS) | 300
|  | SR | Karnataka | Bidar PS |  | SPRNG POWERINFRA PRIVATE LIMITED |  | 2200000560 | [6 empty] | Wind | 200
|  | WR | Maharashtra | Dhule PS (Sec-I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001150 | [6 empty] | Wind | 200
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | Sprng Pavana Urja Private Limited |  | 1200003719 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | SPRNG PAVANA URJA PRIVATE LIMITED |  | 2200000018 | [6 empty] | Solar | 100
|  | WR | Gujarat | Jam Khambhaliya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000253 | [6 empty] | Wind | 100
|  | WR | Gujarat | Lakadiya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000376 | [6 empty] | Wind | 300
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-II) |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001280 | [6 empty] | Solar | 300
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-II) |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001279 | [6 empty] | Solar | 300
|  | WR | Madhya Pradesh | Pachora PS (Sec- III) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001325 | [6 empty] | Solar | 47
|  | WR | Gujarat | Radhanesda PS |  | SPRNG ENERGY PRIVATE LIMITED |  | 2200000460 | [6 empty] | Solar | 150
|  | WR | Gujarat | Radhanesda PS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000546 | [6 empty] | Solar | 50
|  | WR | Gujarat | Raghanesda PS |  | JSW NEO ENERGY LIMITED |  | 2200001014 | [6 empty] | Solar | 200
|  | WR | Gujarat | Raghanesda PS |  | JSW NEO ENERGY LIMITED |  | 2200001020 | [6 empty] | Solar | 200
|  | WR | Gujarat | Raghanesda PS |  | ACME SOLAR HOLDINGS LIMITED |  | 2200001064 | [6 empty] | Solar | 400
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000340 | [6 empty] | Wind | 82
|  | NR | Rajasthan | Sirohi |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000779 | [6 empty] | Solar | 300
|  | SR | Karnataka | Bidar PS |  | QUEST HYBREN PRIVATE LIMITED |  | 2200001002 | [6 empty] | Solar | 300
|  | WR | Madhya Pradesh | Morena PS |  | GREENKO RJ01 IREP PRIVATE LIMITED |  | 2200000685 | [6 empty] | Pump Storage | 880
|  | NR | Rajasthan | Merta-II |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200000842 | [6 empty] | Solar | 300
|  | SR | Karnataka | Bellary PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000825 | [6 empty] | Wind | 76
|  | SR | Karnataka | Bellary PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001103 | [6 empty] | Wind | 55
|  | SR | Karnataka | Bellary PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001102 | [6 empty] | Wind | 345
|  | SR | Karnataka | Bellary PS |  | GENTARI RENEWABLES INDIA UTILITIES 2 PRIVATE LIMITED |  | 2200001113 | [6 empty] | Solar | 400
|  | SR | Karnataka | Bellary PS |  | GENTARI RENEWABLES INDIA UTILITIES 2 PRIVATE LIMITED |  | 2200001114 | [6 empty] | Wind | 132
|  | SR | Karnataka | Bellary PS |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED |  | 2200001140 | [6 empty] | Solar | 300
|  | SR | Karnataka | Bellary PS |  | SERENTICA RENEWABLES INDIA 11 PRIVATE LIMITED |  | 2200001138 | [6 empty] | Wind | 100
|  | SR | Karnataka | Davangere PS |  | JADE HYBREN PRIVATE LIMITED |  | 2200000876 | [6 empty] | Hybrid (RHGS) | 300
|  | SR | Karnataka | Davangere PS |  | JSW NEO ENERGY LIMITED |  | 2200000932 | [6 empty] | Wind | 325
|  | SR | Karnataka | Davangere PS |  | JSW NEO ENERGY LIMITED |  | 2200001019 | [6 empty] | Wind | 100
|  | SR | Karnataka | Davangere PS |  | JSW NEO ENERGY LIMITED |  | 2200001015 | [6 empty] | Wind | 100
|  | WR | Madhya Pradesh | Neemuch PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000991 | [6 empty] | Solar | 200
|  | WR | Gujarat | Raghanesda PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000993 | [6 empty] | Solar | 300
|  | WR | Gujarat | Raghanesda PS |  | AZURE POWER SIXTY THREE PRIVATE LIMITED |  | 2200001107 | [6 empty] | Solar | 300
|  | SR | Karnataka | Bijapur PS |  | VISMAYA RENEWABLES INDIA PROJECT PRIVATELIMITED |  | 2200000692 | [6 empty] | Wind | 300
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | CLEAN MAX SOLARIS PRIVATE LIMITED |  | 2200000676 | [6 empty] | Hybrid (RHGS) | 150MW: Wind 50MW: Solar
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | CLEAN MAX ALCHEMY PRIVATE LIMITED |  | 2200000678 | [6 empty] | Hybrid (RHGS) | 150MW: Wind 50MW: Solar
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | TEQ GREEN POWER XIII PRIVATE LIMITED |  | 2200000669 | [6 empty] | Wind | 120.9
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200000737 | [6 empty] | Hybrid (RHGS) | Solar 120 MW, Wind 180 MW & BESS 30 MW)
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000750 | [6 empty] | Solar | 300
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | AZURE POWER SIXTY THREE PRIVATE LIMITED |  | 2200000799 | [6 empty] | Hybrid (RHGS) | 300
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | FEMUND SOLAR PRIVATE LIMITED |  | 2200000902 | [6 empty] | Solar | 150
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | RELIANCE INDUSTRIES LIMITED |  | 2200001104 | [6 empty] | Solar | 1000
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | RELIANCE INDUSTRIES LIMITED |  | 2200001105 | [6 empty] | Solar | 1000
|  | WR | Gujarat | Lakadia-II (Sec-II) |  | JSW NEO ENERGY LIMITED |  | 2200000705 | [6 empty] | Wind | 700
|  | WR | Gujarat | Lakadia-II (Sec-II) |  | BN DISPATCHABLE-2 PRIVATE LIMITED |  | 2200000986 | [6 empty] | Hybrid (RHGS) | 250
|  | WR | Gujarat | Lakadia-II (Sec-II) |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200001004 | [6 empty] | Hybrid (RHGS) | 272.8
|  | WR | Gujarat | Lakadia-II (Sec-II) |  | BN PEAK POWER-2 PRIVATE LIMITED |  | 2200000987 | [6 empty] | Hybrid (RHGS) | 250
|  | WR | Gujarat | Lakadia-II (Sec-II) |  | ADANI RENEWABLE ENERGY TEN LIMITED |  | 2200001071 | [6 empty] | Wind | 225
|  | WR | Gujarat | Lakadia-II (Sec-II) |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200001093 | [6 empty] | Solar | 150
|  | WR | Gujarat | Lakadia-II (Sec-II) |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200001127 | [6 empty] | Hybrid (RHGS) | 139
|  | WR | Maharashtra | Solapur PS (400 Sec-II) |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200001135 | [6 empty] | Solar | 350
|  | WR | Maharashtra | Solapur PS (400 Sec-II) |  | TORRENT URJA 18 PRIVATE LIMITED |  | 2200001223 | [6 empty] | Hybrid (RHGS) | 650
|  | WR | Maharashtra | Solapur PS (400 Sec-II) |  | UNIQUE HYBRID GLOBAL RENEWABLE ENERGY PRIVATE LIMITED |  | 2200001359 | [6 empty] | Solar | 390
|  | WR | Gujarat | Raghanesda PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000988 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 31-12-27 | Anantapur-II PS |  | GANEKO THREE ENERGY PRIVATE LIMITED |  | 2200000869 | [6 empty] | Hybrid (RHGS) | 354
|  | SR | Karnataka | Bidar PS |  | AMPIN ENERGY UTILITY PRIVATE LIMITED |  | 2200000762 | [6 empty] | Hybrid (RHGS) | 185.4
|  | SR | Karnataka | Bidar PS |  | AMPIN ENERGY UTILITY PRIVATE LIMITED |  | 2200000763 | [6 empty] | Hybrid (RHGS) | 185.4
|  | SR | Karnataka | Bidar PS |  | AMPIN ENERGY UTILITY PRIVATE LIMITED |  | 2200000892 | [6 empty] | Hybrid (RHGS) | 185.4
|  | SR | Karnataka | Bidar PS |  | AMP ENERGY C&I THIRTEEN PRIVATE LIMITED |  | 2200000893 | [6 empty] | Hybrid (RHGS) | 68.9
|  | SR | Karnataka | Bijapur PS |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200000708 | [6 empty] | Wind | 48
|  | WR | Gujarat | Jam Khambhaliya PS |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED |  | 2200000917 | [6 empty] | Wind | 207.9
|  | WR | Gujarat | Jam Khambhaliya PS |  | K.P. ENERGY LIMITED |  | 2200000913 | [6 empty] | Wind | 100
|  | SR | Tamil Nadu | Karur PS |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000967 | [6 empty] | Wind | 82.5
|  | SR | Tamil Nadu | Karur PS |  | NANNAI SOLAR PARK PRIVATE LIMITED |  | 2200001023 | [6 empty] | Wind | 57
|  | SR | Tamil Nadu | Karur PS |  | NAVALADI WIND PARK PRIVATE LIMITED |  | 2200001033 | [6 empty] | Wind | 100
|  | SR | Andhra Pradesh 31-12-27 | Kurnool-IV PS |  | PRATAPATI ENERGY (SEVEN) PRIVATE LIMITED |  | 2200001099 | [6 empty] | Hybrid (RHGS) | 354
|  | NR | Rajasthan | Merta-II |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000879 | [6 empty] | Solar | 300
|  | WR | Gujarat | Jamnagar S/s |  | MFA RENEWABLES PRIVATE LIMITED |  | 2200001137 | [6 empty] | Wind | 297
|  | WR | Gujarat | Jamnagar S/s |  | OPWIND ENERGY PRIVATE LIMITED |  | 2200001189 | [6 empty] | Hybrid (RHGS) | 254
|  | WR | Gujarat | Jamnagar S/s |  | KADODIYA WIND ENERGY PRIVATE LIMITED |  | 2200001230 | [6 empty] | Wind | 100
|  | WR | Gujarat | Jamnagar S/s |  | SATPURA RENEWABLE PRIVATE LIMITED |  | 2200001349 | [6 empty] | Solar | 349
|  | SR | Andhra Pradesh 01-01-28 | Kurnool-III PS |  | ADANI RENEWABLE ENERGY FIFTY ONE LIMITED |  | 2200000508 | [6 empty] | Pump Storage | 1250
|  | WR | Maharashtra | South Kalamb |  | THE TATA POWER COMPANY LIMITED |  | 2200000177 | [6 empty] | Pump Storage | 1150
|  | WR | Gujarat | Raghanesda PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001048 | [6 empty] | Solar | 200
|  | SR | Andhra Pradesh 29-02-28 | Anantapur PS |  | RENEW VIKRAM SHAKTI PRIVATE LIMITED |  | 2200000372 | [6 empty] | Hybrid (RHGS) | 160 (Solar:40 MW, Wind:
|  | SR | Andhra Pradesh 29-02-28 | Anantapur PS |  | RENEW VIKRAM SHAKTI PRIVATE LIMITED |  | 2200000583 | [6 empty] | Wind | 140
|  | WR | Gujarat | Raghanesda PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000989 | [6 empty] | Solar | 100
|  | WR | Gujarat | Raghanesda PS |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000992 | [6 empty] | Solar | 100
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-III) |  | TEQ GREEN POWER XXII PRIVATE LIMITED |  | 2200001431 | [6 empty] | Hybrid (RHGS) | 250
|  | SR | Andhra Pradesh 31-03-28 | Anantapur-II PS |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200001294 | [6 empty] | Hybrid (RHGS) | 272.8
|  | SR | Andhra Pradesh 31-03-28 | Anantapur-II PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001303 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 31-03-28 | Anantapur-II PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001304 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 31-03-28 | Anantapur-II PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001318 | [6 empty] | Wind | 300
|  | SR | Andhra Pradesh 31-03-28 | Anantapur-II PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001319 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 31-03-28 | Anantapur-II PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001341 | [6 empty] | Wind | 300
|  | SR | Andhra Pradesh 31-03-28 | Anantapur-II PS |  | HERO SOLAR ENERGY PRIVATE LIMITED |  | 2200001416 | [6 empty] | Hybrid (RHGS) | 281.8
|  | SR | Andhra Pradesh 31-03-28 | Kurnool-IV PS |  | ESSAR RENEWABLES LIMITED |  | 2200001364 | [6 empty] | Solar | 300
|  | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | [6 empty] | #REF! | #REF!
|  | SR | Andhra Pradesh 31-03-28 | Kurnool-IV PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001362 | [6 empty] | Solar | 300
|  | SR | Andhra Pradesh 31-03-28 | Kurnool-IV PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001363 | [6 empty] | Solar | 600
|  | SR | Andhra Pradesh 31-03-28 | Kurnool-IV PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001383 | [6 empty] | Wind | 300
|  | SR | Andhra Pradesh 31-03-28 | Kurnool-IV PS |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001384 | [6 empty] | Wind | 300
|  | WR | Gujarat | Raghanesda PS |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200001018 | [6 empty] | Solar | 350
|  | NR | Rajasthan | Sirohi |  | IZHMA SOLAR PRIVATE LIMITED |  | 2200000743 | [6 empty] | Solar | 200
|  | SR | Karnataka | Tumkur-II PS |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200001017 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III |  | FRUGAL ENERGY PRIVATE LIMITED |  | 2200000118 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bhadla-III |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED |  | 2200000144 | [6 empty] | Solar | 300
|  | WR | Maharashtra | Dhule PS (Sec-I) |  | JUNIPER GREEN GEM PRIVATE LIMITED |  | 2200001276 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Fatehgarh-IV (Sec- II) |  | SPRNG PAVANA URJA PRIVATE LIMITED |  | 2200000034 | [6 empty] | Solar | 150
|  | WR | Gujarat | Jam Khambhaliya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000379 | [6 empty] | Wind | 200
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000926 | [6 empty] | Wind | 150
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000428 | [6 empty] | Wind | 300
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED |  | 2200001037 | [6 empty] | Hybrid (RHGS) | 295
|  | WR | Gujarat | Raghanesda PS |  | SPRNG WIND ENERGY PRIVATE LIMITED |  | 2200000612 | [6 empty] | Solar | 200
|  | WR | Madhya Pradesh | Rajgarh SS |  | SPRNG VAYU VIDYUT PRIVATE LIMITED |  | 2200000819 | [6 empty] | Wind | 16.8
|  | NR | Rajasthan | Bhadla-III |  | SOLARCRAFT POWER INDIA 4 PRIVATE LIMITED |  | 2200000192 | [6 empty] | Solar | 110
|  | NR | Rajasthan | Bhadla-III |  | GREEN INFRA CLEAN ENERGY GENERATION LIMITED |  | 2200000232 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-III |  | RENEW SOLAR (SHAKTI SIX) PRIVATE LIMITED |  | 2200000275 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bhadla-III |  | MALUR RENEWABLES PRIVATE LIMITED |  | 2200000266 | [6 empty] | Solar | 650
|  | NR | Rajasthan | Bhadla-III |  | SOLARCRAFT POWER INDIA 4 PRIVATE LIMITED |  | 2200000300 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Bhadla-III |  | RENEW SOLAR (SHAKTI SIX) PRIVATE LIMITED |  | 2200000309 | [6 empty] | Solar | 400
|  | SR | Andhra Pradesh 30-09-28 | Anantapur-II PS |  | GREEN INFRA WIND ENERGY PRIVATE LIMITED |  | 2200000820 | [6 empty] | Solar | 300
|  | WR | Gujarat | KPS-2 (Sec-I) |  | GUJARAT INDUSTRIES POWER COMPANY LTD. |  | 2200000159 | [6 empty] | Solar | 2375
|  | WR | Gujarat | Jam Khambhaliya PS |  | MIYANI POWER INFRA LLP |  | 2200001156 | [6 empty] | Wind | 321.3
|  | WR | Gujarat | Jam Khambhaliya PS |  | MIYANI POWER INFRA LLP |  | 2200001155 | [6 empty] | Wind | 321.3
|  | WR | Gujarat | Kalyanpur PS (Sec-I) |  | IRIS RENEWABLES ALPHA TWO PRIVATE LIMITED |  | 2200000674 | [6 empty] | Wind | 300
|  | WR | Gujarat | Kalyanpur PS (Sec-I) |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000935 | [6 empty] | Wind | 300
|  | WR | Gujarat | Kalyanpur PS (Sec-I) |  | TORRENT SAURYA URJA 2 PRIVATE LIMITED |  | 2200001069 | [6 empty] | Hybrid (RHGS) | 1200
|  | WR | Gujarat | Kalyanpur PS (Sec-I) |  | DEVPUR RENEWABLES PRIVATE LIMITED |  | 2200001132 | [6 empty] | Hybrid (RHGS) | 200
|  | WR | Gujarat | Kalyanpur PS (Sec-I) |  | ADITYA BIRLA RENEWABLES LIMITED |  | 2200001133 | [6 empty] | Hybrid (RHGS) | 300
|  | WR | Gujarat | Kalyanpur PS (Sec-I) |  | TORRENT SAURYA URJA 2 PRIVATE LIMITED |  | 2200001159 | [6 empty] | Hybrid (RHGS) | 300
|  | WR | Gujarat | Kalyanpur PS (Sec-I) |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200001209 | [6 empty] | Wind | 50
|  | NR | Rajasthan | Bhadla-III |  | PRERAK SOLAR URJA PRIVATE LIMITED |  | 2200000360 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bhadla-III |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000407 | [6 empty] | Solar | 1000
|  | SR | Karnataka | Bidar PS |  | SPRNG GREEN ENERGY PRIVATE LIMITED |  | 2200000753 | [6 empty] | Wind | 100
|  | WR | Gujarat | Raghanesda PS |  | SPRNG OJAS PRIVATE LIMITED |  | 2200000614 | [6 empty] | Solar | 200
|  | WR | Gujarat | Raghanesda PS |  | SPRNG WIND ENERGY PRIVATE LIMITED |  | 2200001160 | [6 empty] | Hybrid (RHGS) | 164
|  | WR | Gujarat | Raghanesda PS |  | SPRNG OJAS PRIVATE LIMITED |  | 2200000651 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Ramgarh |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000499 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Ramgarh |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000550 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Ramgarh |  | MIGOS HYBREN PRIVATE LIMITED |  | 2200000618 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Ramgarh |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000598 | [6 empty] | Solar | 500
|  | NR | Rajasthan | Ramgarh |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000599 | [6 empty] | Solar | 500
|  | NR | UP | Robertsganj |  | AVAADA WATERBATTERY PRIVATE LIMITED |  | 2200000553 | [6 empty] | Pump Storage | 1120
|  | NR | Rajasthan | Ramgarh |  | PRAVAT RENEWABLES INDIA PROJECT PRIVATE LIMITED |  | 2200000452 | [6 empty] | Solar | 300
|  | WR | Gujarat | Lakadiya PS |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200000511 | [6 empty] | Solar | 200
|  | WR | Gujarat | KPS-1 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000478 | [6 empty] | Hybrid (RHGS) | 650
|  | WR | Gujarat | KPS-1 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000479 | [6 empty] | Hybrid (RHGS) | 100
|  | WR | Gujarat | KPS-1 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000784 | [6 empty] | Wind | 60
|  | WR | Gujarat | KPS-3 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000476 | [6 empty] | Hybrid (RHGS) | 1250
|  | WR | Gujarat | KPS-3 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000477 | [6 empty] | Hybrid (RHGS) | 75
|  | WR | Gujarat | KPS-3 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000602 | [6 empty] | Hybrid (RHGS) | 65 MW (Solar: 50MW
|  | WR | Gujarat | KPS-3 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000603 | [6 empty] | Wind | 75
|  | WR | Gujarat | KPS-3 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000785 | [6 empty] | Wind | 100
|  | WR | Gujarat | KPS-3 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000786 | [6 empty] | Wind | 195
|  | WR | Gujarat | KPS-3 (Sec-II) |  | ADANI GREEN ENERGY LIMITED |  | 2200000953 | [6 empty] | Hybrid (RHGS) | 1530
|  | SR | Karnataka | Bidar PS |  | SPRNG VAYU KIRAN PRIVATE LIMITED |  | 2200000751 | [6 empty] | Wind | 200
|  | WR | Gujarat | Lakadia-II (Sec-I) |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200001062 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Barmer-II |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000636 | [6 empty] | Solar | 450
|  | NR | Rajasthan | Barmer-II |  | SPRNG URJA PRIVATE LIMITED |  | 2200000681 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Barmer-II |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000810 | [6 empty] | Solar | 717
|  | NR | Rajasthan | Barmer-II |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000906 | [6 empty] | Solar | 500
|  | NR | Rajasthan | Barmer-II |  | SPRNG RENEWABLE RESOURCES PRIVATE LIMITED |  | 2200000531 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Barmer-II |  | SPRNG URJA PRIVATE LIMITED |  | 2200000539 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Barmer-II |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000567 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-II |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200000580 | [6 empty] | Solar | 500
|  | NR | Rajasthan | Barmer-II |  | AMARESHA RENAWABLES INDIA PROJECT PRIVATE LIMITED |  | 2200000715 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-II |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000778 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-II |  | ADANI RENEWABLE ENERGY TWO LIMITED |  | 2200000809 | [6 empty] | Wind | 595
|  | NR | Rajasthan | Barmer-II |  | ADANI RENEWABLE ENERGY TWO LIMITED |  | 2200000807 | [6 empty] | Wind | 600
|  | NR | Rajasthan | Bikaner-V |  | SAURYA URJA COMPANY OF RAJASTHAN LIMITED |  | 2200000475 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-V |  | IRAAX INTERNATIONAL (OPC) PRIVATE LIMITED |  | 2200000484 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-V |  | IRAAX INTERNATIONAL (OPC) PRIVATE LIMITED |  | 2200000540 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Bikaner-V |  | AVAADA RJBIKANER PRIVATE LIMITED |  | 2200000561 | [6 empty] | Solar | 136
|  | NR | Rajasthan | Fatehgarh-III (Sec- II) |  | ADITYA BIRLA RENEWABLES LIMITED |  | 2200001128 | [6 empty] | Hybrid (RHGS) | 100
|  | WR | Madhya Pradesh | Mandsaur PS (Sec-I) |  | SPRNG GREEN ENERGY 2 PRIVATE LIMITED |  | 2200000824 | [6 empty] | Solar | 600
|  | WR | Gujarat | Raghanesda PS |  | JSW Energy Utkal Limited |  | 2200000650 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Bhadla-IV |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000516 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000521 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Bhadla-IV |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000522 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | KANTIDA RENEWABLES INDIA PROJECT PRIVATE LIMITED |  | 2200000761 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000811 | [6 empty] | Solar | 765
|  | NR | Rajasthan | Bhadla-IV |  | DEMETER SUN POWER PRIVATE LIMITED |  | 2200000875 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001085 | [6 empty] | Solar | 700
|  | NR | Rajasthan | Bhadla-IV |  | AVAADA RJSUSTAINABLE PRIVATE LIMITED |  | 2200001316 | [6 empty] | Solar | 660
|  | NR | Rajasthan | Bhadla-IV |  | ARIGHT FOODS AND ENERGY PRIVATE LIMITED |  | 2200001404 | [6 empty] | Solar | 2000
|  | NR | Rajasthan | Bikaner-V |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000726 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bikaner-V |  | SA RENEWABLE INFRA PRIVATE LIMITED |  | 2200000755 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Bikaner-V |  | VENA ENERGY VINDHYA WIND POWER PRIVATE LIMITED |  | 2200000796 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | SOLARCRAFT POWER INDIA 8 PRIVATE LIMITED |  | 2200000866 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED |  | 2200001021 | [6 empty] | Solar | 350
|  | NR | Rajasthan | Bikaner-V |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200001056 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bikaner-V |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200001126 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Bikaner-V |  | JUNIPER GREEN ENERGY PRIVATE LIMITED |  | 2200001210 | [6 empty] | Solar | 130
|  | NR | Rajasthan | Bikaner-V |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200001261 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | PURVAH GREEN POWER PRIVATE LIMITED |  | 2200001262 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bikaner-V |  | AVAADA SURYAENERGY PRIVATE LIMITED |  | 2200001254 | [6 empty] | Solar | 560
|  | NR | Rajasthan | Bikaner-V |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001353 | [6 empty] | Solar | 350
|  | NR | Rajasthan | Bikaner-V |  | AVAADA RJBIKANER PRIVATE LIMITED |  | 2200001326 | [6 empty] | Solar | 354
|  | NR | Rajasthan | Ramgarh |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000661 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Ramgarh |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED |  | 2200000662 | [6 empty] | Solar | 284
|  | NR | Rajasthan | Ramgarh |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200000672 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Ramgarh-II |  | ADANI RENEWABLE ENERGY PARK RAJASTHAN LIMITED |  | 2200000600 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Ramgarh-II |  | ADANI RENEWABLE ENERGY PARK RAJASTHAN LIMITED |  | 2200000601 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Ramgarh-II |  | JSW NEO ENERGY LIMITED |  | 2200000689 | [6 empty] | Solar | 700
|  | NR | Rajasthan | Ramgarh-II |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000777 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Ramgarh-II |  | RJS RENEWABLES PRIVATE LIMITED |  | 2200000782 | [6 empty] | Wind | 150
|  | NR | Rajasthan | Ramgarh-II |  | SHN GREEN POWER PRIVATE LIMITED |  | 2200001198 | [6 empty] | Wind | 297
|  | NR | Rajasthan | Ramgarh-II |  | JUNACHAY WIND ENERGY PRIVATE LIMITED |  | 2200001382 | [6 empty] | Wind | 100
|  | NR | Rajasthan | Ramgarh-II |  | DHARVI KALAN WIND ENERGY PRIVATE LIMITED |  | 2200001391 | [6 empty] | Wind | 100
|  | NR | Rajasthan | Ramgarh-II |  | DANGRI WIND ENERGY PRIVATE LIMITED |  | 2200001390 | [6 empty] | Wind | 100
|  | NR | Rajasthan | Ramgarh-II |  | TATA POWER RENEWABLE ENERGY LIMITED |  | 2200001523 | [6 empty] | Wind | 300
|  | NR | Rajasthan | Bhadla-IV |  | VISMAYA FOUR RENEWABLES PRIVATE LIMITED |  | 2200000910 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-II |  | NTPC RENEWABLE ENERGY LIMITED |  | 2200000973 | [6 empty] | Solar | 100
|  | SR | Karnataka | Bidar PS |  | SPRNG ENERGY PRIVATE LIMITED |  | 2200000767 | [6 empty] | Wind | 100
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000850 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000886 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000887 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000888 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000889 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000890 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Jalore |  | SPRNG VAAYU URJA PRIVATE LIMITED |  | 2200001006 | [6 empty] | Solar | 600
|  | WR | Gujarat | Raghanesda PS |  | SPRNG VAYU KIRAN PRIVATE LIMITED |  | 2200001161 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Sanchore |  | HR SARASWATI ENERGY PRIVATE LIMITED |  | 2200000946 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001026 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Barmer-III |  | TEQ GREEN POWER IX PRIVATE LIMITED |  | 2200001300 | [6 empty] | Solar | 208.5
|  | NR | Rajasthan | Barmer-III |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001352 | [6 empty] | Solar | 750
|  | NR | Rajasthan | Barmer-III |  | ACME GAMMA URJA PRIVATE LIMITED |  | 2200001366 | [6 empty] | Solar | 350
|  | NR | Rajasthan | Barmer-III |  | ENREN-IV ENERGY PRIVATE LIMITED |  | 2200001398 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001422 | [6 empty] | Solar | 800
|  | NR | Rajasthan | Barmer-III |  | POKHRAN WIND ENERGY PRIVATE LIMITED |  | 2200001440 | [6 empty] | Wind | 99
|  | NR | Rajasthan | Barmer-III |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001503 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | APRAAVA ENERGY PRIVATE LIMITED |  | 2200001557 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | UNIQUE HYTECH RENEWABLE ENERGY PRIVATE LIMITED |  | 2200001622 | [6 empty] | Hybrid (RHGS) | 1000
|  | NR | Rajasthan | Jalore |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200001087 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | VISMAYA FOUR RENEWABLES PRIVATE LIMITED |  | 2200001284 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Barmer-II |  | VISMAYA FIVE RENEWABLES PRIVATE LIMITED |  | 2200000954 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-II |  | VISMAYA FIVE RENEWABLES PRIVATE LIMITED |  | 2200001285 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Barmer-III |  | FOXTROT SOLAR RENEWABLES ENERGY PRIVATE LIMITED |  | 2200001057 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Barmer-III |  | GREEN INFRA RENEWABLE ENERGY FARMS PRIVATE LIMITED |  | 2200001141 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | GREEN INFRA RENEWABLE ENERGY FARMS PRIVATE LIMITED |  | 2200001194 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001188 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-III |  | FOXTROT SOLAR RENEWABLES ENERGY PRIVATE LIMITED |  | 2200001252 | [6 empty] | Solar | 74
|  | NR | Rajasthan | Merta-III |  | ENREN-III ENERGY PRIVATE LIMITED |  | 2200000860 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Pali |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200001089 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Pali |  | DIYOS THREE RENEWABLES PRIVATE LIMITED |  | 2200001100 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-V |  | SPRNG GREEN ENERGY 4 PRIVATE LIMITED |  | 2200001417 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bhadla-V |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001464 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Barmer-III |  | FOXTROT SOLAR RENEWABLES ENERGY PRIVATE LIMITED |  | 2200001088 | [6 empty] | Solar | 80
|  | NR | Rajasthan | Jalore |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200000890 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Jalore |  | SPRNG VAAYU URJA PRIVATE LIMITED |  | 2200001006 | [6 empty] | Solar | 600
|  | WR | Gujarat | Raghanesda PS |  | SPRNG VAYU KIRAN PRIVATE LIMITED |  | 2200001161 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Sanchore |  | HR SARASWATI ENERGY PRIVATE LIMITED |  | 2200000946 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001026 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Barmer-III |  | TEQ GREEN POWER IX PRIVATE LIMITED |  | 2200001300 | [6 empty] | Solar | 208.5
|  | NR | Rajasthan | Barmer-III |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001352 | [6 empty] | Solar | 750
|  | NR | Rajasthan | Barmer-III |  | ACME GAMMA URJA PRIVATE LIMITED |  | 2200001366 | [6 empty] | Solar | 350
|  | NR | Rajasthan | Barmer-III |  | ENREN-IV ENERGY PRIVATE LIMITED |  | 2200001398 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001422 | [6 empty] | Solar | 800
|  | NR | Rajasthan | Barmer-III |  | ROHAT SOLAR PARK PRIVATE LIMITED |  | 2200001372 | [6 empty] | Solar | 350
|  | NR | Rajasthan | Barmer-III |  | UNIQUE HYTECH RENEWABLE ENERGY PRIVATE LIMITED |  | 2200001407 | [6 empty] | Wind | 150
|  | NR | Rajasthan | Barmer-III |  | POKHRAN WIND ENERGY PRIVATE LIMITED |  | 2200001440 | [6 empty] | Wind | 99
|  | NR | Rajasthan | Barmer-III |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001503 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | APRAAVA ENERGY PRIVATE LIMITED |  | 2200001557 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | UNIQUE HYTECH RENEWABLE ENERGY PRIVATE LIMITED |  | 2200001622 | [6 empty] | Hybrid (RHGS) | 1000
|  | NR | Rajasthan | Jalore |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200001087 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-IV |  | VISMAYA FOUR RENEWABLES PRIVATE LIMITED |  | 2200001284 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Barmer-II |  | VISMAYA FIVE RENEWABLES PRIVATE LIMITED |  | 2200000954 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bikaner-V |  | ADYANT ENERSOL PRIVATE LIMITED |  | 2200001786 | [6 empty] | Solar | 150
|  | NR | Rajasthan | Ramgarh-II |  | JIRE GREEN ENERGY PROJECT THREE LIMITED |  | 2200001717 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Ramgarh-II |  | WAAREE FOREVER ENERGIES PRIVATE LIMITED |  | 2200001735 | [6 empty] | Hybrid (RHGS) | 600
|  | NR | Rajasthan | Barmer-II |  | VISMAYA FIVE RENEWABLES PRIVATE LIMITED |  | 2200001285 | [6 empty] | Solar | 50
|  | NR | Rajasthan | Barmer-III |  | FOXTROT SOLAR RENEWABLES ENERGY PRIVATE LIMITED |  | 2200001057 | [6 empty] | Solar | 100
|  | NR | Rajasthan | Barmer-III |  | GREEN INFRA RENEWABLE ENERGY FARMS PRIVATE LIMITED |  | 2200001141 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | GREEN INFRA RENEWABLE ENERGY FARMS PRIVATE LIMITED |  | 2200001194 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Barmer-III |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001188 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Barmer-III |  | FOXTROT SOLAR RENEWABLES ENERGY PRIVATE LIMITED |  | 2200001252 | [6 empty] | Solar | 74
|  | NR | Rajasthan | Merta-III |  | ENREN-III ENERGY PRIVATE LIMITED |  | 2200000860 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Pali |  | TEQ GREEN POWER XV PRIVATE LIMITED |  | 2200001089 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Pali |  | DIYOS THREE RENEWABLES PRIVATE LIMITED |  | 2200001100 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-V |  | SPRNG GREEN ENERGY 4 PRIVATE LIMITED |  | 2200001417 | [6 empty] | Solar | 400
|  | NR | Rajasthan | Bhadla-V |  | AVAADA ENERGY PRIVATE LIMITED |  | 2200001464 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Pali |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001866 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sanchore |  | GODAVARI GREEN ENERGY PRIVATE LIMITED |  | 2200001810 | [6 empty] | Solar | 250
|  | NR | Rajasthan | Bhadla-V |  | AZURE POWER FIFTY ONE PRIVATE LIMITED |  | 2200001420 | [6 empty] | Solar | 600
|  | NR | Rajasthan | Bhadla-V |  | TORRENT GREEN ENERGY PRIVATE LIMITED |  | 2200001642 | [6 empty] | Solar | 1000
|  | NR | Rajasthan | Bhadla-V |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED |  | 2200001700 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-V |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001781 | [6 empty] | Solar | 200
|  | NR | Rajasthan | Bhadla-V |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001864 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-V |  | RENEW SOLAR POWER PRIVATE LIMITED |  | 2200001865 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Bhadla-V |  | VISMAYA FOUR RENEWABLES PRIVATE LIMITED |  | 2200001827 | [6 empty] | Solar | 300
|  | NR | Rajasthan | Sanchore |  | WAAREE FOREVER ENERGIES PRIVATE LIMITED |  | 2200001901 | [6 empty] | Solar | 300
|  | WR |  | 400/220kV Jam Khambhaliya (GIS) PS # | 22°08'41"N 69°40'38"E
|  | WR |  | 765/400/220kV Bhuj PS# | 23.45583333˚ N, 69.56235833˚ E
|  | WR |  | 765/400/220kV Bhuj-II PS# | Boundary Coordinates 23°22'29.92"N 69° 8'32.39"E 23°22'26.60"N 69° 8'55.06"E 23°22'6.44"N 69° 8'43.33"E 23°22'15.91"N 69° 8'24.01"E
|  | WR |  | 400/220kV Bhachau S/s | 23.20613889˚ N, 70.18733333˚ E
|  | WR |  | Khavda PS-I | Boundary Coordinates: 534252.00 m E 2665370.00 m N 534924.00 m E 2665328.00 m N 534892.00 m E 2664895.00 m N 534253.00 m E 2664935.00 m N
|  | WR |  | Khavda PS-II
|  | WR |  | Banaskantha (Radhanesda) PS [GIS] (Vav) | Boundary Coordinates: 24°20'33.9"N 71°29'08.3"E 24°20'40.4"N 71°29'13.5"E 24°20'35.5"N 71°29'20.6"E 24°20'29.0"N 71°29'15.3"E
|  | WR |  | 400/220kV Rajgarh (PG) (existing) S/s# | 22.68222222˚ N, 74.92444444˚ E
|  | WR |  | 400/220kV Indore (PG) (existing) S/s | 22°54'31.81"N, 75°53'58.87"E
|  | WR |  | Pachora PS# | 23.7177N 76.12333E
|  | WR |  | Neemuch PS
|  | WR |  | Khandwa S/s (PG) (existing S/s) | 21.83240889˚ N, 76.40401778˚ E
|  | WR |  | Raipur S/s (PG) (Existing S/s)# | 21˚ 14ʼ 00ˮN, 81˚ 29ʼ 00ˮE
|  | WR |  | Kallam PS# | 18°37'21.05"N, 75°52'17.08"E
|  | WR |  | 765/400/220kV Solapur (PG) (existing S/s)# | 17˚ 36ʼ 31.21ˮ N, 76˚ 2ʼ 59.98ˮE
|  | SR |  | 400/230 kV Tuticorin-II S/s | 9°3'02.1'' N 77°55'31.6''E
|  | SR |  | 400/230 kV Pugalur S/s | 10°57'42"N 77°55'22"E
|  | SR |  | 400/220 kV Palakkad S/s 10°46'22"N 76°45'36"E
|  | SR |  | 400/220 kV NP Kunta S/s | 14° 2'53.18"N, 78°25'43.01"E
|  | SR |  | 400/220 kV Pavagada S/s | 14.318579N 77.385479E
|  | SR |  | 400/220 kV Hiriyur S/s | 13°57'12.33"N 76°32'11.40"E
|  | SR |  | 765/400 kV Kurnool(new) S/s | 15°40'28.6" N 78°10'35.23" E
|  | SR |  | 400/220 kV Koppal S/s | 15°21'55.49"N 75°59'24.61"E
|  | SR |  | 400/230 kV Karur S/s | 10°50'34.10"N 77°39'32.91"E
|  | SR |  | 400/220 kV Gadag S/s | Boundary coordinates 15°47'13.673"N , 75°51'35.001" E 15°47'13.207" N, 75°51'22.707" E 15°46'58.257" N, 75°51'20.956" E 15°46'57.085" N, 75°51'34.122" E
|  | SR |  | 765/400/220kV Koppal- II PS
|  | SR |  | 400/220kV Gadag-II PS
|  | NR |  | 765/400/220kV Bhadla PS # | 27 25 10 N, 72 04 20E
|  | NR |  | 765/400/220kV Bikaner S/s # | 28 14 57 N, 73 22 55 E
|  | NR |  | 400kV Fatehgarh PS (TBCB) # | 26°51'8.48"N, 71°30'34.29"E
|  | NR |  | 765/400/220kV Bhadla- II PS # | Boundary Coordinates Point1:- 27.5047695, 72.4764157 Point2:- 27.5103991, 72.4844684 Point3:- 27.5160828, 72.4792790 Point4:- 27.5109950, 72.4713292
|  | NR |  | 765/400/220kV Fatehgarh-II PS # | Boundary Coordinates Point1:- N 26°42'13.3884", E 71°16'48.936 Point2:- N 26°42'13.5936", E 71°16'19.9956" Point3:- N 26°42'45.9396", E 71°16'19.8588" Point4:- N 26°42'45.6912", E 71°16'48.666"
|  | NR |  | 765/400/220kV Fatehgarh-III PS # | 26°21' 00" N, 71°06' 00" E
|  | NR |  | 400/220kV Bikaner-II PS# | 28°09'20"N, 73*00'23.4"E
|  | NR |  | 400/220kV Fatehgarh-IV PS# | Boundary Coordinates* Point1:- N 26°13'38.76", E 71°15'42.74" Point2:- N 26°13'59.62", E 71°15'53.12" Point3:- N 26°14'11.27", E 71°15'23.11" Point4:- N 26°13'50.22", E 71°15'12.67"
|  | NR |  | 765/400/220kV Bhadla- III PS# | Boundary Coordinates* Point1:- N 27°40'15.65", E 72°12'12.17" Point2:- N 27°40'2.8", E 72°12'20.84" Point3:- N 27°40'10.33", E 72°12'37.23" Point4:- N 27°40'23.54", E 72°12'29.23"
|  | NR |  | 765/400/220kV Ramgarh PS# | Boundary Coordinates* Point1:- N 27°26'39.53", E 70°28'33.75" Point2:- N 27°26'40.33", E 70°29'2.68" Point3:- N 27°27'5.74", E 70°28'52.85" Point4:- N 27°27'5.92", E 70°28'21.92"
|  | NR |  | 765/400/220kV Bikaner- III PS# | Location to be identified
Disclaimer :- # In addition space provision has been kept for future I/c or drawl arrangement. 1. Boundary coordinates indicates the periphery within which the Sub-station is located. 2. Bay numbers are indicative in nature and may be co-related with SLD issued by concerned ISTS Licensee. 3. *The co-ordinates are tentative in nature and subject to change as per availablity of land with in boundary limit. Boundary limit is 3 km radius of above plot (3 km from any of the corner).

## RE Potential
| Region | State | District | Complex | S/s | Location (Village/Tehsil) | Solar | Wind | Hybrid | Others (CTUIL) | RE Potential (GW) | Installed Capacity | U/c & granted Capacity | Transmission Scheme | Complex | Remarks
|  |  | Bikaner |  |  | Bikaner | 1.85
Data Scoure (Sl. No.(s)9, 10a, ) |  |  | Bikaner |  |  | Bikaner | 2.95
|  |  | Kurnool |  |  | Kurnool | 5.5
|  |  | Anantapur |  |  | Anantapur | 2.5
|  |  | Gadag |  |  | Gadag | 2.5
|  |  | Koppal |  |  | Koppal | 2.5
|  | Rajasthan |  |  |  |  | 15 | 1 |  |  | 60 |  |  |  |  | 45 GW (15 GW Wind & 30 GW solar in GIB Zone)
|  | Andhra Pradesh |  |  |  |  | 18 | 2 |  |  | 33
|  | Karnataka |  |  |  |  | 8 | 3 |  |  | 9
|  | Tamil Nadu |  |  |  |  | 5 | 4 |  |  | 5 |  |  |  |  | Offshore wind
|  | Telangana |  |  |  |  | 3 | 5 |  |  | 10
|  | Madhya Pradesh |  |  |  |  | 2 | 6 |  |  | 6
|  | Gujarat |  |  |  |  | 5 | 7 |  |  | 5 |  |  |  |  | Offshore wind
|  | Maharashtra |  |  |  |  | 2 | 8 |  |  | 5.5
|  | Rajasthan |  |  |  |  | 30 | 75
|  | Andhra Pradesh |  |  |  |  | 10 | 51 |  |  | 10
|  | Karnataka |  |  |  |  | 2 | 17 |  |  | 2
|  | Tamil Nadu |  |  |  |  | 5 | 5
|  | Telangana |  |  |  |  | 1 | 13 |  |  | 2.5
|  | Madhya Pradesh |  |  |  |  | 2 | 8
|  | Gujarat |  |  |  |  | 5 | 5
|  | Maharashtra |  |  |  |  | 1 | 7.5 |  |  | 1
|  | Rajasthan |  |  |  |  | 60 | 15 |  |  | 67.5
Gujarat
Maharashtra
|  | Maharashtra |  |  |  |  | 5.5 | 2 |  |  | 6.5 |  |  |  |  | 5.4
Madhya Pradesh
|  | Madhya Pradesh |  |  |  |  | 6 | 2 |  |  | 8
Andhra Pradesh
|  | Andhra Pradesh |  |  |  |  | 33 | 18 |  |  | 41
Karnataka
|  | Karnataka |  |  |  |  | 9 | 8 |  |  | 14
Telangana
|  | Telangana |  |  |  |  | 10 | 3 |  |  | 11.5 |  |  |  |  | 8.5
Tamil Nadu
|  | Telangana | Bikaner |  |  | Bikaner | 8 | 8.1 |  |  | 400
|  | Telangana | Bikaner |  |  | Bikaner | 400
|  | Telangana | Bikaner |  |  | Bikaner | 300
|  | Telangana | Bikaner |  |  | Bikaner | 9 | 8.1 |  |  | 400
|  | Telangana | Gadag |  |  | Gadag | 12 | 1000 |  |  | 400
|  | Telangana | Gadag |  |  | Gadag | 400
|  | Telangana | Koppal |  |  | Koppal | 13 | 2500 |  |  | 400
|  | Telangana | Koppal |  |  | Koppal | 400
|  | Telangana | Koppal |  |  | Koppal | 2
|  | Telangana | Gadag |  |  | Gadag | 11 | 1500 |  |  | 400
|  | Telangana | Kurnool |  |  | Kurnool | 1 | 2500 |  |  | 400
|  | Telangana | Kurnool |  |  | Kurnool | 400
|  | Telangana | Anantapur |  |  | Anantapur | 400
|  | Telangana | Kurnool |  |  | Kurnool | 3 | 3000 |  |  | 765
|  | Telangana | Kurnool |  |  | Kurnool | 765
|  | Rajasthan |  |  |  |  | 7 | 0 |  |  | 7
|  | Rajasthan |  |  |  |  | 6 | 6 |  |  | 12
|  | Rajasthan |  |  |  |  | 6 | 4 |  |  | 10
|  | Rajasthan |  |  |  |  | 3 | 0 |  |  | 3
|  | Rajasthan |  |  |  |  | 2 | 0 |  |  | 2
|  | Rajasthan |  |  |  |  | 3 | 2 |  |  | 5
|  | Rajasthan |  |  |  |  | 4 | 3 |  |  | 7
|  | Rajasthan |  |  |  |  | 6 | 0 |  |  | 6
|  | Rajasthan |  |  |  |  | 5 | 0 |  |  | 5
|  | Maharashtra |  |  |  |  | 1 | 0 |  |  | 1
|  | Maharashtra |  |  |  |  | 1 | 1 |  |  | 2
|  | Maharashtra |  |  |  |  | 2.5 | 2.5 |  |  | 0 |  |  |  |  | 2.5
|  | Gujarat |  |  |  |  | 5 | 5 |  |  | 2
|  | Telangana |  |  |  |  | 2.5 | 1 |  |  | 3.5
|  | Telangana |  |  |  |  | 2.5 | 0 |  |  | 2.5 |  |  |  |  | 0.5
|  | Karnataka |  |  |  |  | 2 | 2 |  |  | 4
|  | Karnataka |  |  |  |  | 0 | 2 |  |  | 2
|  | Karnataka |  |  |  |  | 1.5 | 0 |  |  | 1.5
|  | Tamil Nadu |  |  |  |  | 5 | 5 |  |  | 0
|  | Tamil Nadu |  | Bikaner-II | Bikaner-II |  | 7 | 0 |  | 0 | 7
|  | Tamil Nadu |  | Bikaner-III | Bikaner-III |  | 7 | 0 |  | 0 | 7
|  | Tamil Nadu |  | Fatehgarh-IV | Fatehgarh-IV |  | 6 | 6 |  | 2 | 12
|  | Tamil Nadu |  | Ramgarh | Ramgarh |  | 6 | 4 |  | 2 | 10
|  | Tamil Nadu |  | Jalore | Jalore |  | 3 | 0 |  | 0 | 3
|  | Tamil Nadu |  | Sanchore | Sanchore |  | 3 | 0 |  | 0 | 3
|  | Tamil Nadu |  | Sirohi | Sirohi |  | 3 | 0 |  | 0 | 3
|  | Tamil Nadu |  | Pali | Pali |  | 3 | 0 |  | 0 | 3
|  | Tamil Nadu |  | Ajmer | Ajmer |  | 2 | 0 |  | 0 | 2
|  | Tamil Nadu |  | Nagaur | Nagaur |  | 2 | 0 |  | 0 | 2
|  | Tamil Nadu |  | Bhadla-IV | Bhadla-IV |  | 3 | 2 |  | 0 | 5
|  | Tamil Nadu |  | Barmer-I | Barmer-I |  | 4 | 3 |  | 2 | 7
|  | Tamil Nadu |  | Barmer-II | Barmer-II |  | 6 | 0 |  | 0 | 6
|  | Tamil Nadu |  | Jaisalmer/ Jodhpur (Intra-State) | Jaisalmer/ Jodhpur (Intra-State) |  | 5 | 0 |  | 0 | 5
|  | Tamil Nadu |  | Total | Total |  | 60 | 15 |  | 6 | 75
|  | Tamil Nadu |  | Jaisalmer/ Jodhpur (Intra-State) | Jaisalmer/ Jodhpur (Intra-State) |  | 5 | 0 |  | 0 | 5
|  | Tamil Nadu |  | Jaisalmer/ Jodhpur (Intra-State) | Jaisalmer/ Jodhpur (Intra-State) |  | 5 | 0 |  | 0 | 5
|  | Tamil Nadu |  | Kurnool-IV | Kurnool-IV |  | 7.5 | 4 |  | 3 | 11.5
|  | Tamil Nadu |  | Kurnool-V | Kurnool-V |  | 7.5 | 4 |  | 3 | 11.5
|  | Tamil Nadu |  | Anantapur | Anantapur |  | 2 | 2 |  | 1 | 4
|  | Tamil Nadu |  | Anantapur-II | Anantapur-II |  | 8 | 8 |  | 4 | 16
|  | Tamil Nadu |  | Kadapa-II | Kadapa-II |  | 8 | 0 |  | 3 | 8
|  | Tamil Nadu |  | Total | Total |  | 33 | 18 |  | 14 | 51
|  | Tamil Nadu |  | Koppal-II | Koppal-II |  | 2 | 2 |  | 1 | 4
|  | Tamil Nadu |  | Gadag-II | Gadag-II |  | 2 | 2 |  | 1 | 4
|  | Tamil Nadu |  | Devanagere/ Chitragurga | Devanagere/ Chitragurga |  | 2 | 2 |  | 1 | 4
|  | Tamil Nadu |  | Bijapur | Bijapur |  | 0 | 2 |  | 0 | 2
|  | Tamil Nadu |  | Bellary | Bellary |  | 1.5 | 0 |  | 0 | 1.5
|  | Tamil Nadu |  | Tumkur-II | Tumkur-II |  | 1.5 | 0 |  | 0 | 1.5
|  | Tamil Nadu |  | Total | Total |  | 9 | 8 |  | 3 | 17
|  | Tamil Nadu |  | Nizamabad-II | Nizamabad-II |  | 2.5 | 1 |  | 1 | 3.5
|  | Tamil Nadu |  | Medak | Medak |  | 2.5 | 1 |  | 1 | 3.5
|  | Tamil Nadu |  | Rangareddy | Rangareddy |  | 2.5 | 1 |  | 1 | 3.5
|  | Tamil Nadu |  | Karimnagar | Karimnagar |  | 2.5 | 0 |  | 0 | 2.5
|  | Tamil Nadu |  | Total | Total |  | 10 | 3 |  | 3 | 13
|  | Tamil Nadu |  | Sl. No. | Sl. No.

## Margin
Sl.No. | State | Region | Pooling S/s | Additional Information of Pooling S/s | Timelines | RE Potential |  |  | Expected CoD of Pooling Station | Connectivity Granted/ Agreed |  |  | Connectivity Granted/ Agreed |  |  | Margin for Connectivity |  |  | Additional Margin for Connectivity requiring ICT Augmentation / additional Tr. System |  |  | Effectiveness of GNA for Capacity mentioned under "Margin for Connectivity
[6 empty] | RE Potential (MW) [A] | BESS (MW) [B] | S/s Evacuation Capacity (RE Potential - BESS [AB]) |  | 200 kV | 400 kV | Total (MW) | 200 kV | 400 kV | Total (MW) | 200 kV | 400 kV | Total (MW) | 200 kV | 400 kV | Total (MW)
Existing PS
1 | Rajasthan | NR | Bhadla Complex |  | Existing | 8430 | 0 | 8430 | Existing | 7475 | 2050 | 9525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5251.375MW: Existing 4273.625MW: Nov'25 onwards (Ph-II/Ph-III/Ph-IV) (upto Mar'27)
1a | Rajasthan | NR | Bhadla |  | Existing | 3380 | 0 | 3380 | Existing | 3580 | 0 | 3580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3580MW: Existing
1b | Rajasthan | NR | Bhadla-II |  | Existing | 5050 | 0 | 5050 | Existing | 3895 | 2050 | 5945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1671.375MW: Existing 4273.625MW: Nov'25 onwards (Ph-II/Ph-III/Ph-IV) (upto Mar'27)
2 | Rajasthan | NR | Fatehgarh-Barmer Complex |  | Existing | 9600 | 0 | 9600 | Existing | 6940 | 3200 | 10140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7225.83MW: Existing 2914.17MW: Nov'25 onwards (Ph-II/Ph-III/Ph-IV) (upto Mar'27)
2a | Rajasthan | NR | Fatehgarh |  | Existing | 2200 | 0 | 2200 | Existing | 0 | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Existing Tr. System
2b | Rajasthan | NR | Fatehgarh-II |  | Existing | 5500 | 0 | 5500 | Existing | 4460 | 1000 | 5460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3525.83MW: Existing 1934.17MW: Nov'25 onwards (Ph-II/Ph-III/Ph-IV) (upto Mar'27)
2c | Rajasthan | NR | Fatehgarh-III | Section-I | Existing | 1900 | 0 | 1900 | Existing | 2480 | 0 | 2480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500MW: Existing 480MW: Nov'25 (Ph-II) Including 2x250MW BESS granted at Fatehgarh-III (Section-I) 250MW: Existing 250MW: Mar'26
3 | Rajasthan | NR | Bikaner Complex |  | Existing | 8850 | 3000 | 5850 | Existing | 5695 | 3940 | 9635 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 2865MW: Existing 3360MW: Nov'25 onwards (Ph-II/Ph-IV/Ph-V) (upto Mar'27)
3a | Rajasthan | NR | Bikaner |  | Existing | 1850 | 0 | 1850 | Existing | 1235 | 2940 | 4175 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 2865MW: Existing 1360MW: Nov'25 onwards (Ph-II/Ph-IV/Ph-V) (Upto Mar'27)
3b | Rajasthan | NR | Bikaner-II |  | Existing | 7000 | 3000 | 4000 | Existing | 4460 | 1000 | 5460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5760MW:Nov'25 onwards (Upto Aug'26) (Ph-II/Ph-IV Part-I&II)
4 | Rajasthan | NR | Bhadla-III |  | Between Jul-25 to Dec-25 | 3500 | 0 | 3500 | Sep'25 | 2750 | 1000 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700MW : Feb'26 onwards (Upto Aug'26 (Ph-IV)): cumulative at Ramgarh & Bhadla-III: Raj. (Ph-III) Beyond 3700MW : Bhadla HVDC (Jan'29 Pole-1 & Jul'29 Pole-2) Out of 3750MW, 250MW connectvity of standalone BESS agreed for grant recently
5 | Rajasthan | NR | Fatehgarh-Barmer Complex |  | Between Jul-25 to Dec-25 | 7333 | 0 | 7333 |  | 4185 | 3450 | 7635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Dec'25 onwards (Ph-III) (Upto Mar' 27(Ph-IV/V) )
5a | Rajasthan | NR | Fatehgarh-III | Section-II | Between Jul-25 to Dec-25 | 5233 | 0 | 5233 | Jul'25 onwards | 2160 | 3450 | 5610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Dec'25 onwards- (Ph-III) (Upto Mar'27 (Ph-IV/V) )
5b | Rajasthan | NR | Fatehgarh-IV | Section-I | Between Jul-25 to Dec-25 | 2100 | 0 | 2100 | Aug'25 | 2025 | 0 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Dec'25 onwards (Ph-III) (Upto Aug26)
6 | Rajasthan | NR | Ramgarh |  | Between Jul-25 to Dec-25 | 4000 | 0 | 4000 | Sep'25 | 1200 | 2784 | 3984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650W-3100MW : Bhadla HVDC (Jan'29 Pole-1 & Jul'29 Pole-2) Transmission system for evacuation of power (beyond 2.9GW and upto 4 GW) HVDC sys. is under planning (Exp Comm. up to Oct'30).
7 | Rajasthan | NR | Bikaner-III |  | Between Jul-25 to Dec-25 | 7000 | 3000 | 4000 | Dec'25 | 2267 | 2400 | 4667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000MW: Dec'25 (Ph-IV, Part-I&II) (Upto Aug'26) 667MW: with Bikaner-IV tr. System having schedule Nov'26
8 | Rajasthan | NR | Fatehgarh-IV | Section-II | Between Jul-26 to Dec-31 | 9000 | 4000 | 5000 | Aug'26 | 3480 | 1500 | 4980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hybrid RE Potential : 9GW (Wind+Solar) along with BESS (4 GW), S/s Evacuation Capacity: 5GW For 4000MW (out of 5000MW): Nov'26 (Ph-IV, Part-II). For evacuation of balance 980MW : Dec'26 (Ph-IV, Part-IV).
9 | Rajasthan | NR | Barmer-I |  | Between Jul-26 to Dec-31 | 5500 | 1500 | 4000 | Nov'26 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hybrid RE Potential: 5.5GW (Wind+Solar) along with BESS (1.5 GW), S/s Evacuation Capacity: 4GW. About 1.5GW: Nov'26 (Ph-IV, Part-II) For evacuation of >1.5GW (upto 4GW) : Upto Mar'27 (Ph-IV, Part-IV & Ph- V Part-1) For application of >4GW, connectvity will be provided at Barmer-II PS for which system is under approval (sch. Pole-I : Sep'29, Pole-2: Mar'30 ).
10 | Rajasthan | NR | Barmer-II |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Jan'30 to Jul'30 (HVDC) | 2080 | 3812 | 5892 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 0 | 108 | HVDC Corridor is recently approved for total 6 GW capacity (Expected Sch.Pole-1:Jan'30, Pole-2: Jul'30].
11 | Rajasthan | NR | Barmer-III |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Oct'30 to Apr'31 (HVDC) | 2462 | 3450 | 5912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 88 | HVDC Corridor is under planning for total 6 GW capacity (Expected Sch.Pole-1:Oct'30, Pole-2: Apr'31].
12 | Rajasthan | NR | Barmer-IV |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Jun'31 to Dec'31 (HVDC) | 600 | 2103 | 2703 | 575 | 950 | 1525 | 0 | 0 | 0 | 1772 | 0 | 1772 | HVDC Transmission system (6GW) for evacuation of power from Barmer- IV complexes is under planning (Exp. Comm. Schedule up to Dec'31).
13 | Rajasthan | NR | Bikaner-IV |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Nov'26 | 3150 | 2850 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Comprehensive Transmission scheme for Bikaner-IV PS (6GW) is under implementation (Sch. -Nov'26).
14 | Rajasthan | NR | Bikaner-V |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Apr'30 to Oct'30 (HVDC) | 3490 | 2510 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Corridor is being planned for total 6 GW capacity (Expected Sch.Pole- 1:Apr'30, Pole-2: Oct'30].
15 | Rajasthan | NR | Bikaner-VI |  | Between Jul-26 to Dec-31 | 3548 | 0 | 3548 | Jun'31 to Dec'31 (HVDC) | 600 | 0 | 600 | 1750 | 600 | 2350 | 0 | 0 | 0 | 1850 | 1200 | 3050 | HVDC Transmission system (6GW) for evacuation of power from Bikaner- VI complexes is under planning (Exp. Comm. Schedule up to Dec'31).
16 | Rajasthan | NR | Sirohi |  | Between Jul-26 to Dec-31 | 3000 | 1000 | 2000 | Aug'26 | 1400 | 700 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Connectivity at Sirohi PS will be granted upto 2 GW only. Tr. System for evacuation of power from Sirohi PS is under implementation (sch. Mar'27). Beyond 2 GW in Sirohi complex, HVDC Transmission system for evacuation of power from Jalore complex (Jalore/Sanchore/Sirohi) for comined RE capacity of 6GW is under planning (HVDC) (Exp. Comm. Schedule up to Jun'31).
17 | Rajasthan | NR | Bhadla-III | Section linked to Bhadla HVDC station & system | Between Jul-26 to Dec-31 | 3000 | 0 | 3000 | Jan'29 (Pole-1) to Jul'29 (Pole-2) | 1550 | 1450 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700MW : Jun'25 onwards (Upto Aug'26): cumulative at Ramgarh & Bhadla-III: Raj. (Ph-III) Beyond 3700MW : Bhadla HVDC (Jan'29 Pole-1 & Jul'29 Pole-2).
18 | Rajasthan | NR | Bhadla-IV |  | Between Jul-26 to Dec-31 | 5000 | 2000 | 2000 | Apr'30 to Oct'30 (HVDC) | 300 | 5525 | 5825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 175 | Transmission system for evacauation of power from Bhadla-IV PS is under planning (6GW HVDC) (Expected Sch.Pole-1:Apr'30, Pole-2: Oct'30]). Connectivity beyond 6 GW at Bhadla-IV PS to be processed at Bhadla-V (Bhadla complex) for which transmission system (HVDC) from Bhadla Complex to be evolved.
19 | Rajasthan | NR | Merta-II |  | Between Jul-26 to Dec-31 | 2000 | 0 | 2000 | Dec'26 | 2100 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tr. System for evacuation of power from Sirohi PS is under implementation (sch. Mar'27). Beyond 2 GW in Merta/Nagaur complex, Tr. system (HVDC) to be evolved
20 | Rajasthan | NR | Jalore |  | Between Jul-26 to Dec-31 | 3000 | 1000 | 2000 | Dec'30 to Jun'31 (HVDC) | 1150 | 1000 | 2150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Transmission system for evacuation of power from Jalore complex (Jalore/Sanchore/Sirohi) for comined RE capacity of 6GW is under planning (HVDC) (Exp. Comm. Schedule up to Jun'31). At present 5220MW capacity granted/Agreed for grant at Sanchore & Jalore combindely. Balance capacity 780MW (6000-5220) is available for connectvity at Jalore/Sanchore/Sirohi-II PS
21 | Rajasthan | NR | Sanchore |  | Between Jul-26 to Dec-31 | 3000 | 1000 | 2000 | Dec'30 to Jun'31 (HVDC) | 1050 | 2020 | 3070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Transmission system for evacuation of power from Jalore complex (Jalore/Sanchore/Sirohi) for comined RE capacity of 6GW is under planning (HVDC) (Exp. Comm. Schedule up to Jun'31). At present 5220MW capacity granted/agreed for grant at Sanchore & Jalore combindely. Balance capacity 780MW (6000-5220) is available for connectvity at Jalore/Sanchore/Sirohi-II PS
22 | Rajasthan | NR | Ramgarh-II |  | Between Jul-26 to Dec-31 | 8000 | 3000 | 5000 | Apr'30 to Oct'30 (HVDC) | 1647 | 3300 | 4947 | 150 | 0 | 150 | 0 | 0 | 0 | 19 | 0 | 19 | Hybrid RE Potential: 8GW (Wind+Solar) along with BESS (3 GW), S/s Evacuation Capacity: 5GW. HVDC Transmission system for evacuation of power from Ramgarh-II PS for evacuation of 6GW RE power (Ramgarh-I:0.9GW, Ramgarh-II:5.1 GW) is under planning (Exp Comm. Schedule up to Oct'30). Connectivity beyond 5.1 GW at Ramgarh-II PS to be processed at Ramgarh- III PS (Ramgarh complex) for which transmission system (HVDC) from Ramgarh Complex to be evolved.
23 | Rajasthan | NR | Ramgarh-III |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Jun'31 to Dec'31 (HVDC) | 930 | 3282 | 4212 | 500 | 1177.33 | 1677 | 0 | 0 | 0 | 111 | 0 | 111 | HVDC Transmission system (6GW) for evacuation of power from Ramgarh-III complexes is under planning (Exp. Comm. Schedule up to Dec'31).
24 | Rajasthan | NR | Pali |  | Between Jul-26 to Dec-31 | 3000 | 1000 | 2000 | Dec'30 to Jun'31 (HVDC) | 1705 | 600 | 2305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Transmission system (6GW) for combined capacity 6GW RE from Nagaur(Merta) & Pali complexes is under planning (Exp. Comm. Schedule up to Jun'31). At present 3205MW capacity granted/agreed for grant at Pali and Merta-III combindely. Balance capacity 2795MW (6000-3205)( is available for connectvity at Pali/Merta-III PS
25 | Rajasthan | NR | Merta-III |  | Between Jul-26 to Dec-31 |  |  |  | Dec'30 to Jun'31 (HVDC) | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 900 | 1100 | Beyond 2 GW in Merta/Nagaur complex, HVDC Transmission system (6GW) for combined capacity 6GW RE from Nagaur(Merta) & Pali complexes is under planning (Exp. Comm. Schedule up to Jun'31). At present 3205MW capacity granted/agreed for grant at Pali and Merta-III combindely. Balance capacity 2795MW (6000-3205)( is available for connectvity at Pali/Merta-III PS
26 | Ladakh | NR | Pang | Leh | Between Jul-26 to Dec-31 | 13000 | 0 | 13000 | 2029-30 (VSC HVDC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | Leh - Ensviaged RE Capacity (13 GW) for connnectivity in Ladakh including Solar, Wind & BESS. However, net evacaution capacity of HVDC tr. system is 5000MW. Connectivity applications in Ladakh are yet to be received.
27 | Rajasthan | NR | Bhadla-V |  | Between Jul-26 to Dec-31 | 6000 | 0 | 6000 | Mar'31 to Sep'31 (HVDC) | 1300 | 4700 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVDC Transmission system (6GW) for evacuation of power from Bhadla- V complexes is under planning (Exp. Comm. Schedule up to Sep'31).
28 | Rajasthan | NR | Bhadla-VI |  | Between Jul-26 to Dec-31 | 4830 | 0 | 4830 | Mar'32 to Sep'32 (HVDC) | 300 | 0 | 300 | 700 | 2100 | 2800 | 0 | 0 | 0 | 2000 | 900 | 2900 | HVDC Transmission system (6GW) for evacuation of power from Bhadla- VI complexes is under planning (Exp. Comm. Schedule up to Sep'32).
29 | Andhra Pradesh | SR | NP Kunta |  | Existing | 1500 | 0 | 1500 | Existing | 2200 | 0 | 2200 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 MW : Existing Tr. System 5th & 6th ICT (Dec'25) 7th ICT required for appplications beyond 2.5 GW
30 | Karnataka | SR | Pavagada |  | Existing | 2050 | 0 | 2050 | Existing | 2550 | 0 | 2550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050 MW : Existing Tr. System 500 MW : Dec'25: Narendra-Pune
31 | Tamil Nadu | SR | Tuticorin-II |  | Existing | 2500 | 0 | 2500 | Existing | 2848 | 0 | 2848 | 100 | 0 | 100 | 52 | 0 | 52 |  |  |  | 1870 MW : Existing Tr. System 640 MW: Dec'25: Narendra-Pune & 6th ICT 438 MW : Mar'27 : 7th ICT
32 | Karnataka | SR | Koppal |  | Existing | 2500 | 0 | 2500 | Existing | 2753 | 0 | 2753 | 300 | 0 | 300 | 0 | 0 | 0 |  |  |  | 1260 MW : Existing Tr. System 1493 MW:Dec'25: Narendra-Pune Koppal PS has been closed for all purposes and under process applications may not be accommodated.
33 | Tamil Nadu | SR | Karur | Phase-1 | Existing | 1000 | 0 | 1000 | Existing | 918 | 0 | 918 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 100 MW : Existing Tr. System 818 MW: Dec'25: Narendra-Pune
34 | Karnataka | SR | Gadag |  | Existing | 2500 | 0 | 2500 | Existing | 2243 | 0 | 2243 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 460 MW : Existing Tr. System 1923 MW: Dec'25: Narendra-Pune
35 | Andhra Pradesh | SR | Kurnool-III |  | Existing | 4500 | 0 | 4500 | Existing | 2250 | 1850 | 4100 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Kurnool-III PS commissioned, entire system expected by Sept'25 Kurnool-III PS has been closed for all purposes.
36 | Tamil Nadu | SR | Karur | Phase-II | Between Jul-25 to Dec-25 | 1500 | 0 | 1500 | Feb'26 | 1351 | 0 | 1351 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | Augmentation of ICTs and transmission line is required to accommodate under process applications Entire quantum of the under process applicatiuon cannot be accomadetd
37 | Karnataka | SR | Koppal-II/ Gadag-II Complex |  | Between Jul-25 to Dec-25 | 8000 | 2000 | 6000 |  | 6620 | 1800 | 8420 | 635 | 0 | 635 | 600 | 0 | 600 | 0 | 0 | 0
37a | Karnataka | SR | Koppal-II |  | Between Jul-25 to Dec-25 | 4000 | 1000 | 3000 | Dec'25 | 3305 | 0 | 3305 | 175 | 0 | 175 | 600 | 0 | 600 | 0 |  | 0 | Dec'25
37b | Karnataka | SR | Gadag-II |  | Between Jul-25 to Dec-25 | 4000 | 1000 | 3000 | Dec'25 | 3316 | 1800 | 5116 | 460 | 0 | 460 | 0 | 0 | 0 | 0 |  | 0 | Dec'25 PSP not considered for determination of margins.
38 | Andhra Pradesh | SR | Ananthapuram |  | Between Jul-25 to Dec-25 | 3500 | 0 | 3500 | Sept'25 | 1545 | 2484 | 4029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sept'25 Ananthapuram PS has been closed for all purposes
39 | Karnataka | SR | Pavagada | expansion with ICTs | Between Jul-25 to Dec-25 | 0 | 0 | 0 | Sept'25 | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 MW : Sep'25 : 7th ICT
40 | Karnataka | SR | Davangere Complex |  | Beyond Dec-25 | 8500 | 1000 | 7500 | Mar'27 | 7022 | 850 | 7872 | 2989 | 0 | 2989 | 0 | 0 | 0 | 0 | 0 | 0 | Mar'27 to Sep'27 (assuming SPV transfer by Mar'25)
40a | Karnataka | SR | Davangere |  | Beyond Dec-25 | 4250 | 1000 | 3250 | Mar'27 | 3388 | 850 | 4238 | 724 | 0 | 724 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 MW :Mar'27 Balance tr. System under bidding All under process applications may not be accommodated.
40b | Karnataka | SR | Bellary |  | Beyond Dec-25 | 4250 | 0 | 4250 | Sep'27 | 3634 | 0 | 3634 | 2265 | 0 | 2265 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 MW :Sep'27 Balance tr. System under bidding All under process applications may not be accommodated.
41 | Karnataka | SR | Bijapur |  | Beyond Dec-25 | 3500 | 0 | 3500 | Jan'27 | 1962 | 0 | 1962 | 4431 | 1200 | 5631 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 MW :Jan'27 All under process applications may not be accommodated.
42 | Karnataka | SR | Bidar |  | Beyond Dec-25 | 2500 | 0 | 2500 | Feb'26 | 3350 | 0 | 3350 | 1650 | 1100 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 MW : Feb'26 1000 MW: Feb'27 (Augmentation of 3x500 MVA ICTs (6th - 8th) & 1x1500 MVA ICT(4th)) Transmission system for application beyond 3.5 GW has been put-on hold by NCT
43 | Andhra Pradesh | SR | Ananthapuram/ Kurnool complex |  | Beyond Dec-25 | 19500 | 0 | 19500 |  | 10410 | 7730 | 18140 | 0 | 1450 | 1763 | 180 | 0 | 180 | 0 | 0 | 0 | Progressivly from Mar'27 to Apr'27
43a | Andhra Pradesh | SR | Kurnool-III | Expansion with ICTs | Beyond Dec-25 | 4500 | 0 | 4500 | Mar'27 | 0 | 3500 | 3500 | 0 | 1450 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | • PSP not considered for determination of margins • Kurnool-III PS has been closed for all purposes. All under process applications may not be accommodated.
43b | Andhra Pradesh | SR | Ananthapuram-II |  | Beyond Dec-25 | 7500 | 0 | 7500 | Mar'27 (Ph-I) Mar'28 (Ph-II) | 5420 | 1900 | 7320 | 0 | 0 | 313 | 0 | 0 | 0 | 0 | 0 | 0 | Mar'27 (Phase-1) Progressively from Sept'27 to Mar'28 (Phase-2) All under process applications may not be accommodated.
43c | Andhra Pradesh | SR | Kurnool-IV |  | Beyond Dec-25 | 7500 | 0 | 7500 | Mar'27 (Ph-I) Mar'28 (Ph-II) | 4990 | 2330 | 7320 | 0 | 0 | 0 | 180 | 0 | 180 | 0 | 0 | 0 | Mar'27 (Phase-1) Progressively from Sept'27 to Mar'28 (Phase-2)
44 | Karnataka | SR | Tumkur-II |  | Beyond Dec-25 | 3000 | 0 | 3000 | Sep'26 | 2100 | 0 | 2100 | 2450 | 0 | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 MW : Sep'26 All under process applications may not be accommodated.
45 | Telangana | SR | Nizamabad Complex |  | Beyond Dec-25 | 5000 | 0 | 5000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 8500 | 0 | 8500 | Locations for RE potential declared in Telanagana under review by MNRE/SECI. Transmisison system put on-hold by NCT till finalization of same.
45a | Telangana | SR | Nizamabad-II |  | Beyond Dec-25 | 2000 | 0 | 2000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 2500 |  | 2500 | Locations for RE potential declared in Telanagana under review by MNRE/SECI. Transmisison system put on-hold by NCT till finalization of same.
45b | Telangana | SR | Medak |  | Beyond Dec-25 | 1500 | 0 | 1500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 3000 |  | 3000 | Locations for RE potential declared in Telanagana under review by MNRE/SECI. Transmisison system put on-hold by NCT till finalization of same.
45c | Telangana | SR | Rangareddy |  | Beyond Dec-25 | 1500 | 0 | 1500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 3000 |  | 3000 | Locations for RE potential declared in Telanagana under review by MNRE/SECI. Transmisison system put on-hold by NCT till finalization of same.
46 | Tamil Nadu | SR | Avairakulam | Off shore | Beyond Dec-25 | 500 | 0 | 500 | Dec'30 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 4500 | 0 | 4500 | Mar'2030
47 | Karnataka | SR | Pavagada | expansion with ICTs | Beyond Dec-25 | 0 | 0 | 0 | May'26 | 1150 | 0 | 1150 | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 8th, 9th & 10th ICTs : May'26 Under process applications may not be accommodated.
48 | Andhra Pradesh | SR | Ananthapuram-III |  | Beyond Dec-25 | 7500 | 0 | 7500 | Sep'28 | 3630 | 0 | 3630 | 1360 | 0 | 1360 | 2510 | 0 | 2510 | 0 | 0 | 0 | Ph-I (4.5 GW) Sep'28
49 | Andhra Pradesh | SR | Kurnool-V |  | Beyond Dec-25 | 7500 | 0 | 7500 | Sep'28 | 1330 | 0 | 1330 | 570 | 0 | 570 | 5600 | 0 | 5600 | 0 | 0 | 0 | Ph-I (4.5 GW) Sep'28
50 | Andhra Pradesh | SR | Kadapa-II |  | Beyond Dec-25 | 7500 | 0 | 7500 | Dec'28 | 600 | 0 | 600 | 0 | 0 | 0 | 1400 | 2500 | 3900 | 2000 | 1000 | 3000 | Dec'28
51 | Gujarat | WR | Bhuj complex |  | Existing | 5500 |  | 5500 | Existing | 5559 | 0 | 5559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Existing Tr. System
51a | Gujarat | WR | Bhuj |  | Existing | 3500 |  | 3500 | Existing | 3500 |  | 3500 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | Existing Tr. System.
51b | Gujarat | WR | Bhuj-II |  | Existing | 2000 |  | 2000 | Existing | 2059 |  | 2059 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Existing Tr. System.
52 | Gujarat | WR | Radhanesda |  | Existing | 700 |  | 700 | Existing | 1250 |  | 1250 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | Existing Tr. System.
53 | Gujarat | WR | Jam Khambhaliya |  | Existing | 2000 |  | 2000 | Existing | 1969 | 0 | 1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Existing Tr. System.
54 | Maharashtra | WR | Kallam | Ph-I | Existing | 1000 |  | 1000 | Existing | 916 | 0 | 916 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1GW: Commissioned
55 | Madhya Pradesh | WR | Pachora |  | Existing | 1500 |  | 1500 | Existing | 1398 |  | 1398 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 1.5GW: Commissioned
56 | Madhya Pradesh | WR | Neemuch |  | Existing | 1000 |  | 1000 | Existing | 950 |  | 950 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1GW: Commissioned
57 | Maharashtra | WR | Solapur |  | Existing | 2000 |  | 2000 | Existing |  | 2000 | 2000 |  | 0 | 0 |  | 0 | 0 |  |  |  | Sep-24: Under Scope of applicant (ReNew). NO FURTHER MARGINS LEFT BEYOND 2GW. Application for 237MW needs to be deliberated. Connectivity of (100+76+48MW) of Renew has been revoked under non- compliance of 24.6 & the matter is presently subjudice.
58 | Gujarat | WR | Khavda I | Sec I | Existing | 3000 |  | 3000 | Existing |  | 3000 | 3000 |  |  | 0 | 0 | 0 | 0 |  |  |  | 3GW: Commissioned
59 | Gujarat | WR | Khavda complex |  | Between Jul-26 to Jun'25 | 10500 |  | 10500 |  | 0 | 10500 | 10500 | 0 | 0 | 0 | 0 | 0 | 0
59a | Gujarat | WR | Khavda I | Sec II | Between Jul-26 to Jun'25 | 4500 |  | 4500 | Sec-II: Jan'25 |  | 4500 | 4500 |  |  | 0 | 0 | 0 | 0 |  |  |  | •Ph-1: 3GW - KPS1 (Comm) / KPS2: Jan'25(SCOD)/ Sep'25 (ACOD) •Ph-2: 5GW- Mar'25 (SCOD)/Nov'25 (ACOD) •Ph-3: 7GW- Dec'25 (SCOD)/ Jun'26 (ACOD)
59b | Gujarat | WR | Khavda II | Sec-I & II | Between Jul-26 to Jun'25 | 3000 |  | 3000 | Sec-I & II: Jan'25 |  | 3000 | 3000 |  |  | 0 | 0 | 0 | 0
59c | Gujarat | WR | Khvada III | Sec-I | Between Jul-26 to Jun'25 | 3000 |  | 3000 | Jan'25 |  | 3000 | 3000 |  |  | 0 | 0 | 0 | 0
60 | Madhya Pradesh | WR | Chhatarpur |  | Between Jul-26 to Jun'25 | 0 |  | 0 | Scheme dropped. | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | Scheme has been dropped as decided in NCT meeting & to be denotified by MoP.
61 | Maharashtra | WR | Kallam | Ph-II | Between Jul-26 to Jun'25 | 1000 |  | 1000 | Dec-24 (1GW) | 835 | 1022 | 1856 | 0 | 200 | 200 | 150 | 78 | 228 |  |  |  | 1GW ICTs: Dec-24 & System for 2.25GW: Under Implementation-Oct-25 (exptd) 148.75MW Connectivity granted to Anupavan has been revoked under 11A. Further, 200MW connectivity of Serentica & 117MW of Renew(MHP) has been revoked under 24.6, however, matter is presently subjudice.
62 | Gujarat | WR | Khavda complex |  | Between Jul-25 to Dec-25 | 9000 |  | 9000 |  | 0 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | •Ph-1: 3GW - Completed in Feb-24. However, 2GW at KPS2 using Ph-I system would also require KPS2 S/s (Jan'25) •Ph-2: 5GW- Mar'25 (SCOD) •Ph-3: 7GW- Dec'25 (SCOD) •Ph-4: 7GW-Nov'26 (SCOD) •Ph-V: LCC Bipole-I:Nov'28) & LCC Bipole-II: May'29 (SCOD) / VSC 48 months from SPV transfer
62a | Gujarat | WR | Khavda I | Sec-I | Between Jul-25 to Dec-25 | 1500 |  | 1500 | Sec-I ICT: Jul'25 |  | 1500 | 1500 |  |  | 0 | 0 | 0 | 0 |  |  |  | Total transformation capacity at Khavda complex (considering N-1 on each section): KPS1 - Sec-I: 4.5GW ; Sec-2: 6GW Total KPS1: 10.5GW KPS2 - Sec-I: 6GW ; Sec-2: 4.5GW Total KPS2: 10.5GW KPS3 - Sec-I: 4.5GW ; Sec-2: 4.5GW
62b | Gujarat | WR | Khavda II | Sec-I & II | Between Jul-25 to Dec-25 | 6000 |  | 6000 | Sec-I & II ICTs : Feb'26 |  | 6000 | 6000 |  | 0 | 0 | 0 | 0 | 0
62c | Gujarat | WR | Khvada III | Sec-I | Between Jul-25 to Dec-25 | 1500 |  | 1500 | Sec-I ICT : Jul'25 |  | 1500 | 1500 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | Total KPS3: 9GW Total (KPS1, KPS2 & KPS3): 30GW
63 | Gujarat | WR | Bhuj |  | Between Jul-25 to Dec-25 | 500 |  | 500 | Jul'25 | 464 |  | 464 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 9th ICT at Bhuj PS shall be required for applications beyond 3500MW NO FURTHER MARGINS ARE NOW AVAILABLE. Applications reeived beyond margins.
64 | Gujarat | WR | Lakadia |  | Between Jul-25 to Dec-25 | 1000 |  | 1000 | Oct'25 | 950 | 0 | 950 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Oct-25: Under Implementation
65 | Maharashtra | WR | Parli |  | Between Jul-25 to Dec-25 | 1000 |  | 1000 | Dec'25 (Bay) |  | 800 | 800 |  | 0 | 0 |  | 200 | 200 |  |  |  | 400kV bay under construction (suitable for 1000MW evacuation): Dec'25
66 | Gujarat | WR | Khavda complex |  | Beyond Dec-25 | 7500 |  | 7500 |  | 0 | 19390 | 19390 | 0 | 1600 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | •Ph-1: 3GW - Completed in Feb-24. However, 2GW at KPS2 using Ph-I system would also require KPS2 S/s (Jan'25) •Ph-2: 5GW- Mar'25 (SCOD) •Ph-3: 7GW- Dec'25 (SCOD) •Ph-4: 7GW-Nov'26 (SCOD) •Ph-V: LCC Bipole-I:Nov'28) & LCC Bipole-II: May'29 (SCOD) / VSC 48 months from SPV transfer
66a | Gujarat | WR | Khavda I | Sec-I | Beyond Dec-25 | 1500 |  | 1500 | Sec-I ICT: 2026-27 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total transformation capacity at Khavda complex (considering N-1 on each section): KPS1 - Sec-I: 6GW ; Sec-2: 4.5GW Total KPS1: 10.5GW KPS2 - Sec-I: 6GW ; Sec-2: 4.5GW Total KPS2: 10.5GW KPS3 - Sec-I: 4.5GW ; Sec-2: 4.5GW Total KPS3: 9GW Total (KPS1, KPS2 & KPS3): 30GW Under Process Application received for 1250MW at KPS2 is beyond Phase- VII system.
66b | Gujarat | WR | Khavda II | Sec-I & II | Beyond Dec-25 | 1500 |  | 1500 | Sec-I ICT: 2026-27 |  | 250 | 250 |  | 1250 | 1250 | 0 | 0 | 0 |  | 0 | 0
66c | Gujarat | WR | Khvada III | Sec-I & II | Beyond Dec-25 | 4500 |  | 4500 | Sec-II ICTs: Jun-26 (4500) & 2026-27 (1500) |  | 5140 | 5140 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
66d | Gujarat | WR | Khavda IV | Sec-I & II | Beyond Dec-25 | 0 |  | 8750 | 2027-28 |  | 8750 | 8750 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The Khavda Phase-I to Phase-VII shall be required for enabling evacuation of power upto 41.5GW from Khavda area out of which Phase-VI (5.5GW) & Phase-VII (6GW HVDC) are under approval stage.
66e | Gujarat | WR | Khavda V | Sec-I | Beyond Dec-25 | 0 |  | 3750 | 2027-28 |  | 3750 | 3750 |  | 350 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | The Khavda Phase-I to Phase-VII shall be required for enabling evacuation of power upto 41.5GW from Khavda area out of which Phase-VI (5.5GW) & Phase-VII (6GW HVDC) are under approval stage. Under Process Application received for 350MW at KPS5 is beyond Phase- VII system.
67 | Maharashtra | WR | Solapur | 1.5GW | Beyond Dec-25 | 1500 |  | 1500 | Mar-26 (exptd) | 2450 | 800 | 3250 |  | 2207 | 2207 | 0 | 0 | 0 | 0 | 0 | 0 | Solapur Ph-I (1.5GW): Mar-26: Under Implementation Solapur Ph-II (2GW): On hold pending potential declaration by MNRE For balance applications received at Solapur PS beyond 3.5GW, additional System / Pooling Station may be needed. 200MW margin is available at 400kV which will be allocated to applicants in order of priority of applications at Solapur PS.
68 | Madhya Pradesh | WR | Pachora |  | Beyond Dec-25 | 2000 |  | 2000 | Feb-26 (exptd) | 2602 |  | 2602 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Rajgarh Ph-I(1.5GW): Commissioned, Ph-II (1GW): Under Implementation & Ph-III (1.5GW): Under Bidding NO FURTHER MARGINS ARE AVAILABLE (BEYOND 4000MW AT PACHORA PS).
69 | Madhya Pradesh | WR | Mandsaur |  | Beyond Dec-25 | 2000 |  | 2000 | Aug-26 (exptd) | 2998 | 1500 | 4498 |  | 2484 | 2484 | 0 | 0 | 0 | 0 | 0 | 0 | Aug-26 : Under Implementation With grant of connectivity under GNA to PSP at 400kV level (1512MW), it is considered at PSP shall not inject power under high RE period and hence not considered in given table ICT Augmentation (765/400kV as well as 400/220kV ICTs) shall be required at Mandsaur for under process applications, as applicable. NO FURTHER MARGINS ARE AVAILABLE (BEYOND 4500MW AT MANDSAUR PS). Applications received beyond 4500MW would need to be deliberated.
70 | Maharashtra | WR | Dhule |  | Beyond Dec-25 | 2000 |  | 2000 | Feb-26 (exptd) | 1976 |  | 1976 | 2245 |  | 2245 | 0 | 0 | 0 | 0 | 0 | 0 | Feb-26 (SCOD): Under Implementation. NO FURTHER MARGINS ARE AVAILABLE (BEYOND 2000MW. Applications received beyond 2000MW would require additional Tr. System to be planned.
71 | Gujarat | WR | Jamnagar |  | Beyond Dec-25 | 1000 |  | 1000 | Sep-26 (extd). 400/220kV ICT Augmentation under planning | 1000 | 0 | 1000 | 956 | 0 | 956 | 0 | 0 | 0 | 0 | 0 | 0 | 765/400kV Jamnagar S/s is presently under tendering with time-line of 24 months from SPV transfer. ICT Augmentation shall be required for injection at 220kV level. Applications received beyond 1000MW would also require additional Tr. System to be planned.
72 | Gujarat | WR | Lakadia-I |  | Beyond Dec-25 | 2000 |  | 2000 | Aug-26 (exptd) | 2550 | 0 | 2550 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | Total 3.5GW Capacity planned at Lakadia S/s and NO FURTHER MARGINS EXIST AT 220kV LEVEL OF LAKADIA S/s
73 | Gujarat | WR | Jam Khambhaliya-II / Kalyanpur |  | Beyond Dec-25 | 2000 |  | 2000 | 2027-28 | 3500 | 1000 | 4500 |  | 450 | 450 | 0 | 0 | 0 |  |  | 0 | Substation is under planning for 4.5GW in first phase.
74 | Gujarat | WR | Raghanesda | GIS | Beyond Dec-25 | 3000 |  | 3000 | Oct-27 (SCOD) | 650 | 2800 | 3450 | 1105 | 5112 | 6217 |  | 0 | 0 |  |  | 0 | Substation is under implementation. NO FURTHER MARGINS ARE NOW AVAILABLE IN UNDER BIDDING SYSTEM. After 3.5GW, Augmentation shall be required for RE beyond 3.5GW at Raghanesda PS. Applications are received beyond Substation capacity.
75 | Gujarat | WR | Bhuj-II |  | Beyond Dec-25 | 0 |  | 0 | 0.5GW: Nov'26 & 1.5GW: Dec'26 | 1442 |  | 1442 | 0 | 2759 | 2759 |  | 0 | 0 | 0 | 0 | 0 | NO FURTHER MARGINS ARE NOW AVAILABLE. For applications received beyond 2000MW, augmentation needs to be taken up. 500MW (350+50+100MW) Connectivity of Acme has been revoked based on applicants request. Further, 300MW Connectivity of Inox has been revoked under non-compliance of 24.6. The margin would be allocated to applicants after reallocation exercise in order of priority at Bhuj complex.
76 | Gujarat | WR | Jam Khambhaliya |  | Beyond Dec-25 | 1000 |  | 1000 | May'26 | 1031 | 951 | 1982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Augmentation of 400/220kV ICTs is required. Margins are shown considering 9th ICT at JK PS as confirmed by JKTL. NO FURTHER MARGINS ARE NOW AVAILABLE.
77 | Madhya Pradesh | WR | Ishanagar |  | Beyond Dec-25 | 0 |  | 0 | Feb'26 | 0 | 650 | 650 |  | 630 | 630 |  | 0 | 0 |  |  | 0 | Under Implementation. No further margins available at the substation.
78 | Madhya Pradesh | WR | Kurawar |  | Beyond Dec-25 | 0 |  | 0 | Sep'26 | 0 |  | 0 |  | 950 | 950 |  |  | 0 | 350 |  | 350 | Under Implementation
79 | Madhya Pradesh | WR | Neemuch |  | Beyond Dec-25 | 0 |  | 0 | 2027-28 | 1050 |  | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Neemuch Ph-I(1GW): Commissioned, Ph-II (1GW): Under Bidding. NO FURTHER MARGINS ARE AVAILABLE (BEYOND 2000MW AT NEEMUCH PS).
80 | Gujarat | WR | Lakadia-II | Near Chitrod | Beyond Dec-25 | 0 |  | 0 | 2027-28 | 3879 | 3621 | 7500 | 0 | 795 | 795 | 0 | 0 | 0 | 0 | 0 | 0 | Substation is uner planning for 7.5GW. Applications received beyond 7.5GW cannot be accomodated at this substation.
81 | Gujarat | WR | Bhuj |  | Beyond Dec-25 | 500 |  | 500 | 2026-27 | 460 |  | 460 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Margin of 76.4MW is being requested by pending applicants at Bhuj-II PS. Hence, no margin is left. Further, 93.5MW Connectivity of Netra & 2.1MW of Avikiran has been revoked under non-compliance of 24.6. The margin would be allocated to applicants in order of priority after reallocation exercise at Bhuj complex.
82 | Madhya Pradesh | WR | Morena | Ph-I | Beyond Dec-25 | 2500 |  | 2500 | 2027-28 | 1550 | 750 | 2300 | 350 | 500 | 850 | 0 | 0 | 0 | 850 | 0 | 850 | Ph-I (2.5GW) under bidding stage. For applications beyond 2.5GW, additional transmission system is being planned.
83 | Gujarat | WR | Mahuva Offshore | Ph-I | Beyond Dec-25 | 500 |  | 500 | 2029 | 0 |  | 0 | 0 |  | 0 | 500 |  | 500 | 0 | 0 | 0 | Scheme under implementation by POWERGRID with SCOD of Mar-29
84 | Assam | NER | Bokajan |  | Beyond Dec-25 | 1000 | 0 | 1000 | Dec-26 (exptd) | 0 | 750 | 750 | 0 | 0 | 0 | 0 | 250 | 250 | 1500 | 0 | 1500 | Under Implementation

## Non RE proposed RE Integration
State | Name of Station | Capacity (MVA) | Capacity Allocated (MW) | Margin Existing 220kV (MW) | Margin Existing 400kV (MW) | Line Bays 220kV | Line Bays 400kV | Margin with ICT 220kV (MW) | Margin with ICT 400kV (MW) | Line Bays with ICT 220kV | Line Bays with ICT 400kV | No. of Transformers Required | Remarks
Gujarat | Navinal | 6x1500MVA, 765/400kV | 1100 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | Applications beyond 300MW require additional System and are under deliberation | WR
Gujarat | Halvad/Surendranagar area |  | 1350 | [9 empty] | Applications for 820MW received in Halvad area & 530MW received in Surendranagar area which are under deliberations. | WR
Maharashtra | Aurangabad | 2x1500MVA, 765/400kV 2x315MVA, 400/220kV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overloading in 220kV downstream network. | WR
Maharashtra | Kolhapur | 400kV Switching Station | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Overloading observed in 400kV Kolhapur (PG)- Kolhapur(MSETCL) D/c line. | WR
Maharashtra | Parli | 2x500MVA, 400/220kV | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300MW capacity has been allocated at Parli (PG) S/s. Overloading in 220kV downstream & Parli 400kV network. | WR
Madhya Pradesh | Khandwa | 2x315+1x500MVA, 400/220kV | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300MW Stage-II connectivity & 300MW LTA from Masaya Solar at Khandwa has also been granted. Overloading in 220kV downstream network. | WR
Madhya Pradesh | Indore | 2x500MVA, 400/220kV + (1x500MVA with sectionalisation at 220kV for RE injection) | 1224.4 | 150.6 | 100 | 1 | 1 | 0 | 0 | 0 |  | 0 | 324.4MW LTA has been granted on 1x500MVA with sectionalisation at 220kV for RE injection & 900 MW (600+150+150) has been granted on 400kV bay. | WR
Madhya Pradesh | Jabalpur | 2x1500MVA 765/400kV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765/400kV ICT overloading. | WR
Madhya Pradesh | Rajgarh | 2x315MVA, 400/220kV+ (2x500MVA with sectionalisation at 220kV for RE injection) | 892 | 356 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | Margins at 220kV bay of Srpng: 298.24MW has been granted / agreed for grant to M/s Sprng. Overloading in 220kV downstream network. Margins at 400/220kV ICT-III& IV: 593.6MW has been granted/agreed at extended 220kV bus of Rajgarh S/s through addl. 400/220kV, 500MVA ICT(s) for RE injection. | WR
Madhya Pradesh | Karera | 2x1500 MVA, 765/400 kV, 2x500 MVA, 400/220 kV S/s | 700 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | WR
Madhya Pradesh | Sidhi area | No ISTS Substation exists near Sidhi | 300 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Application received for 300MW (requested through LILO of Vindhyachal - Satna line). Studies are underway. | WR
Chhattisgarh | Dharamjaygarh | 2x1500MVA 765/400kV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765/400kV ICT overloading / Fault level issues | WR
Chhattisgarh | Champa | 6x1500MVA 765/400kV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765/400kV ICT overloading / Fault level issues | WR
Chhattisgarh | Bilaspur | 3x1500MVA 765/400kV | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 765/400kV ICT overloading / Fault level issues | WR
Andhra Pradesh | Kurnool | 2X1500 MVA, 765/400 kV | 2714 | 0 | 0 |  | 1 | 0 | 250 |  | 0 | 1 |  | SR
Karnataka | Hiriyur | 2x315 MVA, 400/220 kV + 1x500 MVA, 400/220 kV | 600.3 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | SR
Kerala | Palakkad | 2x315 MVA, 400/220 kV + 1x500 MVA, 400/220 kV | 0 | 300 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 |  | SR
Tamil Nadu | Pugalur | 2X315 MVA + 1X500 MVA, 400/230 kV | 655 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | Pugalur(Existing) has been closed for all purpose regarding grant of Connectivity. | SR
Tamil Nadu | Malekottaiyur | 2X315 MVA + 1X500 MVA, 400/230 kV | NIL | 500 | 0 | 2 |  | 0 | 0 |  | 0 | 0 |  | SR
Tamil Nadu | Nagapattinam | Charged at 400 kV | NIL | 0 | 1000 |  | 2 | 0 | 0 |  | 0 | 0 |  | SR
Tamil Nadu | NLC TS-II | 2x250+1x315 | 160 | 0 | 0 | 0 | [6 empty] | Overloading at 230 kV network | SR
Rajasthan | Chittorgarh | 765/400kV : 2x1500MVA | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NR
Rajasthan | Ajmer | 765/400kV : 2x1500MVA | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NR
Rajasthan | Bassi | 400/220 kV : 2x315MVA +1x500MVA | NIL | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 220kV overloading | NR
Rajasthan | Bhiwadi | 400/220 kV : 3x315MVA | NIL | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 220kV overloading | NR
Rajasthan | Kankroli | 400/220 kV : 3x315MVA | NIL | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 220kV overloading | NR
Rajasthan | Kota | 400/220 kV : 2x315MVA | NIL | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 220kV overloading | NR
Rajasthan | Bhinmal | 400/220 kV : 2x315MVA+1x315 MVA UC | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220kV overloading | NR
Rajasthan | Neemarana | 400/220 kV : 1x315MVA +1x500MVA | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220kV overloading | NR
Rajasthan | Sikar | 400/220 kV : 2x315MVA +1x500MVA | NIL | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 220kV overloading | NR
Rajasthan | Jaipur | 400/220 kV : 2x500MVA | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NR
Rajasthan | Kotputli | 400/220 kV : 2x315MVA+1X500MVA (Planned) | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NR
Haryana | Kaithal | 400/220 kV : 3X315MVA | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NR
Haryana | Bahadurgarh | 400/220 kV : 315MVA +500MVA+500MVA (UC) | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NR
Haryana | Manesar | 400/220 kV : 2X500MVA | NIL | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 400/220kv ICT over loading | NR
Uttar Pradesh | Kanpur | 765/400 kV : 2x1500MVA+1x1500 | NIL | 0 | 500 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 220kV Not available | NR
Uttar Pradesh | Fatehpur | 765/400kV : 2x1500MVA; 400/220 kV : 2X315MVA | NIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NR
Uttar Pradesh | Lucknow | 765/400 kV : 2x1500MVA | NIL | 0 | 500 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | NR
Uttar Pradesh | Balia | 765/400 kV : 2x1500MVA | NIL | 0 | 850 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 220kV Not available. | NR
Uttar Pradesh | Bareilly | 765/400 kV : 2x1500MVA | NIL | 0 | 500 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | NR
Odisha | Jeypore | 400/220kV: 2x630MVA |  | 1500 | 0 | 5 | [7 empty] | ER
Odisha | Keonjhar | 400/220kV: 2x315MVA | 0 | 800 | 0 | 3 | [7 empty] | ER
Odisha | Pandiabil | 400/220kV: 3x500MVA | 0 | 0 | 0 | [8 empty] | ER
Odisha | Rengali | 400/220kV: 2x315MVA | 0 | 500 | 0 | 2 | [7 empty] | ER
Odisha | Angul | 765/400: 4x1500MVA | 0 | 0 | 0 | [8 empty] | ER
Odisha | Baripada | 400/220/132: 2x315MVA + 1x500MVA + 2x160MVA |  | 300 |  | 2 | [7 empty] | ER
Odisha | Bolangir | 400/220kV: 2x315MVA |  | 0 | [9 empty] | ER
Odisha | Indravati | 400/220kV: 1x315MVA |  | 0 | [9 empty] | ER
Odisha | Rourkela | 400/220kV: 4x315MVA |  | 0 | [9 empty] | ER
Odisha | Sundargarh A | 765/400: 2x1500MVA |  |  | 2500 |  | 3 | [6 empty] | ER
Odisha | Sundargarh B | 765/400: 2x1500MVA |  |  | 2500 |  | 3 | [6 empty] | ER
Odisha | Paradeep | 765/400: 2x1500MVA |  |  | 3000 |  | 3 | [6 empty] | ER
Odisha | Gopalpur | 765/400: 2x1500MVA |  |  | 3000 |  | 3 | [6 empty] | ER
Jharkhand | Chaibasa | 400/220kV: 2x315MVA | 0 | 500 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 |  | ER
Jharkhand | Daltonganj | 400/220kV: 2x315MVA | 0 | 500 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 |  | ER
Jharkhand | Ranchi | 400/220kV: 2x315MVA + 1x500MVA |  | 800 |  | 3 |  | 0 | 0 | 0 |  | 0 |  | ER
Jharkhand | Ranchi | 765/400kV: 2x1500MVA | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | ER
Jharkhand | Chandwa | 400kV switching |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | ER
Jharkhand | Dhanbad | 400/200kV: 2x500MVA |  | 500 |  | 2 | [7 empty] | ER
Bihar | Banka | 400/132kV: 2x200MVA + 1x315MVA 400/220kV: 2x500MVA | 0 | 600+700 | 0 | 5 | 0 | 400 | 0 | 0 | 0 | 0 | 100MW at 132kV level in the existing system and 400MW at 220kV level with the implementation of "Augmentation of 400/220kV, 2x500MVA ICT at Banka" Scheme expected by Oct 2024 | ER
Bihar | Lakhisarai | 400/132kV: 2x200MVA + 1x315MVA | 0 | 300 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 132kV level | ER
Bihar | Motihari | 400/132kV: 2x200MVA + 1x315MVA | 0 | 500 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 132kV level | ER
Bihar | Chandauti | 400/220kV: 3x500MVA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ER
Bihar | Muzaffarpur | 400/220kV: 2x315MVA + 2x500MVA | 0 | 800 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | line corridor available for 2 lines | ER
Bihar | Saharsa | 400/220kV: 2x500MVA | 0 | 700 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | ER
Bihar | Sitamarhi | 400/220kV: 2x500MVA | 0 | 800+200 | 0 | 4 | 0 | 0 | 0 |  |  |  |  | ER
Bihar | Gaya | 400/220kV: 2x500MVA + 1x315MVA |  | 2000+1000 |  | 10 | [7 empty] | ER
Bihar | Darbhanga | 400/220kV: 2x500MVA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ER
Bihar | Kishanganj | 400/220kV: 2x500MVA | 0 | 500 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | ER
Bihar | New Purnea | 400/220kV: 2x500MVA | 0 | 1000 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | ER
Bihar | Patna | 400/220kV: 3x500MVA | 0 | 100 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | ER
Bihar | Purnea | 220/132kV: 3x160MVA | 0 | 900 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | ER
Bihar | Sasaram | 220/132kV: 3x160MVA | 0 | 600 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | ER
West Bengal | Durgapur-B | 400/220kV: 3x315MVA | 0 | 0 | [8 empty] | 220kV overloaded in present case under N-1. | ER
West Bengal | Maithon-B | 400/220kV: 3x500MVA | 0 | 0 | [8 empty] | 220kV overloaded in Base case (Maithon B - Asansol). | ER
West Bengal | Subhasgram | 400/220kV: 2x315MVA + 1x500MVA | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 220kV overloaded in present case under N-1 (Subhasgram). | ER
West Bengal | Jeerat-New | 765/400: 2x1500MVA | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 400/220kV ICT overloaded in present case under N-1 | ER
West Bengal | Medinipur | 765/400: 2x1500MVA | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 400/220kV ICT overloaded in present case | ER
West Bengal | Alipurduar | 400/220kV: 2x315MVA | 0 | 0 | [9 empty] | ER
West Bengal | Baharampur | 400kV switching | 0 | 0 | [9 empty] | ER
West Bengal | Rajarhat | 400/220kV: 3x500MVA | 0 | 0 | [8 empty] | 220kV overloaded in present case under N-1 (Subhasgram). | ER
West Bengal | Birpara | 220/132kV: 2x160MVA | 0 | 0 | [9 empty] | ER
West Bengal | Dalkhola | 220kV switching | 0 | 0 | [9 empty] | ER
West Bengal | Durgapur-A | 400kV switching | 0 | 0 | [9 empty] | ER
West Bengal | Maithon-A | 400kV switching | 0 | 0 | [9 empty] | ER
West Bengal | Farakka T | 400/220kV: 2x315MVA | 0 | 0 | [9 empty] | ER
West Bengal | Malda | 400/220kV: 2x500MVA | 0 | 0 | [9 empty] | ER
West Bengal | New Siliguri | 400/220kV: 3x315MVA | 0 | 0 | [8 empty] | 132kV overloaded in present case under N-1 (Siliguri). | ER
West Bengal | Siliguri | 220/132kV: 2x160MVA | 0 | 0 | [8 empty] | 132kV overloaded in present case under N-1 (Siliguri). | ER

## Transformation Capacity
S.No. | Region | State | Substation | Voltage level (kV) | Existing Capacity (MVA) | Under Implementation Capacity (MVA) | Planned Capacity (MVA)
1 | WR | Gujarat | Jam Khambhaliya | 220 | 2000
2 | WR | Gujarat | Bhuj | 400 | 6000
2 | WR | Gujarat | Bhuj | 220 | 4000
3 | WR | Gujarat | Bhuj-II | 400 | 1500 | 1500
3 | WR | Gujarat | Bhuj-II | 220 | 2000
4 | WR |  | Bhachau | 220 | 630
6 | WR | Gujarat | Khavda-II | 400 |  | 3000
7 | WR |  | Banaskantha | 220 | 1000
8 | WR | Madhya Pradesh | Rajgarh | 220 | 630 |  | 500
9 | WR | Madhya Pradesh | Indore | 220 | 4500
10 | WR | Madhya Pradesh | Pachora | 220 |  | 1500
11 | WR | Madhya Pradesh | Neemuch | 220 |  | 1000
12 | WR |  | Khandwa | 220 | 1130
13 | WR |  | Raipur | 220 | 945
15 | WR | Maharashtra | Solapur | 400 | 3000
15 | WR | Maharashtra | Solapur | 220 | 630
15 | WR | Maharashtra | Solapur | 220 | 500
16 | SR | Tamil Nadu | Tuticorin-II | 230 | 1500 | 1000
17 | SR | Tamil Nadu | Pugalur | 230 | 1130
18 | SR |  | Palakkad | 220 | 630 | 500
19 | SR | Andhra Pradesh | NP Kunta | 220 | 2000
21 | SR | Karnataka | Hiriyur | 220 | 630 | 500
22 | SR | Andhra Pradesh | Kurnool | 400 | 3000
23 | SR | Karnataka | Koppal | 220 |  | 2500
24 | SR | Tamil Nadu | Karur | 230 |  | 2500
25 | SR | Karnataka | Gadag | 220 |  | 2500
27 | SR | Karnataka | Gadag-II | 220 |  |  | 2000
29 | NR | Rajasthan | Bikaner | 400 | 3000 | 1500 | 1500
29 | NR | Rajasthan | Bikaner | 220 | 1000 | 500
30 | NR | Rajasthan | Fatehgarh
31 | NR | Rajasthan | Bhadla- II | 400 | 3000 | 3000 | 1500
31 | NR | Rajasthan | Bhadla- II | 220 | 1500 | 2500
32 | NR | Rajasthan | Fatehgarh-II | 400 | 6000 | 3000
32 | NR | Rajasthan | Fatehgarh-II | 220 | 2500 | 2000 | 1000
34 | NR | Rajasthan | Bikaner-II | 220 |  | 1000 | 2500
35 | NR | Rajasthan | Fatehgarh-IV | 220 |  |  | 2500
36 | NR | Rajasthan | Bhadla- III | 400 |  |  | 3000
36 | NR | Rajasthan | Bhadla- III | 220 |  |  | 5000
37 | NR | Rajasthan | Ramgarh | 400 |  |  | 4500
37 | NR | Rajasthan | Ramgarh | 220 |  |  | 1000
38 | NR | Rajasthan | Bikaner- III | 400 |  |  | 9000
38 | NR | Rajasthan | Bikaner- III | 220 |  |  | 2500

## Element Status
| Element Code | Inter/Intra Tx. Element | Transmission Scheme | Transmission Scope | MVA | Status | Approval of Elements in which NCT | Mode (TBCB/RTM) | Tender Issuing Authority | Date of tender issuance | Date of Bid Submission | Execution Timeline | Tentative SCOD | Awarded To | SPV Transfer Date | Physical Progress S/s of Tx. Line | [7 empty] | Physical Progress Substation |  |  | Original SCOD | Anticipated SCOD | Remarks
[16 empty] | Length | Location | Foundation | Erection | Stringing | Foundation (%) | Erection (%) | Stringing (%) | Civil Work (%) | Equipment Received (%) | Equipment Erected (%)
|  |  |  | Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan (8.1 GW) under phase- II- Part G SPV Name: POWERGRID Narela Transmission Ltd. (CKM-408, MVA-4500) | [7 empty] | 24 |  |  | May-22 | [11 empty] | Nov-23 | Dec - 25
|  |  |  | Khetri-Narela 765kV D/C Line | [7 empty] | 21 |  |  | May-22 | 340 | 463 | 463 | 463 | 340 | 1 | 1 | 1 |  |  |  | Nov-23 | Dec - 25 | Forest Delhi (0.95 Ha, 3 locs, 82.58 Ckm): Stage I&II received.Tree felling permission received from Hon'ble Supreme court vide order dated 26.05.25.
Data Scoure (Sl. No.(s)1, 2, 5, 6, 10b, 10c, 10d, 10e, 12) |  |  |  | LILO of 765kV S/c Meerut – Bhiwani line at Narela | [10 empty] | May-22 |  | 97 | 97 | 97 | 68 | 1 | 1 |  |  |  |  | Nov-23 | Oct - 25 | Line charged on 01.10.2025
|  |  |  | 3x1500MVA ,765/400kV GIS substation at Narela | [10 empty] | May-22 | [8 empty] | 100.00% | 100.00% | 100.00% | Nov-23 | Dec - 25 | ICT-1&3 Charged on 01.10.2025 ICT-2 Charged on 02.10.2025 Bays commissioning matching with Tx. Line
|  |  |  | Transmission system associated with LTA applications from Rajasthan SEZ Part-E, Phase-II (SPV: POWERGRID Bhadla Sikar Transmission Limited) (CKM-600) | [10 empty] | Mar-23 | [11 empty] | Sep-24 | Dec - 25
|  |  |  | Bhadla II - Sikar II 765 kV D/C line (2nd) | [10 empty] | Mar-23 | 628 | 816 | 816 | 816 | 524.24 | 1 | 1 | 0.83 |  |  |  | Sep-24 | Dec - 25 | Stringing RoW (10 locs): Sikar Dist. (10) in Rajasthan
|  |  |  | Transmission scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase II- Part B (SPV Name: POWERGRID KHAVDA II-B TRANSMISSION LIMITED) (CKM-368) | [10 empty] | Mar-23 | [11 empty] | Mar-25 | Dec - 25
|  |  |  | 765kV D/C Lakadia PS-Ahmedabad Line | [10 empty] | Mar-23 | 368 | 476 | 476 | 476 | 335.16 | 1 | 1 | 0.91 |  |  |  | Mar-25 | Dec - 25 | Work affected due to severe RoW Issue.
|  |  |  | Transmission scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase II- Part C (SPV Name: POWERGRID KHAVDA II-C TRANSMISSION LIMITED) (CKM-577, MVA-4500) | [10 empty] | Mar-23 | [11 empty] | Mar-25 | Dec - 25
|  |  |  | 765kV D/C Ahemdabad- New Navsari (South Gujrat) line | [10 empty] | Mar-23 | 590 | 804 | 803 | 755 | 426.44 | 1 | 0.94 | 0.72 |  |  |  | Mar-25 | Dec - 25 | Forest (5.13 Ha):Stage-II received on 04.02.2025
|  |  |  | 765/400kV 3x1500MVA Ahmedabad New S/s | [10 empty] | Mar-23 | [8 empty] | 98.00% | 100.00% | 98.00% | Mar-25 | Dec - 25 | ICT-I & II charged on 06.09.2025. ICT-III charged on 14.11.2025.
|  |  |  | Establishment of Khavda Pooling Station-2 (KPS2) in Khavda RE Park (SPV: POWERGRID KPS2 TRANSMISSION SYSTEM LIMITED) (MVA-6000) | [10 empty] | Mar-23 | [11 empty] | Dec-24 | Dec - 25
|  |  |  | 765/400kV 4x1500MVA KPS2 New SS (GIS) | [10 empty] | Mar-23 | [8 empty] | 98.00% | 100.00% | 98.00% | Dec-24 | Dec - 25 | 330 MVAr 765kV BR-1 charged on 01.04.25. ICT-1 charged on 12.04.2025. ICT-2 charged on 25.07.2025. ICT-3 charged on 07.11.2025.
|  |  |  | Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh | [10 empty] | Sep-23 | [11 empty] | Sep-25 | Mar - 26
|  |  |  | 7x500 MVA , 400/220 KV Ananthpuram S/s | [10 empty] | Sep-23 | [8 empty] | 90.00% | 85.00% | 30.00% | Sep-25 | Mar - 26 | Land (63.69 Acre) acquired
|  |  |  | Ananthpuram PS-Kurnool-III PS 400 kV (Quad moose) D/c Line | [10 empty] | Sep-23 | 171 | 222 | 222 | 222 | 146 | 1 | 1 | 0.85 |  |  |  | Sep-25 | Dec - 25
|  |  |  | Ananthpuram PS-Cuddapah-400kV (Quad moose) D/c Line | [10 empty] | Sep-23 | 371 | 490 | 470 | 423 | 149.3 | 0.96 | 0.86 | 0.4 |  |  |  | Sep-25 | Mar - 26 | Foundation RoW (2 loc.): YSR kadapa (2) in Andhra pradesh.
|  |  |  | Transmission system for evacuation of power from REZ in Rajasthan (20 GW) under Phase-III part B1 SPV: POWERGRID Bhadla III Transmission Ltd | [10 empty] | Sep-23 | [11 empty] | Mar-25 | Dec - 25
|  |  |  | Bhadla-III PS – Sikar-II S/s 765 kV D/c line | [10 empty] | Sep-23 | 650 | 847 | 847 | 823 | 395.84 | 1 | 0.97 | 0.61 |  |  |  | Mar-25 | Dec - 25 | Stringing RoW Locs. (1 section): Didwana Kuchanamn (1) in Rajasthan. Forest :Rajasthan (24.32 Ha, 5 locs, 25 km ): Stage-I issued on 08.05.25. Stage-II issued on 08.09.2025.
|  |  |  | 2x1500MVA, 765/400KV & 3x500 MVA, 400/220 kV Bhadla III New S/s | [10 empty] | Sep-23 | [8 empty] | 100.00% | 99.00% | 98.00% | Mar-25 | Dec - 25
|  |  |  | Transmission system associated with LTA applications from Rajasthan SEZ Phase-III Part-C1, SPV: POWERGRID Ramgarh II Transmission Ltd | [10 empty] | Oct-23 | [11 empty] | Apr-25 | Mar - 26
|  |  |  | 2x1500MVA, 765/400KV & 2X500MVA, 400/220 kV Ramgarh PS | [10 empty] | Oct-23 | [8 empty] | 99.00% | 100.00% | 99.00% | Apr-25 | Dec - 25 | 400kV ICT-1 Test charged from 33kV on 16.09.25. awaiting for readiness of Bhadla-3 Substation & B3S2 Line for evacuation of Power.
|  |  |  | Ramgarh PS- Bhadla-III PS 765kV D/C line | [10 empty] | Oct-23 | 372 | 467 | 467 | 467 | 372 | 1 | 1 | 1 |  |  |  | Apr-25 | Dec - 25 | Line is Ready for charging.
|  |  |  | 2x300 MVAr Statcom with 4x125 MVAr MSC, 2x125 MVAr MSR at Ramgarh PS | [10 empty] | Oct-23 | [8 empty] | 85.00% | 42.00% | 20.00% | Oct-25 | Mar - 26 | Work under progress
|  |  |  | Transmission system for evacuation of power from REZ in Rajasthan (20 GW) under Phase-III part H SPV: POWERGRID Beawar DausaTransmission Ltd | [10 empty] | Oct-23 | [11 empty] | Apr-25 | Jan - 26
|  |  |  | Beawar-Dausa 765kV D/C line | [10 empty] | Oct-23 | 474 | 634 | 626 | 572 | 219.86 | 0.99 | 0.9 | 0.46 |  |  |  | Apr-25 | Jan - 26 | Foundation RoW locs.(2): Ajmer Dist. (2) in Rajasthan. Erection RoW Locs. (7): Beawar (3), Ajmer (4) in Rajasthan. Forest: (5.58 Ha, 02 locs, 2 Ckm): Stage-II issued on 24.05.25.
|  |  |  | LILO of both circuits of Jaipur (Phagi)-Gwalior 765 kV D/c at Dausa | [10 empty] | Oct-23 | 133 | 173 | 173 | 160 | 61.62 | 1 | 0.92 | 0.46 |  |  |  | Apr-25 | Dec - 25 | Under progress
|  |  |  | LILO of both circuits of Agra – Jaipur (south) 400kV D/c at Dausa | [10 empty] | Oct-23 |  | 59 | 59 | 59 | 45 | 1 | 1 |  |  |  |  | Apr-25 | Jul - 25 | Line charged on 13.07.2025
|  |  |  | 2x1500MVA, 765/400KV Dausa S/s | [10 empty] | Oct-23 | [8 empty] | 100.00% | 100.00% | 99.00% | Apr-25 | Dec - 25 | Land (114.879 Acre): All Acquired
|  |  |  | Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & B) and Gadag-II (Phase- A) in Karnataka SPV: POWERGRID Koppal Gadag Transmission Ltd | [10 empty] | Dec-23 | [11 empty] | Dec-25 | Jun - 26
|  |  |  | Establishment of 765/400 kV 2x1500 MVA, 400/220 kV, 2x500 MVA Koppal-II (Phase- A) | [10 empty] | Dec-23 | [8 empty] | 80.00% | 50.00% | 10.00% | Dec-25 | Mar - 26 | Pvt. Land (174.575 Acre): Registry of 132.125 out of 140 acres of consented land complete. advance possesion of remaining land has been given to POWERGRID by Dist. Administration on 18.12.24.
|  |  |  | Establishment of 400/220 kV, 2x500 MVA Gadag-II (Phase -A) Pooling Station | [10 empty] | Dec-23 | [8 empty] | 85.00% | 95.00% | 20.00% | Dec-25 | Mar - 26 | Pvt. Land (50.97 Acre): All acquired
|  |  |  | Koppal-II PS – Narendra (New) 765 kV D/c line | [10 empty] | Dec-23 | 238 | 310 | 257 | 134 |  | 0.83 | 0.43 | 0 |  |  |  | Dec-25 | Jun - 26 | Foundation RoW (36 loc.): Koppal (8), Vijaypura (24), Bagalkote (4) in Karnataka Forest,Karnataka, Koppal (0.657 Ha, Nil locs., 0.2 Ckm)- Stage-II awaited
|  |  |  | Gadag-II PS – Koppal-II PS 400 kV (Quad Moose) D/c line | [10 empty] | Dec-23 | 77 | 104 | 70 | 44 |  | 0.67 | 0.42 | 0 |  |  |  | Dec-25 | Mar - 26 | Foundation RoW (42 loc.): Koppal Dist. (31), Gadag Dist. (11) in Karnataka
|  |  |  | Koppal-II PS – Raichur 765 kV D/c line | [10 empty] | Dec-23 | 293 | 375 | 346 | 209 | 31.38 | 0.92 | 0.56 | 0.11 |  |  |  | Dec-25 | Mar - 26 | Foundation RoW (12 loc.): Koppal Dist. (11), Raichur (1) in Karnataka Erection RoW (1 loc): Koppal Dist. (1) in Karnataka.
|  |  |  | Augmentation by 2x1500 MVA, 765/400 kV ICTs at Koppal-II PS | [10 empty] | Dec-23 | [8 empty] | 80.00% | 50.00% | 10.00% | Dec-25 | Mar - 26 | Under progress
|  |  |  | Augmentation by 2x500 MVA, 400/220 kV ICTs at Koppal-II PS | [10 empty] | Dec-23 | [8 empty] | 80.00% | 50.00% | 10.00% | Dec-25 | Mar - 26 | Under progress
|  |  |  | Transmission System for evacuation of additional 7 GW RE Power from Khavda RE Park under Phase-III Part B SPV: POWERGRID Vataman Transmission Ltd | [10 empty] | Dec-23 | [11 empty] | Dec-25 | Dec - 26
|  |  |  | Establishment of 765 kV switching station near Vataman | [10 empty] | Dec-23 | [8 empty] | 10.00% | 35.00% |  | Dec-25 | Dec - 26 | Land (154.36 Acre): Acquired
|  |  |  | Halvad – Vataman 765 kV D/c line | [10 empty] | Dec-23 | 254 | 336 | 143 | 14 |  | 0.43 | 0.04 | 0 |  |  |  | Dec-25 | Dec - 26 | Forest,Gujarat (2.717 Ha, 1 loc, 1.28Ckm) Stage-II issued on 20.10.2025.
|  |  |  | LILO of Lakadia – Vadodara 765 kV D/c line at Vataman 765 kV switching station | [10 empty] | Dec-23 | 56 | 82 | 54 |  |  | 0.66 | 0 | 0 |  |  |  | Dec-25 | Dec - 26 | Gujarat (0.5424 Ha, Nil locs, 0.16Ckm) Stage-II issued on 11.11.2025
|  |  |  | Vataman switching station – Navsari (New)(GIS) 765 kV D/c line | [10 empty] | Dec-23 | 495 | 690 | 353 | 46 |  | 0.51 | 0.07 | 0 |  |  |  | Dec-25 | Dec - 26 | Gujarat (15.2371 Ha, 2 locs, 4.54 Ckm )- Stage-II issued on 17.11.2025.
|  |  |  | Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-1) (Bikaner Complex): PART-A SPV: POWERGRID Bikaner Neemrana Transmission Ltd | [10 empty] | Dec-23 | [11 empty] | Dec-25 | Jun - 26
|  |  |  | Establishment of 6x1500 MVA (along with one spare unit of 500 MVA), 765/400 kV & 5x500 MVA 400/220 kV Bikaner-III Pooling Station | [10 empty] | Dec-23 | [8 empty] | 90.00% | 70.00% | 30.00% | Dec-25 | Mar - 26 | Land (213.78 Acre): All Acquired.
|  |  |  | Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) | [10 empty] | Dec-23 | 62 | 86 | 66 | 37 |  | 0.77 | 0.43 | 0 |  |  |  | Dec-25 | Mar - 26 | Stringing RoW (3 locs.): Bikaner (5) in Rajasthan Forest in Bikaner (0.442 Ha, Nil locs, 0.5km), Stage-II received on 24.11.25.
|  |  |  | Bikaner-III - Neemrana-II 765 kV D/c line | [10 empty] | Dec-23 | 682 | 905 | 865 | 688 | 61.82 | 0.96 | 0.76 | 0.09 |  |  |  | Dec-25 | Jun - 26 | Foundation RoW (25 loc.): Churu (14), Jhunjhunu (8), Kotputli Behror (1) in Rajasthan, Mahendragarh (1) in Haryana Erection RoW (10 loc.):Mahendragarh (1) in Haryana, Bikaner (9) in Rajasthan Forest: i) Haryana (0.8361 Ha,6 loc, 1 km): Stage-II Awaited ii) Rajasthan (1.916 Ha, 3 loc, 0.5 km) : Stage-II Awaited.
|  |  |  | LILO of both circuits of 400 kV Bikaner (PG)-Bikaner-II D/c line at Bikaner-III PS | [10 empty] | Dec-23 | 74 | 102 | 102 | 94 | 31.52 | 1 | 0.92 | 0.43 |  |  |  | Dec-25 | Mar - 26 | Stringing RoW (3 locs.): Bikaner (5) in Rajasthan
|  |  |  | Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-1) (Bikaner Complex): PART-D SPV: POWERGRID Neemrana Bareilly Transmission Ltd | [10 empty] | Dec-23 | [11 empty] | Dec-25 | Jun - 26
|  |  |  | Neemrana-II- Bareilly (PG) 765 kV D/c line | [10 empty] | Dec-23 | 666 | 863 | 837 | 732 | 257.4 | 0.97 | 0.85 | 0.39 |  |  |  | Dec-25 | Jun - 26 | i)Forest,Rajasthan, Alwar (16.054 Ha,6 loc, 3km) Division: Stage-II Awaited ii) Forest, Haryana (11.849 Ha,2 loc, 2 km): Stage-I awaited iii) Forest,Haryana, Palwal (2.37 Ha,19 loc, 24.2km): Stage-II obtained on 20.11.25. iv) Forest, Uttar Pradesh (2.44 Ha,24loc, 5.5km): Stage-II Awaited
|  |  |  | Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka (SPV Name: POWERGRID Bidar Transmission Limited) | [10 empty] | Feb-24 | [11 empty] | Feb-26 | Jun - 26
|  |  |  | Bidar PS–Maheshwaram (PG) 765KV D/C line | [10 empty] | Feb-24 | 479 | 628 | 606 | 506 | 133.3 | 0.96 | 0.81 | 0.28 |  |  |  | Feb-26 | Jun - 26 | Foundation RoW (22 loc.): Bidar District (2), Ranga Reddy District (20) in Telangana. Erection RoW (11 loc.): Ranga Reddy District (11) in Telangana.
|  |  |  | Establishement of Bidar PS 3x1500 MVA, 765/400 kV and 5x500 MVA, 400/220 kV ICTs | [10 empty] | Feb-24 | [8 empty] | 80.00% | 80.00% | 20.00% | Feb-26 | Jun - 26 | Pvt Land (162.07 Acre), Pending (8.87) Acre The pending land (8.87 acres) is being acquired through RFTLARR Act, 2013.
|  |  |  | Transmission Scheme for Evacuation of power from REZ in Rajasthan (20 GW) under Phase-III Part D (SPV: POWERGRIDSikar Khetri Transmission Limited) | [10 empty] | Feb-24 | [11 empty] | Aug-25 | Jun - 26
|  |  |  | Sikar-II –Narela 765 kV D/C line | [10 empty] | Feb-24 | 473 | 630 | 482 | 386 | 99.5 | 0.77 | 0.61 | 0.21 |  |  |  | Aug-25 | Jun - 26 | Forest: i)Haryana (16.75 Ha, 0 loc, 6 km)- Stage-I Awaited. ii) Delhi (1.319 ha, 0 loc, 1.2 km): Stage-I awaited.
|  |  |  | Sikar-II –Khetri765 kV D/C line | [10 empty] | Feb-24 | 144 | 198 | 173 | 150 | 33.7 | 0.87 | 0.76 | 0.23 |  |  |  | Aug-25 | Jun - 26 | Forest i)Rajasthan (29.97 Ha, 15 locs, 8km)- Stage-I Awaited Proposal submitted 22.07.24. Area modified to 29.9758 ha. Revised documents uploaded on 28.07.25. Proposal forwarded by NO to SG on 28.11.25.
|  |  |  | Transmission Scheme for Evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7 GW):Part E2 (SPV: POWERGRID Khavda IV-E2 Power Transmission Ltd) | [10 empty] | May-24 | [11 empty] | Feb-26 | Jun - 26
|  |  |  | Augmentaion of transformation capacity at KPS2 GIS by 2x1500 MVA, 765/400 kV ICT on Bus Section-I (5th & 6th) & 2x1500 MVA, 765/400 kV ICT on Bus Section-II (7th & 8th) | [10 empty] | May-24 | [8 empty] | 50.00% | 20.00% |  | Feb-26 | Jun - 26 | Work under progress.
|  |  |  | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex): Part C (SPV Name: POWERGRID Mandsaur Transmission Limited) | [10 empty] | Aug-24 | [11 empty] | Aug-26 | Dec - 26
|  |  |  | Establishment of 3x1500 MVA, 765/400 kV and 5x500 MVA, 400/220 kV Mandsaur Pooling Station | [10 empty] | Aug-24 | [8 empty] | 58.00% | 22.00% | 2.00% | Aug-26 | Dec - 26 | Pvt. land (36.32 Acre): Pending (5.24 Acre). Registry of remaining land 5.24 acre is under process. Patta (16.8 Acre): Pending (16.8) Acre. Applied on 29.04.2024. Sale permission notification under process. Regular followup with DM is being made.
|  |  |  | Mandsaur PS - Indore (PG) 765 kV D/C Line | [10 empty] | Aug-24 | 338 | 445 | 329 | 201 |  | 0.74 | 0.45 | 0 |  |  |  | Aug-26 | Aug - 26 | Foundation RoW (12 locs): Indore (8), Ujjain(4) in Madhya Pradesh.
|  |  |  | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex): Part E (SPV Name: POWERGRID Mewar Transmission Limited) | [10 empty] | Aug-24 | [11 empty] | Aug-26 | Mar - 27
|  |  |  | Establishment of 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) | [10 empty] | Aug-24 | [11 empty] | Aug-26 | Mar - 27 | Land (197.68 Acre): Pending (197.68) Acre *Govt . Land acquisition was completed, now acquired land has been converted to wet land. Subsequently two alternative sites has been identified.
|  |  |  | Sirohi PS - Rishabdeo 765 kV D/C line | [10 empty] | Aug-24 | 421 | 582 | 365 | 173 | 3.28 | 0.63 | 0.3 | 0.01 |  |  |  | Aug-26 | Mar - 27 | Foundation RoW (13 locs): Sirohi (9), Udaipur (4) in Rajasthan. Forest: Rajasthan (101.29 Ha, 46 locs, 15.15 km)- Stage-I Awaited
|  |  |  | Rishabdeo - Mandsaur PS 765 kV D/C line | [10 empty] | Aug-24 | 250 | 327 | 247 | 141 |  | 0.76 | 0.43 | 0 |  |  |  | Aug-26 | Mar - 27 | Forest: Rajasthan (6.458 Ha, 3 locs, 3 km)- Stage-II received on 20.11.25.
|  |  |  | LILO of one circuit of 765 kV Chittorgarh - Banaskanta D/C line at Rishabdeo S/S | [10 empty] | Aug-24 | 25 | 34 | 5 |  |  | 0.15 | 0 | 0 |  |  |  | Aug-26 | Mar - 27 | Survey under progress
|  |  |  | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex): Part B (SPV Name: POWERGRID Sirohi Transmission Limited) | [10 empty] | Aug-24 | [11 empty] | Aug-26 | Dec - 26
|  |  |  | Establishment of 2x1500MVA, 765/400 KV Substation at suitable location near Sirohi | [10 empty] | Aug-24 | [8 empty] | 20.00% | 15.00% |  | Aug-26 | Dec - 26 | Work under progress
|  |  |  | Fatehgarh-IV (Section-2) PS-Sirohi PS 765KV D/C Line | [10 empty] | Aug-24 | 412 | 537 | 318 | 184 | 17.46 | 0.59 | 0.34 | 0.04 |  |  |  | Aug-26 | Dec - 26 | Foundation RoW (58 loc.): Balotra (41), Jalore (6), Barmer (11)in Rajasthan
|  |  |  | Sirohi PS-Chhitorgarh (PG) 400KV D/C Line (Quad) | [10 empty] | Aug-24 | 445 | 604 | 370 | 289 |  | 0.61 | 0.48 | 0 |  |  |  | Aug-26 | Dec - 26 | Foundation RoW (6 loc.): Sirohi (6) in Rajasthan i)Forest, Rajasthan (45.88 Ha, 34 locs, 9.97 km)- Stage-I Awaited Proposal submitted on 25.01.2025. SG forwarded proposal to IRO on 10.11.25.
|  |  |  | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex): Part D (SPV Name: POWERGRID Beawar-Mandsaur Transmission | [10 empty] | Aug-24 | [11 empty] | Aug-26 | Aug - 26
|  |  |  | Beawar-Mandsaur PS 765KV D/C line | [10 empty] | Aug-24 | 553 | 742 | 535 | 245 |  | 0.72 | 0.33 | 0 |  |  |  | Aug-26 | Aug - 26 | Foundation RoW (40 loc.): Bhilwara (29), Beawar (11) in Rajasthan i)Rajasthan (49.81 Ha,20 loc, 8km)- Stage-II Awaited ii)Forest, Madhya Pradesh (14.08 Ha,6 loc, 2km)-Stage-II received on 27.11.25.
|  |  |  | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part-2: 5.5 GW) (Jaisalmer/ Barmer Complex): Part H1 (SPV name: POWERGRID Kurawar Transmission Limited) | [10 empty] | Oct-24 | [11 empty] | Oct-26 | Mar - 27
|  |  |  | Establishment of 765/400/220/132kV at Kurawar S/s | [10 empty] | Oct-24 | [8 empty] | 5.00% | 1.00% |  | Oct-26 | Mar - 27 | Land (173.15 Acre): Pending (61.15) Acre Pvt. (149.68 Acre): Pending (37.68) Acre. Registration of 112 acres of land completed. Govt. (23.47 Acre): Pending (23.47). Proposal has been marked to SDM.
|  |  |  | a) 765/400 kV (2x1500 MVA) Kurawar S/s | [10 empty] | Oct-24 | [11 empty] | Oct-26 | Mar - 27 | Engg. Under Progress
|  |  |  | b) 400/220 kV (2x500 MVA) Kurawar S/s | [10 empty] | Oct-24 | [11 empty] | Oct-26 | Mar - 27 | Engg. Under Progress
|  |  |  | c) 220/132 kV (3x200 MVA) Kurawar S/s | [10 empty] | Oct-24 | [11 empty] | Oct-26 | Mar - 27 | Engg. Under Progress
|  |  |  | Mandsaur – Kurawar 765 kV D/c line | [10 empty] | Oct-24 | 402 | 522 | 412 | 168 |  | 0.79 | 0.32 | 0 |  |  |  | Oct-26 | Mar - 27 | work under progress.
|  |  |  | Kurawar – Ashta 400 kV D/c line | [10 empty] | Oct-24 | 112 | 159 | 9 |  |  | 0.06 | 0 | 0 |  |  |  | Oct-26 | Mar - 27 | work under progress.
|  |  |  | Shujalpur – Kurawar 400 kV D/c line | [10 empty] | Oct-24 | 57 | 77 | 7 |  |  | 0.09 | 0 | 0 |  |  |  | Oct-26 | Mar - 27 | Engg. & survey Under Progress
|  |  |  | LILO of one circuit of Indore – Itarsi 400 kV D/c line at Ashta S/s | [10 empty] | Oct-24 | 112 | 154 |  |  |  | 0 | 0 | 0 |  |  |  | Oct-26 | Mar - 27 | Madhya Pradesh (31.97 Ha, 18 locs., 6.95 km )- Stage-I Awaited
|  |  |  | LILO of one circuit of Indore – Bhopal 765 kV S/c line at Kurawar S/s | [10 empty] | Oct-24 | 53 | 69 | 35 |  |  | 0.51 | 0 | 0 |  |  |  | Oct-26 | Mar - 27 | work under progress.
|  |  |  | Augmentation of transformation capacity at Jam Khambhaliya PS(GIS) (SPV: POWERGRID Jam Khambaliya Transmisison Ltd.) | [10 empty] | Oct-24 | [11 empty] | Jul-26 | Jul - 26
|  |  |  | Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 2x500MVA, 400/220kV ICT (5th and 6th) (terminated on New 220kV bus section-II) | [10 empty] | Oct-24 | [8 empty] | 15.00% | 1.00% |  | Jul-26 | Jul - 26 | Work under progress
|  |  |  | Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 1x500MVA, 400/220kV ICT (7th) (terminated on New 220kV bus section- II) | [10 empty] | Oct-24 | [8 empty] | 15.00% | 1.00% |  | Jul-26 | Jul - 26 | Work under progress
|  |  |  | Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 1x500MVA, 400/220kV ICT (8th) (terminated on New 220kV bus section- III) | [10 empty] | Oct-24 | [8 empty] | 15.00% | 1.00% |  | Jul-26 | Jul - 26 | Work under progress
|  |  |  | Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 1x500MVA, 400/220kV (9th) ICT terminated on New 220kV bus section-III | [10 empty] | Oct-24 | [8 empty] | 15.00% | 1.00% |  | Jul-26 | Jul - 26 | Work under progress
|  |  |  | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM POTENTIAL RENEWABLE ENERGY ZONE IN KHAVDA AREA OF GUJARAT UNDER PHASE-IV (7 GW): PART B (SPV: POWERGRID South Olpad Transmission Ltd.) | [10 empty] | Oct-24 | [11 empty] | Oct-26 | Mar - 27
|  |  |  | Establishment of 2x1500 MVA, 765/400 kV & 2x500 MVA, 400/220 kV GIS S/s at a suitable location in South Olpad (between Olpad and Ichhapore) | [10 empty] | Oct-24 | [11 empty] | Oct-26 | Mar - 27 | Land (107 Acre): Pending (107) Acre Pvt. (107 Acre): Pending (107 ) Acre. Application for acquisition of land under LARR,2013 submitted on 27.11.2024. Negotiation with land owners failed. Joint Measurement of lands belonging to aggrieved land conducted on 14.11.25 under police protection.
|  |  |  | Vadodara (GIS) –South Olpad (GIS) 765 kV D/C line | [10 empty] | Oct-24 | 249 | 343 | 38 |  |  | 0.11 | 0 | 0 |  |  |  | Oct-26 | Mar - 27 | Foundation RoW (242 locs.): Vadodara (95), Bharuch (147) Forest, Gujarat (2.4897 ha, Nil Locs, 0.351 Km) : Stage-I Awaited
|  |  |  | LILO of Gandhar – Hazira 400 kV D/c line at South Olpad (GIS) | [10 empty] | Oct-24 | 8 | 12 | 0 |  |  | 0 | 0 | 0 |  |  |  | Oct-26 | Mar - 27 | Engg & Survey under Progress
|  |  |  | Ahmedabad – South Olpad (GIS) 765 kV D/c line | [10 empty] | Oct-24 | 455 | 607 | 144 | 8 |  | 0.24 | 0.01 | 0 |  |  |  | Oct-26 | Mar - 27 | Foundation RoW (75 locs.): Ahmedabad (15), Anand (8), Vadodara (7), Bharuch (45) in Gujarat Forest, Gujarat (28.5931 ha, Nil Locs, 4.268 Km) : Stage-I Awaited Proposal submitted online on 14.04.25 . Proposal recommended in PSC I on 12.06.25. MoM issued on 07.07.25 and proposal fowarded to DFOs for filling of Part-II.
|  |  |  | Transmission System Strengthening for interconnections of Bhadla-III and Bikaner-III complex (SPV: POWERGRID BHADLA BIKANER TRANSMISSION LIMITED ) | [10 empty] | Aug-24 | [11 empty] | Aug-26 | Dec - 26
|  |  |  | Bhadla-III - Bikaner-III 765 kV D/c line | [10 empty] | Aug-24 | 254 | 328 | 106 | 10 |  | 0.32 | 0.03 | 0 |  |  |  | Aug-26 | Dec - 26 | Erection RoW Locs. (2): Bikaner District (2) in Rajasthan Forest, Rajasthan (6.8714 ha) : Stage-I Awaited Proposal submitted on 06.05.25. SG forwarded proposal to IRO on 20.11.25.
|  |  |  | Transmission System for Evacuation of Power from Rajasthan REZ Ph- IV (Part-2 : 5.5 GW) (Jaisalmer/ Barmer Complex): Part F (by clubbing Part F1 & F2) (SPV Name: POWERGRID BARMER I TRANSMISSION LIMITED) | [10 empty] | Nov-24 | [11 empty] | Nov-26 | Jun - 27
|  |  |  | Establishment of 3x1500 MVA, 765/400 kV & 2x500 MVA, 400/220 kV Barmer-I Pooling Station | [10 empty] | Nov-24 | [11 empty] | Nov-26 | Jun - 27 | Govt. (143.5 Acre): Pending (143.5 Acre). Demand note is under process, expected by 05.12.25
|  |  |  | Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) | [10 empty] | Nov-24 | 102 | 103 | 30 |  |  | 0.29 | 0 | 0 |  |  |  | Nov-26 | Jun - 27 | Foundation RoW (13 loc.): Barmer (13) in Rajasthan.
|  |  |  | Barmer-I PS– Sirohi PS 765 kV D/c line | [10 empty] | Nov-24 | 419 | 543 | 329 | 22 |  | 0.61 | 0.04 | 0 |  |  |  | Nov-26 | Jun - 27 | Forest, Rajasthan (0.2412 ha) : Stage-II Awaited Proposaal submitted on 01.05.2025. Stage-I issued on 03.09.25. Compliance forwarded by NO to SG on 27.11.25..
|  |  |  | Transmission System for Evacuation of Power from Rajasthan REZ PH-IV (PART-3: 6GW) [BIKANER COMPLEX]:PART-A (SPV Name: POWERGRID Bikaner IV Transmission Limited) | [10 empty] | Nov-24 | [11 empty] | Nov-26 | Mar - 27
|  |  |  | Establishment of 6x1500 MVA, 765/400 kV & 6x500 MVA, 400/220 kV Bikaner-IV Pooling Station. | [10 empty] | Nov-24 | [11 empty] | Nov-26 | Mar - 27 | Land (235.86 Acre): Land Acquisition process completed on 16.09.25.
|  |  |  | LILO of both ckts of Bikaner II PS - Bikaner III PS (Quad) at Bikaner-IV PS | [10 empty] | Nov-24 | 65 | 68 | 0 |  |  | 0 | 0 | 0 |  |  |  | Nov-26 | Mar - 27 | Engg under progress
|  |  |  | Bikaner-IV PS – Siwani 765 kV D/c line | [10 empty] | Nov-24 | 481 | 622 | 298 | 29 |  | 0.48 | 0.05 | 0 |  |  |  | Nov-26 | Mar - 27 | Forest, Rajasthan (1.2609 ha): Stage-II Awaited Forest, Haryana (0.7817 ha): Stage-I Awaited
|  |  |  | Siwani– Fatehabad (PG) 400 kV D/c line (Quad) | [10 empty] | Nov-24 | 165 | 220 | 23 | 7 |  | 0.1 | 0.03 | 0 |  |  |  | Nov-26 | Mar - 27 | Forest, Haryana (3.448 ha, Nil locs, 0.0205 km): Stage-I Awaited. Proposal submitted on 16.02.25. PSC I raised queries. CA Land alotted by MP and detailed CA scheme forwarded to Region on 23.04.25. Revised proposal with reduced forest area submitted on 17.11.25.
|  |  |  | Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) | [10 empty] | Nov-24 | 281 | 377 | 39 | 6 |  | 0.1 | 0.02 | 0 |  |  |  | Nov-26 | Mar - 27 | i) Forest, Haryana (13.12 ha, Nil locs., 0.0323 Km) :Proposal submitted on 16.02.25. PSC I raised queries. CA Land alotted by MP and detailed CA scheme forwarded to Region on 23.04.25. ii)Forest, Punjab (2.43ha, Nil locs., 0.00597Km) : Proposal submitted on 15.02.25. Under process with DFOs for Part II.
|  |  |  | STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) at Bikaner-IV PS | [10 empty] | Nov-24 | [11 empty] | Nov-26 | Mar - 27 | Engg under progress
|  |  |  | Transmission System for Evacuation of Power from potential renewable energy zone in Khavda area of Gujarat under Phase-V (8GW): Part A (SPV Name: POWERGRID West Central Transmission Limited) | [10 empty] | Nov-24 | [11 empty] | May-29 | May - 29
|  |  |  | Establishment of 6000 MW (4x1500 MW), ± 800 kV (HVDC) [LCC] at KPS2 and Nagpur terminal station (Bipole-1: 3000 MW) | [10 empty] | Nov-24 | [8 empty] | 5.00% | 1.00% |  | Nov-28 | Nov - 28 | Land (405 Acre, All Pvt.): Pending (284) Acre
|  |  |  | Establishment of 6000 MW (4x1500 MW), ± 800 kV (HVDC) [LCC] at KPS2 and Nagpur terminal station (Bipole-2: 3000 MW) | [10 empty] | Nov-24 | [11 empty] | May-29 | May - 29 | Engg. Under Progress
|  |  |  | Establishment of 6x1500 MVA, 765/400 kV ICTs at Nagpur S/s along with associated interconnections with HVDC Switchyard | [10 empty] | Nov-24 | [11 empty] | Nov-28 | Nov - 28 | Engg. Under Progress
|  |  |  | ±800 kV HVDC Bipole line (Hexa lapwing) between KPS2 (HVDC) and Nagpur (HVDC) | [10 empty] | Nov-24 | 2,409 | 3,152 | 64 | [8 empty] | Nov-28 | Nov - 28 | i)Forest, Gujarat (373.89 ha, 54.188 Km) : Proposal submitted on 03.06.25. Proposal recommended in PSC I on 12.06.25 & fowarded to DFOs for filling of Part- II. ii) WL- Wild Ass Sanctuary (26.4907 ha): Proposal submitted online on 03.06.25.Query raised by wildlife warden replied on 02.11.25. Site inspection to be done by wildlife warden. iii)Forest, Madhya Pradesh (156.936 ha) :Proposal submitted online on 28.08.25. Proposal discussed in PSC-I meeting on 08.09.25 and further forwarded to DFO for filling of Part-II on 09.09.25. iv)Forest, Maharashtra (57.71 ha) :Proposal submitted online on 21.10.25 & discussed in PSC-I meeting on 27.10.25. Proposal not accepted in PSC and it has been asked to confirm forest area from Amravati division.
|  |  |  | LILO of Wardha – Raipur 765 kV one D/c line (out of 2xD/c lines) at Nagpur | [10 empty] | Nov-24 | 68 | 86 | 5 |  |  | 0.06 | 0 | 0 |  |  |  | Nov-28 | Nov - 28 | Engg. Under Progress
|  |  |  | Dynamic Reactive Compensation at KPS1 and KPS3 (SPV name: POWERGRID KHAVDA PS1 AND 3 TRANSMISSION LIMITED) | [10 empty] | Nov-24 | [11 empty] | Nov-26 | Nov - 26
|  |  |  | ± 300 MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS1 400 kV Bus section-1 (GIS) | [10 empty] | Nov-24 | [11 empty] | Nov-26 | Nov - 26 | Land : Govt. Land (7.41 Acres): Pending (7.41 Acres): Proposal is has been marked to Secretariat , Gandhinagar by DM. Sectratariat has sent file to DM kutch for valuation of land.
|  |  |  | ± 300 MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS1 400 kV Bus section-2 (GIS) | [10 empty] | Nov-24 | [11 empty] | Nov-26 | Nov - 26 | Land : Govt. Land (7.41 Acres): Pending (7.41 Acres): Proposal is has been marked to Secretariat , Gandhinagar by DM. Sectratariat has sent file to DM kutch for valuation of land.
|  |  |  | ± 300 MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS3 400 kV Bus section-1 (GIS) | [10 empty] | Nov-24 | [8 empty] | 10.00% | 1.00% |  | Nov-26 | Nov - 26 | Work under progress
|  |  |  | Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-3: 6GW) [Bikaner complex]: Part-B (SPV Name: POWERGRID Siwani Transmission Limited) | [10 empty] | Nov-24 | [11 empty] | Nov-26 | Mar - 27
|  |  |  | Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) | [10 empty] | Nov-24 | [8 empty] | 3.00% | 1.00% |  | Nov-26 | Mar - 27 | Land (139 Acre): Pending (Nil) Acre
|  |  |  | Bikaner-IV PS – Siwani 765 kV D/C (2nd) line | [10 empty] | Nov-24 | 480 | 625 | 400 | 84 |  | 0.64 | 0.13 | 0 |  |  |  | Nov-26 | Mar - 27 | Forest, Rajasthan (1.2462 ha): Stage-II Awaited. Proposal submitted on 18.05.25. Stage-I issued on 01.10.25. Demand for compensatory levies approved by NO on 07.10.25.Payment deposited on 13.11.25. Forest, Haryana (0.5504 ha): Stage-I Awaited. Proposal submitted on 18.06.25. Proposal with revised forest area submitted on 22.11.25.
|  |  |  | Siwani – Sonipat (PG) 400 kV D/C line (Quad) | [10 empty] | Nov-24 | 273 | 378 | 1 |  |  | 0 | 0 | 0 |  |  |  | Nov-26 | Mar - 27 | Forest, Haryana (9.5307 ha): Stage-I Awaited. Route alignment approved on 08.04.25. Proposal submitted on 20.06.25. Proposal discussed in PSC I meeting on 16.07.25. Proposal returned to UA on 22.07.25. Main query is pertaining to CA land in other States. Request letter given to ACS (Forest), MP for allotment of DFL land on 23.07.25. Reply submitted to MS(PSC-I) on 07.11.25.
|  |  |  | Siwani – Jind (PG) 400 kV D/C line (Quad) (93.69 km). | [10 empty] | Nov-24 | 187 | 258 |  |  |  | 0 | 0 | 0 |  |  |  | Nov-26 | Mar - 27 | Forest, Haryana (4.2216 ha): Stage-I Awaited. Proposal submitted online on 28.10.2025. DFO raised query regarding DFL land on 29.10.25.Query replied back on 12.11.25
|  |  |  | STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) and MSR (2x125 MVAr) at Siwani S/s. | [10 empty] | Nov-24 | [11 empty] | Nov-26 | Mar - 27 | Engg under progress
|  |  |  | Additional Transmission System for evacuation of Power from Bhadla-III PS as part of Rajasthan REZ Phase III Scheme (20 GW) (SPV Name: POWERGRID Bhadla-III Power Transmission Limited) | [10 empty] | Aug-24 | [11 empty] | Feb-26 | Mar - 26
|  |  |  | Augmentation of 2x500 MVA (4th & 5th)., 400/220 KV ICTs at Bhadla- III PS | [10 empty] | Aug-24 | [8 empty] | 50.00% | 25.00% | 10.00% | Feb-26 | Mar - 26 | work under progress
|  |  |  | Augmentation of 1x1500 MVA 765/400 KV (3rd) ICT at Bhadla-III PS | [10 empty] | Aug-24 | [8 empty] | 50.00% | 25.00% | 10.00% | Feb-26 | Mar - 26 | work under progress
|  |  |  | Augmentation of 1x1500 MVA 765/400KV (4th) ICT at Bhadla-III PS | [10 empty] | Aug-24 | [8 empty] | 40.00% | 20.00% | 10.00% | Dec-25 | Mar - 26 | work under progress
|  |  |  | Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-4: 3.5 GW): Part A (SPV Name: POWERGRID Ghiror Transmission Limited) | [10 empty] | Dec-24 | [11 empty] | Dec-26 | Mar - 27
|  |  |  | Establishment of 765/400kV, 2x1500 MVA S/s at Ghiror (Distt. Mainpuri) (UP) | [10 empty] | Dec-24 | [8 empty] | 1.00% | 2.00% |  | Dec-26 | Mar - 27 | Pvt. (146.50 Acre): Pending (16.7) Acre. Proposal submitted to DM on 25.11.2024 , for purchase of land on tripartite mode. Registry of 129.8 acres land completed & remaining is under process.
|  |  |  | Augmentation by 765/400 kV, 2x1500 MVA Transformer (4th& 5th) at Barmer-I PS. | [10 empty] | Dec-24 | [11 empty] | Dec-26 | Mar - 27 | Engg Under Progress
|  |  |  | Augmentation by 5x500 MVA (5th to 9th), 400/220 kV ICTs at Barmer-I PS. | [10 empty] | Dec-24 | [11 empty] | Dec-26 | Mar - 27 | Engg Under Progress
|  |  |  | Fatehgarh-IV PS (Sec-2) – Barmer-I PS 400kV D/c line. | [10 empty] | Dec-24 | 74 | 108 | 2 |  |  | 0.02 | 0 | 0 |  |  |  | Dec-26 | Mar - 27 | Foundation RoW (13 loc.): Barmer (13) in Rajasthan. Forest, Rajasthan (0.1656 ha, ): Stage-II Awaited. Proposal submitted on 06.05.25. Stage-I issued on 14.09.25. Stage-I compliance forwarded to NO on 26.11.25. NO forwarded to SG on 27.11.25.
|  |  |  | Dausa - Ghiror 765 kV D/c line | [10 empty] | Dec-24 | 545 | 714 | 234 | 50 |  | 0.33 | 0.07 | 0 |  |  |  | Dec-26 | Mar - 27 | Forest, Uttar Pradesh (15.77 ha, ): Stage-I Awaited Forest, Rajasthan (16.2877 ha, ): Stage-I Awaited
|  |  |  | LILO of both ckt of 765 kV Aligarh (PG) - Orai (PG) D/c line at Ghiror S/s | [10 empty] | Dec-24 | 49 | 70 | 19 | 4 |  | 0.27 | 0.06 | 0 |  |  |  | Dec-26 | Mar - 27 | Forest, Uttar Pradesh (2.689 ha, ): Stage-II Awaited
|  |  |  | LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 2xS/c line at Ghiror S/s | [10 empty] | Dec-24 | 50 | 66 | 21 | 1 |  | 0.32 | 0.02 | 0 |  |  |  | Dec-26 | Mar - 27 | Forest, Uttar Pradesh (0.410 ha, ): Stage-II Awaited
|  |  |  | 400kV Ghiror-Firozabad (UPPTCL) D/c line. | [10 empty] | Dec-24 | 97 | 132 | 40 |  |  | 0.3 | 0 | 0 |  |  |  | Dec-26 | Mar - 27 | Forest, Uttar Pradesh (22.8045 ha, ): Stage-I Awaited
|  |  |  | STATCOM (2X±300 MVAr) along with MSC (4X125 MVAr) and MSR (2X125 MVAr) at Barmer-I PS | [10 empty] | Dec-24 | [11 empty] | Dec-26 | Mar - 27
|  |  |  | Transmission System under ISTS for evacuation of power from Kudankulam Unit - 3 & 4 (2x1000 MW) (SPV Name: POWERGRID Kudankulam Transmission Limited) | [10 empty] | Jan-25 | [11 empty] | Dec-26 | Dec - 26
|  |  |  | Kudankulam Nuclear Power Plant (3&4) – Tuticorin-II GIS PS 400 kV (quad) D/c line | [10 empty] | Jan-25 | 208 | 278 | 90 | 31 |  | 0.32 | 0.11 | 0 |  |  |  | Dec-26 | Dec - 26 | Foundation RoW (11 loc.): Tirunelveli District (11) in Tamilnadu.
|  |  |  | System Strengthening at Koppal-II and Gadag-II for integration of RE generation projects (SPV Name: POWERGRID Koppal Gadag Augmentation Transmission Limited) | [10 empty] | Jan-25 | [11 empty] | Jan-27 | Jan - 27
|  |  |  | Gadag-II PS – Koppal-II PS 400 kV (Quad) 2nd D/c line | [10 empty] | Jan-25 | 77 | 102 | 7 |  |  | 0.07 | 0 | 0 |  |  |  | Jan-27 | Jan - 27 | Work under progress.
|  |  |  | Augmentation by 3x1500 MVA (5th, 6th & 7th), 765/400kV ICTs at Koppal-II PS | [10 empty] | Jan-25 | [8 empty] | 10.00% |  |  | Dec-25 | Aug - 26 | Work under progress.
|  |  |  | Augmentation by 5x500 MVA, 400/220kV ICTs (5th, 6th, 7th, 8th & 9th) at Koppal-II PS | [10 empty] | Jan-25 | [8 empty] | 10.00% |  |  | Dec-25 | Aug - 26 | Work under progress.
|  |  |  | Augmentation by 7x500 MVA, 400/220kV ICTs (3rd, 4th, 5th, 6th, 7th, 8th & 9th) at Gadag-II PS | [10 empty] | Jan-25 | [8 empty] | 2.00% |  |  | Jan-27 | Jan - 27
|  |  |  | Augmentation of transformation capacity at Bidar PS (SPV Name: POWERGRID Bidar Augmentation Transmission Limited) | [10 empty] | Feb-25 | [11 empty] | Feb-27 | Feb - 27
|  |  |  | Augmentation by 1x1500 MVA (4th), 765/400kV ICT at Bidar PS | [10 empty] | Feb-25 | [8 empty] | 2.00% |  |  | Feb-27 | Feb - 27 | Work under progress.
|  |  |  | Augmentation by 3x500 MVA, 400/220kV ICTs (6th, 7th, & 8th) at Bidar PS | [10 empty] | Feb-25 | [8 empty] | 2.00% |  |  | Feb-27 | Feb - 27 | Work under progress.
|  |  |  | Augmentation of transformation capacity at KPS2 & KPS2 (Phase V Part B1 & B2) (SPV Name: POWERGRID KPS1 and 2 Augmentation Transmission Limited) | [10 empty] | Feb-25 | [11 empty] | Feb-27 | Feb - 27
|  |  |  | Augmentation by 1x1500 MVA (9th), 765/400kV ICT at KPS1(GIS) on Bus section-II | [10 empty] | Feb-25 | [11 empty] | Feb-27 | Feb - 27 | Engg under progress
|  |  |  | Augmentation by 1x1500 MVA (9th), 765/400kV ICT at KPS2(GIS) on Bus section-I | [10 empty] | Feb-25 | [8 empty] | 1.00% |  |  | Feb-27 | Feb - 27 | Work under progress.
|  |  |  | Augmentation of Banaskantha (Raghanesda) PS (GIS) (SPV Name: POWERGRID Banaskantha Augmentation Transmission Limited) | [10 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27
|  |  |  | Augmentation of transformation capacity at Banaskantha (Raghanesda) PS (GIS) by 2x500 MVA, 400/220 kV ICTs (3rd and 4th) | [10 empty] | Mar-25 | [8 empty] | 30.00% |  |  | Mar-27 | Mar - 27 | Work under progress.
|  |  |  | Transmission System for Integration of Kurnool-IV REZ – Phase-I (for 4.5 GW) (SPV Name: POWERGRID Kurnool-IV Transmission Limited) | [10 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27
|  |  |  | Establishment of 4x1500 MVA, 765/400 kV and 4x500 MVA, 400/220 kV Kurnool-IV Pooling Station | [10 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Pvt Land (191 Acre): Pending (191) Acre. RDO held meeting with land owners on 19.06.2025 and third tripartite meeting held on 02.07.2025 and land rate has been finalised. 33 out of 96 landowners have given consent for 74.69 acres of land and remaining are being pursued.
|  |  |  | Kurnool-IV – Bidar 765 kV D/C line | [10 empty] | Mar-25 | 533 | 698 | 41 |  |  | 0.06 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | Forest, Telangana (11.66 ha, ): Stage-I Awaited
|  |  |  | Kurnool-IV – Kurnool-III PS 765 kV D/C line | [10 empty] | Mar-25 | 252 | 333 | 51 | 6 |  | 0.15 | 0.02 | 0 |  |  |  | Mar-27 | Mar - 27 | Work under progress.
|  |  |  | 300 MVAr STATCOM at Kurnool-IV PS along with 2x125 MVAr MSR | [10 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Engg under progress
|  |  |  | Augmentation by 1x1500 MVA, 765/400 kV ICT (3rd) at C’Peta | [10 empty] | Mar-25 | [8 empty] | 1.00% |  |  | Mar-27 | Mar - 27 | Work under progress.
|  |  |  | LILO of Vijayawada-Nellore 400 kV D/C line at C’Peta | [10 empty] | Mar-25 | 64 | 99 |  |  |  | 0 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | Engg under progress
|  |  |  | Rajasthan REZ Ph-V (Part-1: 4 GW) [Sirohi/Nagaur] Complex (SPV Name: Rajasthan V Power Transmission Limited) | [10 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27
|  |  |  | Aaugmentation by 4x500 MVA, 400/220 kV ICTs at Sirohi S/s | [10 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Engg. under progress.
|  |  |  | Sirohi – Mandsaur PS 765 kV D/C line | [10 empty] | Mar-25 | 622 | 861 | 93 |  |  | 0.11 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | (i) Forest,Rajasthan (53.2984 ha, ): Stage-I Awaited (ii) Forest,Madhya Pradesh (10.9947 ha, ): Stage-I Awaited
|  |  |  | Mandsaur PS – Khandwa (New) 765 kV D/C line | [10 empty] | Mar-25 | 535 | 712 | 162 | 20 |  | 0.23 | 0.03 | 0 |  |  |  | Mar-27 | Mar - 27 | Forest,Madhya Pradesh (87.68 ha, ): Stage-I Awaited
|  |  |  | Transmission Scheme for integration of Davanagere/ Chitradurga and Bellary REZ in Karnataka (SPV Name: POWERGRID Chitradurga Bellary Transmission | [10 empty] | Mar-25 | [11 empty] | Sep-27 | Sep - 27
|  |  |  | Establishment of 765/400 kV, 4x1500 MVA, 400/220 kV 4x500 MVA Pooling Station near Davanagere / Chitradurga, Karnataka | [10 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Land (145 Acre), all Pvt: Pending (145) Acre
|  |  |  | LILO of Narendra New – Madhugiri 765 kV D/C line at Davanagere / Chitradurga 765/400 kV PS | [10 empty] | Mar-25 | 137 | 204 |  |  |  | 0 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | Engg. under progress.
|  |  |  | Upgradation of Madhugiri {Tumkur (Vasantnarsapura)} substation to its rated voltage of 765 kV level alongwith 3x1500 MVA, 765/400 kV ICTs | [10 empty] | Mar-25 | [8 empty] | 7.00% |  |  | Mar-27 | Mar - 27 | work under progress
|  |  |  | Upgradation of Narendra New – Madhugiri 765 kV D/C line (presently charged at 400 kV level) at its rated 765 kV voltage level | [10 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Engg. under progress.
|  |  |  | Establishment of 4x500 MVA, 400/220 kV Pooling Station near Bellary area (Bellary PS), Karnataka | [10 empty] | Mar-25 | [11 empty] | Sep-27 | Sep - 27 | Pvt. (68 Acre): Pending (68) Acre. Request letter has been submitted to DC, Vijayanagar on 27.02.25 for voluntary acquisition of land under Karnataka state specific amendments/rules in RFTLARR Act, 2013.
|  |  |  | Bellary PS – Davanagere / Chitradurga 400 kV D/C line | [10 empty] | Mar-25 | 200 | 183 | 7 |  |  | 0.04 | 0 | 0 |  |  |  | Sep-27 | Sep - 27
|  |  |  | Augmentation at Fatehgarh-II PS, Fatehgarh-IV PS (Section-II) and Barmer-I PS (SPV Name: POWERGRID Fatehgarh Barmer Augmentation Transmission Limited) | [10 empty] | Mar-25 | [11 empty] | Dec-26 | Mar - 27
|  |  |  | Augmentation with 765/400 kV, 1x1500 MVA Transformer (7th ) at Fatehgarh-II PS | [10 empty] | Mar-25 | [11 empty] | Dec-26 | Mar - 27 | Engg Under Progress
|  |  |  | Augmentation with 400/220 kV, 3x500 MVA (6th ,7th & 8th) ICTs at Fatehgarh-IV PS(Section-II) | [10 empty] | Mar-25 | [11 empty] | Nov-26 | Mar - 27 | Engg Under Progress
|  |  |  | Augmentation with 400/220 kV, 2x500 MVA (3rd & 4th) ICTs at Barmer-I PS | [10 empty] | Mar-25 | [11 empty] | Nov-26 | Mar - 27 | Engg Under Progress
|  |  |  | Transmission system strengthening at Kurnool- III PS for integration of additional RE generation projects (SPV Name: POWERGRID Kurnool-III CPETA Transmission Limited) | [10 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27
|  |  |  | Augmentation of transformation capacity by 3x1500 MVA, 765/400 kV ICTs at Kurnool-III PS | [10 empty] | Mar-25 | [8 empty] | 2.00% |  |  | Mar-27 | Mar - 27 | Work Under Progress
|  |  |  | Kurnool-III PS – Chilakaluripeta 765 kV D/c line | [10 empty] | Mar-25 | 584 | 778 | 28 |  |  | 0.04 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | Work Under Progress
|  |  |  | Augmentation of 1x1500 MVA 765/400 kV ICT (7th) at Kurnool-II PS | [10 empty] | Mar-25 | [8 empty] | 5.00% |  |  | Mar-27 | Mar - 27 | Work Under Progress
|  |  |  | Transmission System for evacuation of power from Mahan Energen Limited Generating Station in Madhya Pradesh (SPV Name: POWERGRID MEL Power Transmission Limited) | [10 empty] | Jun-25 | [11 empty] | Dec-27 | Dec - 27
|  |  |  | Mahan (existing bus) – Rewa PS (PG) 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | [10 empty] | Jun-25 | 277 | 399 |  |  |  | 0 | 0 | 0 |  |  |  | Dec-27 | Dec - 27 | Forest,Madhya Pradesh (140.47 ha, ): Stage-I Awaited. Proposal submitted on 16.09.2025. Proposal recommended in PSC-I meeting on 23.09.2025 and forwarded to DFO for filing of part-II on 24.09.2025. Wildlife (2.039 Ha), Madhya Pradesh: Proposal submitted online on 16.09.2025. Queries raised for revision in wildlife area on 25.10.25. Reply under process.
|  |  |  | 2 Nos. 400 kV bays at Rewa PS (PG) for termination of Mahan (existing bus) – Rewa PS (PG) 400 kV D/c line (Quad ACSR/AAAC/AL59 moose equivalent) line | [10 empty] | Jun-25 | [11 empty] | Dec-27 | Dec - 27 | Engg Under Progress
|  |  |  | Transmission System Strengthening at Davanagere for Integration of RE Generation (SPV Name: POWERGRID Davanagere Power Transmission | [10 empty] | Sep-25 | [11 empty] | Sep-27 | Sep - 27 | SPV Acquired on 24.09.2025
|  |  |  | Augmentation of Transformation Capacity by 4x500 MVA, 400/220 kV ICTs (5th-8th) at Davanagere PS | [10 empty] | Sep-25 | [11 empty] | Sep-27 | Sep - 27
|  |  |  | Augmentation of Davanagere/Chitradurga PS by 765/400kV, 1x1500 MVA ICTs | [10 empty] | Sep-25 | [11 empty] | Sep-27 | Sep - 27
|  |  |  | 02 Nos. of 220kV line bays at Davanagere/Chitradurga PS for termination of dedicated transmission lines of RE generation Projects. | [10 empty] | Sep-25 | [11 empty] | Sep-27 | Sep - 27
|  |  |  | Augmentation of Transformation Capacity and Implementation of Line Bays at Mandsaur S/S for RE Interconnection (SPV Name: POWERGRID Mandsaur I RE Transmission Limited) | [10 empty] | Oct-25 | [11 empty] | Mar-27 | Mar - 27 | SPV Acquired on 08.10.2025
|  |  |  | Augmentation of Transformation capacity by 1x1500MVA, 765/400 kV ICT (4th) (Terminated at 400 kV & 765kV Bus Section-II). | [10 empty] | Oct-25 | [11 empty] | Mar-27 | Mar - 27
|  |  |  | Augmentation of Transformation capacity by 1x500MVA, 400/220kV ICT (6th) (Terminated on 400 kV Bus Section-I & 220kV Bus Section- II). | [10 empty] | Oct-25 | [11 empty] | Mar-27 | Mar - 27
|  |  |  | Augmentation of Transformation capacity by 1x500MVA, 400/220kV ICT (7th) (Terminated on 400 kV Bus Section-II & 220kV Bus Section- III) at Mandsaur PS | [10 empty] | Oct-25 | [11 empty] | Mar-27 | Mar - 27
|  |  |  | Inter-regional (NR-WR) Transmission System strengthening to relieve the loading of 765 kV Vindhyachal-Varanasi D/c line | [10 empty] | Oct-25 | [11 empty] | Oct-27 | Oct - 27 | SPV Acquired on 16.10.2025
|  |  |  | Establishment of 765 kV Prayagraj S/s near Prayagraj (Uttar Pradesh) along with 2x330 MVAr 765 kV Bus reactors | [10 empty] | Oct-25 | [11 empty] | Oct-27 | Oct - 27 | Pvt. (123 Acre): Pending (123) Acre.
|  |  |  | LILO of 765 kV Fatehpur-Varanasi S/C line at Prayagraj | [10 empty] | Oct-25 | 30 | [6 empty] | 0 |  |  |  | Oct-27 | Oct - 27
|  |  |  | LILO of 765 kV Fatehpur-Sasaram S/C line at Prayagraj | [10 empty] | Oct-25 | 28 | [6 empty] | 0 |  |  |  | Oct-27 | Oct - 27
|  |  |  | 765 kV Vindhyachal Pool - Prayagraj D/C line along with 330 MVAr line reactor (switchable) at Prayagraj end on each circuit of 765 Kv Vindhyachal Pool - Prayagraj D/C line | [10 empty] | Oct-25 | 440 | [6 empty] | 0 |  |  |  | Oct-27 | Oct - 27
|  |  |  | Bypassing of both circuits of 765 kV Sasan – Vindhyachal Pool 2xS/C line at Vindhyachal Pool and connecting it with 765 kV Vindhyachal Pool - Prayagraj D/C line, thus forming 765 kV Sasan - Prayagraj D/C line | [10 empty] | Oct-25 | 1 | [6 empty] | 0 |  |  |  | Oct-27 | Oct - 27
|  |  |  | Inter-Regional Strengthening between SR Grid and WR Grid | [10 empty] | Oct-25 | [11 empty] | Oct-27 | Oct - 27 | SPV Acquired on 17.10.2025
|  |  |  | Parli New – Bidar 765 kV D/C line with 240 MVAr SLR at Bidar end on both circuits | [10 empty] | Oct-25 | 240 | [6 empty] | 0 |  |  |  | Oct-27 | Oct - 27
|  |  |  | Additional 400 kV feed to Goa and additional system for power evacuation from generation projects pooled at Raigarh (Tamnar) Pool - Goa Tamnar Transmission Project (GTTPL) | [10 empty] | Mar-18 | [11 empty] | Nov-21 | Mar - 27
|  |  |  | LILO of one ckt. of Narendra (existing) - Narendra (New) 400kV D/c line at Xeldem | [10 empty] | Mar-18 | 210 | 279 | 77 | 35 | 0 | 0.28 | 0.13 | 0 |  |  |  | Nov-21 | Mar - 27 | 1.RoW (7 locs.) : Dharwad (7) 2. Forest (174.634 Ha, 104 locs, 75.928 cKm) in Karnataka (Wildlife area included): Stage I Pending. Applied on 22-07-2023 3. Wildlife (32.06 Ha, 22 locs, 13.92 cKm) in Karnataka: Pending with the Chief Wildlife Warden on account of SBWL recommendation. 4. Forest (76.994 Ha, 49 locs, 33.478 cKm) in Goa (Wildlife area included): Stage I Pending. 5. Wildlife (27.092 Ha, 16 locs, 11.78 cKm) in Goa: Received on 23-08-24 from NBWL.
|  |  |  | Xeldem - Mapusa 400kV D/c line | [10 empty] | Mar-18 |  | 142 | 142 | 142 | 105.64 | 1 | 1 |  |  |  |  | May-21 | Nov - 24 | Deemed COD declared w.e.f 00:00 hrs of 19-11-2024. Powerflow commenced on 31-05-2025.
|  |  |  | Xeldem (existing) – Xeldem (new) 220kV D/C line | [10 empty] | Mar-18 |  | 66 | 66 | 66 | 45.4 | 1 | 1 |  |  |  |  | May-21 | Nov - 24 | Deemed COD declared w.e.f 00:00 hrs of 19-11-2024. Powerflow commenced on 31-05-2025.
|  |  |  | Dharamjaygarh Pool section B - Raigarh (Tamnar) Pool 765kV D/c line | [10 empty] | Mar-18 |  | 179 |  |  | 137 | 0 | 0 |  |  |  |  | Jul-21 | Jun - 22 | TL Completed
|  |  |  | 2x500MVA, 400/220kV Xeldem | [10 empty] | Mar-18 | [8 empty] | 100.00% | 100.00% | 100.00% | May-21 | Nov - 24 | Charged on no load basis on 05-11-2024. Deemed COD declared w.e.f 19-11- 2024.Powerflow commenced on 31-05-2025.
|  |  |  | Transmission System for 400 kV Udupi (UPCL) – Kasargode D/C Line | [10 empty] | Sep-19 | [11 empty] | Nov-22 | Jun - 26
|  |  |  | Mangalore (Udupi PCL) – Kasargode 400kV D/c line | [10 empty] | Sep-19 | 232 | 281 | 212 | 173 | 7.8 | 0.75 | 0.62 | 0.03 |  |  |  | Nov-22 | Jun - 26 | 1.RoW (31locs.) in Karnataka: Dakshin Kannada (31locs.) 2. Row in Kerala: 87 ckm of stringing halted due to non finalisation of land compensation order by Govt. of Kerala. 3. Forest (31.07 Ha, 17 locs, 13.5 ckm) in Karnataka: Stage II awaited. Stage-I received on 27-10-2022. Mangalore Division (22.11 Ha) & Kundapur Division (8.96 Ha): WP received in Oct'24 & TCP received in Jan'25 and Nov'24 resp. 4. Forest (17.07 Ha, 8 locs, 7.8 ckm) in Kerala: Stage II awaited. WP & TCP received on 15-10-2024. Stage-I received on 27-10-2022.
|  |  |  | 2x500MVA, 400/220 kV Kasargode | [10 empty] | Sep-19 | [8 empty] | 99.93% | 100.00% | 99.86% | Nov-22 | Jun - 26 | Commissioning is dependent on completion of Udupi – Kasargode 400kV D/c line.
|  |  |  | Transmission System for evacuation of power from Pakaldul HEP in Chenab Valley HEPs – Connectivity System (CKM-2, MVA-400) | [10 empty] | Dec-22 | [11 empty] | Apr-25 | Dec - 25
|  |  |  | LILO of one circuit of Kishenpur – Dulhasti 400 kV D/c at Kishtwar | [10 empty] | Dec-22 | 3 | 5 | 5 | 5 | 2.8 | 1 | 1 | 0.93 |  |  |  | Apr-25 | Dec - 25 | Deemed COD w.e.f 26.11.2025 as per TSA .
|  |  |  | 7x66.67 MVA, 400/132 kV Kishtwar | [10 empty] | Dec-22 | [8 empty] | 100.00% | 100.00% | 100.00% | Apr-25 | Dec - 25 | Deemed COD declared for 400/132 kV pooling station at Kishtwar w.e.f 26.11.2025 as per TSA . Total Land (32 Acres): 1. Pvt. (29.2 Acres): All acquired 2. Govt. (2.8 Acre Non-Forest): Indent given by JKPDD.
|  |  |  | Transmission System for Evacuation of Power from REZ in Rajasthan (20GW) under Phase-III Part G | [10 empty] | Aug-23 | [11 empty] | Feb-25 | Jan - 26
|  |  |  | Fatehgarh3– Beawar 765kV D/c (2nd) | [10 empty] | Aug-23 | 635 | 817 | 815 | 802 | 458 | 1 | 0.98 | 0.72 |  |  |  | Feb-25 | Jan - 26 | 1. RoW (7 locs.) in Rajasthan: Barmer (4 locs.: 1 Foundation & 3 Erection) & Balotra (3 locs.: 3 Erection). 2. Forest (11.35 Ha, 4 locs, 3.39 cKm) in Rajasthan: Stage II received on 29-08- 2025. Stage I received on 11-09-2024, WP received on 26-05-25 & TCP recieved.
|  |  |  | Transmission System for Evacuation of Power from REZ in Rajasthan (20GW) under Phase-III Part F | [10 empty] | Sep-23 | [11 empty] | Mar-25 | Mar - 26
|  |  |  | Fatehgarh3– Beawar 765kV D/c | [10 empty] | Sep-23 | 635 | 806 | 801 | 726 | 265 | 0.99 | 0.9 | 0.42 |  |  |  | Mar-25 | Mar - 26 | 1.RoW (24 locs.) in Rajasthan: Barmer (8 locs.: 3 Foundation & 5 Erection) & Balotra (16 locs.: 16 Erection). 2. Forest (10.89 Ha, 4 locs, 3.26 cKm) in Rajasthan: Stage II awaited. WP recieved on 16-06-25. Stage I received on 05-07-2024.
|  |  |  | LILO of both circuits of Ajmer – Chittorgarh 765 kV D/c at Beawar | [10 empty] | Sep-23 | 136 | 178 | 175 | 168 | 48 | 0.98 | 0.94 | 0.35 |  |  |  | Mar-25 | Mar - 26 | 1. Forest (22.66 Ha, 7 locs, 6.76 cKm) in Rajasthan: Stage II awaited. WP received on 13-05-25 & TCP received on 20-05-25. Stage I received on 05-11-2024. 2. PLC Approval pending with M/s Shree Cement.since mar'24.
|  |  |  | LILO of of Kota – Merta 400 kV D/c at Beawar | [10 empty] | Sep-23 | 66 | 90 | 89 | 81 | 28 | 0.99 | 0.9 | 0.42 |  |  |  | Mar-25 | Mar - 26 | 1. PLC Approval pending with M/s Shree Cement since Mar'24.. 2. Delay in replacement of existing earth wire with OPGW in Kota -Merta TL by PGCIL. .
|  |  |  | 2X1500MVA , 765/400kV Beawar S/s | [10 empty] | Sep-23 | [8 empty] | 98.00% | 100.00% | 94.00% | Mar-25 | Jan - 26 | Total Land (58.28 Ha): Govt. Land (12.32 Ha) & Pvt. Land (45.96 Ha) : All acquired
|  |  |  | (+/-)2x300 MVAr Statcom, 4x125 MVAr MSC, 2x125 MVAr MSR at Fatehgarh-III PS | [10 empty] | Sep-23 | [8 empty] | 98.00% | 100.00% | 75.00% | Sep-25 | Mar - 26
|  |  |  | Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-1) (Bikaner Complex): PART-B | [10 empty] | Dec-23 | [11 empty] | Dec-25 | Aug - 26
|  |  |  | Establishment of 765/400 kV, 4x1500 MVA (along with one spare unit of 500 MVA) Neemrana-II S/s | [10 empty] | Dec-23 | [8 empty] | 0.46% | 78.50% | 0.00% | Dec-25 | Aug - 26 | 1. Total Land (57.96 Ha All private): Pending 39.98 Ha
|  |  |  | Neemrana-II -Kotputli 400 kV D/c line (Quad) | [10 empty] | Dec-23 | 87 | 126 | 107 | 92 | 40 | 0.85 | 0.73 | 0.46 |  |  |  | Dec-25 | Aug - 26 | 1.RoW (10 locs.) in Rajasthan: Kotputli-Behror (10 locs.). 2. Forest (8.39 Ha, 6 locs, 7.09 cKm ) in Rajasthan. Stage II awaited. Stage I received on 14-08-2025.
|  |  |  | LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s | [10 empty] | Dec-23 | 395 | 517 | 429 | 306 | 34.2 | 0.83 | 0.59 | 0.09 |  |  |  | Dec-25 | Aug - 26 | 1. RoW (7 locs.) in Rajasthan: Khairthal-Tijara (7 locs) . 2. RoW (2 locs.) in Haryana: Nuh (2 locs). 3. Forest (22.86 Ha, 14 locs, 11.47 cKm) in Haryana: Stage I is awaited. Recommended in PSC-II dated 18-08-25 . Applied on 30-03-2024. 4. Forest (21.77 Ha, 17 locs, 19.66 cKm) in Rajasthan:Stage I received on 14-08- 2025.
|  |  |  | Transmission System for Evacuation of Power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7 GW): Part C | [10 empty] | Aug-24 | [11 empty] | Oct-26 | Oct - 26
|  |  |  | Establishment of 4x1500 MVA, 765/400 kV & 2x500 MVA, 400/220 kV Boisar-II (GIS) S/s | [10 empty] | Aug-24 | [8 empty] | 30.00% | 44.10% | 0.00% | Oct-26 | Oct - 26 | Total land (142 Acres): Pending 52 Acres. Pvt. (90 Acres): All acquired Forest (52 Acres): Pending 52 Acre, Applied 06-06-2025.
|  |  |  | South Olpad (GIS) – Boisar-II (GIS) 765 kV D/c line | [10 empty] | Aug-24 | 475 | 626 | 240 | 49 | 0 | 0.38 | 0.08 | 0 |  |  |  | Oct-26 | Oct - 26 | 1. RoW (126 locs.) in Gujarat: Olpad tehsil (51), Mangrol (6), Mandvi (7), Kamrej (31), Bardoli (22), Mahuva (2), Chikhli Taluka (7) 2. RoW (02 locs.) in Maharashtra: Palghar (2 locs) 3. Delay in Allocation of Space/Land for establishment of 2 Nos. of 765 kV line bays at south Olpad S/s due to non-finalisation of South Olpad S/s location by PGCIL. 4. PLC approval pending from PGCIL in Gujarat portion. 6. Forest (134.15 Ha, 51 locs., 40 ckm) in Gujarat 7. Forest (180.37 Ha, 61 locs., 50 ckm) in Maharashtra - Accepted in PSC-1 on 07- 04-2025, Tree enumeration completed. File is with DFO for part 2 processing. 8. Forest (8.49 Ha) in DNH: Stage-I approval pending
|  |  |  | Boisar-II (Sec-II) – Velgaon (MH) 400 kV D/c line | [10 empty] | Aug-24 | 50 | 74 | 4 | 0 | 0 | 0.05 | 0 | 0 |  |  |  | Oct-26 | Oct - 26 | 1. RoW (4 locs.) in Maharashtra: Palghar (4) 2. Forest (62.5 Ha, 35 locs., 27.17 ckm) in Maharashtra. Stage I awaited, applied on 07-03-25. PSC-1 accepted on 12-08-2025. 3. 16 locs and 10 Kms of route length are on hold due to non-finalization of S/S land by MSETCL.
|  |  |  | LILO of Babhaleswar – Padghe (M) 400 kV D/c line at Boisar-II (Sec-I) | [10 empty] | Aug-24 | 116 | 174 | 29 | 3 | 0 | 0.17 | 0.02 | 0 |  |  |  | Oct-26 | Oct - 26 | 1. RoW (51 locs.) in Maharashtra: Palghar District (6), Thane District(45) 2. PLC approval between AP 78/0 – 79/0 pending with PGCIL. 3. Forest (66.02 Ha, 46 locs, 28.7 ckm) in Maharashtra: Stage-I awaited. CCF visit done on 27-11-25.
|  |  |  | ± 300 MVAR STATCOM with 3x125 MVAR MSC, 1x125 MVAR MSR at 400 kV level of Navsari (New) (PG) S/s | [10 empty] | Aug-24 | [8 empty] | 34.59% | 36.90% | 0.00% | Oct-26 | Oct - 26
|  |  |  | ±200 MVAR STATCOM with 2x125 MVAR MSC, 1x125 MVAR MSR at 400 kV bus section-I of Boisar-II and ±200 MVAR STATCOM with 2x125 MVAR MSC, 1x125 MVAR MSR at 400 kV bus section-II of Boisar-II. | [10 empty] | Aug-24 | [8 empty] | 7.90% | 35.70% | 0.00% | Oct-26 | Oct - 26
|  |  |  | LILO of Navsari (New) – Padghe (PG) 765 kV D/c line at Boisar-II | [10 empty] | Aug-24 | 51 | 74 | 41 | 9 | 0 | 0.55 | 0.12 | 0 |  |  |  | Oct-26 | Oct - 26 | Forest: (38.94 Ha, 18 Locs, 12.68 cKm) in Maharashtra. Stage 1 awaited. applied on 19-01-2025. EDS rasied, A/p resubmitted on 02-04-2025. PSC 1 accepted on 07- 04-2025.
|  |  |  | Transmission System for Integration of Ananthapur-II REZ - Phase- I (for 4.5 GW) (SPV:ANANTHAPUR II REZ TRANSMISSION LIMITED) | [10 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27
|  |  |  | Establishment of 4x1500 MVA, 765/400 & 6x500 MVA, 400/220 kV Ananthapuram- II Pooling Station near Kurnool, Andhra Pradesh | [10 empty] | Mar-25 | [8 empty] | 0.00% | 22.00% | 0.00% | Mar-27 | Mar - 27 | Present Scope: 238 Ha Acquired Land: 193 Ha
|  |  |  | Ananthapuram- II - Davangere 765 kV D/c line | [10 empty] | Mar-25 | 236 | 236 | 54 | 1 | 0 | 0.23 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | 1. Delay in handover of critical D&E inputs of Davanagere S/s by PGCIL for route finalisation and construction of 2 nos. 765 kV line bays at the Davanagere S/s . 2. RoW (6 locs.) in Andhra Pradesh: Ananthpuram (6 locs.)
|  |  |  | Ananthapuram- II - Cuddapah 765 kV D/c line | [10 empty] | Mar-25 | 565 | 565 | 258 | 4 | 0 | 0.46 | 0.01 | 0 |  |  |  | Mar-27 | Mar - 27 | RoW (50 locs.) in Andhra Pradesh: Ananthpuram (44 locs.) & Y S R Kadapa (6 locs.)
|  |  |  | ±300 MVAr STATCOM at Ananthapuram-II PS along with 2x125 MVAr MSR | [10 empty] | Mar-25 | [8 empty] | 0.00% | 10.27% |  | Mar-27 | Mar - 27
|  |  |  | North-Eastern Region Expansion Scheme-XXV Part-A (NERES) | [10 empty] | Jul-25 | [11 empty] | Jul-28 | Jul - 28
|  |  |  | LILO of both circuits of existing Bongaigaon (POWERGRID) – Balipara (POWERGRID) 400 kV D/C (Quad) line at Bornagar (ISTS) | [10 empty] | Jul-25 | 54 | 85 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Jul-28 | Jul - 28
|  |  |  | Establishment of new 400 kV Bornagar (ISTS) switching station in Assam (765 kV and 220 kV levels to be established in future) | [10 empty] | Jul-25 | [8 empty] | 0.00% | 0.00% | 0.00% | Jul-28 | Jul - 28
|  |  |  | Immediate evacuation for North Karanpura (3x660MW) generation project of NTPC(ERSS XIX) (CKM-303, MVA-1000) | [10 empty] | Jul-16 | [11 empty] | Sep-19 | Dec - 25
|  |  |  | NK – Gaya 400kV D/c line | [10 empty] | Jul-16 | 196 | 285 | 285 | 285 | 196.4 | 1 | 1 | 1 |  |  |  | Sep-19 | Dec - 25
|  |  |  | NK – Chandwa 400kV D/c line | [10 empty] | Jul-16 |  | 115 |  |  |  | 0 | 0 |  |  |  |  | Sep-19 | Oct - 22 | Line charged
|  |  |  | LILO of both circuits of Ranchi – Maithon-RB 400kV D/c line at Dhanbad | [10 empty] | Jul-16 |  | 10 |  |  |  | 0 | 0 |  |  |  |  | Sep-19 | Aug - 21 | Line charged
|  |  |  | 400/220 kV, 2x500 MVA Dhanbad | [10 empty] | Jul-16 | [11 empty] | Sep-19 | Aug - 21 | Substation Charged
|  |  |  | ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | [10 empty] | Jan-23 | [11 empty] | Jul-24 | Mar - 26
|  |  |  | Narendra New (GIS) – Pune (GIS) 765 D/c Line | [10 empty] | Jan-23 | 636 | 795 | 663 | 523 | 133.2 | 0.83 | 0.66 | 0.21 |  |  |  | Jul-24 | Mar - 26 | RoW (88 loc) : a) Pune District (46) in Maharashtra. b) Vijaypura District (40) in Karnataka. 40 locations affected near Kudgi end. Forest (76.87 Ha, 29 loc)- Proposal recommended in PSC-II conducted on 12-Aug- 25. MoM & NO clearance received on 12-Sep-25. Proposal forwarded from SG to IRO on 11-Nov-25. Proposal awaiting recommendation in REC meeting.
|  |  |  | Upgradation of Narendra New (GIS) Substation to rated voltage level of 765 kV alongwith 4x1500 MVA transformer | [10 empty] | Jan-23 | [8 empty] | 97.50% | 100.00% | 96.00% | Jul-24 | Mar - 26 | Outdoor and indoor GIB along with GAB WIP HV Testing has been completed for Pune SS And Narendra SS HV testing under initiation
|  |  |  | Transmission System for evacuation of additional 7 GW RE Power from Khavda RE Park under Phase-III Part A | [10 empty] | Dec-23 | [11 empty] | Dec-25 | Mar - 26
|  |  |  | Establishment of 765 kV Halvad switching station with 765 kV, 2x330 MVAr bus reactors | [10 empty] | Dec-23 | [8 empty] | 97.00% | 97.00% | 80.00% | Dec-25 | Mar - 26 | Land required: 205 Acre (Present scope acquisition completed) Pvt. land (197): Aquired (183) Govt. land (8): Acquired (8)
|  |  |  | KPS2(GIS) - Halvad 765 kV D/c line | [10 empty] | Dec-23 | 492 | 690 | 536 | 400 | 125 | 0.78 | 0.58 | 0.25 |  |  |  | Dec-25 | Mar - 26 | RoW: 101 Locs. Tehsils: Morbi- 75 Nos (35 Morbi, 8 Maliya, 32 Halvad) Kutch 26 Locs Tehsils: (Bhuj- 2 Nos, Bhachau-24) Forest (266.6997 Ha, 99 locs) in Gujarat. Wildlife (36.6493 Ha, 18 locs.) in Gujarat.
|  |  |  | LILO of Lakadia – Ahmedabad 765 kV D/c line at Halvad | [10 empty] | Dec-23 | 68 | 100 | 90 | 59 | 2.96 | 0.9 | 0.59 | 0.04 |  |  |  | Dec-25 | Mar - 26
|  |  |  | Transmission System for Evacuation of Power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7 GW): Part A | [10 empty] | Aug-24 | [11 empty] | Aug-26 | Aug - 26
|  |  |  | Augmentation of KPS3 (GIS) by 3x1500 MVA, 765/400 kV ICTs | [10 empty] | Aug-24 | [8 empty] | 42.00% | 20.00% | 5.00% | Aug-26 | Aug - 26 | Land required for Lakadia bay extension: 13 Acres, same under acquisition
|  |  |  | 765 kV KPS3 (GIS) – Lakadia (AIS) D/C line | [10 empty] | Aug-24 | 404 | 513 | 262 | 121 | 4.8 | 0.51 | 0.24 | 0.01 |  |  |  | Aug-26 | Aug - 26 | 1) ROW: 40 Locs : Khavda (1), Bhuj - (15), Bhachau - (24). Application for Section 16(1) is submitted 2) Forest- KPS3-Lakadia -(317.61 Ha, 128 locs) - Proposal recommended in PSC-II vide MoM dated 23-Sep-25. Proposal forwarded from Nodal officer to state government on 15-Oct-25. Proposal forwarding to IRO is awaited.
|  |  |  | 765 kV KPS1 (GIS)– Bhuj PS D/C line (2nd) | [10 empty] | Aug-24 | 217 | 286 | 185 | 119 | 18.08 | 0.65 | 0.42 | 0.08 |  |  |  | Aug-26 | Aug - 26 | 1) ROW: 4 Locs, Bhuj - (4). Application for Section 16(1) is submitted. 2) Forest (220.81 Ha, 84 locs) - Proposal recommended in PSC-II vide MoM dated 23-Sep-25. Proposal forwarded from Nodal officer to state government on 15-Oct- 25. Proposal forwarding to IRO is awaited.
|  |  |  | ±300MVAR STATCOM with 1x125 MVAR MSC, 2x125 MVAR MSR at KPS3 400 kV. | [10 empty] | Aug-24 | [8 empty] | 5.00% |  |  | Aug-26 | Aug - 26 | Land required: ROU permission required from GPCL/Govt of Gujarat. Letter submitted to GPCL , Further letter written to collector for land handover.
|  |  |  | Transmission System for Network Expansion Scheme in Navinal (Mundra) area of Gujarat for drawal of power in the area (SPV: NavinalTransmission Ltd.) | [10 empty] | Oct-24 | [11 empty] | Jul-26 | Jul - 26
|  |  |  | Establishment of 4x1500 MVA, 765/400 kV Navinal (Mundra) S/s (GIS) | [10 empty] | Oct-24 | [8 empty] | 45.00% | 25.00% | 0.00% | Jul-26 | Jul - 26 | Land (70 Acre): All acquired Supply, Civil & ETC ordering completed. EPC package ordering completed. ICTs, Reactors: Sept;25 to Mar’26
|  |  |  | LILO of Bhuj-II – Lakadia 765 kV D/C line at Navinal (Mundra) (GIS) S/s | [10 empty] | Oct-24 | 257 | 368 | 137 | 65 | 0 | 0.37 | 0.18 | 0 |  |  |  | Jul-26 | Jul - 26 | 1] Forest-(73.9278 Ha, 42 locs) in Gujarat,Proposal from DFO, Kutch East & Kutch SF forwarded to CCF. Kutch West to CCF on 20-Sep-25. Proposal forwarded from CCF to Nodal Officer on 10-Oct-25. PSC-II completed on 6-Nov-25. 2] ROW- Mundra Tehsil. (129 Locs, 44 Km)
|  |  |  | Network Expansion scheme in Gujarat for drawl of about 3.6 GW load under Phase-I in Jamnagar area (SPV: Jamnagar Transmission Ltd.) | [10 empty] | Oct-24 | [11 empty] | Oct-26 | Oct - 26
|  |  |  | Establishment of 2x1500 MVA 765/400 kV Jamnagar (GIS) PS | [10 empty] | Oct-24 | [11 empty] | Oct-26 | Oct - 26 | Land (115 Acre): Land acquisition under progress.
|  |  |  | Halvad – Jamnagar 765 kV D/c line | [10 empty] | Oct-24 | 340 | 391 | 58 | 7 |  | 0.15 | 0.02 | 0 |  |  |  | Oct-26 | Oct - 26 | 1] Check survey under progress 89 km off 147 Km completed 2] Forest: 16.552 Ha, 2 Locations 3.54 km affected- Modification in proposal due to change in Jamnagar SS land. Revised hard copies submitted in all divisions in August 2025 EDS compliance completed.
|  |  |  | LILO of Jam Khambhaliya PS – Lakadia 400 kV D/c (triple snowbird) line at Jamnagar | [10 empty] | Oct-24 | 20 | 28 | 0 |  |  | 0 | 0 | 0 |  |  |  | Oct-26 | Oct - 26 | 1] Check survey under progress. 2] Forest: 0.12 Ha, 0 Locations 0.012 km affected. Proposal submitted on Parivesh portal on 06-08-25.
|  |  |  | Jamnagar – Jam Khambhaliya 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | [10 empty] | Oct-24 | 100 | 112 | 0 |  |  | 0 | 0 | 0 |  |  |  | Oct-26 | Oct - 26 | 1) Forest: 2.43 Ha, 2 Locations 0.528 km affected. Proposal submitted on Parivesh portal on 06-08-25. 2) Check survey completed 37 Km off 41 Km.
|  |  |  | LILO of CGPL – Jetpur 400kV D/c (triple snowbird) line at Jamnagar | [10 empty] | Oct-24 | 260 | 339 | 13 |  |  | 0.04 | 0 | 0 |  |  |  | Oct-26 | Oct - 26 | 1] Check survey under progress 123 Km off 123 Km 2] Forest: 1.08 Ha, 0 Locations 0.234 km affected. Proposal submitted on Parivesh portal on 06-08-25.
|  |  |  | LILO of both ckts of Kalavad – Bhogat 400kV D/c line (Twin AL-59) at Jam Khambhaliya PS | [10 empty] | Oct-24 | 40 | 35 | 0 |  |  | 0 | 0 | 0 |  |  |  | Oct-26 | Oct - 26 | Check survey under progress.
|  |  |  | ±400 MVAr STATCOM with 3x125 MVAr MSC & 2x125 MVAr MSR at Jamnagar 400kV Bus section | [10 empty] | Oct-24 | [11 empty] | Oct-26 | Oct - 26 | Engineering under progress
|  |  |  | Potential REZ in Khavda area of Gujarat under Phase-IV (7GW): Part D (PUNE- III TRANSMISSION LIMITED) | [10 empty] | Nov-24 | [11 empty] | Nov-26 | Nov - 26
|  |  |  | Establishment of 2x1500 MVA, 765/400 kV & 3x500 MVA, 400/220 kV Pune- III (GIS) S/s | [10 empty] | Nov-24 | [11 empty] | Nov-26 | Nov - 26 | Pune - III Substation : Land (105 Acre, all Pvt.): Land under posession and Land development work is in progress. 2 Nos Bays at Boisar II: OGA finalization is on hold due to non availablity of sufficeient space to accomodate scope alocated to Pune - III Tranmsiison limited and mismatch in Future scope of Khavda IV C Transmission Limited and present scope of Pune - III Tranmsission Limited.
|  |  |  | Boisar-II – Pune-III 765 kV D/c line (228 km) | [10 empty] | Nov-24 | 456 | 629 | 5 |  |  | 0.01 | 0 | 0 |  |  |  | Nov-26 | Nov - 26 | ROW: Palghar (2), Pune (4). Forest- Area: (~50 Km) : 765 KV Boisar II to Pune III Transmission Line passes through Jawahar, Thane, Alibaugh, and Pune Forest Divisions.
|  |  |  | LILO of Narendra (New) – Pune (GIS) 765 kV D/c line at Pune-III (85.6 km) | [10 empty] | Nov-24 | 171 | 213 | 20 |  |  | 0.09 | 0 | 0 |  |  |  | Nov-26 | Nov - 26 | RoW : Pune (2, Baramati and Purandar Taluka) Forest ( ~28 Ha combined with 400 KV LILO Line) : Under Sec. (Mantralaya - Mumbai) GOM has recomended proposal to RO MoEF&CC ( GOI)
|  |  |  | LILO of Hinjewadi-Koyna 400 kV S/c line at Pune-III (GIS) S/s (8.516 km) | [10 empty] | Nov-24 | 17 | 24 |  |  |  | 0 | 0 | 0 |  |  |  | Nov-26 | Nov - 26 | RoW : Pune (2, Baramati and Purandar Taluka) Forest ( ~28 Ha combined with 765 KV LILO Line ) : Under Sec. (Mantralaya - Mumbai) GOM has recomended proposal to RO MoEF&CC ( GOI)
|  |  |  | Transmission System for Evacuation of Power from REZ in Rajasthan (20GW) under Phase III Part I (SPV Name: ) | [10 empty] | Jan-25 | [11 empty] | Jul-29 | Jul - 29
|  |  |  | Establishment of 6000 MW (4x1500 MW), ± 800 kV (HVDC) [LCC] near Bhadla-III S/s and at Fatehpur(UP) (Bipole-1: 3000 MW) | [10 empty] | Jan-25 | [11 empty] | Jul-29 | Jul - 29 | Land (156 Acre, all Pvt.): All Acquire Engg. Under progress
|  |  |  | Establishment of 6000 MW (4x1500 MW), ± 800 kV (HVDC) [LCC] near Bhadla-III S/s and at Fatehpur(UP) (Bipole-2: 3000 MW) | [10 empty] | Jan-25 | [11 empty] | Jul-29 | Jul - 29 | Land (270 Acre, all Pvt.): – Under acquisition Engg. Under progress
|  |  |  | Establishment of 5x1500 MVA, 765/400 kV ICTs at Fatehpur HVDC | [10 empty] | Jan-25 | [11 empty] | Jul-29 | Jul - 29 | Engg. Under Progress
|  |  |  | ±800 kV HVDC line (Hexa lapwing) between Bhadla (HVDC) and Fatehpur (HVDC) (with DMR) | [10 empty] | Jan-25 | 955 | 2,173 | [5 empty] | 0 |  |  |  | Jul-29 | Jul - 29 | Forest: Rajasthan State (88 Ha), Madhya Pradesh : (35 Ha) :LoA has been issued Forest: Uttar Pradesh : (4 Ha) Land Finalization under progress. Wildlife: Rajasthan State : (7 Ha) LOA has been issued. Wildlife: Madhya Pradesh : (7 Ha)
|  |  |  | 400 kV 2xD/c Bhadla III-Bhadla (HVDC) line (Quad Moose) | [10 empty] | Jan-25 | 2 | 18 |  |  |  | 0 | 0 | 0 |  |  |  | Jul-29 | Jul - 29 | Engg under progress
|  |  |  | LILO of both ckts of 765 kV Varanasi– Kanpur(GIS) D/c line at Fatehpur | [10 empty] | Jan-25 | 47 | 86 |  |  |  | 0 | 0 | 0 |  |  |  | Jul-29 | Jul - 29 | Engg under progress
|  |  |  | Transmission system for supply of power to Green Hydrogen/ Ammonia manufacturing potential in Mundra area of Gujarat under Phase-I: Part B1 scheme (3 GW at Navinal S/s) (SPV: MUNDRA I TRANSMISSION LIMITED) | [10 empty] | Mar-25 | [11 empty] | Mar-28 | Mar - 28
|  |  |  | Augmentation of Transformation capacity at 765/400 kV Navinal(Mundra) S/s (GIS) by 2x1500 MVA ICTs | [10 empty] | Mar-25 | [11 empty] | Mar-28 | Mar - 28 | Enquiry floated to vendor
|  |  |  | Navinal(Mundra) (GIS) – Bhuj 765 kV D/c line | [10 empty] | Mar-25 | 140 | 202 |  |  |  | 0 | 0 | 0 |  |  |  | Mar-28 | Mar - 28 | Enquiry floated to vendor
|  |  |  | ±300MVAr STATCOM along with 2x125MVAr MSC & 1x125MVAr MSR at Navinal(Mundra) (GIS) 400 kV Bus section-I | [10 empty] | Mar-25 | [11 empty] | Mar-28 | Mar - 28 | Enquiry floated to vendor
|  |  |  | ±300MVAr STATCOM along with 2x125MVAr MSC & 1x125MVAr MSR at Navinal(Mundra) (GIS) 400 kV Bus section-II | [10 empty] | Mar-25 | [11 empty] | Mar-28 | Mar - 28 | Enquiry floated to vendor
|  |  |  | Network Expansion scheme in Western Region to cater to Pumped storage potential near Talegaon (Pune) SPV: WRNES Talegaon Power Transmission Limited | [10 empty] | May-25 | [11 empty] | Jan-28 | Jan - 28
|  |  |  | Establishment 2x1500 MVA, 765/400 kV Substation near South of Kalamb with 2x330 MVAr, 765 kV bus reactor and 2x125 MVAr, 420 kV bus reactor. | [10 empty] | May-25 | [11 empty] | Jan-28 | Jan - 28 | Land (350 Acre, all Pvt.): Pending (350 Acre)
|  |  |  | LILO of Pune-III – Boisar-II 765 kV D/C line at South Kalamb S/s with associated bays at South Kalamb S/s. | [10 empty] | May-25 | 2 | 6 |  |  |  | 0 | 0 | 0 |  |  |  | Jan-28 | Jan - 28 | EPC ordering under progress.
|  |  |  | System strengthening in northern region (NRSS XXXVI) along with LILO of Sikar-Neemrana 400 kV D/C line at Babai(RVPNL) (CKM-305) | [10 empty] | Aug-16 | [11 empty] | Dec-19 | Dec - 25 | Project was awarded to Essel infra Project Limited. Due to insolvency project now transferred to M/s Resurgent Power (JV of TATA and ICICI) in March 2022.
|  |  |  | Koteshwar - Rishikesh 400kV D/C line | [10 empty] | Aug-16 | 77 | 102 | 102 | 102 | 77 | 1 | 1 | 1 | 100.00% | 100.00% | 100.00% | Dec-19 | Dec - 25 | Approval for charging of is in progress.
|  |  |  | LILO of one ckt of 400 kV D/C Sikar (PG)-Neemrana (PG) line at Babai. | [10 empty] | Aug-16 |  | 6 |  |  |  | 0 | 0 |  |  |  |  | Dec-16 | Oct - 17 | Line charged in Oct'17
|  |  |  | Babai (RRVPNL) – Bhiwani (PG) 400 kV D/C line | [10 empty] | Aug-16 |  | 304 |  |  |  | 0 | 0 |  |  |  |  | Jun-19 | Oct - 23 | Line charged in Nov'23
|  |  |  | Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-1) (Bikaner Complex): PART-C | [10 empty] | Dec-23 | [11 empty] | Dec-25 | Jun - 26
|  |  |  | Bikaner-III - Neemrana-II 765 kV D/C line (2nd) | [10 empty] | Dec-23 | 692 | 884 | 861 | 418 | 66 | 0.97 | 0.47 | 0.1 | 50.00% | 57.00% | 0.00% | Dec-25 | Jun - 26 | • RoW Foundation (7 Loc) : Bikaner (1), Kotputli (1), Sikar (1), Jhunjhunu (4) in Rajasthan State • Erection (35 Loc) : Bikaner (7), Churu (0), Kotputli (5), Jhunjhunu (14) Sikar (1) in Rajasthan State & Mahendrgarh (8) in Haryana State • RAC Land work stopped for Erection & Stringing: 1 Location (Distt Kotputli) • Forest (10.66 Ha, 5 Locs, 4 ckm) in Haryana: Stage I awaited • Forest (2.22 Ha) in Rajasthan : Stage I Received on 08.08.2025. Payment deposited.
|  |  |  | Eastern Region Expansion Scheme - XXXIX (ERES-XXXIX) | [10 empty] | Nov-24 | [11 empty] | Dec-27 | Dec - 27
|  |  |  | Establishment of new 765/400 kV, 2x1500 MVA GIS S/s at Gopalpur, Odisha | [10 empty] | Nov-24 | [11 empty] | Dec-27 | Dec - 27 | 70 acres of land at Chattrapur for the Gopalpur substation is in progress
|  |  |  | Angul - Gopalpur 765 kV D/c line | [10 empty] | Nov-24 | 399 | 452 | 33 | 0 | 0 | 0.07 | 0 | 0 | 7.00% |  |  | Dec-27 | Dec - 27
|  |  |  | Gopalpur - Gopalpur (OPTCL) 400 kV D/c (Quad) line | [10 empty] | Nov-24 | 51 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00% |  |  | Dec-27 | Dec - 27
|  |  |  | Extension at 765 kV level at Angul (PG) S/s including bus extension in GIS | [10 empty] | Nov-24 | [8 empty] | 0.00% |  |  | Dec-27 | Dec - 27 | Delay in issuance of tree cutting permission for commencement of 765 kV bay extension works in the premises of PGCIL. FM Notice has been issued.
|  |  |  | Extension at 400 kV level at Gopalpur (OPTCL) GIS S/s | [10 empty] | Nov-24 | [8 empty] | 0.00% |  |  | Dec-27 | Dec - 27
|  |  |  | Eastern Region Expansion Scheme ERES-XXXIV : Paradeep | [10 empty] | Nov-24 | [11 empty] | Nov-26 | Nov - 26
|  |  |  | Establishment of Paradeep 765/400 kV, 2x1500 MVA GIS substation | [10 empty] | Nov-24 | [8 empty] | 0.00% |  |  | Nov-26 | Nov - 26 | Handover of identified land parcel at Jagatsinghpur for Paradeep substation accepted by Revenue Divisional Commissioner on 10.10.2025 and has been forwarded for approval from Revenue Secretary & subsequently Higher Level Committee.
|  |  |  | Angul (POWERGRID) – Paradeep 765 kV D/c line | [10 empty] | Nov-24 | 179 | 477 | 92 | 1 | 0 | 0.19 | 0 | 0 | 20.00% |  |  | Nov-26 | Nov - 26 | Delay in receipt of NOC for revised route from the Aviation Research Center (ARC) affecting civil foundation work at 14 Nos. locations.
|  |  |  | Paradeep – Paradeep (OPTCL) 400 kV D/c (Quad) line | [10 empty] | Nov-24 | 13 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00% |  |  | Nov-26 | Nov - 26 | Tower foundation work is planned to commence from December, 2025 onwards.
|  |  |  | Transmission Scheme for Solar Energy Zone in Gadag (1500 MW), Karnataka – Part-A, Phase-II (CKM-100, MVA-1500) (SPV:Gadag-IIA Transmisison Ltd.) | [10 empty] | Nov-22 | [11 empty] | May-24 | Jan - 26
|  |  |  | Gadag Pooling station – Koppal PS 400 kV D/C line | [10 empty] | Nov-22 | 100 | 127 | 110 | 105 | 72.72 | 0.87 | 0.83 | 0.73 |  |  |  | May-24 | Jan - 26 | Foundation RoW (13 loc.): District Koppal, Taluka Kuknoor, village Tadkal (13 Loc) Erection RoW (01 loc.): District Koppal, Taluka Kuknoor , village Tadkal (01 Loc) in Karnataka.
|  |  |  | 400/220 kV, 3x500MVA ICT Augmentation at Gadag | [10 empty] | Nov-22 | [8 empty] | 100.00% | 100.00% | 100.00% | May-24 | Oct - 25 | Work completed.
|  |  |  | Western Region Expansion Scheme XXXIII (WRES-XXXIII): Part C (CKM-10, MVA-4000) | [10 empty] | Feb-24 | [11 empty] | Feb-26 | Jun - 26
|  |  |  | LILO of one circuit of Jabalpur – Orai 765 kV D/c line at Ishanagar 765 kV S/s | [10 empty] | Feb-24 | 35 | 45 | 19 | 1 |  | 0.42 | 0.02 | 0 |  |  |  | Feb-26 | Jun - 26 | Work under progress
|  |  |  | 2x1500 MVA, 765/400 kV and 2x500 MVA, 400/220 kV S/s at Ishanagar (New) | [10 empty] | Feb-24 | [8 empty] | 2.00% |  |  | Feb-26 | Jun - 26 | Land (157.67 Acre): Pending (30 Acre) Govt. (18.46 Acre): Pending (18.46 Acre) in Chhtarpur District, Govt of MP has issued the working permission for Govt. land vide letter dated 16th Oct’25 for 18.46 Acres. Pvt. (139.21 Acre): Pending (7.21Acre). Registration of 132Acres of Pvt. land completed acqusition of balance land is in Progress. Civil works started on ICT, Reactor, SPR & Gantry Towers
|  |  |  | Transmission scheme for evacuation of Power from Dhule 2 GW REZ (CKM-120, MVA-2000) | [10 empty] | Feb-24 | [11 empty] | Feb-26 | Feb - 26
|  |  |  | Dhule PS – Dhule (BDTCL) 400 kV D/c line | [10 empty] | Feb-24 | 131 | 178 | 58 | 25 | 0 | 0.33 | 0.14 | 0 |  |  |  | Feb-26 | Feb - 26 | RoW (10) : Dhule (10). Forest (25.0593 Ha, 16 Loc, 10.80 ckm) in the State of Maharashtra. Stage-I is pending. Part I and Part II filing done, file is forwarded to State Secretary Forest for signing.
|  |  |  | 4x500 MVA, 400/220 kV Pooling Station near Dhule (New) | [10 empty] | Feb-24 | [8 empty] | 39.00% |  |  | Feb-26 | Feb - 26 | Works in progress
|  |  |  | Western Region Network Expansion Scheme in Kallam area of Maharashtra | [10 empty] | Apr-24 | [11 empty] | Oct-25 | Dec - 25
|  |  |  | LILO of both circuits of Parli(M) – Karjat(M)/Lonikand-II (M) 400 kV D/c line (twin moose) at Kallam PS | [10 empty] | Apr-24 | 54 | 41 | 11 | 2 |  | 0.27 | 0.05 | 0 |  |  |  | Oct-25 | Dec - 25 | Substation element commissioned on 28th Sep'25. RoW resolution with support from administration ongoing.
|  |  |  | Ratle HEP (850 MW) & Kiru HEP (624 MW): Part-A (SPV: Ratle Kiru Power Transmission Limited) | [10 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27
|  |  |  | LILO of 400 kV Kishenpur-Dulhasti line at Kishtwar S/s | [10 empty] | Mar-25 | 2 | 14 |  |  |  | 0 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | Check Survey is completed.
|  |  |  | 400 kV Kishenpur-Samba D/C line . | [10 empty] | Mar-25 | 70 | 122 | 10 |  |  | 0.08 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | Foundation Work Started. All statutory proposal and forest diversion proposal submitted
|  |  |  | Bypassing of one ckt of 400 kV Kishtwar – Kishenpur 400kV D/C line at Kishenpur and connecting it with one of the circuit of Kishenpur- Samba 400 kV D/C line, thus forming 400 kV Kishtwar - Samba direct line (one ckt) | [10 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Check Survey completed.
|  |  |  | 400 kV Samba- Jalandhar D/C line | [10 empty] | Mar-25 | 299 | 397 | 61 |  |  | 0.15 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | Foundation Work Started. All statutory proposal and forest diversion proposal submitted
|  |  |  | Bypassing 400 kV Jalandhar – Nakodar line at Jalandhar and connecting it with one of the circuit of Samba-Jalandhar 400 kV D/C line, thus forming 400 kV Samba – Nakodar direct line | [10 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Check Survey completed.
|  |  |  | Transmission system for evacuation of power from RE projects in Rajgarh (1000 MW) SEZ in Madhya Pradesh-Phase II (CKM-120, MVA-1500) | [10 empty] | Feb-24 | [11 empty] | Feb-26 | Mar - 26
|  |  |  | Pachora PS – Ujjain (MPPTCL) 400 kV D/c line | [10 empty] | Feb-24 | 118 | 145 | 134 | 113 | 19.01 | 0.92 | 0.78 | 0.16 |  | 99.00% |  | Feb-26 | Mar - 26 | RoW (12 locs.): Agar Malwa (Fdn-9 Nos & Erection-1 Nos), Ujjain (Stringing-2 Locs) Forest & WLC: Nil Status of receipt of Conductors- 1440/1440 kms -completed Tower material: 3697/3772 MT, Balance tower to be supplied till 15th Dec’25
|  |  |  | 400/220 kV, 3x500 MVA ICT augmentation (4th, 5th and 6th) at Pachora PS. | [10 empty] | Feb-24 | [8 empty] | 87.00% | 96.00% | 55.00% | Feb-26 | Mar - 26 | Land (11 Acre): 100% Govt.: 100% acquire in Ujjain SS. Pvt: 100% at lease for 35 years, SS Agar Malwa, Dist.- Agar Malwa -Completed
|  |  |  | Transmission scheme for integration of Tumkur-II REZ in Karnataka | [10 empty] | Sep-24 | [11 empty] | Sep-26 | Sep - 26
|  |  |  | Establishment of 400/220 kV 4x500 MVA Pooling Station near Tumkur, Karnatak | [10 empty] | Sep-24 | [8 empty] | 40.00% | 0.00% | 0.00% | Sep-26 | Sep - 26 | Land: 70 Acre acquired. Status of receipt of Transformers/Reactors: Expected by 30.04.2026
|  |  |  | Tumkur-II – Tumkur (Pavagada) line 400 kV (Quad ACSR moose) D/c line. | [10 empty] | Sep-24 | 53 | 73 | 15 | 0 | 0 | 0.21 | 0 | 0 |  |  |  | Sep-26 | Sep - 26 | Status of receipt of conductors/Tower material: Conductor (680 Kms/ 680 Kms ). Tower material: 40/1672 MT;balance expected by 31.01.2026.
|  |  |  | Transmission Scheme for integration of Bijapur REZ in Karnataka (SPV: Bijapur REZ Transmission Limited) | [10 empty] | Jan-25 | [11 empty] | Jan-27 | Jan - 27
|  |  |  | Establishment of 400/220 kV, 5x500 MVA Pooling Station near Bijapur (Vijayapura), Karnataka | [10 empty] | Jan-25 | [8 empty] | 0.00% | 0.00% | 0.00% | Jan-27 | Jan - 27 | Land (65 Acre): Pvt. (65 Acre): 100% acquisition done. Status of receipt of Transformers/ Reactors: Expected by 31.10.2026
|  |  |  | Bijapur PS – Raichur New 400kV (Quad ACSR moose) D/c line | [10 empty] | Jan-25 | 276 | 360 | 21 | 0 | 0 | 0.06 | 0 | 0 |  |  |  | Jan-27 | Jan - 27 | Status of receipt of conductors/Tower material: Expected by 30.05.2026
|  |  |  | Transmission system for Evacuation of Power from RE Projects in Rajgarh (1500 MW) SEZ in Madhya Pradesh-Phase III and Evacuation of Power from RE Projects in Neemuch (1000 MW) SEZ in Madhya Pradesh-Phase II (SPV:M/s G R Infra Projects Limited) | [10 empty] | Sep-25 | [11 empty] | Sep-27 | Sep - 27
|  |  |  | Creation of New 220 kV Bus Section with 220 kV Bus Sectionaliser and 400/220 kV, 3x500 MVA ICT augmentation at Pachora PS. | [10 empty] | Sep-25 | [8 empty] | 0.00% | 0.00% | 0.00% | Sep-27 | Sep - 27 | Land (11.357 Acre - Private): 3.357 Acquired
|  |  |  | Pachora PS – Rajgarh(PG) 400 kV D/c line | [10 empty] | Sep-25 | 185 |  | 0 | 0 | 0 |  |  | 0 |  |  |  | Sep-27 | Sep - 27 | Eco Sensitive Zone: 39.1 Ha (Estimated)
|  |  |  | Creation of New 220 kV Bus Section-II at Neemuch PS with Augmentation of transformation capacity by 3x500 MVA, 400/220 kV ICTs at Neemuch S/s. | [10 empty] | Sep-25 | [8 empty] | 0.00% | 0.00% | 0.00% | Sep-27 | Sep - 27
|  |  |  | Neemuch PS – Pachora PS 400 kV D/c line. | [10 empty] | Sep-25 | 221 |  | 0 | 0 | 0 |  |  | 0 |  |  |  | Sep-27 | Sep - 27 | Forest: 79.80 Ha (Estimated)
|  |  |  | Establishment of 2x500 MVA, 400/220 kV S/s at Handiya. | [10 empty] | Sep-25 | [8 empty] | 0.00% | 0.00% | 0.00% | Sep-27 | Sep - 27 | Land (40 Acre): Land acquisition under process.
|  |  |  | Pachora PS – Handiya 400 kV D/c line. | [10 empty] | Sep-25 | 214 |  | 0 | 0 | 0 |  |  | 0 |  |  |  | Sep-27 | Sep - 27 | Forest: 24.01 Ha (Estimated)
|  |  |  | LILO of Khandwa (PG) – Itarsi (PG) 400 kV D/c line at Handiya S/s. | [10 empty] | Sep-25 | 30 |  | 0 | 0 | 0 |  |  | 0 |  |  |  | Sep-27 | Sep - 27
|  |  |  | 400 kV D/c Khandukhal (Srinagar) – Rampura (Kashipur) line (Twin HTLS) (KRTL) (CKM-388) | [10 empty] | Oct-22 | [11 empty] | Sep-24 | Dec - 25
|  |  |  | 400 kV D/c Khandukhal (Srinagar) – Rampura (Kashipur) line | [10 empty] | Oct-22 | 384 | 498 | 442 | 283 | 24.88 | 0.89 | 0.57 | 0.06 |  |  |  | Sep-24 | Dec - 25 | RoW in Uttarakhand (56 locs.): Pouri Gehwal (52 locs): Udam singh nagar (4 Locs) Forest (191.31Ha, 73 locs., 50 ckm) in Uttarakhand State : Stage I approval granted on 17.02.2025. Estimation received on 11.03.2025 and payment is under process. Status of receipt of conductors/Tower material: All Tower material supplies been completed. Conductor Order given on Sep’2024. For Substation Bay Extension Work: Land Lease / Rent agreement to be finalized by PTCUL for Space to construct Bay Extension at Rampura & Khandhukal Substations.
|  |  |  | Transmission system for evacuation of power from REZ in Rajasthan (20 GW) under phase III –Part A3 (SPV: Fatehgarh-III Transmission Ltd.) | [10 empty] | Aug-23 | [11 empty] | Feb-25 | Jun - 26
|  |  |  | Fatehgarh 3- Bhadla-3 400kV D/C line (Quad) line | [10 empty] | Aug-23 | 446 | 584 | 485 | 389 | 112.14 | 0.83 | 0.67 | 0.25 | 0.00% |  |  | Feb-25 | Jun - 26 | RoW (80 loc.): Barmer (3), Jaisalmer (38), Phalodi (39) in Rajasthan State Forest (22.2778, 9.686 ckm) in Rajasthan: Stage I Pending Applied on 31.07.2024 Curr. Status : Proposal pending at REC.
|  |  |  | Transmission system for evacuation of power from REZ in Rajasthan (20 GW) under phase III –Part A1 (SPV: Fatehgarh-IV Transmission Ltd.) | [10 empty] | Aug-23 | [11 empty] | Feb-25 | Dec - 25
|  |  |  | 5x500MVA, 400/220kV pooling station at Fatehgarh-4 | [10 empty] | Aug-23 | [8 empty] | 95.00% | 99.50% | 100.00% | Feb-25 | Dec - 25 | All land acquired (134.4 Acre, All Private)
|  |  |  | Fatehgarh-4 PS- Fatehgarh-3 PS 400kV D/c | [10 empty] | Aug-23 | 42 | 61 | 61 | 61 | 42.68 | 1 | 1 | 1.02 | 0.00% |  |  | Feb-25 | Dec - 25 | Forest (1.6054 Ha, 5 locs, 0.7 ckm ) in Rajasthan Stage-I In-principle approval is granted on 20/06/2025. Stage-II Final Approval granted in 10/09/2025 Ckt I charged on 29.11.2025, Ckt II charged on 29.11.2025
|  |  |  | Western Region Expansion Scheme XXXIII (WRES-XXXIII): Part B | [10 empty] | Feb-24 |  |  |  |  | 0 | [6 empty] | Feb-26 | Apr - 26
|  |  |  | 2x1500 MVA, 765/400 kV and 2x500 MVA, 400/220 kV S/s at Karera (near Datiya) | [10 empty] | Feb-24 | [11 empty] | Feb-26 | Apr - 26 | Land (165.5): Pending (90 Acre) Govt. (54.215): All Pending Pvt. (111.28): Pending (35.985 Acre) For Govt. Land, DC Datia has allocated Govt. Land to Energy Dept. M.P as per M.P Govt Policy for further leasing to TSP, WP given by Govt. of MP , Energy Dept. on 16.10.2025
|  |  |  | LILO of Satna-Gwalior 765 kV S/c line at Karera | [10 empty] | Feb-24 | 85 | 117 | 89 | 15 | 0 | 0.76 | 0.13 | 0 | 0.00% |  |  | Feb-26 | Apr - 26
|  |  |  | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part -2 : 5.5 GW) (Jaisalmer / Barmer Complex): Part-A | [10 empty] | Aug-24 | [11 empty] | Aug-26 | Aug - 26
|  |  |  | Construction of Section-2 with 4x1500 MVA, 765/400 kV and 5x500 MVA, 400/220 kV ICTs at Fatehgarh-IV PS | [10 empty] | Aug-24 | [8 empty] | 38.00% | 40.00% |  | Aug-26 | Aug - 26 | Land required: Included with Fatehgarh IV PS land
|  |  |  | Fatehgarh-IV PS (Section-2) - Bhinmal (PG) 400 kV D/C line (Twin HTLS) | [10 empty] | Aug-24 | 369 | 512 | 234 | 137 | 0 | 0.46 | 0.27 | 0 |  |  |  | Aug-26 | Aug - 26 | RoW: Bytu ( 15 LOC ), Bagoda ( 11 LOC) , Sayla ( 20 LOC) , Sindhari ( 13 Loc) Forest (0.7636, .332ckm) in Rajasthan) Stage I Pending Applied on 12.04.2025 Current Status : Pending at DFO/CF/Nodal Officer/Jalore
|  |  |  | LILO of both ckts of 765 kV Fatehgarh-III - Beawar D/C line at Fatehgarh-IV PS (Section-2) | [10 empty] | Aug-24 | 17 | 46 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | Aug-26 | Aug - 26 | LILO proposal approved by Beawar Transmission Limited on 3rd Oct. 2025
|  |  |  | Transmission system for evacuation of power from RE projects in Solapur (1500 MW) SEZ in Maharashtra | [10 empty] | Mar-24 | [11 empty] | Mar-26 | Jun - 26
|  |  |  | Establishment of 400/220 kV, 4x500 MVA ICTs at Solapur PS alongwith 2x125 MVAR, 420 kV Bus Reactors. | [10 empty] | Mar-24 | [8 empty] | 20.00% | 0.00% |  | Mar-26 | Mar - 26 | Substation Land ( 80 Acres) : Private land acquired (60.7 Acres).
|  |  |  | Solapur PS – Solapur (PG) 400 kV D/c line | [10 empty] | Mar-24 | 80 | 111 | 71 | 39 |  | 0.64 | 0.35 | 0 |  |  |  | Mar-26 | Jun - 26 | RoW (13 locs) : Dharashiv (13). Applications submitted to DC (Dharashiv Dist.) for all13 locations for resolution under Section 16(1). Orders awaited.
|  |  |  | Transmission Scheme for North Eastern Region Expansion Scheme-XVI (NERES-XVI) | [10 empty] | Jun-24 |  | 100 |  |  |  | 0 | 0 |  |  |  |  | Nov-26 | Nov - 26
|  |  |  | Gogamukh (ISTS) (Assam) – Gerukamukh (Arunachal Pradesh) 132 kV D/c line | [10 empty] | Jun-24 | 58 | [6 empty] | 0 |  |  |  | Nov-26 | Nov - 26 | Route Alignment completed. Design and engineering under process.
|  |  |  | LILO of both circuits of Lower Subansiri - Biswanath Chariali 400 kV D/c line at Gogamukh S/s | [10 empty] | Jun-24 | 31 | [6 empty] | 0 |  |  |  | Nov-26 | Nov - 26 | Route Alignment completed. Design and engineering under process.
|  |  |  | 400/220/132 kV Gogamukh S/s (2x500 MVA, 400/220 kV ICT; 2x200 MVA, 220/132 kV ICT) | [10 empty] | Jun-24 | [11 empty] | Nov-26 | Nov - 26 | Land (58.04 Acre) :Land Parcel finalized and further pursuing with DC, ADC & Circle office of Dhemaji District for acquisition of the Gogamukh Sub Station land. Gogamukh SS Land Acquisition will be completed by Dec-2025.
|  |  |  | Transmission System for North Eastern Region Generation Scheme- I (NERGS-I) | [10 empty] | Jul-24 | [11 empty] | Dec-26 | Dec - 26
|  |  |  | 400 kV Switching Station (to be upgraded to 400/220 kV in future) at Bokajan (Assam) | [10 empty] | Jul-24 | [11 empty] | Dec-26 | Dec - 26 | The project has been suspended.
|  |  |  | LILO of both circuits of 400 kV D/c Misa (PG) to New Mariani (PG) line at Bokajan S/s | [10 empty] | Jul-24 | 24 | [6 empty] | 0 |  |  |  | Dec-26 | Dec - 26 | The project has been suspended.
|  |  |  | Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-4: 3.5 GW): Part B | [10 empty] | Dec-24 | [11 empty] | Dec-26 | Dec - 26
|  |  |  | Establishment of 765/400 kV, 2x1500 MVA S/s at Merta-II Substation | [10 empty] | Dec-24 |  |  | 19 | 0 | 0 |  |  |  | 2.20% | 0.00% | 0.00% | Dec-26 | Dec - 26 | Land (165 Acre)- Acquisition In progress Order Placed for Transformers/Reactors.
|  |  |  | Merta II- Barmer I PS 765 kV D/c line | [10 empty] | Dec-24 | 686 | 864 | 359 | 19 | 0 | 0.42 | 0.02 | 0 | 0.00% | 0.00% | 0.00% | Dec-26 | Dec - 26 | RoW (84 locs) in Rajasthan: Barmer (13), Jodhpur (71) Forest Clearance - Detailed survey in progress.
|  |  |  | Merta II – Beawar 400 kV D/c line (Quad). | [10 empty] | Dec-24 | 143 | 186 | 45 | 0 | 0 | 0.24 | 0 | 0 | 0.00% | 0.00% | 0.00% | Dec-26 | Dec - 26 | RoW (46 Locs) in Rajasthan: Beawar (10) , Nagaur (36) Forest (0.1646 Ha, 2 locs) in Rajasthan: Forest Proposal submitted on 29.05.2025.
|  |  |  | Merta II – Dausa 765 kV D/c line | [10 empty] | Dec-24 | 494 | 619 | 336 | 1 | 0 | 0.54 | 0 | 0 | 0.00% | 0.00% | 0.00% | Dec-26 | Dec - 26 | RoW (42 Locs) in Rajasthan: Ajmer (11) , Jaipur (12) , Dausa(2) , Didwana (17) Forest Clearance - Forest (1.3636 Ha, 5 locs) Forest proposal submitted on 29.05.2025.
|  |  |  | Transmission System for evacuation of RE power from Raghanesda area of Gujarat – 3GW under Phase-I (SPV: Raghanesda RE Transmission Limited) | [10 empty] | Jul-25 | [11 empty] | Oct-27 | Oct - 27
|  |  |  | Establishment 3x1500 MVA, 765/400 kV Substation near Raghanesda (GIS) with 2x330 MVAr, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor | [10 empty] | Jul-25 | [11 empty] | Oct-27 | Oct - 27 | Land is identification in progress Order of Transformer & Reactors are placed. Order of GIS is placed
|  |  |  | Raghanesda (GIS) – Banaskantha (PG) 765 kV D/c line | [10 empty] | Jul-25 | 155 | [6 empty] | 0 |  |  |  | Oct-27 | Oct - 27 | Detailed Survey Work completed.
|  |  |  | 2 Nos. 765 kV line bays at Banaskantha (PG) S/s | [10 empty] | Jul-25 | [11 empty] | Oct-27 | Oct - 27
|  |  |  | Augmentation of transformation capacity at 765/400 kV Lakadia S/s in Gujarat - Part B | [10 empty] | Feb-25 | [8 empty] | 32.72% | 0.00% | 0.00% | Jun-27 | Jun - 27
|  |  |  | Augmentation by 2x500 MVA, 400/220 kV ICTs (3rd & 4th) at Lakadia PS | [10 empty] | Feb-25 | [8 empty] | 36.41% | 0.00% | 0.00% | Aug-26 | Aug - 26 | Land: AESL to provide encumbrance-free land, pending due to an existing 400kV double-circuit Lakadia–Jam Khambaliya transmission line passing over the Bays 4, 5, and 6 at 220kV Bus Section-I. CEA (PSPM) convened a meeting on 08-Sep-25 with RIL, AESL, O2 Power, and CTU, directing CTU to provide technical solution. Transformer Supply: Ordered on 20-Feb-25. Expected by Mar’26.
|  |  |  | Augmentation by 2x500 MVA, 400/220 kV ICTs (5th & 6th) at Lakadia PS on new 220 kV Bus Section-II | [10 empty] | Feb-25 | [8 empty] | 36.85% | 0.00% | 0.00% | Aug-26 | Aug - 26 | Land: AESL to provide encumbrance-free land, pending due to an existing 400kV double-circuit Lakadia–Jam Khambaliya transmission line passing over the Bays 4, 5, and 6 at 220kV Bus Section-I. CEA (PSPM) convened a meeting on 08-Sep-25 with RIL, AESL, O2 Power, and CTU, directing CTU to provide technical solution. Transformer Supply: Ordered on 20-Feb-25. Expected by Mar’26.
|  |  |  | Augmentation by 500 MVA, 400/220 kV ICTs (7th) at Lakadia PS on new 220 kV Bus Section-II | [10 empty] | Feb-25 | [8 empty] | 35.86% | 0.00% | 0.00% | Dec-26 | Dec - 26 | Land: WRSS XXI (A) Transco Limited, to provide the required land for the Lakadia B Power Transmission Limited project. Transformer Supply: Ordered on 20-Feb-25. Expected by Oct’26.
|  |  |  | Augmentation by 500 MVA, 400/220 kV ICTs (8th) at Lakadia PS on new 220 kV Bus Section-II | [10 empty] | Feb-25 | [8 empty] | 39.10% | 0.00% | 0.00% | Jun-27 | Jun - 27 | Land: WRSS XXI (A) Transco Limited, to provide the required land for the Lakadia B Power Transmission Limited project. Transformer Supply: Ordered on 20-Feb-25. Expected by Nov’26.
|  |  |  | Augmentation of transformation capacity at Lakadia PS by 1x1500 MVA, 765/400 kV ICT (3rd) | [10 empty] | Feb-25 | [8 empty] | 32.90% | 0.00% | 0.00% | Aug-26 | Aug - 26 | Land: WRSS XXI (A) Transco Limited, to provide the required land for the Lakadia B Power Transmission Limited project. Transformer Supply: Transformer (03 nos) ordered on 21-Feb-25 & expected by Mar’26; Reactor (03 nos) ordered on 21-Feb-25 & expected by Jun’26.
|  |  |  | Eastern Region Generation Scheme-I (ERGS-I) (SPV: Angul Sundargarh Transmission Limited) | [10 empty] | Jul-25 | [11 empty] | Mar-28 | Mar - 28
|  |  |  | LILO of both circuits of Angul – Sundargarh (Jharsuguda) 765 kV 2xS/c lines at NLC-Talabira generation switchyard | [10 empty] | Jul-25 | 100 | [6 empty] | 0 |  |  |  | Mar-28 | Mar - 28
|  |  |  | Transmission System for Integration of Ananthapuram-II REZ- Phase-II (3 GW) (SPV: Ananthapuram II Power Transmission | [10 empty] | Oct-25 | [11 empty] | Apr-28 | Apr - 28
|  |  |  | Augmentation of Ananthapuram-II PS by 400/220 kV, 1x500 MVA ICT | [22 empty] | Oct-27 | Oct - 27
|  |  |  | Augmentation of Ananthapuram-II PS by 765/400 kV, 2x1500 MVA and 400/220 kV, 6x500 MVA ICTs | [22 empty] | Apr-28 | Apr - 28
|  |  |  | Establishment of 3x1500 MVA, 765/400 kV CN’Halli Station with 2x330 MVAr (765 kV) bus reactors | [22 empty] | Apr-28 | Apr - 28
|  |  |  | Ananthapuram-II PS – CN’Halli 765 kV D/c line with 330 MVAr SLR at Ananthapuram-II end on both circuits | [11 empty] | 363 | [6 empty] | 0 |  |  |  | Apr-28 | Apr - 28
|  |  |  | LILO of one circuit of Talaguppa - Neelmangala 400 kV D/c line at CN’Halli | [11 empty] | 19 | [6 empty] | 0 |  |  |  | Apr-28 | Apr - 28
|  |  |  | LILO at CN’Halli of already LILOed section of one circuit of Talaguppa - Neelmangala 400 kV line at Hassan | [11 empty] | 36 | [6 empty] | 0 |  |  |  | Apr-28 | Apr - 28
Formulas:
Tentative SCOD = DATE(YEAR(TODAY()), MONTH(TODAY()+[Execution Timeline]), DAY(TODAY()))