## Data Sources
SN | Connectivity Application Status | Frequency
1 | CTU ¦ Central Transmission Utility of India Limited CMETS (Agenda and Minutes: Region wise) link:https://ctuil.in/ists-consultation-meeting | Daily
2 | CTU ¦ Central Transmission Utility of India Limited JCC (Region wise as per document release Agenda/Minutes) link https://ctuil.in/ists-joint-coordination-meeting | Daily
3 | Status of effectiveness of connectivity granted to RE generators (Effective date of connectivity wise) link | Daily
4 | CTU ¦ Central Transmission Utility of India Limited Re-allocation meetings (Agenda and Minutes: Region wise) link | Weekly
5 | CTU ¦ Central Transmission Utility of India Limited Bidding Calendar link | Weekly
6 | Transmission Reports - Central Electricity Authority TBCB report from CEA transmission (monthly comparison) link | Daily
7 | CTUIL (OPEN ACCESS) (Compliance of Land and Financial Closure) link | Daily
8 | Monitoring of Connectivity (all 3 Annexures and monthly document release comparison) link | Daily
SN | Substation and Transmission Tracking | Frequency
9 | (Status of allocation of bays at ISTS substations for connectivity grantees, Connectivity margins at existing ISTS (non RE) substations for future RE integration and Connectivity Margin in ISTS RE Substations available by Mar-2030) link | Weekly
10a | Potential RE Zones Report link | Weekly
10b | NCT (Agenda and Minutes Summary and Comparison of Scheme wise elements) link Link: https://cea.nic.in/comm-trans/national-committee-on-transmission/?lang=en | Daily
10c | Tender websites PFCCL and RECPDCL mentioned in NCT under TBCB and RTM (RFP and other tender documents in folders; Bidding Status: Bid Submission Date or Deadline, Commissioning Timeline and Expected SCOD) RECPDCL: https://www.recpdcl.in/rectpcltender PFCCL:https://www.pfcclindia.com/tender-new.php PFCCL Notice: https://www.pfcclindia.com/notice.php?AM1 | Daily
10d | CEA monthly transmission reports: (track status for tender elements timelines from 1) CEA Monthly report for actual physical progress of elements and 2) Actual COD from completion report) CEA https://cea.nic.in/transmission-reports/?lang=en | Daily
10e | Map of the above Section 2 data to be created for review and edit by users
11 | Bulk Consumers and Green Hydrogen link | Weekly
12 | CEA: transmission schemes, substations (transformation capacity) and transmission lines published each month on CEA monthly reports section under transmission. | Weekly
13 | Global Wind Atlas (India Map Visualization) | Weekly
14 | Open Infrastructure Map (India Map Visualization) | Weekly

## Data to be captured
| Sr.no. | Region | State | Substation | Coordinates | Name of Developers | Group | GNA/ST II Application ID | LTA Application ID | Application ID under Enhancement 5.2 or revision | CMETS GNA Approved | CMETS LTA Approved | CMETS GNA Meeting Date | CMETS LTA Meeting Date | Type | Application Quantum (MW)(ST II) | Granted Quantum GNA/LTA(MW) | Installed/Break-up Capacity (MW) |  |  | Battery |  |  | PSP |  |  | Commissioned |  | Application/Submission Date | Mode(Criteria for applying) | Applied Start of Connectivity sought by developer date( start date of connectivity as per the application) | GNA Operationalization Date | GNA Operationalization (Yes/No) | Date from which additional capacity is to be added | Nature of Applicant | Status of application(Withdrawn / granted. Revoked.) | Voltage level | Bay No | CTS Element Unique Code | ATS Element Unique Code | DTL Element Code Unique | Date of Last Element Unique Code | In-principle Grant | Final Grant | In case of Land BG Conversion Date | Remarks
[18 empty] | Solar | Wind | Hybrid | MWh | Injection (MW) | Drawl (MW) | MWh | Injection (MW) | Drawl (MW) | TGNA | GNA
Data Scoure (Sl. No.(s) 1,2,3,4,7,8,9,11)

## RE Potential
| Region | State | District | Complex | S/s | Location (Village/Tehsil) | Solar | Wind | Hybrid | Others (CTUIL) | RE Potential (GW) | Installed Capacity | U/c & granted Capacity | Transmission Scheme | Complex | Remarks
|  |  | Bikaner |  |  | Bikaner | 1.85
Data Scoure (Sl. No.(s)9, 10a, ) |  |  | Bikaner |  |  | Bikaner | 2.95
|  |  | Kurnool |  |  | Kurnool | 5.5
|  |  | Anantapur |  |  | Anantapur | 2.5
|  |  | Gadag |  |  | Gadag | 2.5
|  |  | Koppal |  |  | Koppal | 2.5
|  | Rajasthan |  |  |  |  | 15 | 1 |  |  | 60 |  |  |  |  | 45 GW (15 GW Wind & 30 GW solar in GIB Zone)
|  | Andhra Pradesh |  |  |  |  | 18 | 2 |  |  | 33
|  | Karnataka |  |  |  |  | 8 | 3 |  |  | 9
|  | Tamil Nadu |  |  |  |  | 5 | 4 |  |  | 5 |  |  |  |  | Offshore wind
|  | Telangana |  |  |  |  | 3 | 5 |  |  | 10
|  | Madhya Pradesh |  |  |  |  | 2 | 6 |  |  | 6
|  | Gujarat |  |  |  |  | 5 | 7 |  |  | 5 |  |  |  |  | Offshore wind
|  | Maharashtra |  |  |  |  | 2 | 8 |  |  | 5.5
|  | Rajasthan |  |  |  |  | 30 | 75
|  | Andhra Pradesh |  |  |  |  | 10 | 51 |  |  | 10
|  | Karnataka |  |  |  |  | 2 | 17 |  |  | 2
|  | Tamil Nadu |  |  |  |  | 5 | 5
|  | Telangana |  |  |  |  | 1 | 13 |  |  | 2.5
|  | Madhya Pradesh |  |  |  |  | 2 | 8
|  | Gujarat |  |  |  |  | 5 | 5
|  | Maharashtra |  |  |  |  | 1 | 7.5 |  |  | 1
|  | Rajasthan |  |  |  |  | 60 | 15 |  |  | 67.5
Gujarat
Maharashtra
|  | Maharashtra |  |  |  |  | 5.5 | 2 |  |  | 6.5 |  |  |  |  | 5.4
Madhya Pradesh
|  | Madhya Pradesh |  |  |  |  | 6 | 2 |  |  | 8
Andhra Pradesh
|  | Andhra Pradesh |  |  |  |  | 33 | 18 |  |  | 41
Karnataka
|  | Karnataka |  |  |  |  | 9 | 8 |  |  | 14
Telangana
|  | Telangana |  |  |  |  | 10 | 3 |  |  | 11.5 |  |  |  |  | 8.5
Tamil Nadu
|  | Telangana | Bikaner |  |  | Bikaner | 8 | 8.1 |  |  | 400
|  | Telangana | Bikaner |  |  | Bikaner | 400
|  | Telangana | Bikaner |  |  | Bikaner | 300
|  | Telangana | Bikaner |  |  | Bikaner | 9 | 8.1 |  |  | 400
|  | Telangana | Gadag |  |  | Gadag | 12 | 1000 |  |  | 400
|  | Telangana | Gadag |  |  | Gadag | 400
|  | Telangana | Koppal |  |  | Koppal | 13 | 2500 |  |  | 400
|  | Telangana | Koppal |  |  | Koppal | 400
|  | Telangana | Koppal |  |  | Koppal | 2
|  | Telangana | Gadag |  |  | Gadag | 11 | 1500 |  |  | 400
|  | Telangana | Kurnool |  |  | Kurnool | 1 | 2500 |  |  | 400
|  | Telangana | Kurnool |  |  | Kurnool | 400
|  | Telangana | Anantapur |  |  | Anantapur | 400
|  | Telangana | Kurnool |  |  | Kurnool | 3 | 3000 |  |  | 765
|  | Telangana | Kurnool |  |  | Kurnool | 765
|  | Rajasthan |  |  |  |  | 7 | 0 |  |  | 7
|  | Rajasthan |  |  |  |  | 6 | 6 |  |  | 12
|  | Rajasthan |  |  |  |  | 6 | 4 |  |  | 10
|  | Rajasthan |  |  |  |  | 3 | 0 |  |  | 3
|  | Rajasthan |  |  |  |  | 2 | 0 |  |  | 2
|  | Rajasthan |  |  |  |  | 3 | 2 |  |  | 5
|  | Rajasthan |  |  |  |  | 4 | 3 |  |  | 7
|  | Rajasthan |  |  |  |  | 6 | 0 |  |  | 6
|  | Rajasthan |  |  |  |  | 5 | 0 |  |  | 5
|  | Maharashtra |  |  |  |  | 1 | 0 |  |  | 1
|  | Maharashtra |  |  |  |  | 1 | 1 |  |  | 2
|  | Maharashtra |  |  |  |  | 2.5 | 2.5 |  |  | 0 |  |  |  |  | 2.5
|  | Gujarat |  |  |  |  | 5 | 5 |  |  | 2
|  | Telangana |  |  |  |  | 2.5 | 1 |  |  | 3.5
|  | Telangana |  |  |  |  | 2.5 | 0 |  |  | 2.5 |  |  |  |  | 0.5
|  | Karnataka |  |  |  |  | 2 | 2 |  |  | 4
|  | Karnataka |  |  |  |  | 0 | 2 |  |  | 2
|  | Karnataka |  |  |  |  | 1.5 | 0 |  |  | 1.5
|  | Tamil Nadu |  |  |  |  | 5 | 5 |  |  | 0
|  | Tamil Nadu |  | Bikaner-II | Bikaner-II |  | 7 | 0 |  | 0 | 7
|  | Tamil Nadu |  | Bikaner-III | Bikaner-III |  | 7 | 0 |  | 0 | 7
|  | Tamil Nadu |  | Fatehgarh-IV | Fatehgarh-IV |  | 6 | 6 |  | 2 | 12
|  | Tamil Nadu |  | Ramgarh | Ramgarh |  | 6 | 4 |  | 2 | 10
|  | Tamil Nadu |  | Jalore | Jalore |  | 3 | 0 |  | 0 | 3
|  | Tamil Nadu |  | Sanchore | Sanchore |  | 3 | 0 |  | 0 | 3
|  | Tamil Nadu |  | Sirohi | Sirohi |  | 3 | 0 |  | 0 | 3
|  | Tamil Nadu |  | Pali | Pali |  | 3 | 0 |  | 0 | 3
|  | Tamil Nadu |  | Ajmer | Ajmer |  | 2 | 0 |  | 0 | 2
|  | Tamil Nadu |  | Nagaur | Nagaur |  | 2 | 0 |  | 0 | 2
|  | Tamil Nadu |  | Bhadla-IV | Bhadla-IV |  | 3 | 2 |  | 0 | 5
|  | Tamil Nadu |  | Barmer-I | Barmer-I |  | 4 | 3 |  | 2 | 7
|  | Tamil Nadu |  | Barmer-II | Barmer-II |  | 6 | 0 |  | 0 | 6
|  | Tamil Nadu |  | Jaisalmer/ Jodhpur (Intra-State) | Jaisalmer/ Jodhpur (Intra-State) |  | 5 | 0 |  | 0 | 5
|  | Tamil Nadu |  | Total | Total |  | 60 | 15 |  | 6 | 75
|  | Tamil Nadu |  | Jaisalmer/ Jodhpur (Intra-State) | Jaisalmer/ Jodhpur (Intra-State) |  | 5 | 0 |  | 0 | 5
|  | Tamil Nadu |  | Jaisalmer/ Jodhpur (Intra-State) | Jaisalmer/ Jodhpur (Intra-State) |  | 5 | 0 |  | 0 | 5
|  | Tamil Nadu |  | Kurnool-IV | Kurnool-IV |  | 7.5 | 4 |  | 3 | 11.5
|  | Tamil Nadu |  | Kurnool-V | Kurnool-V |  | 7.5 | 4 |  | 3 | 11.5
|  | Tamil Nadu |  | Anantapur | Anantapur |  | 2 | 2 |  | 1 | 4
|  | Tamil Nadu |  | Anantapur-II | Anantapur-II |  | 8 | 8 |  | 4 | 16
|  | Tamil Nadu |  | Kadapa-II | Kadapa-II |  | 8 | 0 |  | 3 | 8
|  | Tamil Nadu |  | Total | Total |  | 33 | 18 |  | 14 | 51
|  | Tamil Nadu |  | Koppal-II | Koppal-II |  | 2 | 2 |  | 1 | 4
|  | Tamil Nadu |  | Gadag-II | Gadag-II |  | 2 | 2 |  | 1 | 4
|  | Tamil Nadu |  | Devanagere/ Chitragurga | Devanagere/ Chitragurga |  | 2 | 2 |  | 1 | 4
|  | Tamil Nadu |  | Bijapur | Bijapur |  | 0 | 2 |  | 0 | 2
|  | Tamil Nadu |  | Bellary | Bellary |  | 1.5 | 0 |  | 0 | 1.5
|  | Tamil Nadu |  | Tumkur-II | Tumkur-II |  | 1.5 | 0 |  | 0 | 1.5
|  | Tamil Nadu |  | Total | Total |  | 9 | 8 |  | 3 | 17
|  | Tamil Nadu |  | Nizamabad-II | Nizamabad-II |  | 2.5 | 1 |  | 1 | 3.5
|  | Tamil Nadu |  | Medak | Medak |  | 2.5 | 1 |  | 1 | 3.5
|  | Tamil Nadu |  | Rangareddy | Rangareddy |  | 2.5 | 1 |  | 1 | 3.5
|  | Tamil Nadu |  | Karimnagar | Karimnagar |  | 2.5 | 0 |  | 0 | 2.5
|  | Tamil Nadu |  | Total | Total |  | 10 | 3 |  | 3 | 13
|  | Tamil Nadu |  | Sl. No. | Sl. No.

## Margin
| Sl.No. | State | Region | Pooling S/s | Additional Information of Pooling S/s | Timelines | RE Potential |  |  | Expected CoD of Pooling Station | Connectivity Granted/ Agreed |  |  | Connectivity Granted/ Agreed |  |  | Margin for Connectivity |  |  | Additional Margin for Connectivity requiring ICT Augmentation / additional Tr. System |  |  | Effectiveness of GNA for Capacity mentioned under "Margin for Connectivity
[7 empty] | RE Potential (MW) [A] | BESS (MW) [B] | S/s Evacuation Capacity (RE Potential - BESS [AB]) |  | 200 kV | 400 kV | Total (MW) | 200 kV | 400 kV | Total (MW) | 200 kV | 400 kV | Total (MW) | 200 kV | 400 kV | Total (MW)
Existing PS
Jul-25 to Dec-25
Jan-26 to Jun-26
Jul-26 to Dec-31
Beyond Dec-25
Data Scoure (Sl. No.(s)9)

## Non RE proposed RE Integration
State | Name of Station | Capacity (MVA) | Capacity Allocated (MW) | Margin Existing 220kV (MW) | Margin Existing 400kV (MW) | Line Bays 220kV | Line Bays 400kV | Margin with ICT 220kV (MW) | Margin with ICT 400kV (MW) | Line Bays with ICT 220kV | Line Bays with ICT 400kV | No. of Transformers Required | Remarks

## Transformation Capacity
| S.No. | Region | State | Substation | Voltage level (kV) | Existing Capacity (MVA) | Under Implementation Capacity (MVA) | Planned Capacity (MVA)
Data Scoure (Sl. No.(s)9)

## Element Status
Element Code | Inter/Intra Tx. Element | Transmission Scheme | Transmission Scope | MVA | Status | Approval of Elements in which NCT | Mode (TBCB/RTM) | Tender Issuing Authority | Date of tender issuance | Date of Bid Submission | Execution Timeline | Tentative SCOD | Awarded To | SPV Transfer Date | Physical Progress S/s of Tx. Line | [7 empty] | Physical Progress Substation |  |  | Original SCOD | Anticipated SCOD | Remarks
[15 empty] | Length | Location | Foundation | Erection | Stringing | Foundation (%) | Erection (%) | Stringing (%) | Civil Work (%) | Equipment Received (%) | Equipment Erected (%)
| Rajasthan | Rajasthan Part G phase- II | Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan (8.1 GW) under phase- II- Part G SPV Name: POWERGRID Narela Transmission Ltd. (CKM-408, MVA-4500) |  |  |  | TBCB | [6 empty] | May-22 | [11 empty] | Nov-23 | Dec - 25
| Narela | Narela | Khetri-Narela 765kV D/C Line |  |  |  | TBCB | [6 empty] | May-22 | 340 | 463 | 463 | 463 | 340 | 1 | 1 | 1 |  |  |  | Nov-23 | Dec - 25 | Forest Delhi (0.95 Ha, 3 locs, 82.58 Ckm): Stage I&II received.Tree felling permission received from Hon'ble Supreme court vide order dated 26.05.25.
| Narela | Narela | LILO of 765kV S/c Meerut – Bhiwani line at Narela |  |  |  | TBCB | [6 empty] | May-22 |  | 97 | 97 | 97 | 68 | 1 | 1 |  |  |  |  | Nov-23 | Oct - 25 | Line charged on 01.10.2025
| Narela | Narela | 3x1500MVA ,765/400kV GIS substation at Narela |  |  |  | TBCB | [6 empty] | May-22 | [8 empty] | 100.00% | 100.00% | 100.00% | Nov-23 | Dec - 25 | ICT-1&3 Charged on 01.10.2025 ICT-2 Charged on 02.10.2025 Bays commissioning matching with Tx. Line
| Rajasthan | Rajasthan Part-E Phase-II | Transmission system associated with LTA applications from Rajasthan SEZ Part-E, Phase-II (SPV: POWERGRID Bhadla Sikar Transmission Limited) (CKM-600) |  |  |  | TBCB | [6 empty] | Mar-23 | [11 empty] | Sep-24 | Dec - 25
| Bhadla | Bhadla | Bhadla II - Sikar II 765 kV D/C line (2nd) |  |  |  | TBCB | [6 empty] | Mar-23 | 628 | 816 | 816 | 816 | 524.24 | 1 | 1 | 0.83 |  |  |  | Sep-24 | Dec - 25 | Stringing RoW (10 locs): Sikar Dist. (10) in Rajasthan
| Khavda | Khavda Part B Phase II | Transmission scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase II- Part B (SPV Name: POWERGRID KHAVDA II-B TRANSMISSION LIMITED) (CKM-368) |  |  |  | TBCB | [6 empty] | Mar-23 | [11 empty] | Mar-25 | Dec - 25
| Ahmedabad | Ahmedabad | 765kV D/C Lakadia PS-Ahmedabad Line |  |  |  | TBCB | [6 empty] | Mar-23 | 368 | 476 | 476 | 476 | 335.16 | 1 | 1 | 0.91 |  |  |  | Mar-25 | Dec - 25 | Work affected due to severe RoW Issue.
| Khavda | Khavda Part C Phase II | Transmission scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase II- Part C (SPV Name: POWERGRID KHAVDA II-C TRANSMISSION LIMITED) (CKM-577, MVA-4500) |  |  |  | TBCB | [6 empty] | Mar-23 | [11 empty] | Mar-25 | Dec - 25
|  |  | 765kV D/C Ahemdabad- New Navsari (South Gujrat) line |  |  |  | TBCB | [6 empty] | Mar-23 | 590 | 804 | 803 | 755 | 426.44 | 1 | 0.94 | 0.72 |  |  |  | Mar-25 | Dec - 25 | Forest (5.13 Ha):Stage-II received on 04.02.2025
| Ahmedabad | Ahmedabad | 765/400kV 3x1500MVA Ahmedabad New S/s |  |  |  | TBCB | [6 empty] | Mar-23 | [8 empty] | 98.00% | 100.00% | 98.00% | Mar-25 | Dec - 25 | ICT-I & II charged on 06.09.2025. ICT-III charged on 14.11.2025.
| Khavda | Khavda | Establishment of Khavda Pooling Station-2 (KPS2) in Khavda RE Park (SPV: POWERGRID KPS2 TRANSMISSION SYSTEM LIMITED) (MVA-6000) |  |  |  | TBCB | [6 empty] | Mar-23 | [11 empty] | Dec-24 | Dec - 25
|  |  | 765/400kV 4x1500MVA KPS2 New SS (GIS) |  |  |  | TBCB | [6 empty] | Mar-23 | [8 empty] | 98.00% | 100.00% | 98.00% | Dec-24 | Dec - 25 | 330 MVAr 765kV BR-1 charged on 01.04.25. ICT-1 charged on 12.04.2025. ICT-2 charged on 25.07.2025. ICT-3 charged on 07.11.2025.
| Ananthpuram | Ananthpuram | Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh |  |  |  | TBCB | [6 empty] | Sep-23 | [11 empty] | Sep-25 | Mar - 26
|  |  | 7x500 MVA , 400/220 KV Ananthpuram S/s |  |  |  | TBCB | [6 empty] | Sep-23 | [8 empty] | 90.00% | 85.00% | 30.00% | Sep-25 | Mar - 26 | Land (63.69 Acre) acquired
|  |  | Ananthpuram PS-Kurnool-III PS 400 kV (Quad moose) D/c Line |  |  |  | TBCB | [6 empty] | Sep-23 | 171 | 222 | 222 | 222 | 146 | 1 | 1 | 0.85 |  |  |  | Sep-25 | Dec - 25
|  |  | Ananthpuram PS-Cuddapah-400kV (Quad moose) D/c Line |  |  |  | TBCB | [6 empty] | Sep-23 | 371 | 490 | 470 | 423 | 149.3 | 0.96 | 0.86 | 0.4 |  |  |  | Sep-25 | Mar - 26 | Foundation RoW (2 loc.): YSR kadapa (2) in Andhra pradesh.
| Rajasthan | Rajasthan part B1 Phase-III | Transmission system for evacuation of power from REZ in Rajasthan (20 GW) under Phase-III part B1 SPV: POWERGRID Bhadla III Transmission Ltd |  |  |  | TBCB | [6 empty] | Sep-23 | [11 empty] | Mar-25 | Dec - 25
| Bhadla | Bhadla | Bhadla-III PS – Sikar-II S/s 765 kV D/c line |  |  |  | TBCB | [6 empty] | Sep-23 | 650 | 847 | 847 | 823 | 395.84 | 1 | 0.97 | 0.61 |  |  |  | Mar-25 | Dec - 25 | Stringing RoW Locs. (1 section): Didwana Kuchanamn (1) in Rajasthan. Forest :Rajasthan (24.32 Ha, 5 locs, 25 km ): Stage-I issued on 08.05.25. Stage-II issued on 08.09.2025.
| Bhadla | Bhadla | 2x1500MVA, 765/400KV & 3x500 MVA, 400/220 kV Bhadla III New S/s |  |  |  | TBCB | [6 empty] | Sep-23 | [8 empty] | 100.00% | 99.00% | 98.00% | Mar-25 | Dec - 25
| Rajasthan | Rajasthan Part-C1 Phase-III | Transmission system associated with LTA applications from Rajasthan SEZ Phase-III Part-C1, SPV: POWERGRID Ramgarh II Transmission Ltd |  |  |  | TBCB | [6 empty] | Oct-23 | [11 empty] | Apr-25 | Mar - 26
|  |  | 2x1500MVA, 765/400KV & 2X500MVA, 400/220 kV Ramgarh PS |  |  |  | TBCB | [6 empty] | Oct-23 | [8 empty] | 99.00% | 100.00% | 99.00% | Apr-25 | Dec - 25 | 400kV ICT-1 Test charged from 33kV on 16.09.25. awaiting for readiness of Bhadla-3 Substation & B3S2 Line for evacuation of Power.
| Bhadla | Bhadla | Ramgarh PS- Bhadla-III PS 765kV D/C line |  |  |  | TBCB | [6 empty] | Oct-23 | 372 | 467 | 467 | 467 | 372 | 1 | 1 | 1 |  |  |  | Apr-25 | Dec - 25 | Line is Ready for charging.
| Ramgarh | Ramgarh | 2x300 MVAr Statcom with 4x125 MVAr MSC, 2x125 MVAr MSR at Ramgarh PS |  |  |  | TBCB | [6 empty] | Oct-23 | [8 empty] | 85.00% | 42.00% | 20.00% | Oct-25 | Mar - 26 | Work under progress
| Rajasthan | Rajasthan part H Phase-III | Transmission system for evacuation of power from REZ in Rajasthan (20 GW) under Phase-III part H SPV: POWERGRID Beawar DausaTransmission Ltd |  |  |  | TBCB | [6 empty] | Oct-23 | [11 empty] | Apr-25 | Jan - 26
| Beawar-Dausa | Beawar-Dausa | Beawar-Dausa 765kV D/C line |  |  |  | TBCB | [6 empty] | Oct-23 | 474 | 634 | 626 | 572 | 219.86 | 0.99 | 0.9 | 0.46 |  |  |  | Apr-25 | Jan - 26 | Foundation RoW locs.(2): Ajmer Dist. (2) in Rajasthan. Erection RoW Locs. (7): Beawar (3), Ajmer (4) in Rajasthan. Forest: (5.58 Ha, 02 locs, 2 Ckm): Stage-II issued on 24.05.25.
| Dausa | Dausa | LILO of both circuits of Jaipur (Phagi)-Gwalior 765 kV D/c at Dausa |  |  |  | TBCB | [6 empty] | Oct-23 | 133 | 173 | 173 | 160 | 61.62 | 1 | 0.92 | 0.46 |  |  |  | Apr-25 | Dec - 25 | Under progress
| Dausa | Dausa | LILO of both circuits of Agra – Jaipur (south) 400kV D/c at Dausa |  |  |  | TBCB | [6 empty] | Oct-23 |  | 59 | 59 | 59 | 45 | 1 | 1 |  |  |  |  | Apr-25 | Jul - 25 | Line charged on 13.07.2025
|  |  | 2x1500MVA, 765/400KV Dausa S/s |  |  |  | TBCB | [6 empty] | Oct-23 | [8 empty] | 100.00% | 100.00% | 99.00% | Apr-25 | Dec - 25 | Land (114.879 Acre): All Acquired
| Koppal | Koppal Phase-II | Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & B) and Gadag-II (Phase- A) in Karnataka SPV: POWERGRID Koppal Gadag Transmission Ltd |  |  |  | TBCB | [6 empty] | Dec-23 | [11 empty] | Dec-25 | Jun - 26
|  |  | Establishment of 765/400 kV 2x1500 MVA, 400/220 kV, 2x500 MVA Koppal-II (Phase- A) |  |  |  | TBCB | [6 empty] | Dec-23 | [8 empty] | 80.00% | 50.00% | 10.00% | Dec-25 | Mar - 26 | Pvt. Land (174.575 Acre): Registry of 132.125 out of 140 acres of consented land complete. advance possesion of remaining land has been given to POWERGRID by Dist. Administration on 18.12.24.
|  |  | Establishment of 400/220 kV, 2x500 MVA Gadag-II (Phase -A) Pooling Station |  |  |  | TBCB | [6 empty] | Dec-23 | [8 empty] | 85.00% | 95.00% | 20.00% | Dec-25 | Mar - 26 | Pvt. Land (50.97 Acre): All acquired
|  |  | Koppal-II PS – Narendra (New) 765 kV D/c line |  |  |  | TBCB | [6 empty] | Dec-23 | 238 | 310 | 257 | 134 |  | 0.83 | 0.43 |  |  |  |  | Dec-25 | Jun - 26 | Foundation RoW (36 loc.): Koppal (8), Vijaypura (24), Bagalkote (4) in Karnataka Forest,Karnataka, Koppal (0.657 Ha, Nil locs., 0.2 Ckm)- Stage-II awaited
|  |  | Gadag-II PS – Koppal-II PS 400 kV (Quad Moose) D/c line |  |  |  | TBCB | [6 empty] | Dec-23 | 77 | 104 | 70 | 44 |  | 0.67 | 0.42 |  |  |  |  | Dec-25 | Mar - 26 | Foundation RoW (42 loc.): Koppal Dist. (31), Gadag Dist. (11) in Karnataka
|  |  | Koppal-II PS – Raichur 765 kV D/c line |  |  |  | TBCB | [6 empty] | Dec-23 | 293 | 375 | 346 | 209 | 31.38 | 0.92 | 0.56 | 0.11 |  |  |  | Dec-25 | Mar - 26 | Foundation RoW (12 loc.): Koppal Dist. (11), Raichur (1) in Karnataka Erection RoW (1 loc): Koppal Dist. (1) in Karnataka.
| Koppal | Koppal | Augmentation by 2x1500 MVA, 765/400 kV ICTs at Koppal-II PS |  |  |  | TBCB | [6 empty] | Dec-23 | [8 empty] | 80.00% | 50.00% | 10.00% | Dec-25 | Mar - 26 | Under progress
| Koppal | Koppal | Augmentation by 2x500 MVA, 400/220 kV ICTs at Koppal-II PS |  |  |  | TBCB | [6 empty] | Dec-23 | [8 empty] | 80.00% | 50.00% | 10.00% | Dec-25 | Mar - 26 | Under progress
| Khavda | Khavda Part B Phase-III | Transmission System for evacuation of additional 7 GW RE Power from Khavda RE Park under Phase-III Part B SPV: POWERGRID Vataman Transmission Ltd |  |  |  | TBCB | [6 empty] | Dec-23 | [11 empty] | Dec-25 | Dec - 26
|  |  | Establishment of 765 kV switching station near Vataman |  |  |  | TBCB | [6 empty] | Dec-23 | [8 empty] | 10.00% | 35.00% |  | Dec-25 | Dec - 26 | Land (154.36 Acre): Acquired
|  |  | Halvad – Vataman 765 kV D/c line |  |  |  | TBCB | [6 empty] | Dec-23 | 254 | 336 | 143 | 14 |  | 0.43 | 0.04 |  |  |  |  | Dec-25 | Dec - 26 | Forest,Gujarat (2.717 Ha, 1 loc, 1.28Ckm) Stage-II issued on 20.10.2025.
| Lakadia | Lakadia | LILO of Lakadia – Vadodara 765 kV D/c line at Vataman 765 kV switching station |  |  |  | TBCB | [6 empty] | Dec-23 | 56 | 82 | 54 |  |  | 0.66 | [5 empty] | Dec-25 | Dec - 26 | Gujarat (0.5424 Ha, Nil locs, 0.16Ckm) Stage-II issued on 11.11.2025
|  |  | Vataman switching station – Navsari (New)(GIS) 765 kV D/c line |  |  |  | TBCB | [6 empty] | Dec-23 | 495 | 690 | 353 | 46 |  | 0.51 | 0.07 |  |  |  |  | Dec-25 | Dec - 26 | Gujarat (15.2371 Ha, 2 locs, 4.54 Ckm )- Stage-II issued on 17.11.2025.
| Rajasthan | Rajasthan Part-1 Ph-IV | Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-1) (Bikaner Complex): PART-A SPV: POWERGRID Bikaner Neemrana Transmission Ltd |  |  |  | TBCB | [6 empty] | Dec-23 | [11 empty] | Dec-25 | Jun - 26
|  |  | Establishment of 6x1500 MVA (along with one spare unit of 500 MVA), 765/400 kV & 5x500 MVA 400/220 kV Bikaner-III Pooling Station |  |  |  | TBCB | [6 empty] | Dec-23 | [8 empty] | 90.00% | 70.00% | 30.00% | Dec-25 | Mar - 26 | Land (213.78 Acre): All Acquired.
|  |  | Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) |  |  |  | TBCB | [6 empty] | Dec-23 | 62 | 86 | 66 | 37 |  | 0.77 | 0.43 |  |  |  |  | Dec-25 | Mar - 26 | Stringing RoW (3 locs.): Bikaner (5) in Rajasthan Forest in Bikaner (0.442 Ha, Nil locs, 0.5km), Stage-II received on 24.11.25.
|  |  | Bikaner-III - Neemrana-II 765 kV D/c line |  |  |  | TBCB | [6 empty] | Dec-23 | 682 | 905 | 865 | 688 | 61.82 | 0.96 | 0.76 | 0.09 |  |  |  | Dec-25 | Jun - 26 | Foundation RoW (25 loc.): Churu (14), Jhunjhunu (8), Kotputli Behror (1) in Rajasthan, Mahendragarh (1) in Haryana Erection RoW (10 loc.):Mahendragarh (1) in Haryana, Bikaner (9) in Rajasthan Forest: i) Haryana (0.8361 Ha,6 loc, 1 km): Stage-II Awaited ii) Rajasthan (1.916 Ha, 3 loc, 0.5 km) : Stage-II Awaited.
| Bikaner | Bikaner | LILO of both circuits of 400 kV Bikaner (PG)-Bikaner-II D/c line at Bikaner-III PS |  |  |  | TBCB | [6 empty] | Dec-23 | 74 | 102 | 102 | 94 | 31.52 | 1 | 0.92 | 0.43 |  |  |  | Dec-25 | Mar - 26 | Stringing RoW (3 locs.): Bikaner (5) in Rajasthan
| Rajasthan | Rajasthan Part-1 Ph-IV | Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-1) (Bikaner Complex): PART-D SPV: POWERGRID Neemrana Bareilly Transmission Ltd |  |  |  | TBCB | [6 empty] | Dec-23 | [11 empty] | Dec-25 | Jun - 26
|  |  | Neemrana-II- Bareilly (PG) 765 kV D/c line |  |  |  | TBCB | [6 empty] | Dec-23 | 666 | 863 | 837 | 732 | 257.4 | 0.97 | 0.85 | 0.39 |  |  |  | Dec-25 | Jun - 26 | i)Forest,Rajasthan, Alwar (16.054 Ha,6 loc, 3km) Division: Stage-II Awaited ii) Forest, Haryana (11.849 Ha,2 loc, 2 km): Stage-I awaited iii) Forest,Haryana, Palwal (2.37 Ha,19 loc, 24.2km): Stage-II obtained on 20.11.25. iv) Forest, Uttar Pradesh (2.44 Ha,24loc, 5.5km): Stage-II Awaited
| Bidar | Bidar | Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka (SPV Name: POWERGRID Bidar Transmission Limited) |  |  |  | TBCB | [6 empty] | Feb-24 | [11 empty] | Feb-26 | Jun - 26
|  |  | Bidar PS–Maheshwaram (PG) 765KV D/C line |  |  |  | TBCB | [6 empty] | Feb-24 | 479 | 628 | 606 | 506 | 133.3 | 0.96 | 0.81 | 0.28 |  |  |  | Feb-26 | Jun - 26 | Foundation RoW (22 loc.): Bidar District (2), Ranga Reddy District (20) in Telangana. Erection RoW (11 loc.): Ranga Reddy District (11) in Telangana.
|  |  | Establishement of Bidar PS 3x1500 MVA, 765/400 kV and 5x500 MVA, 400/220 kV ICTs |  |  |  | TBCB | [6 empty] | Feb-24 | [8 empty] | 80.00% | 80.00% | 20.00% | Feb-26 | Jun - 26 | Pvt Land (162.07 Acre), Pending (8.87) Acre The pending land (8.87 acres) is being acquired through RFTLARR Act, 2013.
| Rajasthan | Rajasthan Part D Phase-III | Transmission Scheme for Evacuation of power from REZ in Rajasthan (20 GW) under Phase-III Part D (SPV: POWERGRIDSikar Khetri Transmission Limited) |  |  |  | TBCB | [6 empty] | Feb-24 | [11 empty] | Aug-25 | Jun - 26
| Narela | Narela | Sikar-II –Narela 765 kV D/C line |  |  |  | TBCB | [6 empty] | Feb-24 | 473 | 630 | 482 | 386 | 99.5 | 0.77 | 0.61 | 0.21 |  |  |  | Aug-25 | Jun - 26 | Forest: i)Haryana (16.75 Ha, 0 loc, 6 km)- Stage-I Awaited. ii) Delhi (1.319 ha, 0 loc, 1.2 km): Stage-I awaited.
| Sikar | Sikar | Sikar-II –Khetri765 kV D/C line |  |  |  | TBCB | [6 empty] | Feb-24 | 144 | 198 | 173 | 150 | 33.7 | 0.87 | 0.76 | 0.23 |  |  |  | Aug-25 | Jun - 26 | Forest i)Rajasthan (29.97 Ha, 15 locs, 8km)- Stage-I Awaited Proposal submitted 22.07.24. Area modified to 29.9758 ha. Revised documents uploaded on 28.07.25. Proposal forwarded by NO to SG on 28.11.25.
| Khavda | Khavda Part E2 Phase-IV | Transmission Scheme for Evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7 GW):Part E2 (SPV: POWERGRID Khavda IV-E2 Power Transmission Ltd) |  |  |  | TBCB | [6 empty] | May-24 | [11 empty] | Feb-26 | Jun - 26
|  |  | Augmentaion of transformation capacity at KPS2 GIS by 2x1500 MVA, 765/400 kV ICT on Bus Section-I (5th & 6th) & 2x1500 MVA, 765/400 kV ICT on Bus Section-II (7th & 8th) |  |  |  | TBCB | [6 empty] | May-24 | [8 empty] | 50.00% | 20.00% |  | Feb-26 | Jun - 26 | Work under progress.
| Rajasthan | Rajasthan Part-2 Ph-IV | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex): Part C (SPV Name: POWERGRID Mandsaur Transmission Limited) |  |  |  | TBCB | [6 empty] | Aug-24 | [11 empty] | Aug-26 | Dec - 26
|  |  | Establishment of 3x1500 MVA, 765/400 kV and 5x500 MVA, 400/220 kV Mandsaur Pooling Station |  |  |  | TBCB | [6 empty] | Aug-24 | [8 empty] | 58.00% | 22.00% | 2.00% | Aug-26 | Dec - 26 | Pvt. land (36.32 Acre): Pending (5.24 Acre). Registry of remaining land 5.24 acre is under process. Patta (16.8 Acre): Pending (16.8) Acre. Applied on 29.04.2024. Sale permission notification under process. Regular followup with DM is being made.
|  |  | Mandsaur PS - Indore (PG) 765 kV D/C Line |  |  |  | TBCB | [6 empty] | Aug-24 | 338 | 445 | 329 | 201 |  | 0.74 | 0.45 |  |  |  |  | Aug-26 | Aug - 26 | Foundation RoW (12 locs): Indore (8), Ujjain(4) in Madhya Pradesh.
| Rajasthan | Rajasthan Part-2 Ph-IV | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex): Part E (SPV Name: POWERGRID Mewar Transmission Limited) |  |  |  | TBCB | [6 empty] | Aug-24 | [11 empty] | Aug-26 | Mar - 27
|  |  | Establishment of 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) |  |  |  | TBCB | [6 empty] | Aug-24 | [11 empty] | Aug-26 | Mar - 27 | Land (197.68 Acre): Pending (197.68) Acre *Govt . Land acquisition was completed, now acquired land has been converted to wet land. Subsequently two alternative sites has been identified.
|  |  | Sirohi PS - Rishabdeo 765 kV D/C line |  |  |  | TBCB | [6 empty] | Aug-24 | 421 | 582 | 365 | 173 | 3.28 | 0.63 | 0.3 | 0.01 |  |  |  | Aug-26 | Mar - 27 | Foundation RoW (13 locs): Sirohi (9), Udaipur (4) in Rajasthan. Forest: Rajasthan (101.29 Ha, 46 locs, 15.15 km)- Stage-I Awaited
|  |  | Rishabdeo - Mandsaur PS 765 kV D/C line |  |  |  | TBCB | [6 empty] | Aug-24 | 250 | 327 | 247 | 141 |  | 0.76 | 0.43 |  |  |  |  | Aug-26 | Mar - 27 | Forest: Rajasthan (6.458 Ha, 3 locs, 3 km)- Stage-II received on 20.11.25.
| Rishabdeo | Rishabdeo | LILO of one circuit of 765 kV Chittorgarh - Banaskanta D/C line at Rishabdeo S/S |  |  |  | TBCB | [6 empty] | Aug-24 | 25 | 34 | 5 |  |  | 0.15 | [5 empty] | Aug-26 | Mar - 27 | Survey under progress
| Rajasthan | Rajasthan Part-2 Ph-IV | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex): Part B (SPV Name: POWERGRID Sirohi Transmission Limited) |  |  |  | TBCB | [6 empty] | Aug-24 | [11 empty] | Aug-26 | Dec - 26
|  |  | Establishment of 2x1500MVA, 765/400 KV Substation at suitable location near Sirohi |  |  |  | TBCB | [6 empty] | Aug-24 | [8 empty] | 20.00% | 15.00% |  | Aug-26 | Dec - 26 | Work under progress
|  |  | Fatehgarh-IV (Section-2) PS-Sirohi PS 765KV D/C Line |  |  |  | TBCB | [6 empty] | Aug-24 | 412 | 537 | 318 | 184 | 17.46 | 0.59 | 0.34 | 0.04 |  |  |  | Aug-26 | Dec - 26 | Foundation RoW (58 loc.): Balotra (41), Jalore (6), Barmer (11)in Rajasthan
|  |  | Sirohi PS-Chhitorgarh (PG) 400KV D/C Line (Quad) |  |  |  | TBCB | [6 empty] | Aug-24 | 445 | 604 | 370 | 289 |  | 0.61 | 0.48 |  |  |  |  | Aug-26 | Dec - 26 | Foundation RoW (6 loc.): Sirohi (6) in Rajasthan i)Forest, Rajasthan (45.88 Ha, 34 locs, 9.97 km)- Stage-I Awaited Proposal submitted on 25.01.2025. SG forwarded proposal to IRO on 10.11.25.
| Rajasthan | Rajasthan Part-2 Ph-IV | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part-2: 5.5 GW) (Jaisalmer/Barmer Complex): Part D (SPV Name: POWERGRID Beawar-Mandsaur Transmission |  |  |  | TBCB | [6 empty] | Aug-24 | [11 empty] | Aug-26 | Aug - 26
|  |  | Beawar-Mandsaur PS 765KV D/C line |  |  |  | TBCB | [6 empty] | Aug-24 | 553 | 742 | 535 | 245 |  | 0.72 | 0.33 |  |  |  |  | Aug-26 | Aug - 26 | Foundation RoW (40 loc.): Bhilwara (29), Beawar (11) in Rajasthan i)Rajasthan (49.81 Ha,20 loc, 8km)- Stage-II Awaited ii)Forest, Madhya Pradesh (14.08 Ha,6 loc, 2km)-Stage-II received on 27.11.25.
| Rajasthan | Rajasthan Part-2 Ph-IV | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part-2: 5.5 GW) (Jaisalmer/ Barmer Complex): Part H1 (SPV name: POWERGRID Kurawar Transmission Limited) |  |  |  | TBCB | [6 empty] | Oct-24 | [11 empty] | Oct-26 | Mar - 27
| Kurawar | Kurawar | Establishment of 765/400/220/132kV at Kurawar S/s |  |  |  | TBCB | [6 empty] | Oct-24 | [8 empty] | 5.00% | 1.00% |  | Oct-26 | Mar - 27 | Land (173.15 Acre): Pending (61.15) Acre Pvt. (149.68 Acre): Pending (37.68) Acre. Registration of 112 acres of land completed. Govt. (23.47 Acre): Pending (23.47). Proposal has been marked to SDM.
|  |  | a) 765/400 kV (2x1500 MVA) Kurawar S/s |  |  |  | TBCB | [6 empty] | Oct-24 | [11 empty] | Oct-26 | Mar - 27 | Engg. Under Progress
|  |  | b) 400/220 kV (2x500 MVA) Kurawar S/s |  |  |  | TBCB | [6 empty] | Oct-24 | [11 empty] | Oct-26 | Mar - 27 | Engg. Under Progress
|  |  | c) 220/132 kV (3x200 MVA) Kurawar S/s |  |  |  | TBCB | [6 empty] | Oct-24 | [11 empty] | Oct-26 | Mar - 27 | Engg. Under Progress
|  |  | Mandsaur – Kurawar 765 kV D/c line |  |  |  | TBCB | [6 empty] | Oct-24 | 402 | 522 | 412 | 168 |  | 0.79 | 0.32 |  |  |  |  | Oct-26 | Mar - 27 | work under progress.
|  |  | Kurawar – Ashta 400 kV D/c line |  |  |  | TBCB | [6 empty] | Oct-24 | 112 | 159 | 9 |  |  | 0.06 | [5 empty] | Oct-26 | Mar - 27 | work under progress.
|  |  | Shujalpur – Kurawar 400 kV D/c line |  |  |  | TBCB | [6 empty] | Oct-24 | 57 | 77 | 7 |  |  | 0.09 | [5 empty] | Oct-26 | Mar - 27 | Engg. & survey Under Progress
| Ashta | Ashta | LILO of one circuit of Indore – Itarsi 400 kV D/c line at Ashta S/s |  |  |  | TBCB | [6 empty] | Oct-24 | 112 | 154 | [9 empty] | Oct-26 | Mar - 27 | Madhya Pradesh (31.97 Ha, 18 locs., 6.95 km )- Stage-I Awaited
| Kurawar | Kurawar | LILO of one circuit of Indore – Bhopal 765 kV S/c line at Kurawar S/s |  |  |  | TBCB | [6 empty] | Oct-24 | 53 | 69 | 35 |  |  | 0.51 | [5 empty] | Oct-26 | Mar - 27 | work under progress.
| Jam Khambhaliya | Jam Khambhaliya | Augmentation of transformation capacity at Jam Khambhaliya PS(GIS) (SPV: POWERGRID Jam Khambaliya Transmisison Ltd.) |  |  |  | TBCB | [6 empty] | Oct-24 | [11 empty] | Jul-26 | Jul - 26
| Jam Khambhaliya | Jam Khambhaliya | Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 2x500MVA, 400/220kV ICT (5th and 6th) (terminated on New 220kV bus section-II) |  |  |  | TBCB | [6 empty] | Oct-24 | [8 empty] | 15.00% | 1.00% |  | Jul-26 | Jul - 26 | Work under progress
| Jam Khambhaliya | Jam Khambhaliya | Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 1x500MVA, 400/220kV ICT (7th) (terminated on New 220kV bus section- II) |  |  |  | TBCB | [6 empty] | Oct-24 | [8 empty] | 15.00% | 1.00% |  | Jul-26 | Jul - 26 | Work under progress
| Jam Khambhaliya | Jam Khambhaliya | Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 1x500MVA, 400/220kV ICT (8th) (terminated on New 220kV bus section- III) |  |  |  | TBCB | [6 empty] | Oct-24 | [8 empty] | 15.00% | 1.00% |  | Jul-26 | Jul - 26 | Work under progress
| Jam Khambhaliya | Jam Khambhaliya | Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 1x500MVA, 400/220kV (9th) ICT terminated on New 220kV bus section-III |  |  |  | TBCB | [6 empty] | Oct-24 | [8 empty] | 15.00% | 1.00% |  | Jul-26 | Jul - 26 | Work under progress
|  | PART B PHASE-IV | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM POTENTIAL RENEWABLE ENERGY ZONE IN KHAVDA AREA OF GUJARAT UNDER PHASE-IV (7 GW): PART B (SPV: POWERGRID South Olpad Transmission Ltd.) |  |  |  | TBCB | [6 empty] | Oct-24 | [11 empty] | Oct-26 | Mar - 27
| South Olpad | South Olpad | Establishment of 2x1500 MVA, 765/400 kV & 2x500 MVA, 400/220 kV GIS S/s at a suitable location in South Olpad (between Olpad and Ichhapore) |  |  |  | TBCB | [6 empty] | Oct-24 | [11 empty] | Oct-26 | Mar - 27 | Land (107 Acre): Pending (107) Acre Pvt. (107 Acre): Pending (107 ) Acre. Application for acquisition of land under LARR,2013 submitted on 27.11.2024. Negotiation with land owners failed. Joint Measurement of lands belonging to aggrieved land conducted on 14.11.25 under police protection.
|  |  | Vadodara (GIS) –South Olpad (GIS) 765 kV D/C line |  |  |  | TBCB | [6 empty] | Oct-24 | 249 | 343 | 38 |  |  | 0.11 | [5 empty] | Oct-26 | Mar - 27 | Foundation RoW (242 locs.): Vadodara (95), Bharuch (147) Forest, Gujarat (2.4897 ha, Nil Locs, 0.351 Km) : Stage-I Awaited
| South Olpad | South Olpad | LILO of Gandhar – Hazira 400 kV D/c line at South Olpad (GIS) |  |  |  | TBCB | [6 empty] | Oct-24 | 8 | 12 | 0 |  |  | 0 | [5 empty] | Oct-26 | Mar - 27 | Engg & Survey under Progress
| Ahmedabad | Ahmedabad | Ahmedabad – South Olpad (GIS) 765 kV D/c line |  |  |  | TBCB | [6 empty] | Oct-24 | 455 | 607 | 144 | 8 |  | 0.24 | 0.01 |  |  |  |  | Oct-26 | Mar - 27 | Foundation RoW (75 locs.): Ahmedabad (15), Anand (8), Vadodara (7), Bharuch (45) in Gujarat Forest, Gujarat (28.5931 ha, Nil Locs, 4.268 Km) : Stage-I Awaited Proposal submitted online on 14.04.25 . Proposal recommended in PSC I on 12.06.25. MoM issued on 07.07.25 and proposal fowarded to DFOs for filling of Part-II.
| Bhadla | Bhadla | Transmission System Strengthening for interconnections of Bhadla-III and Bikaner-III complex (SPV: POWERGRID BHADLA BIKANER TRANSMISSION LIMITED ) |  |  |  | TBCB | [6 empty] | Aug-24 | [11 empty] | Aug-26 | Dec - 26
| Bhadla | Bhadla | Bhadla-III - Bikaner-III 765 kV D/c line |  |  |  | TBCB | [6 empty] | Aug-24 | 254 | 328 | 106 | 10 |  | 0.32 | 0.03 |  |  |  |  | Aug-26 | Dec - 26 | Erection RoW Locs. (2): Bikaner District (2) in Rajasthan Forest, Rajasthan (6.8714 ha) : Stage-I Awaited Proposal submitted on 06.05.25. SG forwarded proposal to IRO on 20.11.25.
| Rajasthan | Rajasthan Part-2 Ph- IV | Transmission System for Evacuation of Power from Rajasthan REZ Ph- IV (Part-2 : 5.5 GW) (Jaisalmer/ Barmer Complex): Part F (by clubbing Part F1 & F2) (SPV Name: POWERGRID BARMER I TRANSMISSION LIMITED) |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | Nov-26 | Jun - 27
|  |  | Establishment of 3x1500 MVA, 765/400 kV & 2x500 MVA, 400/220 kV Barmer-I Pooling Station |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | Nov-26 | Jun - 27 | Govt. (143.5 Acre): Pending (143.5 Acre). Demand note is under process, expected by 05.12.25
|  |  | Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) |  |  |  | TBCB | [6 empty] | Nov-24 | 102 | 103 | 30 |  |  | 0.29 | [5 empty] | Nov-26 | Jun - 27 | Foundation RoW (13 loc.): Barmer (13) in Rajasthan.
|  |  | Barmer-I PS– Sirohi PS 765 kV D/c line |  |  |  | TBCB | [6 empty] | Nov-24 | 419 | 543 | 329 | 22 |  | 0.61 | 0.04 |  |  |  |  | Nov-26 | Jun - 27 | Forest, Rajasthan (0.2412 ha) : Stage-II Awaited Proposaal submitted on 01.05.2025. Stage-I issued on 03.09.25. Compliance forwarded by NO to SG on 27.11.25..
| Rajasthan | Rajasthan PART-3 PH-IV | Transmission System for Evacuation of Power from Rajasthan REZ PH-IV (PART-3: 6GW) [BIKANER COMPLEX]:PART-A (SPV Name: POWERGRID Bikaner IV Transmission Limited) |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | Nov-26 | Mar - 27
|  |  | Establishment of 6x1500 MVA, 765/400 kV & 6x500 MVA, 400/220 kV Bikaner-IV Pooling Station. |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | Nov-26 | Mar - 27 | Land (235.86 Acre): Land Acquisition process completed on 16.09.25.
| Bikaner | Bikaner | LILO of both ckts of Bikaner II PS - Bikaner III PS (Quad) at Bikaner-IV PS |  |  |  | TBCB | [6 empty] | Nov-24 | 65 | 68 | 0 |  |  | 0 | [5 empty] | Nov-26 | Mar - 27 | Engg under progress
|  |  | Bikaner-IV PS – Siwani 765 kV D/c line |  |  |  | TBCB | [6 empty] | Nov-24 | 481 | 622 | 298 | 29 |  | 0.48 | 0.05 |  |  |  |  | Nov-26 | Mar - 27 | Forest, Rajasthan (1.2609 ha): Stage-II Awaited Forest, Haryana (0.7817 ha): Stage-I Awaited
|  |  | Siwani– Fatehabad (PG) 400 kV D/c line (Quad) |  |  |  | TBCB | [6 empty] | Nov-24 | 165 | 220 | 23 | 7 |  | 0.1 | 0.03 |  |  |  |  | Nov-26 | Mar - 27 | Forest, Haryana (3.448 ha, Nil locs, 0.0205 km): Stage-I Awaited. Proposal submitted on 16.02.25. PSC I raised queries. CA Land alotted by MP and detailed CA scheme forwarded to Region on 23.04.25. Revised proposal with reduced forest area submitted on 17.11.25.
|  |  | Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) |  |  |  | TBCB | [6 empty] | Nov-24 | 281 | 377 | 39 | 6 |  | 0.1 | 0.02 |  |  |  |  | Nov-26 | Mar - 27 | i) Forest, Haryana (13.12 ha, Nil locs., 0.0323 Km) :Proposal submitted on 16.02.25. PSC I raised queries. CA Land alotted by MP and detailed CA scheme forwarded to Region on 23.04.25. ii)Forest, Punjab (2.43ha, Nil locs., 0.00597Km) : Proposal submitted on 15.02.25. Under process with DFOs for Part II.
| Bikaner | Bikaner | STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) at Bikaner-IV PS |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | Nov-26 | Mar - 27 | Engg under progress
| Khavda | Khavda Part A Phase-V | Transmission System for Evacuation of Power from potential renewable energy zone in Khavda area of Gujarat under Phase-V (8GW): Part A (SPV Name: POWERGRID West Central Transmission Limited) |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | May-29 | May - 29
|  |  | Establishment of 6000 MW (4x1500 MW), ± 800 kV (HVDC) [LCC] at KPS2 and Nagpur terminal station (Bipole-1: 3000 MW) |  |  |  | TBCB | [6 empty] | Nov-24 | [8 empty] | 5.00% | 1.00% |  | Nov-28 | Nov - 28 | Land (405 Acre, All Pvt.): Pending (284) Acre
|  |  | Establishment of 6000 MW (4x1500 MW), ± 800 kV (HVDC) [LCC] at KPS2 and Nagpur terminal station (Bipole-2: 3000 MW) |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | May-29 | May - 29 | Engg. Under Progress
| Nagpur | Nagpur | Establishment of 6x1500 MVA, 765/400 kV ICTs at Nagpur S/s along with associated interconnections with HVDC Switchyard |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | Nov-28 | Nov - 28 | Engg. Under Progress
|  |  | ±800 kV HVDC Bipole line (Hexa lapwing) between KPS2 (HVDC) and Nagpur (HVDC) |  |  |  | TBCB | [6 empty] | Nov-24 | 2,409 | 3,152 | 64 | [8 empty] | Nov-28 | Nov - 28 | i)Forest, Gujarat (373.89 ha, 54.188 Km) : Proposal submitted on 03.06.25. Proposal recommended in PSC I on 12.06.25 & fowarded to DFOs for filling of Part- II. ii) WL- Wild Ass Sanctuary (26.4907 ha): Proposal submitted online on 03.06.25.Query raised by wildlife warden replied on 02.11.25. Site inspection to be done by wildlife warden. iii)Forest, Madhya Pradesh (156.936 ha) :Proposal submitted online on 28.08.25. Proposal discussed in PSC-I meeting on 08.09.25 and further forwarded to DFO for filling of Part-II on 09.09.25. iv)Forest, Maharashtra (57.71 ha) :Proposal submitted online on 21.10.25 & discussed in PSC-I meeting on 27.10.25. Proposal not accepted in PSC and it has been asked to confirm forest area from Amravati division.
| Nagpur | Nagpur | LILO of Wardha – Raipur 765 kV one D/c line (out of 2xD/c lines) at Nagpur |  |  |  | TBCB | [6 empty] | Nov-24 | 68 | 86 | 5 |  |  | 0.06 | [5 empty] | Nov-28 | Nov - 28 | Engg. Under Progress
|  |  | Dynamic Reactive Compensation at KPS1 and KPS3 (SPV name: POWERGRID KHAVDA PS1 AND 3 TRANSMISSION LIMITED) |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | Nov-26 | Nov - 26
|  |  | ± 300 MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS1 400 kV Bus section-1 (GIS) |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | Nov-26 | Nov - 26 | Land : Govt. Land (7.41 Acres): Pending (7.41 Acres): Proposal is has been marked to Secretariat , Gandhinagar by DM. Sectratariat has sent file to DM kutch for valuation of land.
|  |  | ± 300 MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS1 400 kV Bus section-2 (GIS) |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | Nov-26 | Nov - 26 | Land : Govt. Land (7.41 Acres): Pending (7.41 Acres): Proposal is has been marked to Secretariat , Gandhinagar by DM. Sectratariat has sent file to DM kutch for valuation of land.
|  |  | ± 300 MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS3 400 kV Bus section-1 (GIS) |  |  |  | TBCB | [6 empty] | Nov-24 | [8 empty] | 10.00% | 1.00% |  | Nov-26 | Nov - 26 | Work under progress
| Rajasthan | Rajasthan Part-3 Ph-IV | Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-3: 6GW) [Bikaner complex]: Part-B (SPV Name: POWERGRID Siwani Transmission Limited) |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | Nov-26 | Mar - 27
|  |  | Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) |  |  |  | TBCB | [6 empty] | Nov-24 | [8 empty] | 3.00% | 1.00% |  | Nov-26 | Mar - 27 | Land (139 Acre): Pending (Nil) Acre
|  |  | Bikaner-IV PS – Siwani 765 kV D/C (2nd) line |  |  |  | TBCB | [6 empty] | Nov-24 | 480 | 625 | 400 | 84 |  | 0.64 | 0.13 |  |  |  |  | Nov-26 | Mar - 27 | Forest, Rajasthan (1.2462 ha): Stage-II Awaited. Proposal submitted on 18.05.25. Stage-I issued on 01.10.25. Demand for compensatory levies approved by NO on 07.10.25.Payment deposited on 13.11.25. Forest, Haryana (0.5504 ha): Stage-I Awaited. Proposal submitted on 18.06.25. Proposal with revised forest area submitted on 22.11.25.
|  |  | Siwani – Sonipat (PG) 400 kV D/C line (Quad) |  |  |  | TBCB | [6 empty] | Nov-24 | 273 | 378 | 1 |  |  | 0 | [5 empty] | Nov-26 | Mar - 27 | Forest, Haryana (9.5307 ha): Stage-I Awaited. Route alignment approved on 08.04.25. Proposal submitted on 20.06.25. Proposal discussed in PSC I meeting on 16.07.25. Proposal returned to UA on 22.07.25. Main query is pertaining to CA land in other States. Request letter given to ACS (Forest), MP for allotment of DFL land on 23.07.25. Reply submitted to MS(PSC-I) on 07.11.25.
|  |  | Siwani – Jind (PG) 400 kV D/C line (Quad) (93.69 km). |  |  |  | TBCB | [6 empty] | Nov-24 | 187 | 258 | [9 empty] | Nov-26 | Mar - 27 | Forest, Haryana (4.2216 ha): Stage-I Awaited. Proposal submitted online on 28.10.2025. DFO raised query regarding DFL land on 29.10.25.Query replied back on 12.11.25
| Siwani | Siwani | STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) and MSR (2x125 MVAr) at Siwani S/s. |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | Nov-26 | Mar - 27 | Engg under progress
| Rajasthan | Rajasthan part of Phase III | Additional Transmission System for evacuation of Power from Bhadla-III PS as part of Rajasthan REZ Phase III Scheme (20 GW) (SPV Name: POWERGRID Bhadla-III Power Transmission Limited) |  |  |  | TBCB | [6 empty] | Aug-24 | [11 empty] | Feb-26 | Mar - 26
| Bhadla | Bhadla | Augmentation of 2x500 MVA (4th & 5th)., 400/220 KV ICTs at Bhadla- III PS |  |  |  | TBCB | [6 empty] | Aug-24 | [8 empty] | 50.00% | 25.00% | 10.00% | Feb-26 | Mar - 26 | work under progress
| Bhadla | Bhadla | Augmentation of 1x1500 MVA 765/400 KV (3rd) ICT at Bhadla-III PS |  |  |  | TBCB | [6 empty] | Aug-24 | [8 empty] | 50.00% | 25.00% | 10.00% | Feb-26 | Mar - 26 | work under progress
| Bhadla | Bhadla | Augmentation of 1x1500 MVA 765/400KV (4th) ICT at Bhadla-III PS |  |  |  | TBCB | [6 empty] | Aug-24 | [8 empty] | 40.00% | 20.00% | 10.00% | Dec-25 | Mar - 26 | work under progress
| Rajasthan | Rajasthan Part-4 Ph-IV | Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-4: 3.5 GW): Part A (SPV Name: POWERGRID Ghiror Transmission Limited) |  |  |  | TBCB | [6 empty] | Dec-24 | [11 empty] | Dec-26 | Mar - 27
| Ghiror | Ghiror | Establishment of 765/400kV, 2x1500 MVA S/s at Ghiror (Distt. Mainpuri) (UP) |  |  |  | TBCB | [6 empty] | Dec-24 | [8 empty] | 1.00% | 2.00% |  | Dec-26 | Mar - 27 | Pvt. (146.50 Acre): Pending (16.7) Acre. Proposal submitted to DM on 25.11.2024 , for purchase of land on tripartite mode. Registry of 129.8 acres land completed & remaining is under process.
| Barmer | Barmer | Augmentation by 765/400 kV, 2x1500 MVA Transformer (4th& 5th) at Barmer-I PS. |  |  |  | TBCB | [6 empty] | Dec-24 | [11 empty] | Dec-26 | Mar - 27 | Engg Under Progress
| Barmer | Barmer | Augmentation by 5x500 MVA (5th to 9th), 400/220 kV ICTs at Barmer-I PS. |  |  |  | TBCB | [6 empty] | Dec-24 | [11 empty] | Dec-26 | Mar - 27 | Engg Under Progress
|  |  | Fatehgarh-IV PS (Sec-2) – Barmer-I PS 400kV D/c line. |  |  |  | TBCB | [6 empty] | Dec-24 | 74 | 108 | 2 |  |  | 0.02 | [5 empty] | Dec-26 | Mar - 27 | Foundation RoW (13 loc.): Barmer (13) in Rajasthan. Forest, Rajasthan (0.1656 ha, ): Stage-II Awaited. Proposal submitted on 06.05.25. Stage-I issued on 14.09.25. Stage-I compliance forwarded to NO on 26.11.25. NO forwarded to SG on 27.11.25.
|  |  | Dausa - Ghiror 765 kV D/c line |  |  |  | TBCB | [6 empty] | Dec-24 | 545 | 714 | 234 | 50 |  | 0.33 | 0.07 |  |  |  |  | Dec-26 | Mar - 27 | Forest, Uttar Pradesh (15.77 ha, ): Stage-I Awaited Forest, Rajasthan (16.2877 ha, ): Stage-I Awaited
| Ghiror | Ghiror | LILO of both ckt of 765 kV Aligarh (PG) - Orai (PG) D/c line at Ghiror S/s |  |  |  | TBCB | [6 empty] | Dec-24 | 49 | 70 | 19 | 4 |  | 0.27 | 0.06 |  |  |  |  | Dec-26 | Mar - 27 | Forest, Uttar Pradesh (2.689 ha, ): Stage-II Awaited
| Ghiror | Ghiror | LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 2xS/c line at Ghiror S/s |  |  |  | TBCB | [6 empty] | Dec-24 | 50 | 66 | 21 | 1 |  | 0.32 | 0.02 |  |  |  |  | Dec-26 | Mar - 27 | Forest, Uttar Pradesh (0.410 ha, ): Stage-II Awaited
|  |  | 400kV Ghiror-Firozabad (UPPTCL) D/c line. |  |  |  | TBCB | [6 empty] | Dec-24 | 97 | 132 | 40 |  |  | 0.3 | [5 empty] | Dec-26 | Mar - 27 | Forest, Uttar Pradesh (22.8045 ha, ): Stage-I Awaited
| Barmer | Barmer | STATCOM (2X±300 MVAr) along with MSC (4X125 MVAr) and MSR (2X125 MVAr) at Barmer-I PS |  |  |  | TBCB | [6 empty] | Dec-24 | [11 empty] | Dec-26 | Mar - 27
| Kudankulam Unit | Kudankulam Unit | Transmission System under ISTS for evacuation of power from Kudankulam Unit - 3 & 4 (2x1000 MW) (SPV Name: POWERGRID Kudankulam Transmission Limited) |  |  |  | TBCB | [6 empty] | Jan-25 | [11 empty] | Dec-26 | Dec - 26
|  |  | Kudankulam Nuclear Power Plant (3&4) – Tuticorin-II GIS PS 400 kV (quad) D/c line |  |  |  | TBCB | [6 empty] | Jan-25 | 208 | 278 | 90 | 31 |  | 0.32 | 0.11 |  |  |  |  | Dec-26 | Dec - 26 | Foundation RoW (11 loc.): Tirunelveli District (11) in Tamilnadu.
| Koppal | Koppal | System Strengthening at Koppal-II and Gadag-II for integration of RE generation projects (SPV Name: POWERGRID Koppal Gadag Augmentation Transmission Limited) |  |  |  | TBCB | [6 empty] | Jan-25 | [11 empty] | Jan-27 | Jan - 27
|  |  | Gadag-II PS – Koppal-II PS 400 kV (Quad) 2nd D/c line |  |  |  | TBCB | [6 empty] | Jan-25 | 77 | 102 | 7 |  |  | 0.07 | [5 empty] | Jan-27 | Jan - 27 | Work under progress.
| Koppal | Koppal | Augmentation by 3x1500 MVA (5th, 6th & 7th), 765/400kV ICTs at Koppal-II PS |  |  |  | TBCB | [6 empty] | Jan-25 | [8 empty] | 10.00% |  |  | Dec-25 | Aug - 26 | Work under progress.
| Koppal | Koppal | Augmentation by 5x500 MVA, 400/220kV ICTs (5th, 6th, 7th, 8th & 9th) at Koppal-II PS |  |  |  | TBCB | [6 empty] | Jan-25 | [8 empty] | 10.00% |  |  | Dec-25 | Aug - 26 | Work under progress.
| Gadag | Gadag | Augmentation by 7x500 MVA, 400/220kV ICTs (3rd, 4th, 5th, 6th, 7th, 8th & 9th) at Gadag-II PS |  |  |  | TBCB | [6 empty] | Jan-25 | [8 empty] | 2.00% |  |  | Jan-27 | Jan - 27
| Bidar | Bidar | Augmentation of transformation capacity at Bidar PS (SPV Name: POWERGRID Bidar Augmentation Transmission Limited) |  |  |  | TBCB | [6 empty] | Feb-25 | [11 empty] | Feb-27 | Feb - 27
| Bidar | Bidar | Augmentation by 1x1500 MVA (4th), 765/400kV ICT at Bidar PS |  |  |  | TBCB | [6 empty] | Feb-25 | [8 empty] | 2.00% |  |  | Feb-27 | Feb - 27 | Work under progress.
| Bidar | Bidar | Augmentation by 3x500 MVA, 400/220kV ICTs (6th, 7th, & 8th) at Bidar PS |  |  |  | TBCB | [6 empty] | Feb-25 | [8 empty] | 2.00% |  |  | Feb-27 | Feb - 27 | Work under progress.
|  | Part B1 Phase V | Augmentation of transformation capacity at KPS2 & KPS2 (Phase V Part B1 & B2) (SPV Name: POWERGRID KPS1 and 2 Augmentation Transmission Limited) |  |  |  | TBCB | [6 empty] | Feb-25 | [11 empty] | Feb-27 | Feb - 27
|  |  | Augmentation by 1x1500 MVA (9th), 765/400kV ICT at KPS1(GIS) on Bus section-II |  |  |  | TBCB | [6 empty] | Feb-25 | [11 empty] | Feb-27 | Feb - 27 | Engg under progress
|  |  | Augmentation by 1x1500 MVA (9th), 765/400kV ICT at KPS2(GIS) on Bus section-I |  |  |  | TBCB | [6 empty] | Feb-25 | [8 empty] | 1.00% |  |  | Feb-27 | Feb - 27 | Work under progress.
|  |  | Augmentation of Banaskantha (Raghanesda) PS (GIS) (SPV Name: POWERGRID Banaskantha Augmentation Transmission Limited) |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27
| Banaskantha | Banaskantha | Augmentation of transformation capacity at Banaskantha (Raghanesda) PS (GIS) by 2x500 MVA, 400/220 kV ICTs (3rd and 4th) |  |  |  | TBCB | [6 empty] | Mar-25 | [8 empty] | 30.00% |  |  | Mar-27 | Mar - 27 | Work under progress.
|  | Phase-I | Transmission System for Integration of Kurnool-IV REZ – Phase-I (for 4.5 GW) (SPV Name: POWERGRID Kurnool-IV Transmission Limited) |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27
|  |  | Establishment of 4x1500 MVA, 765/400 kV and 4x500 MVA, 400/220 kV Kurnool-IV Pooling Station |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Pvt Land (191 Acre): Pending (191) Acre. RDO held meeting with land owners on 19.06.2025 and third tripartite meeting held on 02.07.2025 and land rate has been finalised. 33 out of 96 landowners have given consent for 74.69 acres of land and remaining are being pursued.
|  |  | Kurnool-IV – Bidar 765 kV D/C line |  |  |  | TBCB | [6 empty] | Mar-25 | 533 | 698 | 41 |  |  | 0.06 | [5 empty] | Mar-27 | Mar - 27 | Forest, Telangana (11.66 ha, ): Stage-I Awaited
|  |  | Kurnool-IV – Kurnool-III PS 765 kV D/C line |  |  |  | TBCB | [6 empty] | Mar-25 | 252 | 333 | 51 | 6 |  | 0.15 | 0.02 |  |  |  |  | Mar-27 | Mar - 27 | Work under progress.
| Kurnool | Kurnool | 300 MVAr STATCOM at Kurnool-IV PS along with 2x125 MVAr MSR |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Engg under progress
|  |  | Augmentation by 1x1500 MVA, 765/400 kV ICT (3rd) at C’Peta |  |  |  | TBCB | [6 empty] | Mar-25 | [8 empty] | 1.00% |  |  | Mar-27 | Mar - 27 | Work under progress.
|  |  | LILO of Vijayawada-Nellore 400 kV D/C line at C’Peta |  |  |  | TBCB | [6 empty] | Mar-25 | 64 | 99 | [9 empty] | Mar-27 | Mar - 27 | Engg under progress
| Rajasthan | Rajasthan Part-1 Ph-V | Rajasthan REZ Ph-V (Part-1: 4 GW) [Sirohi/Nagaur] Complex (SPV Name: Rajasthan V Power Transmission Limited) |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27
| Sirohi | Sirohi | Aaugmentation by 4x500 MVA, 400/220 kV ICTs at Sirohi S/s |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Engg. under progress.
|  |  | Sirohi – Mandsaur PS 765 kV D/C line |  |  |  | TBCB | [6 empty] | Mar-25 | 622 | 861 | 93 |  |  | 0.11 | [5 empty] | Mar-27 | Mar - 27 | (i) Forest,Rajasthan (53.2984 ha, ): Stage-I Awaited (ii) Forest,Madhya Pradesh (10.9947 ha, ): Stage-I Awaited
|  |  | Mandsaur PS – Khandwa (New) 765 kV D/C line |  |  |  | TBCB | [6 empty] | Mar-25 | 535 | 712 | 162 | 20 |  | 0.23 | 0.03 |  |  |  |  | Mar-27 | Mar - 27 | Forest,Madhya Pradesh (87.68 ha, ): Stage-I Awaited
| Karnataka | Karnataka | Transmission Scheme for integration of Davanagere/ Chitradurga and Bellary REZ in Karnataka (SPV Name: POWERGRID Chitradurga Bellary Transmission |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Sep-27 | Sep - 27
|  |  | Establishment of 765/400 kV, 4x1500 MVA, 400/220 kV 4x500 MVA Pooling Station near Davanagere / Chitradurga, Karnataka |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Land (145 Acre), all Pvt: Pending (145) Acre
| Davanagere | Davanagere | LILO of Narendra New – Madhugiri 765 kV D/C line at Davanagere / Chitradurga 765/400 kV PS |  |  |  | TBCB | [6 empty] | Mar-25 | 137 | 204 | [9 empty] | Mar-27 | Mar - 27 | Engg. under progress.
|  |  | Upgradation of Madhugiri {Tumkur (Vasantnarsapura)} substation to its rated voltage of 765 kV level alongwith 3x1500 MVA, 765/400 kV ICTs |  |  |  | TBCB | [6 empty] | Mar-25 | [8 empty] | 7.00% |  |  | Mar-27 | Mar - 27 | work under progress
|  |  | Upgradation of Narendra New – Madhugiri 765 kV D/C line (presently charged at 400 kV level) at its rated 765 kV voltage level |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Engg. under progress.
|  |  | Establishment of 4x500 MVA, 400/220 kV Pooling Station near Bellary area (Bellary PS), Karnataka |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Sep-27 | Sep - 27 | Pvt. (68 Acre): Pending (68) Acre. Request letter has been submitted to DC, Vijayanagar on 27.02.25 for voluntary acquisition of land under Karnataka state specific amendments/rules in RFTLARR Act, 2013.
|  |  | Bellary PS – Davanagere / Chitradurga 400 kV D/C line |  |  |  | TBCB | [6 empty] | Mar-25 | 200 | 183 | 7 |  |  | 0.04 | [5 empty] | Sep-27 | Sep - 27
| Fatehgarh | Fatehgarh | Augmentation at Fatehgarh-II PS, Fatehgarh-IV PS (Section-II) and Barmer-I PS (SPV Name: POWERGRID Fatehgarh Barmer Augmentation Transmission Limited) |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Dec-26 | Mar - 27
| Fatehgarh | Fatehgarh | Augmentation with 765/400 kV, 1x1500 MVA Transformer (7th ) at Fatehgarh-II PS |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Dec-26 | Mar - 27 | Engg Under Progress
| Fatehgarh | Fatehgarh | Augmentation with 400/220 kV, 3x500 MVA (6th ,7th & 8th) ICTs at Fatehgarh-IV PS(Section-II) |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Nov-26 | Mar - 27 | Engg Under Progress
| Barmer | Barmer | Augmentation with 400/220 kV, 2x500 MVA (3rd & 4th) ICTs at Barmer-I PS |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Nov-26 | Mar - 27 | Engg Under Progress
| Kurnool | Kurnool | Transmission system strengthening at Kurnool- III PS for integration of additional RE generation projects (SPV Name: POWERGRID Kurnool-III CPETA Transmission Limited) |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27
| Kurnool | Kurnool | Augmentation of transformation capacity by 3x1500 MVA, 765/400 kV ICTs at Kurnool-III PS |  |  |  | TBCB | [6 empty] | Mar-25 | [8 empty] | 2.00% |  |  | Mar-27 | Mar - 27 | Work Under Progress
|  |  | Kurnool-III PS – Chilakaluripeta 765 kV D/c line |  |  |  | TBCB | [6 empty] | Mar-25 | 584 | 778 | 28 |  |  | 0.04 | [5 empty] | Mar-27 | Mar - 27 | Work Under Progress
| Kurnool | Kurnool | Augmentation of 1x1500 MVA 765/400 kV ICT (7th) at Kurnool-II PS |  |  |  | TBCB | [6 empty] | Mar-25 | [8 empty] | 5.00% |  |  | Mar-27 | Mar - 27 | Work Under Progress
| Mahan Energen Limited Generating Station | Mahan Energen Limited Generating Station | Transmission System for evacuation of power from Mahan Energen Limited Generating Station in Madhya Pradesh (SPV Name: POWERGRID MEL Power Transmission Limited) |  |  |  | TBCB | [6 empty] | Jun-25 | [11 empty] | Dec-27 | Dec - 27
|  |  | Mahan (existing bus) – Rewa PS (PG) 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line |  |  |  | TBCB | [6 empty] | Jun-25 | 277 | 399 | [9 empty] | Dec-27 | Dec - 27 | Forest,Madhya Pradesh (140.47 ha, ): Stage-I Awaited. Proposal submitted on 16.09.2025. Proposal recommended in PSC-I meeting on 23.09.2025 and forwarded to DFO for filing of part-II on 24.09.2025. Wildlife (2.039 Ha), Madhya Pradesh: Proposal submitted online on 16.09.2025. Queries raised for revision in wildlife area on 25.10.25. Reply under process.
| Rewa | Rewa | 2 Nos. 400 kV bays at Rewa PS (PG) for termination of Mahan (existing bus) – Rewa PS (PG) 400 kV D/c line (Quad ACSR/AAAC/AL59 moose equivalent) line |  |  |  | TBCB | [6 empty] | Jun-25 | [11 empty] | Dec-27 | Dec - 27 | Engg Under Progress
| Davanagere | Davanagere | Transmission System Strengthening at Davanagere for Integration of RE Generation (SPV Name: POWERGRID Davanagere Power Transmission |  |  |  | TBCB | [6 empty] | Sep-25 | [11 empty] | Sep-27 | Sep - 27 | SPV Acquired on 24.09.2025
| Davanagere | Davanagere | Augmentation of Transformation Capacity by 4x500 MVA, 400/220 kV ICTs (5th-8th) at Davanagere PS |  |  |  | TBCB | [6 empty] | Sep-25 | [11 empty] | Sep-27 | Sep - 27
|  |  | Augmentation of Davanagere/Chitradurga PS by 765/400kV, 1x1500 MVA ICTs |  |  |  | TBCB | [6 empty] | Sep-25 | [11 empty] | Sep-27 | Sep - 27
| Davanagere | Davanagere | 02 Nos. of 220kV line bays at Davanagere/Chitradurga PS for termination of dedicated transmission lines of RE generation Projects. |  |  |  | TBCB | [6 empty] | Sep-25 | [11 empty] | Sep-27 | Sep - 27
| Mandsaur | Mandsaur | Augmentation of Transformation Capacity and Implementation of Line Bays at Mandsaur S/S for RE Interconnection (SPV Name: POWERGRID Mandsaur I RE Transmission Limited) |  |  |  | TBCB | [6 empty] | Oct-25 | [11 empty] | Mar-27 | Mar - 27 | SPV Acquired on 08.10.2025
|  |  | Augmentation of Transformation capacity by 1x1500MVA, 765/400 kV ICT (4th) (Terminated at 400 kV & 765kV Bus Section-II). |  |  |  | TBCB | [6 empty] | Oct-25 | [11 empty] | Mar-27 | Mar - 27
|  |  | Augmentation of Transformation capacity by 1x500MVA, 400/220kV ICT (6th) (Terminated on 400 kV Bus Section-I & 220kV Bus Section- II). |  |  |  | TBCB | [6 empty] | Oct-25 | [11 empty] | Mar-27 | Mar - 27
| Mandsaur | Mandsaur | Augmentation of Transformation capacity by 1x500MVA, 400/220kV ICT (7th) (Terminated on 400 kV Bus Section-II & 220kV Bus Section- III) at Mandsaur PS |  |  |  | TBCB | [6 empty] | Oct-25 | [11 empty] | Mar-27 | Mar - 27
|  |  | Inter-regional (NR-WR) Transmission System strengthening to relieve the loading of 765 kV Vindhyachal-Varanasi D/c line |  |  |  | TBCB | [6 empty] | Oct-25 | [11 empty] | Oct-27 | Oct - 27 | SPV Acquired on 16.10.2025
|  |  | Establishment of 765 kV Prayagraj S/s near Prayagraj (Uttar Pradesh) along with 2x330 MVAr 765 kV Bus reactors |  |  |  | TBCB | [6 empty] | Oct-25 | [11 empty] | Oct-27 | Oct - 27 | Pvt. (123 Acre): Pending (123) Acre.
| Prayagraj | Prayagraj | LILO of 765 kV Fatehpur-Varanasi S/C line at Prayagraj |  |  |  | TBCB | [6 empty] | Oct-25 | 30 | [10 empty] | Oct-27 | Oct - 27
| Prayagraj | Prayagraj | LILO of 765 kV Fatehpur-Sasaram S/C line at Prayagraj |  |  |  | TBCB | [6 empty] | Oct-25 | 28 | [10 empty] | Oct-27 | Oct - 27
| Prayagraj | Prayagraj | 765 kV Vindhyachal Pool - Prayagraj D/C line along with 330 MVAr line reactor (switchable) at Prayagraj end on each circuit of 765 Kv Vindhyachal Pool - Prayagraj D/C line |  |  |  | TBCB | [6 empty] | Oct-25 | 440 | [10 empty] | Oct-27 | Oct - 27
| Vindhyachal Pool | Vindhyachal Pool | Bypassing of both circuits of 765 kV Sasan – Vindhyachal Pool 2xS/C line at Vindhyachal Pool and connecting it with 765 kV Vindhyachal Pool - Prayagraj D/C line, thus forming 765 kV Sasan - Prayagraj D/C line |  |  |  | TBCB | [6 empty] | Oct-25 | 1 | [10 empty] | Oct-27 | Oct - 27
|  |  | Inter-Regional Strengthening between SR Grid and WR Grid |  |  |  | TBCB | [6 empty] | Oct-25 | [11 empty] | Oct-27 | Oct - 27 | SPV Acquired on 17.10.2025
| Bidar | Bidar | Parli New – Bidar 765 kV D/C line with 240 MVAr SLR at Bidar end on both circuits |  |  |  | TBCB | [6 empty] | Oct-25 | 240 | [10 empty] | Oct-27 | Oct - 27
| Raigarh | Raigarh | Additional 400 kV feed to Goa and additional system for power evacuation from generation projects pooled at Raigarh (Tamnar) Pool - Goa Tamnar Transmission Project (GTTPL) |  |  |  | TBCB | [6 empty] | Mar-18 | [11 empty] | Nov-21 | Mar - 27
| Xeldem | Xeldem | LILO of one ckt. of Narendra (existing) - Narendra (New) 400kV D/c line at Xeldem |  |  |  | TBCB | [6 empty] | Mar-18 | 210 | 279 | 77 | 35 | 0 | 0.28 | 0.13 | 0 |  |  |  | Nov-21 | Mar - 27 | 1.RoW (7 locs.) : Dharwad (7) 2. Forest (174.634 Ha, 104 locs, 75.928 cKm) in Karnataka (Wildlife area included): Stage I Pending. Applied on 22-07-2023 3. Wildlife (32.06 Ha, 22 locs, 13.92 cKm) in Karnataka: Pending with the Chief Wildlife Warden on account of SBWL recommendation. 4. Forest (76.994 Ha, 49 locs, 33.478 cKm) in Goa (Wildlife area included): Stage I Pending. 5. Wildlife (27.092 Ha, 16 locs, 11.78 cKm) in Goa: Received on 23-08-24 from NBWL.
| Xeldem - Mapusa | Xeldem - Mapusa | Xeldem - Mapusa 400kV D/c line |  |  |  | TBCB | [6 empty] | Mar-18 |  | 142 | 142 | 142 | 105.64 | 1 | 1 |  |  |  |  | May-21 | Nov - 24 | Deemed COD declared w.e.f 00:00 hrs of 19-11-2024. Powerflow commenced on 31-05-2025.
|  |  | Xeldem (existing) – Xeldem (new) 220kV D/C line |  |  |  | TBCB | [6 empty] | Mar-18 |  | 66 | 66 | 66 | 45.4 | 1 | 1 |  |  |  |  | May-21 | Nov - 24 | Deemed COD declared w.e.f 00:00 hrs of 19-11-2024. Powerflow commenced on 31-05-2025.
|  |  | Dharamjaygarh Pool section B - Raigarh (Tamnar) Pool 765kV D/c line |  |  |  | TBCB | [6 empty] | Mar-18 |  | 179 |  |  | 137 | [6 empty] | Jul-21 | Jun - 22 | TL Completed
|  |  | 2x500MVA, 400/220kV Xeldem |  |  |  | TBCB | [6 empty] | Mar-18 | [8 empty] | 100.00% | 100.00% | 100.00% | May-21 | Nov - 24 | Charged on no load basis on 05-11-2024. Deemed COD declared w.e.f 19-11- 2024.Powerflow commenced on 31-05-2025.
|  |  | Transmission System for 400 kV Udupi (UPCL) – Kasargode D/C Line |  |  |  | TBCB | [6 empty] | Sep-19 | [11 empty] | Nov-22 | Jun - 26
|  |  | Mangalore (Udupi PCL) – Kasargode 400kV D/c line |  |  |  | TBCB | [6 empty] | Sep-19 | 232 | 281 | 212 | 173 | 7.8 | 0.75 | 0.62 | 0.03 |  |  |  | Nov-22 | Jun - 26 | 1.RoW (31locs.) in Karnataka: Dakshin Kannada (31locs.) 2. Row in Kerala: 87 ckm of stringing halted due to non finalisation of land compensation order by Govt. of Kerala. 3. Forest (31.07 Ha, 17 locs, 13.5 ckm) in Karnataka: Stage II awaited. Stage-I received on 27-10-2022. Mangalore Division (22.11 Ha) & Kundapur Division (8.96 Ha): WP received in Oct'24 & TCP received in Jan'25 and Nov'24 resp. 4. Forest (17.07 Ha, 8 locs, 7.8 ckm) in Kerala: Stage II awaited. WP & TCP received on 15-10-2024. Stage-I received on 27-10-2022.
|  |  | 2x500MVA, 400/220 kV Kasargode |  |  |  | TBCB | [6 empty] | Sep-19 | [8 empty] | 99.93% | 100.00% | 99.86% | Nov-22 | Jun - 26 | Commissioning is dependent on completion of Udupi – Kasargode 400kV D/c line.
| Pakaldul | Pakaldul | Transmission System for evacuation of power from Pakaldul HEP in Chenab Valley HEPs – Connectivity System (CKM-2, MVA-400) |  |  |  | TBCB | [6 empty] | Dec-22 | [11 empty] | Apr-25 | Dec - 25
| Kishtwar | Kishtwar | LILO of one circuit of Kishenpur – Dulhasti 400 kV D/c at Kishtwar |  |  |  | TBCB | [6 empty] | Dec-22 | 3 | 5 | 5 | 5 | 2.8 | 1 | 1 | 0.93 |  |  |  | Apr-25 | Dec - 25 | Deemed COD w.e.f 26.11.2025 as per TSA .
|  |  | 7x66.67 MVA, 400/132 kV Kishtwar |  |  |  | TBCB | [6 empty] | Dec-22 | [8 empty] | 100.00% | 100.00% | 100.00% | Apr-25 | Dec - 25 | Deemed COD declared for 400/132 kV pooling station at Kishtwar w.e.f 26.11.2025 as per TSA . Total Land (32 Acres): 1. Pvt. (29.2 Acres): All acquired 2. Govt. (2.8 Acre Non-Forest): Indent given by JKPDD.
| Rajasthan | Rajasthan Part G Phase-III | Transmission System for Evacuation of Power from REZ in Rajasthan (20GW) under Phase-III Part G |  |  |  | TBCB | [6 empty] | Aug-23 | [11 empty] | Feb-25 | Jan - 26
|  |  | Fatehgarh3– Beawar 765kV D/c (2nd) |  |  |  | TBCB | [6 empty] | Aug-23 | 635 | 817 | 815 | 802 | 458 | 1 | 0.98 | 0.72 |  |  |  | Feb-25 | Jan - 26 | 1. RoW (7 locs.) in Rajasthan: Barmer (4 locs.: 1 Foundation & 3 Erection) & Balotra (3 locs.: 3 Erection). 2. Forest (11.35 Ha, 4 locs, 3.39 cKm) in Rajasthan: Stage II received on 29-08- 2025. Stage I received on 11-09-2024, WP received on 26-05-25 & TCP recieved.
| Rajasthan | Rajasthan Part F Phase-III | Transmission System for Evacuation of Power from REZ in Rajasthan (20GW) under Phase-III Part F |  |  |  | TBCB | [6 empty] | Sep-23 | [11 empty] | Mar-25 | Mar - 26
|  |  | Fatehgarh3– Beawar 765kV D/c |  |  |  | TBCB | [6 empty] | Sep-23 | 635 | 806 | 801 | 726 | 265 | 0.99 | 0.9 | 0.42 |  |  |  | Mar-25 | Mar - 26 | 1.RoW (24 locs.) in Rajasthan: Barmer (8 locs.: 3 Foundation & 5 Erection) & Balotra (16 locs.: 16 Erection). 2. Forest (10.89 Ha, 4 locs, 3.26 cKm) in Rajasthan: Stage II awaited. WP recieved on 16-06-25. Stage I received on 05-07-2024.
| Beawar | Beawar | LILO of both circuits of Ajmer – Chittorgarh 765 kV D/c at Beawar |  |  |  | TBCB | [6 empty] | Sep-23 | 136 | 178 | 175 | 168 | 48 | 0.98 | 0.94 | 0.35 |  |  |  | Mar-25 | Mar - 26 | 1. Forest (22.66 Ha, 7 locs, 6.76 cKm) in Rajasthan: Stage II awaited. WP received on 13-05-25 & TCP received on 20-05-25. Stage I received on 05-11-2024. 2. PLC Approval pending with M/s Shree Cement.since mar'24.
| Beawar | Beawar | LILO of of Kota – Merta 400 kV D/c at Beawar |  |  |  | TBCB | [6 empty] | Sep-23 | 66 | 90 | 89 | 81 | 28 | 0.99 | 0.9 | 0.42 |  |  |  | Mar-25 | Mar - 26 | 1. PLC Approval pending with M/s Shree Cement since Mar'24.. 2. Delay in replacement of existing earth wire with OPGW in Kota -Merta TL by PGCIL. .
|  |  | 2X1500MVA , 765/400kV Beawar S/s |  |  |  | TBCB | [6 empty] | Sep-23 | [8 empty] | 98.00% | 100.00% | 94.00% | Mar-25 | Jan - 26 | Total Land (58.28 Ha): Govt. Land (12.32 Ha) & Pvt. Land (45.96 Ha) : All acquired
| Fatehgarh | Fatehgarh | (+/-)2x300 MVAr Statcom, 4x125 MVAr MSC, 2x125 MVAr MSR at Fatehgarh-III PS |  |  |  | TBCB | [6 empty] | Sep-23 | [8 empty] | 98.00% | 100.00% | 75.00% | Sep-25 | Mar - 26
| Rajasthan | Rajasthan Part-1 Ph-IV | Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-1) (Bikaner Complex): PART-B |  |  |  | TBCB | [6 empty] | Dec-23 | [11 empty] | Dec-25 | Aug - 26
|  |  | Establishment of 765/400 kV, 4x1500 MVA (along with one spare unit of 500 MVA) Neemrana-II S/s |  |  |  | TBCB | [6 empty] | Dec-23 | [8 empty] | 0.46% | 78.50% | 0.00% | Dec-25 | Aug - 26 | 1. Total Land (57.96 Ha All private): Pending 39.98 Ha
|  |  | Neemrana-II -Kotputli 400 kV D/c line (Quad) |  |  |  | TBCB | [6 empty] | Dec-23 | 87 | 126 | 107 | 92 | 40 | 0.85 | 0.73 | 0.46 |  |  |  | Dec-25 | Aug - 26 | 1.RoW (10 locs.) in Rajasthan: Kotputli-Behror (10 locs.). 2. Forest (8.39 Ha, 6 locs, 7.09 cKm ) in Rajasthan. Stage II awaited. Stage I received on 14-08-2025.
| Neemrana | Neemrana | LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s |  |  |  | TBCB | [6 empty] | Dec-23 | 395 | 517 | 429 | 306 | 34.2 | 0.83 | 0.59 | 0.09 |  |  |  | Dec-25 | Aug - 26 | 1. RoW (7 locs.) in Rajasthan: Khairthal-Tijara (7 locs) . 2. RoW (2 locs.) in Haryana: Nuh (2 locs). 3. Forest (22.86 Ha, 14 locs, 11.47 cKm) in Haryana: Stage I is awaited. Recommended in PSC-II dated 18-08-25 . Applied on 30-03-2024. 4. Forest (21.77 Ha, 17 locs, 19.66 cKm) in Rajasthan:Stage I received on 14-08- 2025.
| Khavda | Khavda Part C Phase-IV | Transmission System for Evacuation of Power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7 GW): Part C |  |  |  | TBCB | [6 empty] | Aug-24 | [11 empty] | Oct-26 | Oct - 26
|  |  | Establishment of 4x1500 MVA, 765/400 kV & 2x500 MVA, 400/220 kV Boisar-II (GIS) S/s |  |  |  | TBCB | [6 empty] | Aug-24 | [8 empty] | 30.00% | 44.10% | 0.00% | Oct-26 | Oct - 26 | Total land (142 Acres): Pending 52 Acres. Pvt. (90 Acres): All acquired Forest (52 Acres): Pending 52 Acre, Applied 06-06-2025.
|  |  | South Olpad (GIS) – Boisar-II (GIS) 765 kV D/c line |  |  |  | TBCB | [6 empty] | Aug-24 | 475 | 626 | 240 | 49 | 0 | 0.38 | 0.08 | 0 |  |  |  | Oct-26 | Oct - 26 | 1. RoW (126 locs.) in Gujarat: Olpad tehsil (51), Mangrol (6), Mandvi (7), Kamrej (31), Bardoli (22), Mahuva (2), Chikhli Taluka (7) 2. RoW (02 locs.) in Maharashtra: Palghar (2 locs) 3. Delay in Allocation of Space/Land for establishment of 2 Nos. of 765 kV line bays at south Olpad S/s due to non-finalisation of South Olpad S/s location by PGCIL. 4. PLC approval pending from PGCIL in Gujarat portion. 6. Forest (134.15 Ha, 51 locs., 40 ckm) in Gujarat 7. Forest (180.37 Ha, 61 locs., 50 ckm) in Maharashtra - Accepted in PSC-1 on 07- 04-2025, Tree enumeration completed. File is with DFO for part 2 processing. 8. Forest (8.49 Ha) in DNH: Stage-I approval pending
|  |  | Boisar-II (Sec-II) – Velgaon (MH) 400 kV D/c line |  |  |  | TBCB | [6 empty] | Aug-24 | 50 | 74 | 4 | 0 | 0 | 0.05 | 0 | 0 |  |  |  | Oct-26 | Oct - 26 | 1. RoW (4 locs.) in Maharashtra: Palghar (4) 2. Forest (62.5 Ha, 35 locs., 27.17 ckm) in Maharashtra. Stage I awaited, applied on 07-03-25. PSC-1 accepted on 12-08-2025. 3. 16 locs and 10 Kms of route length are on hold due to non-finalization of S/S land by MSETCL.
| Boisar | Boisar | LILO of Babhaleswar – Padghe (M) 400 kV D/c line at Boisar-II (Sec-I) |  |  |  | TBCB | [6 empty] | Aug-24 | 116 | 174 | 29 | 3 | 0 | 0.17 | 0.02 | 0 |  |  |  | Oct-26 | Oct - 26 | 1. RoW (51 locs.) in Maharashtra: Palghar District (6), Thane District(45) 2. PLC approval between AP 78/0 – 79/0 pending with PGCIL. 3. Forest (66.02 Ha, 46 locs, 28.7 ckm) in Maharashtra: Stage-I awaited. CCF visit done on 27-11-25.
|  |  | ± 300 MVAR STATCOM with 3x125 MVAR MSC, 1x125 MVAR MSR at 400 kV level of Navsari (New) (PG) S/s |  |  |  | TBCB | [6 empty] | Aug-24 | [8 empty] | 34.59% | 36.90% | 0.00% | Oct-26 | Oct - 26
|  |  | ±200 MVAR STATCOM with 2x125 MVAR MSC, 1x125 MVAR MSR at 400 kV bus section-I of Boisar-II and ±200 MVAR STATCOM with 2x125 MVAR MSC, 1x125 MVAR MSR at 400 kV bus section-II of Boisar-II. |  |  |  | TBCB | [6 empty] | Aug-24 | [8 empty] | 7.90% | 35.70% | 0.00% | Oct-26 | Oct - 26
| Boisar | Boisar | LILO of Navsari (New) – Padghe (PG) 765 kV D/c line at Boisar-II |  |  |  | TBCB | [6 empty] | Aug-24 | 51 | 74 | 41 | 9 | 0 | 0.55 | 0.12 | 0 |  |  |  | Oct-26 | Oct - 26 | Forest: (38.94 Ha, 18 Locs, 12.68 cKm) in Maharashtra. Stage 1 awaited. applied on 19-01-2025. EDS rasied, A/p resubmitted on 02-04-2025. PSC 1 accepted on 07- 04-2025.
|  | Phase- I | Transmission System for Integration of Ananthapur-II REZ - Phase- I (for 4.5 GW) (SPV:ANANTHAPUR II REZ TRANSMISSION LIMITED) |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27
|  |  | Establishment of 4x1500 MVA, 765/400 & 6x500 MVA, 400/220 kV Ananthapuram- II Pooling Station near Kurnool, Andhra Pradesh |  |  |  | TBCB | [6 empty] | Mar-25 | [8 empty] | 0.00% | 22.00% | 0.00% | Mar-27 | Mar - 27 | Present Scope: 238 Ha Acquired Land: 193 Ha
|  |  | Ananthapuram- II - Davangere 765 kV D/c line |  |  |  | TBCB | [6 empty] | Mar-25 | 236 | 236 | 54 | 1 | 0 | 0.23 | 0 | 0 |  |  |  | Mar-27 | Mar - 27 | 1. Delay in handover of critical D&E inputs of Davanagere S/s by PGCIL for route finalisation and construction of 2 nos. 765 kV line bays at the Davanagere S/s . 2. RoW (6 locs.) in Andhra Pradesh: Ananthpuram (6 locs.)
|  |  | Ananthapuram- II - Cuddapah 765 kV D/c line |  |  |  | TBCB | [6 empty] | Mar-25 | 565 | 565 | 258 | 4 | 0 | 0.46 | 0.01 | 0 |  |  |  | Mar-27 | Mar - 27 | RoW (50 locs.) in Andhra Pradesh: Ananthpuram (44 locs.) & Y S R Kadapa (6 locs.)
| Ananthapuram | Ananthapuram | ±300 MVAr STATCOM at Ananthapuram-II PS along with 2x125 MVAr MSR |  |  |  | TBCB | [6 empty] | Mar-25 | [8 empty] | 0.00% | 10.27% |  | Mar-27 | Mar - 27
|  | Part-A | North-Eastern Region Expansion Scheme-XXV Part-A (NERES) |  |  |  | TBCB | [6 empty] | Jul-25 | [11 empty] | Jul-28 | Jul - 28
| Bornagar | Bornagar | LILO of both circuits of existing Bongaigaon (POWERGRID) – Balipara (POWERGRID) 400 kV D/C (Quad) line at Bornagar (ISTS) |  |  |  | TBCB | [6 empty] | Jul-25 | 54 | 85 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Jul-28 | Jul - 28
| Assam | Assam | Establishment of new 400 kV Bornagar (ISTS) switching station in Assam (765 kV and 220 kV levels to be established in future) |  |  |  | TBCB | [6 empty] | Jul-25 | [8 empty] | 0.00% | 0.00% | 0.00% | Jul-28 | Jul - 28
|  |  | Immediate evacuation for North Karanpura (3x660MW) generation project of NTPC(ERSS XIX) (CKM-303, MVA-1000) |  |  |  | TBCB | [6 empty] | Jul-16 | [11 empty] | Sep-19 | Dec - 25
|  |  | NK – Gaya 400kV D/c line |  |  |  | TBCB | [6 empty] | Jul-16 | 196 | 285 | 285 | 285 | 196.4 | 1 | 1 | 1 |  |  |  | Sep-19 | Dec - 25
|  |  | NK – Chandwa 400kV D/c line |  |  |  | TBCB | [6 empty] | Jul-16 |  | 115 | [9 empty] | Sep-19 | Oct - 22 | Line charged
| Dhanbad | Dhanbad | LILO of both circuits of Ranchi – Maithon-RB 400kV D/c line at Dhanbad |  |  |  | TBCB | [6 empty] | Jul-16 |  | 10 | [9 empty] | Sep-19 | Aug - 21 | Line charged
|  |  | 400/220 kV, 2x500 MVA Dhanbad |  |  |  | TBCB | [6 empty] | Jul-16 | [11 empty] | Sep-19 | Aug - 21 | Substation Charged
| Western Region | Western Region | ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region |  |  |  | TBCB | [6 empty] | Jan-23 | [11 empty] | Jul-24 | Mar - 26
|  |  | Narendra New (GIS) – Pune (GIS) 765 D/c Line |  |  |  | TBCB | [6 empty] | Jan-23 | 636 | 795 | 663 | 523 | 133.2 | 0.83 | 0.66 | 0.21 |  |  |  | Jul-24 | Mar - 26 | RoW (88 loc) : a) Pune District (46) in Maharashtra. b) Vijaypura District (40) in Karnataka. 40 locations affected near Kudgi end. Forest (76.87 Ha, 29 loc)- Proposal recommended in PSC-II conducted on 12-Aug- 25. MoM & NO clearance received on 12-Sep-25. Proposal forwarded from SG to IRO on 11-Nov-25. Proposal awaiting recommendation in REC meeting.
|  |  | Upgradation of Narendra New (GIS) Substation to rated voltage level of 765 kV alongwith 4x1500 MVA transformer |  |  |  | TBCB | [6 empty] | Jan-23 | [8 empty] | 97.50% | 100.00% | 96.00% | Jul-24 | Mar - 26 | Outdoor and indoor GIB along with GAB WIP HV Testing has been completed for Pune SS And Narendra SS HV testing under initiation
| Khavda | Khavda Part A Phase-III | Transmission System for evacuation of additional 7 GW RE Power from Khavda RE Park under Phase-III Part A |  |  |  | TBCB | [6 empty] | Dec-23 | [11 empty] | Dec-25 | Mar - 26
|  |  | Establishment of 765 kV Halvad switching station with 765 kV, 2x330 MVAr bus reactors |  |  |  | TBCB | [6 empty] | Dec-23 | [8 empty] | 97.00% | 97.00% | 80.00% | Dec-25 | Mar - 26 | Land required: 205 Acre (Present scope acquisition completed) Pvt. land (197): Aquired (183) Govt. land (8): Acquired (8)
|  |  | KPS2(GIS) - Halvad 765 kV D/c line |  |  |  | TBCB | [6 empty] | Dec-23 | 492 | 690 | 536 | 400 | 125 | 0.78 | 0.58 | 0.25 |  |  |  | Dec-25 | Mar - 26 | RoW: 101 Locs. Tehsils: Morbi- 75 Nos (35 Morbi, 8 Maliya, 32 Halvad) Kutch 26 Locs Tehsils: (Bhuj- 2 Nos, Bhachau-24) Forest (266.6997 Ha, 99 locs) in Gujarat. Wildlife (36.6493 Ha, 18 locs.) in Gujarat.
| Ahmedabad | Ahmedabad | LILO of Lakadia – Ahmedabad 765 kV D/c line at Halvad |  |  |  | TBCB | [6 empty] | Dec-23 | 68 | 100 | 90 | 59 | 2.96 | 0.9 | 0.59 | 0.04 |  |  |  | Dec-25 | Mar - 26
| Khavda | Khavda Part A Phase-IV | Transmission System for Evacuation of Power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7 GW): Part A |  |  |  | TBCB | [6 empty] | Aug-24 | [11 empty] | Aug-26 | Aug - 26
|  |  | Augmentation of KPS3 (GIS) by 3x1500 MVA, 765/400 kV ICTs |  |  |  | TBCB | [6 empty] | Aug-24 | [8 empty] | 42.00% | 20.00% | 5.00% | Aug-26 | Aug - 26 | Land required for Lakadia bay extension: 13 Acres, same under acquisition
| Lakadia | Lakadia | 765 kV KPS3 (GIS) – Lakadia (AIS) D/C line |  |  |  | TBCB | [6 empty] | Aug-24 | 404 | 513 | 262 | 121 | 4.8 | 0.51 | 0.24 | 0.01 |  |  |  | Aug-26 | Aug - 26 | 1) ROW: 40 Locs : Khavda (1), Bhuj - (15), Bhachau - (24). Application for Section 16(1) is submitted 2) Forest- KPS3-Lakadia -(317.61 Ha, 128 locs) - Proposal recommended in PSC-II vide MoM dated 23-Sep-25. Proposal forwarded from Nodal officer to state government on 15-Oct-25. Proposal forwarding to IRO is awaited.
|  |  | 765 kV KPS1 (GIS)– Bhuj PS D/C line (2nd) |  |  |  | TBCB | [6 empty] | Aug-24 | 217 | 286 | 185 | 119 | 18.08 | 0.65 | 0.42 | 0.08 |  |  |  | Aug-26 | Aug - 26 | 1) ROW: 4 Locs, Bhuj - (4). Application for Section 16(1) is submitted. 2) Forest (220.81 Ha, 84 locs) - Proposal recommended in PSC-II vide MoM dated 23-Sep-25. Proposal forwarded from Nodal officer to state government on 15-Oct- 25. Proposal forwarding to IRO is awaited.
|  |  | ±300MVAR STATCOM with 1x125 MVAR MSC, 2x125 MVAR MSR at KPS3 400 kV. |  |  |  | TBCB | [6 empty] | Aug-24 | [8 empty] | 5.00% |  |  | Aug-26 | Aug - 26 | Land required: ROU permission required from GPCL/Govt of Gujarat. Letter submitted to GPCL , Further letter written to collector for land handover.
| Navinal | Navinal | Transmission System for Network Expansion Scheme in Navinal (Mundra) area of Gujarat for drawal of power in the area (SPV: NavinalTransmission Ltd.) |  |  |  | TBCB | [6 empty] | Oct-24 | [11 empty] | Jul-26 | Jul - 26
|  |  | Establishment of 4x1500 MVA, 765/400 kV Navinal (Mundra) S/s (GIS) |  |  |  | TBCB | [6 empty] | Oct-24 | [8 empty] | 45.00% | 25.00% | 0.00% | Jul-26 | Jul - 26 | Land (70 Acre): All acquired Supply, Civil & ETC ordering completed. EPC package ordering completed. ICTs, Reactors: Sept;25 to Mar’26
| Lakadia | Lakadia | LILO of Bhuj-II – Lakadia 765 kV D/C line at Navinal (Mundra) (GIS) S/s |  |  |  | TBCB | [6 empty] | Oct-24 | 257 | 368 | 137 | 65 | 0 | 0.37 | 0.18 | 0 |  |  |  | Jul-26 | Jul - 26 | 1] Forest-(73.9278 Ha, 42 locs) in Gujarat,Proposal from DFO, Kutch East & Kutch SF forwarded to CCF. Kutch West to CCF on 20-Sep-25. Proposal forwarded from CCF to Nodal Officer on 10-Oct-25. PSC-II completed on 6-Nov-25. 2] ROW- Mundra Tehsil. (129 Locs, 44 Km)
| Gujarat | Gujarat Phase-I | Network Expansion scheme in Gujarat for drawl of about 3.6 GW load under Phase-I in Jamnagar area (SPV: Jamnagar Transmission Ltd.) |  |  |  | TBCB | [6 empty] | Oct-24 | [11 empty] | Oct-26 | Oct - 26
|  |  | Establishment of 2x1500 MVA 765/400 kV Jamnagar (GIS) PS |  |  |  | TBCB | [6 empty] | Oct-24 | [11 empty] | Oct-26 | Oct - 26 | Land (115 Acre): Land acquisition under progress.
|  |  | Halvad – Jamnagar 765 kV D/c line |  |  |  | TBCB | [6 empty] | Oct-24 | 340 | 391 | 58 | 7 |  | 0.15 | 0.02 |  |  |  |  | Oct-26 | Oct - 26 | 1] Check survey under progress 89 km off 147 Km completed 2] Forest: 16.552 Ha, 2 Locations 3.54 km affected- Modification in proposal due to change in Jamnagar SS land. Revised hard copies submitted in all divisions in August 2025 EDS compliance completed.
| Lakadia | Lakadia | LILO of Jam Khambhaliya PS – Lakadia 400 kV D/c (triple snowbird) line at Jamnagar |  |  |  | TBCB | [6 empty] | Oct-24 | 20 | 28 | 0 |  |  | 0 | [5 empty] | Oct-26 | Oct - 26 | 1] Check survey under progress. 2] Forest: 0.12 Ha, 0 Locations 0.012 km affected. Proposal submitted on Parivesh portal on 06-08-25.
|  |  | Jamnagar – Jam Khambhaliya 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line |  |  |  | TBCB | [6 empty] | Oct-24 | 100 | 112 | 0 |  |  | 0 | [5 empty] | Oct-26 | Oct - 26 | 1) Forest: 2.43 Ha, 2 Locations 0.528 km affected. Proposal submitted on Parivesh portal on 06-08-25. 2) Check survey completed 37 Km off 41 Km.
| Jamnagar | Jamnagar | LILO of CGPL – Jetpur 400kV D/c (triple snowbird) line at Jamnagar |  |  |  | TBCB | [6 empty] | Oct-24 | 260 | 339 | 13 |  |  | 0.04 | [5 empty] | Oct-26 | Oct - 26 | 1] Check survey under progress 123 Km off 123 Km 2] Forest: 1.08 Ha, 0 Locations 0.234 km affected. Proposal submitted on Parivesh portal on 06-08-25.
| Jam Khambhaliya | Jam Khambhaliya | LILO of both ckts of Kalavad – Bhogat 400kV D/c line (Twin AL-59) at Jam Khambhaliya PS |  |  |  | TBCB | [6 empty] | Oct-24 | 40 | 35 | 0 |  |  | 0 | [5 empty] | Oct-26 | Oct - 26 | Check survey under progress.
| Jamnagar | Jamnagar | ±400 MVAr STATCOM with 3x125 MVAr MSC & 2x125 MVAr MSR at Jamnagar 400kV Bus section |  |  |  | TBCB | [6 empty] | Oct-24 | [11 empty] | Oct-26 | Oct - 26 | Engineering under progress
| Khavda | Khavda Part D Phase-IV | Potential REZ in Khavda area of Gujarat under Phase-IV (7GW): Part D (PUNE- III TRANSMISSION LIMITED) |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | Nov-26 | Nov - 26
|  |  | Establishment of 2x1500 MVA, 765/400 kV & 3x500 MVA, 400/220 kV Pune- III (GIS) S/s |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | Nov-26 | Nov - 26 | Pune - III Substation : Land (105 Acre, all Pvt.): Land under posession and Land development work is in progress. 2 Nos Bays at Boisar II: OGA finalization is on hold due to non availablity of sufficeient space to accomodate scope alocated to Pune - III Tranmsiison limited and mismatch in Future scope of Khavda IV C Transmission Limited and present scope of Pune - III Tranmsission Limited.
|  |  | Boisar-II – Pune-III 765 kV D/c line (228 km) |  |  |  | TBCB | [6 empty] | Nov-24 | 456 | 629 | 5 |  |  | 0.01 | [5 empty] | Nov-26 | Nov - 26 | ROW: Palghar (2), Pune (4). Forest- Area: (~50 Km) : 765 KV Boisar II to Pune III Transmission Line passes through Jawahar, Thane, Alibaugh, and Pune Forest Divisions.
| Pune | Pune | LILO of Narendra (New) – Pune (GIS) 765 kV D/c line at Pune-III (85.6 km) |  |  |  | TBCB | [6 empty] | Nov-24 | 171 | 213 | 20 |  |  | 0.09 | [5 empty] | Nov-26 | Nov - 26 | RoW : Pune (2, Baramati and Purandar Taluka) Forest ( ~28 Ha combined with 400 KV LILO Line) : Under Sec. (Mantralaya - Mumbai) GOM has recomended proposal to RO MoEF&CC ( GOI)
| Pune | Pune | LILO of Hinjewadi-Koyna 400 kV S/c line at Pune-III (GIS) S/s (8.516 km) |  |  |  | TBCB | [6 empty] | Nov-24 | 17 | 24 | [9 empty] | Nov-26 | Nov - 26 | RoW : Pune (2, Baramati and Purandar Taluka) Forest ( ~28 Ha combined with 765 KV LILO Line ) : Under Sec. (Mantralaya - Mumbai) GOM has recomended proposal to RO MoEF&CC ( GOI)
| Rajasthan | Rajasthan Part I Phase III | Transmission System for Evacuation of Power from REZ in Rajasthan (20GW) under Phase III Part I (SPV Name: ) |  |  |  | TBCB | [6 empty] | Jan-25 | [11 empty] | Jul-29 | Jul - 29
| Bhadla | Bhadla | Establishment of 6000 MW (4x1500 MW), ± 800 kV (HVDC) [LCC] near Bhadla-III S/s and at Fatehpur(UP) (Bipole-1: 3000 MW) |  |  |  | TBCB | [6 empty] | Jan-25 | [11 empty] | Jul-29 | Jul - 29 | Land (156 Acre, all Pvt.): All Acquire Engg. Under progress
| Bhadla | Bhadla | Establishment of 6000 MW (4x1500 MW), ± 800 kV (HVDC) [LCC] near Bhadla-III S/s and at Fatehpur(UP) (Bipole-2: 3000 MW) |  |  |  | TBCB | [6 empty] | Jan-25 | [11 empty] | Jul-29 | Jul - 29 | Land (270 Acre, all Pvt.): – Under acquisition Engg. Under progress
| Fatehpur | Fatehpur | Establishment of 5x1500 MVA, 765/400 kV ICTs at Fatehpur HVDC |  |  |  | TBCB | [6 empty] | Jan-25 | [11 empty] | Jul-29 | Jul - 29 | Engg. Under Progress
| Bhadla | Bhadla | ±800 kV HVDC line (Hexa lapwing) between Bhadla (HVDC) and Fatehpur (HVDC) (with DMR) |  |  |  | TBCB | [6 empty] | Jan-25 | 955 | 2,173 | [9 empty] | Jul-29 | Jul - 29 | Forest: Rajasthan State (88 Ha), Madhya Pradesh : (35 Ha) :LoA has been issued Forest: Uttar Pradesh : (4 Ha) Land Finalization under progress. Wildlife: Rajasthan State : (7 Ha) LOA has been issued. Wildlife: Madhya Pradesh : (7 Ha)
| Bhadla | Bhadla | 400 kV 2xD/c Bhadla III-Bhadla (HVDC) line (Quad Moose) |  |  |  | TBCB | [6 empty] | Jan-25 | 2 | 18 | [9 empty] | Jul-29 | Jul - 29 | Engg under progress
| Fatehpur | Fatehpur | LILO of both ckts of 765 kV Varanasi– Kanpur(GIS) D/c line at Fatehpur |  |  |  | TBCB | [6 empty] | Jan-25 | 47 | 86 | [9 empty] | Jul-29 | Jul - 29 | Engg under progress
| Mundra | Mundra Part B1 Phase-I | Transmission system for supply of power to Green Hydrogen/ Ammonia manufacturing potential in Mundra area of Gujarat under Phase-I: Part B1 scheme (3 GW at Navinal S/s) (SPV: MUNDRA I TRANSMISSION LIMITED) |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-28 | Mar - 28
|  |  | Augmentation of Transformation capacity at 765/400 kV Navinal(Mundra) S/s (GIS) by 2x1500 MVA ICTs |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-28 | Mar - 28 | Enquiry floated to vendor
|  |  | Navinal(Mundra) (GIS) – Bhuj 765 kV D/c line |  |  |  | TBCB | [6 empty] | Mar-25 | 140 | 202 | [9 empty] | Mar-28 | Mar - 28 | Enquiry floated to vendor
| Navinal | Navinal | ±300MVAr STATCOM along with 2x125MVAr MSC & 1x125MVAr MSR at Navinal(Mundra) (GIS) 400 kV Bus section-I |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-28 | Mar - 28 | Enquiry floated to vendor
| Navinal | Navinal | ±300MVAr STATCOM along with 2x125MVAr MSC & 1x125MVAr MSR at Navinal(Mundra) (GIS) 400 kV Bus section-II |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-28 | Mar - 28 | Enquiry floated to vendor
| Western Region | Western Region | Network Expansion scheme in Western Region to cater to Pumped storage potential near Talegaon (Pune) SPV: WRNES Talegaon Power Transmission Limited |  |  |  | TBCB | [6 empty] | May-25 | [11 empty] | Jan-28 | Jan - 28
|  |  | Establishment 2x1500 MVA, 765/400 kV Substation near South of Kalamb with 2x330 MVAr, 765 kV bus reactor and 2x125 MVAr, 420 kV bus reactor. |  |  |  | TBCB | [6 empty] | May-25 | [11 empty] | Jan-28 | Jan - 28 | Land (350 Acre, all Pvt.): Pending (350 Acre)
| South Kalamb | South Kalamb | LILO of Pune-III – Boisar-II 765 kV D/C line at South Kalamb S/s with associated bays at South Kalamb S/s. |  |  |  | TBCB | [6 empty] | May-25 | 2 | 6 | [9 empty] | Jan-28 | Jan - 28 | EPC ordering under progress.
| Sikar | Sikar | System strengthening in northern region (NRSS XXXVI) along with LILO of Sikar-Neemrana 400 kV D/C line at Babai(RVPNL) (CKM-305) |  |  |  | TBCB | [6 empty] | Aug-16 | [11 empty] | Dec-19 | Dec - 25 | Project was awarded to Essel infra Project Limited. Due to insolvency project now transferred to M/s Resurgent Power (JV of TATA and ICICI) in March 2022.
| Koteshwar - Rishikesh | Koteshwar - Rishikesh | Koteshwar - Rishikesh 400kV D/C line |  |  |  | TBCB | [6 empty] | Aug-16 | 77 | 102 | 102 | 102 | 77 | 1 | 1 | 1 | 100.00% | 100.00% | 100.00% | Dec-19 | Dec - 25 | Approval for charging of is in progress.
| Sikar | Sikar | LILO of one ckt of 400 kV D/C Sikar (PG)-Neemrana (PG) line at Babai. |  |  |  | TBCB | [6 empty] | Aug-16 |  | 6 | [9 empty] | Dec-16 | Oct - 17 | Line charged in Oct'17
|  |  | Babai (RRVPNL) – Bhiwani (PG) 400 kV D/C line |  |  |  | TBCB | [6 empty] | Aug-16 |  | 304 | [9 empty] | Jun-19 | Oct - 23 | Line charged in Nov'23
| Rajasthan | Rajasthan Part-1 Ph-IV | Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-1) (Bikaner Complex): PART-C |  |  |  | TBCB | [6 empty] | Dec-23 | [11 empty] | Dec-25 | Jun - 26
|  |  | Bikaner-III - Neemrana-II 765 kV D/C line (2nd) |  |  |  | TBCB | [6 empty] | Dec-23 | 692 | 884 | 861 | 418 | 66 | 0.97 | 0.47 | 0.1 | 50.00% | 57.00% | 0.00% | Dec-25 | Jun - 26 | • RoW Foundation (7 Loc) : Bikaner (1), Kotputli (1), Sikar (1), Jhunjhunu (4) in Rajasthan State • Erection (35 Loc) : Bikaner (7), Churu (0), Kotputli (5), Jhunjhunu (14) Sikar (1) in Rajasthan State & Mahendrgarh (8) in Haryana State • RAC Land work stopped for Erection & Stringing: 1 Location (Distt Kotputli) • Forest (10.66 Ha, 5 Locs, 4 ckm) in Haryana: Stage I awaited • Forest (2.22 Ha) in Rajasthan : Stage I Received on 08.08.2025. Payment deposited.
|  |  | Eastern Region Expansion Scheme - XXXIX (ERES-XXXIX) |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | Dec-27 | Dec - 27
| Gopalpur | Gopalpur | Establishment of new 765/400 kV, 2x1500 MVA GIS S/s at Gopalpur, Odisha |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | Dec-27 | Dec - 27 | 70 acres of land at Chattrapur for the Gopalpur substation is in progress
|  |  | Angul - Gopalpur 765 kV D/c line |  |  |  | TBCB | [6 empty] | Nov-24 | 399 | 452 | 33 | 0 | 0 | 0.07 | 0 | 0 | 7.00% |  |  | Dec-27 | Dec - 27
|  |  | Gopalpur - Gopalpur (OPTCL) 400 kV D/c (Quad) line |  |  |  | TBCB | [6 empty] | Nov-24 | 51 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00% |  |  | Dec-27 | Dec - 27
| Angul | Angul | Extension at 765 kV level at Angul (PG) S/s including bus extension in GIS |  |  |  | TBCB | [6 empty] | Nov-24 | [8 empty] | 0.00% |  |  | Dec-27 | Dec - 27 | Delay in issuance of tree cutting permission for commencement of 765 kV bay extension works in the premises of PGCIL. FM Notice has been issued.
| Gopalpur | Gopalpur | Extension at 400 kV level at Gopalpur (OPTCL) GIS S/s |  |  |  | TBCB | [6 empty] | Nov-24 | [8 empty] | 0.00% |  |  | Dec-27 | Dec - 27
|  |  | Eastern Region Expansion Scheme ERES-XXXIV : Paradeep |  |  |  | TBCB | [6 empty] | Nov-24 | [11 empty] | Nov-26 | Nov - 26
|  |  | Establishment of Paradeep 765/400 kV, 2x1500 MVA GIS substation |  |  |  | TBCB | [6 empty] | Nov-24 | [8 empty] | 0.00% |  |  | Nov-26 | Nov - 26 | Handover of identified land parcel at Jagatsinghpur for Paradeep substation accepted by Revenue Divisional Commissioner on 10.10.2025 and has been forwarded for approval from Revenue Secretary & subsequently Higher Level Committee.
|  |  | Angul (POWERGRID) – Paradeep 765 kV D/c line |  |  |  | TBCB | [6 empty] | Nov-24 | 179 | 477 | 92 | 1 | 0 | 0.19 | 0 | 0 | 20.00% |  |  | Nov-26 | Nov - 26 | Delay in receipt of NOC for revised route from the Aviation Research Center (ARC) affecting civil foundation work at 14 Nos. locations.
|  |  | Paradeep – Paradeep (OPTCL) 400 kV D/c (Quad) line |  |  |  | TBCB | [6 empty] | Nov-24 | 13 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00% |  |  | Nov-26 | Nov - 26 | Tower foundation work is planned to commence from December, 2025 onwards.
| Gadag | Gadag Part-A Phase-II | Transmission Scheme for Solar Energy Zone in Gadag (1500 MW), Karnataka – Part-A, Phase-II (CKM-100, MVA-1500) (SPV:Gadag-IIA Transmisison Ltd.) |  |  |  | TBCB | [6 empty] | Nov-22 | [11 empty] | May-24 | Jan - 26
|  |  | Gadag Pooling station – Koppal PS 400 kV D/C line |  |  |  | TBCB | [6 empty] | Nov-22 | 100 | 127 | 110 | 105 | 72.72 | 0.87 | 0.83 | 0.73 |  |  |  | May-24 | Jan - 26 | Foundation RoW (13 loc.): District Koppal, Taluka Kuknoor, village Tadkal (13 Loc) Erection RoW (01 loc.): District Koppal, Taluka Kuknoor , village Tadkal (01 Loc) in Karnataka.
| Gadag | Gadag | 400/220 kV, 3x500MVA ICT Augmentation at Gadag |  |  |  | TBCB | [6 empty] | Nov-22 | [8 empty] | 100.00% | 100.00% | 100.00% | May-24 | Oct - 25 | Work completed.
|  | Part C | Western Region Expansion Scheme XXXIII (WRES-XXXIII): Part C (CKM-10, MVA-4000) |  |  |  | TBCB | [6 empty] | Feb-24 | [11 empty] | Feb-26 | Jun - 26
| Ishanagar | Ishanagar | LILO of one circuit of Jabalpur – Orai 765 kV D/c line at Ishanagar 765 kV S/s |  |  |  | TBCB | [6 empty] | Feb-24 | 35 | 45 | 19 | 1 |  | 0.42 | 0.02 |  |  |  |  | Feb-26 | Jun - 26 | Work under progress
| Ishanagar | Ishanagar | 2x1500 MVA, 765/400 kV and 2x500 MVA, 400/220 kV S/s at Ishanagar (New) |  |  |  | TBCB | [6 empty] | Feb-24 | [8 empty] | 2.00% |  |  | Feb-26 | Jun - 26 | Land (157.67 Acre): Pending (30 Acre) Govt. (18.46 Acre): Pending (18.46 Acre) in Chhtarpur District, Govt of MP has issued the working permission for Govt. land vide letter dated 16th Oct’25 for 18.46 Acres. Pvt. (139.21 Acre): Pending (7.21Acre). Registration of 132Acres of Pvt. land completed acqusition of balance land is in Progress. Civil works started on ICT, Reactor, SPR & Gantry Towers
| Dhule | Dhule | Transmission scheme for evacuation of Power from Dhule 2 GW REZ (CKM-120, MVA-2000) |  |  |  | TBCB | [6 empty] | Feb-24 | [11 empty] | Feb-26 | Feb - 26
|  |  | Dhule PS – Dhule (BDTCL) 400 kV D/c line |  |  |  | TBCB | [6 empty] | Feb-24 | 131 | 178 | 58 | 25 | 0 | 0.33 | 0.14 | 0 |  |  |  | Feb-26 | Feb - 26 | RoW (10) : Dhule (10). Forest (25.0593 Ha, 16 Loc, 10.80 ckm) in the State of Maharashtra. Stage-I is pending. Part I and Part II filing done, file is forwarded to State Secretary Forest for signing.
|  |  | 4x500 MVA, 400/220 kV Pooling Station near Dhule (New) |  |  |  | TBCB | [6 empty] | Feb-24 | [8 empty] | 39.00% |  |  | Feb-26 | Feb - 26 | Works in progress
| Kallam | Kallam | Western Region Network Expansion Scheme in Kallam area of Maharashtra |  |  |  | TBCB | [6 empty] | Apr-24 | [11 empty] | Oct-25 | Dec - 25
| Kallam | Kallam | LILO of both circuits of Parli(M) – Karjat(M)/Lonikand-II (M) 400 kV D/c line (twin moose) at Kallam PS |  |  |  | TBCB | [6 empty] | Apr-24 | 54 | 41 | 11 | 2 |  | 0.27 | 0.05 |  |  |  |  | Oct-25 | Dec - 25 | Substation element commissioned on 28th Sep'25. RoW resolution with support from administration ongoing.
|  | Part-A | Ratle HEP (850 MW) & Kiru HEP (624 MW): Part-A (SPV: Ratle Kiru Power Transmission Limited) |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27
| Kishtwar | Kishtwar | LILO of 400 kV Kishenpur-Dulhasti line at Kishtwar S/s |  |  |  | TBCB | [6 empty] | Mar-25 | 2 | 14 | [9 empty] | Mar-27 | Mar - 27 | Check Survey is completed.
|  |  | 400 kV Kishenpur-Samba D/C line . |  |  |  | TBCB | [6 empty] | Mar-25 | 70 | 122 | 10 |  |  | 0.08 | [5 empty] | Mar-27 | Mar - 27 | Foundation Work Started. All statutory proposal and forest diversion proposal submitted
| Kishenpur | Kishenpur | Bypassing of one ckt of 400 kV Kishtwar – Kishenpur 400kV D/C line at Kishenpur and connecting it with one of the circuit of Kishenpur- Samba 400 kV D/C line, thus forming 400 kV Kishtwar - Samba direct line (one ckt) |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Check Survey completed.
|  |  | 400 kV Samba- Jalandhar D/C line |  |  |  | TBCB | [6 empty] | Mar-25 | 299 | 397 | 61 |  |  | 0.15 | [5 empty] | Mar-27 | Mar - 27 | Foundation Work Started. All statutory proposal and forest diversion proposal submitted
| Jalandhar | Jalandhar | Bypassing 400 kV Jalandhar – Nakodar line at Jalandhar and connecting it with one of the circuit of Samba-Jalandhar 400 kV D/C line, thus forming 400 kV Samba – Nakodar direct line |  |  |  | TBCB | [6 empty] | Mar-25 | [11 empty] | Mar-27 | Mar - 27 | Check Survey completed.
| Rajgarh | Rajgarh Phase II | Transmission system for evacuation of power from RE projects in Rajgarh (1000 MW) SEZ in Madhya Pradesh-Phase II (CKM-120, MVA-1500) |  |  |  | TBCB | [6 empty] | Feb-24 | [11 empty] | Feb-26 | Mar - 26
|  |  | Pachora PS – Ujjain (MPPTCL) 400 kV D/c line |  |  |  | TBCB | [6 empty] | Feb-24 | 118 | 145 | 134 | 113 | 19.01 | 0.92 | 0.78 | 0.16 |  | 99.00% |  | Feb-26 | Mar - 26 | RoW (12 locs.): Agar Malwa (Fdn-9 Nos & Erection-1 Nos), Ujjain (Stringing-2 Locs) Forest & WLC: Nil Status of receipt of Conductors- 1440/1440 kms -completed Tower material: 3697/3772 MT, Balance tower to be supplied till 15th Dec’25
| Pachora | Pachora | 400/220 kV, 3x500 MVA ICT augmentation (4th, 5th and 6th) at Pachora PS. |  |  |  | TBCB | [6 empty] | Feb-24 | [8 empty] | 87.00% | 96.00% | 55.00% | Feb-26 | Mar - 26 | Land (11 Acre): 100% Govt.: 100% acquire in Ujjain SS. Pvt: 100% at lease for 35 years, SS Agar Malwa, Dist.- Agar Malwa -Completed
| Karnataka | Karnataka | Transmission scheme for integration of Tumkur-II REZ in Karnataka |  |  |  | TBCB | [6 empty] | Sep-24 | [11 empty] | Sep-26 | Sep - 26
|  |  | Establishment of 400/220 kV 4x500 MVA Pooling Station near Tumkur, Karnatak |  |  |  | TBCB | [6 empty] | Sep-24 | [8 empty] | 40.00% | 0.00% | 0.00% | Sep-26 | Sep - 26 | Land: 70 Acre acquired. Status of receipt of Transformers/Reactors: Expected by 30.04.2026
|  |  | Tumkur-II – Tumkur (Pavagada) line 400 kV (Quad ACSR moose) D/c line. |  |  |  | TBCB | [6 empty] | Sep-24 | 53 | 73 | 15 | 0 | 0 | 0.21 | 0 | 0 |  |  |  | Sep-26 | Sep - 26 | Status of receipt of conductors/Tower material: Conductor (680 Kms/ 680 Kms ). Tower material: 40/1672 MT;balance expected by 31.01.2026.
| Karnataka | Karnataka | Transmission Scheme for integration of Bijapur REZ in Karnataka (SPV: Bijapur REZ Transmission Limited) |  |  |  | TBCB | [6 empty] | Jan-25 | [11 empty] | Jan-27 | Jan - 27
|  |  | Establishment of 400/220 kV, 5x500 MVA Pooling Station near Bijapur (Vijayapura), Karnataka |  |  |  | TBCB | [6 empty] | Jan-25 | [8 empty] | 0.00% | 0.00% | 0.00% | Jan-27 | Jan - 27 | Land (65 Acre): Pvt. (65 Acre): 100% acquisition done. Status of receipt of Transformers/ Reactors: Expected by 31.10.2026
|  |  | Bijapur PS – Raichur New 400kV (Quad ACSR moose) D/c line |  |  |  | TBCB | [6 empty] | Jan-25 | 276 | 360 | 21 | 0 | 0 | 0.06 | 0 | 0 |  |  |  | Jan-27 | Jan - 27 | Status of receipt of conductors/Tower material: Expected by 30.05.2026
| Rajgarh | Rajgarh Phase III | Transmission system for Evacuation of Power from RE Projects in Rajgarh (1500 MW) SEZ in Madhya Pradesh-Phase III and Evacuation of Power from RE Projects in Neemuch (1000 MW) SEZ in Madhya Pradesh-Phase II (SPV:M/s G R Infra Projects Limited) |  |  |  | TBCB | [6 empty] | Sep-25 | [11 empty] | Sep-27 | Sep - 27
| Pachora | Pachora | Creation of New 220 kV Bus Section with 220 kV Bus Sectionaliser and 400/220 kV, 3x500 MVA ICT augmentation at Pachora PS. |  |  |  | TBCB | [6 empty] | Sep-25 | [8 empty] | 0.00% | 0.00% | 0.00% | Sep-27 | Sep - 27 | Land (11.357 Acre - Private): 3.357 Acquired
|  |  | Pachora PS – Rajgarh(PG) 400 kV D/c line |  |  |  | TBCB | [6 empty] | Sep-25 | 185 |  | 0 | 0 | 0 |  |  | 0 |  |  |  | Sep-27 | Sep - 27 | Eco Sensitive Zone: 39.1 Ha (Estimated)
| Neemuch | Neemuch | Creation of New 220 kV Bus Section-II at Neemuch PS with Augmentation of transformation capacity by 3x500 MVA, 400/220 kV ICTs at Neemuch S/s. |  |  |  | TBCB | [6 empty] | Sep-25 | [8 empty] | 0.00% | 0.00% | 0.00% | Sep-27 | Sep - 27
|  |  | Neemuch PS – Pachora PS 400 kV D/c line. |  |  |  | TBCB | [6 empty] | Sep-25 | 221 |  | 0 | 0 | 0 |  |  | 0 |  |  |  | Sep-27 | Sep - 27 | Forest: 79.80 Ha (Estimated)
| Handiya | Handiya | Establishment of 2x500 MVA, 400/220 kV S/s at Handiya. |  |  |  | TBCB | [6 empty] | Sep-25 | [8 empty] | 0.00% | 0.00% | 0.00% | Sep-27 | Sep - 27 | Land (40 Acre): Land acquisition under process.
|  |  | Pachora PS – Handiya 400 kV D/c line. |  |  |  | TBCB | [6 empty] | Sep-25 | 214 |  | 0 | 0 | 0 |  |  | 0 |  |  |  | Sep-27 | Sep - 27 | Forest: 24.01 Ha (Estimated)
| Handiya | Handiya | LILO of Khandwa (PG) – Itarsi (PG) 400 kV D/c line at Handiya S/s. |  |  |  | TBCB | [6 empty] | Sep-25 | 30 |  | 0 | 0 | 0 |  |  | 0 |  |  |  | Sep-27 | Sep - 27
|  |  | 400 kV D/c Khandukhal (Srinagar) – Rampura (Kashipur) line (Twin HTLS) (KRTL) (CKM-388) |  |  |  | TBCB | [6 empty] | Oct-22 | [11 empty] | Sep-24 | Dec - 25
|  |  | 400 kV D/c Khandukhal (Srinagar) – Rampura (Kashipur) line |  |  |  | TBCB | [6 empty] | Oct-22 | 384 | 498 | 442 | 283 | 24.88 | 0.89 | 0.57 | 0.06 |  |  |  | Sep-24 | Dec - 25 | RoW in Uttarakhand (56 locs.): Pouri Gehwal (52 locs): Udam singh nagar (4 Locs) Forest (191.31Ha, 73 locs., 50 ckm) in Uttarakhand State : Stage I approval granted on 17.02.2025. Estimation received on 11.03.2025 and payment is under process. Status of receipt of conductors/Tower material: All Tower material supplies been completed. Conductor Order given on Sep’2024. For Substation Bay Extension Work: Land Lease / Rent agreement to be finalized by PTCUL for Space to construct Bay Extension at Rampura & Khandhukal Substations.
| Rajasthan | Rajasthan Part A3 phase III | Transmission system for evacuation of power from REZ in Rajasthan (20 GW) under phase III –Part A3 (SPV: Fatehgarh-III Transmission Ltd.) |  |  |  | TBCB | [6 empty] | Aug-23 | [11 empty] | Feb-25 | Jun - 26
| Bhadla | Bhadla | Fatehgarh 3- Bhadla-3 400kV D/C line (Quad) line |  |  |  | TBCB | [6 empty] | Aug-23 | 446 | 584 | 485 | 389 | 112.14 | 0.83 | 0.67 | 0.25 | 0.00% |  |  | Feb-25 | Jun - 26 | RoW (80 loc.): Barmer (3), Jaisalmer (38), Phalodi (39) in Rajasthan State Forest (22.2778, 9.686 ckm) in Rajasthan: Stage I Pending Applied on 31.07.2024 Curr. Status : Proposal pending at REC.
| Rajasthan | Rajasthan Part A1 phase III | Transmission system for evacuation of power from REZ in Rajasthan (20 GW) under phase III –Part A1 (SPV: Fatehgarh-IV Transmission Ltd.) |  |  |  | TBCB | [6 empty] | Aug-23 | [11 empty] | Feb-25 | Dec - 25
| Fatehgarh | Fatehgarh | 5x500MVA, 400/220kV pooling station at Fatehgarh-4 |  |  |  | TBCB | [6 empty] | Aug-23 | [8 empty] | 95.00% | 99.50% | 100.00% | Feb-25 | Dec - 25 | All land acquired (134.4 Acre, All Private)
| Fatehgarh-4 PS- Fatehgarh-3 PS | Fatehgarh-4 PS- Fatehgarh-3 PS | Fatehgarh-4 PS- Fatehgarh-3 PS 400kV D/c |  |  |  | TBCB | [6 empty] | Aug-23 | 42 | 61 | 61 | 61 | 42.68 | 1 | 1 | 1.02 | 0.00% |  |  | Feb-25 | Dec - 25 | Forest (1.6054 Ha, 5 locs, 0.7 ckm ) in Rajasthan Stage-I In-principle approval is granted on 20/06/2025. Stage-II Final Approval granted in 10/09/2025 Ckt I charged on 29.11.2025, Ckt II charged on 29.11.2025
|  | Part B | Western Region Expansion Scheme XXXIII (WRES-XXXIII): Part B |  |  |  | TBCB | [6 empty] | Feb-24 |  |  |  |  | 0 | [6 empty] | Feb-26 | Apr - 26
| Karera | Karera | 2x1500 MVA, 765/400 kV and 2x500 MVA, 400/220 kV S/s at Karera (near Datiya) |  |  |  | TBCB | [6 empty] | Feb-24 | [11 empty] | Feb-26 | Apr - 26 | Land (165.5): Pending (90 Acre) Govt. (54.215): All Pending Pvt. (111.28): Pending (35.985 Acre) For Govt. Land, DC Datia has allocated Govt. Land to Energy Dept. M.P as per M.P Govt Policy for further leasing to TSP, WP given by Govt. of MP , Energy Dept. on 16.10.2025
| Karera | Karera | LILO of Satna-Gwalior 765 kV S/c line at Karera |  |  |  | TBCB | [6 empty] | Feb-24 | 85 | 117 | 89 | 15 | 0 | 0.76 | 0.13 | 0 | 0.00% |  |  | Feb-26 | Apr - 26
| Rajasthan | Rajasthan Part -2 Ph-IV | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part -2 : 5.5 GW) (Jaisalmer / Barmer Complex): Part-A |  |  |  | TBCB | [6 empty] | Aug-24 | [11 empty] | Aug-26 | Aug - 26
| Fatehgarh | Fatehgarh | Construction of Section-2 with 4x1500 MVA, 765/400 kV and 5x500 MVA, 400/220 kV ICTs at Fatehgarh-IV PS |  |  |  | TBCB | [6 empty] | Aug-24 | [8 empty] | 38.00% | 40.00% |  | Aug-26 | Aug - 26 | Land required: Included with Fatehgarh IV PS land
|  |  | Fatehgarh-IV PS (Section-2) - Bhinmal (PG) 400 kV D/C line (Twin HTLS) |  |  |  | TBCB | [6 empty] | Aug-24 | 369 | 512 | 234 | 137 | 0 | 0.46 | 0.27 | 0 |  |  |  | Aug-26 | Aug - 26 | RoW: Bytu ( 15 LOC ), Bagoda ( 11 LOC) , Sayla ( 20 LOC) , Sindhari ( 13 Loc) Forest (0.7636, .332ckm) in Rajasthan) Stage I Pending Applied on 12.04.2025 Current Status : Pending at DFO/CF/Nodal Officer/Jalore
| Fatehgarh | Fatehgarh | LILO of both ckts of 765 kV Fatehgarh-III - Beawar D/C line at Fatehgarh-IV PS (Section-2) |  |  |  | TBCB | [6 empty] | Aug-24 | 17 | 46 | 0 |  | 0 | 0 |  | 0 |  |  |  | Aug-26 | Aug - 26 | LILO proposal approved by Beawar Transmission Limited on 3rd Oct. 2025
| Solapur | Solapur | Transmission system for evacuation of power from RE projects in Solapur (1500 MW) SEZ in Maharashtra |  |  |  | TBCB | [6 empty] | Mar-24 | [11 empty] | Mar-26 | Jun - 26
| Solapur | Solapur | Establishment of 400/220 kV, 4x500 MVA ICTs at Solapur PS alongwith 2x125 MVAR, 420 kV Bus Reactors. |  |  |  | TBCB | [6 empty] | Mar-24 | [8 empty] | 20.00% | 0.00% |  | Mar-26 | Mar - 26 | Substation Land ( 80 Acres) : Private land acquired (60.7 Acres).
|  |  | Solapur PS – Solapur (PG) 400 kV D/c line |  |  |  | TBCB | [6 empty] | Mar-24 | 80 | 111 | 71 | 39 |  | 0.64 | 0.35 |  |  |  |  | Mar-26 | Jun - 26 | RoW (13 locs) : Dharashiv (13). Applications submitted to DC (Dharashiv Dist.) for all13 locations for resolution under Section 16(1). Orders awaited.
|  |  | Transmission Scheme for North Eastern Region Expansion Scheme-XVI (NERES-XVI) |  |  |  | TBCB | [6 empty] | Jun-24 |  | 100 | [9 empty] | Nov-26 | Nov - 26
|  |  | Gogamukh (ISTS) (Assam) – Gerukamukh (Arunachal Pradesh) 132 kV D/c line |  |  |  | TBCB | [6 empty] | Jun-24 | 58 | [10 empty] | Nov-26 | Nov - 26 | Route Alignment completed. Design and engineering under process.
| Gogamukh | Gogamukh | LILO of both circuits of Lower Subansiri - Biswanath Chariali 400 kV D/c line at Gogamukh S/s |  |  |  | TBCB | [6 empty] | Jun-24 | 31 | [10 empty] | Nov-26 | Nov - 26 | Route Alignment completed. Design and engineering under process.
|  |  | 400/220/132 kV Gogamukh S/s (2x500 MVA, 400/220 kV ICT; 2x200 MVA, 220/132 kV ICT) |  |  |  | TBCB | [6 empty] | Jun-24 | [11 empty] | Nov-26 | Nov - 26 | Land (58.04 Acre) :Land Parcel finalized and further pursuing with DC, ADC & Circle office of Dhemaji District for acquisition of the Gogamukh Sub Station land. Gogamukh SS Land Acquisition will be completed by Dec-2025.
|  |  | Transmission System for North Eastern Region Generation Scheme- I (NERGS-I) |  |  |  | TBCB | [6 empty] | Jul-24 | [11 empty] | Dec-26 | Dec - 26
| Bokajan | Bokajan | 400 kV Switching Station (to be upgraded to 400/220 kV in future) at Bokajan (Assam) |  |  |  | TBCB | [6 empty] | Jul-24 | [11 empty] | Dec-26 | Dec - 26 | The project has been suspended.
| Bokajan | Bokajan | LILO of both circuits of 400 kV D/c Misa (PG) to New Mariani (PG) line at Bokajan S/s |  |  |  | TBCB | [6 empty] | Jul-24 | 24 | [10 empty] | Dec-26 | Dec - 26 | The project has been suspended.
| Rajasthan | Rajasthan Part-4 Ph-IV | Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-4: 3.5 GW): Part B |  |  |  | TBCB | [6 empty] | Dec-24 | [11 empty] | Dec-26 | Dec - 26
| Merta | Merta | Establishment of 765/400 kV, 2x1500 MVA S/s at Merta-II Substation |  |  |  | TBCB | [6 empty] | Dec-24 |  |  | 19 | 0 | 0 |  |  |  | 2.20% | 0.00% | 0.00% | Dec-26 | Dec - 26 | Land (165 Acre)- Acquisition In progress Order Placed for Transformers/Reactors.
|  |  | Merta II- Barmer I PS 765 kV D/c line |  |  |  | TBCB | [6 empty] | Dec-24 | 686 | 864 | 359 | 19 | 0 | 0.42 | 0.02 | 0 | 0.00% | 0.00% | 0.00% | Dec-26 | Dec - 26 | RoW (84 locs) in Rajasthan: Barmer (13), Jodhpur (71) Forest Clearance - Detailed survey in progress.
|  |  | Merta II – Beawar 400 kV D/c line (Quad). |  |  |  | TBCB | [6 empty] | Dec-24 | 143 | 186 | 45 | 0 | 0 | 0.24 | 0 | 0 | 0.00% | 0.00% | 0.00% | Dec-26 | Dec - 26 | RoW (46 Locs) in Rajasthan: Beawar (10) , Nagaur (36) Forest (0.1646 Ha, 2 locs) in Rajasthan: Forest Proposal submitted on 29.05.2025.
|  |  | Merta II – Dausa 765 kV D/c line |  |  |  | TBCB | [6 empty] | Dec-24 | 494 | 619 | 336 | 1 | 0 | 0.54 | 0 | 0 | 0.00% | 0.00% | 0.00% | Dec-26 | Dec - 26 | RoW (42 Locs) in Rajasthan: Ajmer (11) , Jaipur (12) , Dausa(2) , Didwana (17) Forest Clearance - Forest (1.3636 Ha, 5 locs) Forest proposal submitted on 29.05.2025.
| Raghanesda | Raghanesda Phase-I | Transmission System for evacuation of RE power from Raghanesda area of Gujarat – 3GW under Phase-I (SPV: Raghanesda RE Transmission Limited) |  |  |  | TBCB | [6 empty] | Jul-25 | [11 empty] | Oct-27 | Oct - 27
|  |  | Establishment 3x1500 MVA, 765/400 kV Substation near Raghanesda (GIS) with 2x330 MVAr, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor |  |  |  | TBCB | [6 empty] | Jul-25 | [11 empty] | Oct-27 | Oct - 27 | Land is identification in progress Order of Transformer & Reactors are placed. Order of GIS is placed
|  |  | Raghanesda (GIS) – Banaskantha (PG) 765 kV D/c line |  |  |  | TBCB | [6 empty] | Jul-25 | 155 | [10 empty] | Oct-27 | Oct - 27 | Detailed Survey Work completed.
| Banaskantha | Banaskantha | 2 Nos. 765 kV line bays at Banaskantha (PG) S/s |  |  |  | TBCB | [6 empty] | Jul-25 | [11 empty] | Oct-27 | Oct - 27
| Lakadia | Lakadia Part B | Augmentation of transformation capacity at 765/400 kV Lakadia S/s in Gujarat - Part B |  |  |  | TBCB | [6 empty] | Feb-25 | [8 empty] | 32.72% | 0.00% | 0.00% | Jun-27 | Jun - 27
| Lakadia | Lakadia | Augmentation by 2x500 MVA, 400/220 kV ICTs (3rd & 4th) at Lakadia PS |  |  |  | TBCB | [6 empty] | Feb-25 | [8 empty] | 36.41% | 0.00% | 0.00% | Aug-26 | Aug - 26 | Land: AESL to provide encumbrance-free land, pending due to an existing 400kV double-circuit Lakadia–Jam Khambaliya transmission line passing over the Bays 4, 5, and 6 at 220kV Bus Section-I. CEA (PSPM) convened a meeting on 08-Sep-25 with RIL, AESL, O2 Power, and CTU, directing CTU to provide technical solution. Transformer Supply: Ordered on 20-Feb-25. Expected by Mar’26.
| Lakadia | Lakadia | Augmentation by 2x500 MVA, 400/220 kV ICTs (5th & 6th) at Lakadia PS on new 220 kV Bus Section-II |  |  |  | TBCB | [6 empty] | Feb-25 | [8 empty] | 36.85% | 0.00% | 0.00% | Aug-26 | Aug - 26 | Land: AESL to provide encumbrance-free land, pending due to an existing 400kV double-circuit Lakadia–Jam Khambaliya transmission line passing over the Bays 4, 5, and 6 at 220kV Bus Section-I. CEA (PSPM) convened a meeting on 08-Sep-25 with RIL, AESL, O2 Power, and CTU, directing CTU to provide technical solution. Transformer Supply: Ordered on 20-Feb-25. Expected by Mar’26.
| Lakadia | Lakadia | Augmentation by 500 MVA, 400/220 kV ICTs (7th) at Lakadia PS on new 220 kV Bus Section-II |  |  |  | TBCB | [6 empty] | Feb-25 | [8 empty] | 35.86% | 0.00% | 0.00% | Dec-26 | Dec - 26 | Land: WRSS XXI (A) Transco Limited, to provide the required land for the Lakadia B Power Transmission Limited project. Transformer Supply: Ordered on 20-Feb-25. Expected by Oct’26.
| Lakadia | Lakadia | Augmentation by 500 MVA, 400/220 kV ICTs (8th) at Lakadia PS on new 220 kV Bus Section-II |  |  |  | TBCB | [6 empty] | Feb-25 | [8 empty] | 39.10% | 0.00% | 0.00% | Jun-27 | Jun - 27 | Land: WRSS XXI (A) Transco Limited, to provide the required land for the Lakadia B Power Transmission Limited project. Transformer Supply: Ordered on 20-Feb-25. Expected by Nov’26.
| Lakadia | Lakadia | Augmentation of transformation capacity at Lakadia PS by 1x1500 MVA, 765/400 kV ICT (3rd) |  |  |  | TBCB | [6 empty] | Feb-25 | [8 empty] | 32.90% | 0.00% | 0.00% | Aug-26 | Aug - 26 | Land: WRSS XXI (A) Transco Limited, to provide the required land for the Lakadia B Power Transmission Limited project. Transformer Supply: Transformer (03 nos) ordered on 21-Feb-25 & expected by Mar’26; Reactor (03 nos) ordered on 21-Feb-25 & expected by Jun’26.
|  |  | Eastern Region Generation Scheme-I (ERGS-I) (SPV: Angul Sundargarh Transmission Limited) |  |  |  | TBCB | [6 empty] | Jul-25 | [11 empty] | Mar-28 | Mar - 28
|  |  | LILO of both circuits of Angul – Sundargarh (Jharsuguda) 765 kV 2xS/c lines at NLC-Talabira generation switchyard |  |  |  | TBCB | [6 empty] | Jul-25 | 100 | [10 empty] | Mar-28 | Mar - 28
|  | Phase-II | Transmission System for Integration of Ananthapuram-II REZ- Phase-II (3 GW) (SPV: Ananthapuram II Power Transmission |  |  |  | TBCB | [6 empty] | Oct-25 | [11 empty] | Apr-28 | Apr - 28
|  |  | Augmentation of Ananthapuram-II PS by 400/220 kV, 1x500 MVA ICT |  |  |  | TBCB | [18 empty] | Oct-27 | Oct - 27
|  |  | Augmentation of Ananthapuram-II PS by 765/400 kV, 2x1500 MVA and 400/220 kV, 6x500 MVA ICTs |  |  |  | TBCB | [18 empty] | Apr-28 | Apr - 28
|  |  | Establishment of 3x1500 MVA, 765/400 kV CN’Halli Station with 2x330 MVAr (765 kV) bus reactors |  |  |  | TBCB | [18 empty] | Apr-28 | Apr - 28
| Ananthapuram | Ananthapuram | Ananthapuram-II PS – CN’Halli 765 kV D/c line with 330 MVAr SLR at Ananthapuram-II end on both circuits |  |  |  | TBCB | [7 empty] | 363 | [10 empty] | Apr-28 | Apr - 28
|  |  | LILO of one circuit of Talaguppa - Neelmangala 400 kV D/c line at CN’Halli |  |  |  | TBCB | [7 empty] | 19 | [10 empty] | Apr-28 | Apr - 28
| Hassan | Hassan | LILO at CN’Halli of already LILOed section of one circuit of Talaguppa - Neelmangala 400 kV line at Hassan |  |  |  | TBCB | [7 empty] | 36 | [10 empty] | Apr-28 | Apr - 28