## Data Sources
SN | Connectivity Application Status | Frequency
1 | CTU ¦ Central Transmission Utility of India Limited CMETS (Agenda and Minutes: Region wise) link:https://ctuil.in/ists-consultation-meeting | Daily
2 | CTU ¦ Central Transmission Utility of India Limited JCC (Region wise as per document release Agenda/Minutes) link https://ctuil.in/ists-joint-coordination-meeting | Daily
3 | Status of effectiveness of connectivity granted to RE generators (Effective date of connectivity wise) link | Daily
4 | CTU ¦ Central Transmission Utility of India Limited Re-allocation meetings (Agenda and Minutes: Region wise) link | Weekly
5 | CTU ¦ Central Transmission Utility of India Limited Bidding Calendar link | Weekly
6 | Transmission Reports - Central Electricity Authority TBCB report from CEA transmission (monthly comparison) link | Daily
7 | CTUIL (OPEN ACCESS) (Compliance of Land and Financial Closure) link | Daily
8 | Monitoring of Connectivity (all 3 Annexures and monthly document release comparison) link | Daily
SN | Substation and Transmission Tracking | Frequency
9 | (Status of allocation of bays at ISTS substations for connectivity grantees, Connectivity margins at existing ISTS (non RE) substations for future RE integration and Connectivity Margin in ISTS RE Substations available by Mar-2030) link | Weekly
10a | Potential RE Zones Report link | Weekly
10b | NCT (Agenda and Minutes Summary and Comparison of Scheme wise elements) link Link: https://cea.nic.in/comm-trans/national-committee-on-transmission/?lang=en | Daily
10c | Tender websites PFCCL and RECPDCL mentioned in NCT under TBCB and RTM (RFP and other tender documents in folders; Bidding Status: Bid Submission Date or Deadline, Commissioning Timeline and Expected SCOD) RECPDCL: https://www.recpdcl.in/rectpcltender PFCCL:https://www.pfcclindia.com/tender-new.php PFCCL Notice: https://www.pfcclindia.com/notice.php?AM1 | Daily
10d | CEA monthly transmission reports: (track status for tender elements timelines from 1) CEA Monthly report for actual physical progress of elements and 2) Actual COD from completion report) CEA https://cea.nic.in/transmission-reports/?lang=en | Daily
10e | Map of the above Section 2 data to be created for review and edit by users
11 | Bulk Consumers and Green Hydrogen link | Weekly
12 | CEA: transmission schemes, substations (transformation capacity) and transmission lines published each month on CEA monthly reports section under transmission. | Weekly
13 | Global Wind Atlas (India Map Visualization) | Weekly
14 | Open Infrastructure Map (India Map Visualization) | Weekly

## Data to be captured
[8 empty] | 1200002471 |  | 2200002280 | 40 |  | 12.09.2025 |  | Solar + BESS | 300 | 300 | 300 +240 |  |  |  | 300 |  |  |  |  | JCC | JCC | [6 empty] | Generating station(s), including REGS(s), without ESS | Cmets , JCC | CMETS
| Sr.no. | Region | State | Substation | Coordinates | Name of Developers | Group | GNA/ST II Application ID | LTA Application ID | Application ID under Enhancement 5.2 or revision | CMETS GNA Approved | CMETS LTA Approved | CMETS GNA Meeting Date | CMETS LTA Meeting Date | Type | Application Quantum (MW)(ST II) | Granted Quantum GNA/LTA(MW) | Installed/Break-up Capacity (MW) |  |  | Battery |  |  | PSP |  |  | Commissioned |  | Application/Submission Date | Mode(Criteria for applying) | Applied Start of Connectivity sought by developer date( start date of connectivity as per the application) | GNA Operationalization Date | GNA Operationalization (Yes/No) | Date from which additional capacity is to be added | Nature of Applicant | Status of application(Withdrawn / granted. Revoked.) | Voltage level | Bay No | CTS Element Unique Code | ATS Element Unique Code | DTL Element Code Unique | Date of Last Element Unique Code | In-principle Grant | Final Grant | In case of Land BG Conversion Date | Remarks
[18 empty] | Solar | Wind | Hybrid | MWh | Injection (MW) | Drawl (MW) | MWh | Injection (MW) | Drawl (MW) | TGNA | GNA
996
Data Scoure (Sl. No.(s) 1,2,3,4,7,8,9,11)

## RE Potential
| Region | State | District | Complex | S/s | Location (Village/Tehsil) | Solar | Wind | Hybrid | Others (CTUIL) | RE Potential (GW) | Installed Capacity | U/c & granted Capacity | Transmission Scheme | Complex | Remarks
|  |  | Bikaner |  |  | Bikaner | 1.85
Data Scoure (Sl. No.(s)9, 10a, ) |  |  | Bikaner |  |  | Bikaner | 2.95
|  |  | Kurnool |  |  | Kurnool | 5.5
|  |  | Anantapur |  |  | Anantapur | 2.5
|  |  | Gadag |  |  | Gadag | 2.5
|  |  | Koppal |  |  | Koppal | 2.5
|  | Rajasthan |  |  |  |  | 15 | 1 |  |  | 60 |  |  |  |  | 45 GW (15 GW Wind & 30 GW solar in GIB Zone)
|  | Andhra Pradesh |  |  |  |  | 18 | 2 |  |  | 33
|  | Karnataka |  |  |  |  | 8 | 3 |  |  | 9
|  | Tamil Nadu |  |  |  |  | 5 | 4 |  |  | 5 |  |  |  |  | Offshore wind
|  | Telangana |  |  |  |  | 3 | 5 |  |  | 10
|  | Madhya Pradesh |  |  |  |  | 2 | 6 |  |  | 6
|  | Gujarat |  |  |  |  | 5 | 7 |  |  | 5 |  |  |  |  | Offshore wind
|  | Maharashtra |  |  |  |  | 2 | 8 |  |  | 5.5
|  | Rajasthan |  |  |  |  | 30 | 75
|  | Andhra Pradesh |  |  |  |  | 10 | 51 |  |  | 10
|  | Karnataka |  |  |  |  | 2 | 17 |  |  | 2
|  | Tamil Nadu |  |  |  |  | 5 | 5
|  | Telangana |  |  |  |  | 1 | 13 |  |  | 2.5
|  | Madhya Pradesh |  |  |  |  | 2 | 8
|  | Gujarat |  |  |  |  | 5 | 5
|  | Maharashtra |  |  |  |  | 1 | 7.5 |  |  | 1
|  | Rajasthan |  |  |  |  | 60 | 15 |  |  | 67.5
Gujarat
Maharashtra
|  | Maharashtra |  |  |  |  | 5.5 | 2 |  |  | 6.5 |  |  |  |  | 5.4
Madhya Pradesh
|  | Madhya Pradesh |  |  |  |  | 6 | 2 |  |  | 8
Andhra Pradesh
|  | Andhra Pradesh |  |  |  |  | 33 | 18 |  |  | 41
Karnataka
|  | Karnataka |  |  |  |  | 9 | 8 |  |  | 14
Telangana
|  | Telangana |  |  |  |  | 10 | 3 |  |  | 11.5 |  |  |  |  | 8.5
Tamil Nadu
|  | Telangana | Bikaner |  |  | Bikaner | 8 | 8.1 |  |  | 400
|  | Telangana | Bikaner |  |  | Bikaner | 400
|  | Telangana | Bikaner |  |  | Bikaner | 300
|  | Telangana | Bikaner |  |  | Bikaner | 9 | 8.1 |  |  | 400
|  | Telangana | Gadag |  |  | Gadag | 12 | 1000 |  |  | 400
|  | Telangana | Gadag |  |  | Gadag | 400
|  | Telangana | Koppal |  |  | Koppal | 13 | 2500 |  |  | 400
|  | Telangana | Koppal |  |  | Koppal | 400
|  | Telangana | Koppal |  |  | Koppal | 2
|  | Telangana | Gadag |  |  | Gadag | 11 | 1500 |  |  | 400
|  | Telangana | Kurnool |  |  | Kurnool | 1 | 2500 |  |  | 400
|  | Telangana | Kurnool |  |  | Kurnool | 400
|  | Telangana | Anantapur |  |  | Anantapur | 400
|  | Telangana | Kurnool |  |  | Kurnool | 3 | 3000 |  |  | 765
|  | Telangana | Kurnool |  |  | Kurnool | 765
|  | Rajasthan |  |  |  |  | 7 | 0 |  |  | 7
|  | Rajasthan |  |  |  |  | 6 | 6 |  |  | 12
|  | Rajasthan |  |  |  |  | 6 | 4 |  |  | 10
|  | Rajasthan |  |  |  |  | 3 | 0 |  |  | 3
|  | Rajasthan |  |  |  |  | 2 | 0 |  |  | 2
|  | Rajasthan |  |  |  |  | 3 | 2 |  |  | 5
|  | Rajasthan |  |  |  |  | 4 | 3 |  |  | 7
|  | Rajasthan |  |  |  |  | 6 | 0 |  |  | 6
|  | Rajasthan |  |  |  |  | 5 | 0 |  |  | 5
|  | Maharashtra |  |  |  |  | 1 | 0 |  |  | 1
|  | Maharashtra |  |  |  |  | 1 | 1 |  |  | 2
|  | Maharashtra |  |  |  |  | 2.5 | 2.5 |  |  | 0 |  |  |  |  | 2.5
|  | Gujarat |  |  |  |  | 5 | 5 |  |  | 2
|  | Telangana |  |  |  |  | 2.5 | 1 |  |  | 3.5
|  | Telangana |  |  |  |  | 2.5 | 0 |  |  | 2.5 |  |  |  |  | 0.5
|  | Karnataka |  |  |  |  | 2 | 2 |  |  | 4
|  | Karnataka |  |  |  |  | 0 | 2 |  |  | 2
|  | Karnataka |  |  |  |  | 1.5 | 0 |  |  | 1.5
|  | Tamil Nadu |  |  |  |  | 5 | 5 |  |  | 0
|  | Tamil Nadu |  | Bikaner-II | Bikaner-II |  | 7 | 0 |  | 0 | 7
|  | Tamil Nadu |  | Bikaner-III | Bikaner-III |  | 7 | 0 |  | 0 | 7
|  | Tamil Nadu |  | Fatehgarh-IV | Fatehgarh-IV |  | 6 | 6 |  | 2 | 12
|  | Tamil Nadu |  | Ramgarh | Ramgarh |  | 6 | 4 |  | 2 | 10
|  | Tamil Nadu |  | Jalore | Jalore |  | 3 | 0 |  | 0 | 3
|  | Tamil Nadu |  | Sanchore | Sanchore |  | 3 | 0 |  | 0 | 3
|  | Tamil Nadu |  | Sirohi | Sirohi |  | 3 | 0 |  | 0 | 3
|  | Tamil Nadu |  | Pali | Pali |  | 3 | 0 |  | 0 | 3
|  | Tamil Nadu |  | Ajmer | Ajmer |  | 2 | 0 |  | 0 | 2
|  | Tamil Nadu |  | Nagaur | Nagaur |  | 2 | 0 |  | 0 | 2
|  | Tamil Nadu |  | Bhadla-IV | Bhadla-IV |  | 3 | 2 |  | 0 | 5
|  | Tamil Nadu |  | Barmer-I | Barmer-I |  | 4 | 3 |  | 2 | 7
|  | Tamil Nadu |  | Barmer-II | Barmer-II |  | 6 | 0 |  | 0 | 6
|  | Tamil Nadu |  | Jaisalmer/ Jodhpur (Intra-State) | Jaisalmer/ Jodhpur (Intra-State) |  | 5 | 0 |  | 0 | 5
|  | Tamil Nadu |  | Total | Total |  | 60 | 15 |  | 6 | 75
|  | Tamil Nadu |  | Jaisalmer/ Jodhpur (Intra-State) | Jaisalmer/ Jodhpur (Intra-State) |  | 5 | 0 |  | 0 | 5
|  | Tamil Nadu |  | Jaisalmer/ Jodhpur (Intra-State) | Jaisalmer/ Jodhpur (Intra-State) |  | 5 | 0 |  | 0 | 5
|  | Tamil Nadu |  | Kurnool-IV | Kurnool-IV |  | 7.5 | 4 |  | 3 | 11.5
|  | Tamil Nadu |  | Kurnool-V | Kurnool-V |  | 7.5 | 4 |  | 3 | 11.5
|  | Tamil Nadu |  | Anantapur | Anantapur |  | 2 | 2 |  | 1 | 4
|  | Tamil Nadu |  | Anantapur-II | Anantapur-II |  | 8 | 8 |  | 4 | 16
|  | Tamil Nadu |  | Kadapa-II | Kadapa-II |  | 8 | 0 |  | 3 | 8
|  | Tamil Nadu |  | Total | Total |  | 33 | 18 |  | 14 | 51
|  | Tamil Nadu |  | Koppal-II | Koppal-II |  | 2 | 2 |  | 1 | 4
|  | Tamil Nadu |  | Gadag-II | Gadag-II |  | 2 | 2 |  | 1 | 4
|  | Tamil Nadu |  | Devanagere/ Chitragurga | Devanagere/ Chitragurga |  | 2 | 2 |  | 1 | 4
|  | Tamil Nadu |  | Bijapur | Bijapur |  | 0 | 2 |  | 0 | 2
|  | Tamil Nadu |  | Bellary | Bellary |  | 1.5 | 0 |  | 0 | 1.5
|  | Tamil Nadu |  | Tumkur-II | Tumkur-II |  | 1.5 | 0 |  | 0 | 1.5
|  | Tamil Nadu |  | Total | Total |  | 9 | 8 |  | 3 | 17
|  | Tamil Nadu |  | Nizamabad-II | Nizamabad-II |  | 2.5 | 1 |  | 1 | 3.5
|  | Tamil Nadu |  | Medak | Medak |  | 2.5 | 1 |  | 1 | 3.5
|  | Tamil Nadu |  | Rangareddy | Rangareddy |  | 2.5 | 1 |  | 1 | 3.5
|  | Tamil Nadu |  | Karimnagar | Karimnagar |  | 2.5 | 0 |  | 0 | 2.5
|  | Tamil Nadu |  | Total | Total |  | 10 | 3 |  | 3 | 13
|  | Tamil Nadu |  | Sl. No. | Sl. No.

## Margin
| Sl.No. | State | Region | Pooling S/s | Additional Information of Pooling S/s | Timelines | RE Potential |  |  | Expected CoD of Pooling Station | Connectivity Granted/ Agreed |  |  | Connectivity Granted/ Agreed |  |  | Margin for Connectivity |  |  | Additional Margin for Connectivity requiring ICT Augmentation / additional Tr. System |  |  | Effectiveness of GNA for Capacity mentioned under "Margin for Connectivity
[7 empty] | RE Potential (MW) [A] | BESS (MW) [B] | S/s Evacuation Capacity (RE Potential - BESS [AB]) |  | 200 kV | 400 kV | Total (MW) | 200 kV | 400 kV | Total (MW) | 200 kV | 400 kV | Total (MW) | 200 kV | 400 kV | Total (MW)
Existing PS
Jul-25 to Dec-25
Jan-26 to Jun-26
Jul-26 to Dec-31
Beyond Dec-25
Data Scoure (Sl. No.(s)9)

## Non RE proposed RE Integration
State | Name of Station | Capacity (MVA) | Capacity Allocated (MW) | Margin Existing 220kV (MW) | Margin Existing 400kV (MW) | Line Bays 220kV | Line Bays 400kV | Margin with ICT 220kV (MW) | Margin with ICT 400kV (MW) | Line Bays with ICT 220kV | Line Bays with ICT 400kV | No. of Transformers Required | Remarks

## Transformation Capacity
| S.No. | Region | State | Substation | Voltage level (kV) | Existing Capacity (MVA) | Under Implementation Capacity (MVA) | Planned Capacity (MVA)
Data Scoure (Sl. No.(s)9)

## Element Status
| Element Code | Inter/Intra Tx. Element | Transmission Scheme | Transmission Scope | MVA | Status | Approval of Elements in which NCT | Mode (TBCB/RTM) | Tender Issuing Authority | Date of tender issuance | Date of Bid Submission | Execution Timeline | Tentative SCOD | Awarded To | SPV Transfer Date | Physical Progress S/s of Tx. Line | [7 empty] | Physical Progress Substation |  |  | Original SCOD | Anticipated SCOD | Remarks
[16 empty] | Length | Location | Foundation | Erection | Stringing | Foundation (%) | Erection (%) | Stringing (%) | Civil Work (%) | Equipment Received (%) | Equipment Erected (%)
[12 empty] | 24 | 2026-02-15 | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0!
[11 empty] | 2026-01-15 | 21 | 2027-10-15
Data Scoure (Sl. No.(s)1, 2, 5, 6, 10b, 10c, 10d, 10e, 12)
Formulas:
Tentative SCOD = DATE(YEAR(TODAY()), MONTH(TODAY()+[Execution Timeline]), DAY(TODAY()))
Tentative SCOD = DATE(YEAR([Date of Bid Submission]),MONTH([Date of Bid Submission])+[Execution Timeline],DAY([Date of Bid Submission]))